## Summary
PIPELINE PROJECT
Total Schedule C: |  | CO | Extra Work |  | To | 2016-05-15
[5 empty] | From | 2016-05-01
1.0 Base Lay | 205093.5531 | UPI Summary: | 125158.18
2.1 | 3271.42 | CO 001 | 4394.6202
2.2 |  | CO 002 |  | 50000
2.3 | 66806.76 | CO 012
2.11 |  | CO 015 | 2238.76 |  | Contractor: | Contractor
2.14 |  | CO 017 |  |  | Chief Inspector | Construction Manager
2.18 |  | CO 019 |  |  | Project: | PIPELINE PROJECT
2.22 |  | CO 024
2.27 |  | CO 027 |  | 2751.84
2.29 |  | CO 030
2.31 |  | CO 033
2.35 | 55080 | CO 038 | 1480.14
3.1.2-2A |  | CO 039
3.2.2-2A |  | CO 040
|  | CO 052 | 325639.92
|  | CO 053 | 13198.84
|  | CO 054 | 5195.45
|  | CO 055 | 69770.04
CO 056
CO 057
2770000
Total | 330251.7331 | CO Total: | 421917.7702
| Subtotal: | 752169.5034
Difference:
1) Base Lay Total: | 205093.5531 |  |  |  | 0
2) UPI Total: | 125158.18 | UPI CO: | 125158.18
3) Incremental LS Total: | 0
4) Extra Work Total: | 421917.7702
Gross: | 752169.5034
Holdback: | 75216.9503
Subtotal: | 676952.553
GST | 33847.6277
Total: | 710800.1807
Previous Billings To Date W/ COs: | 44853184.41
Total Accrual: | 45605353.9134
Previous Accrual: | 47877000
Difference For Week: | -2271646.0866

## 1.0 BaseLay
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2015-11-15
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 34718 |  | 34718 | 403218.6408 | 0 | 403218.6408
| Grade ROW | Per Lin. m | 8% | 46.4564 | 0 |  |  | 0 | 0 | 0
| Haul and String Ppipe | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Bending | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Welding | Per Lin. m | 17% | 98.7199 | 0 |  |  | 0 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 0 |  |  | 0 | 0 | 0
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Backfill | Per Lin. m | 8% | 46.4564 | 0 |  |  | 0 | 0 | 0
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Testing | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 403218.6408 | 0 | 403218.6408
Contractor
Chief Inspector
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2015-11-30
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 34718 | 34717 | 403207.0266 | 403218.6408 | 806425.6674
| Grade ROW | Per Lin. m | 8% | 46.4564 | 5300 |  | 5300 | 246219.1135 | 0 | 246219.1135
| Haul and String Ppipe | Per Lin. m | 7% | 40.6494 | 400 |  | 400 | 16259.7528 | 0 | 16259.7528
| Bending | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Welding | Per Lin. m | 17% | 98.7199 | 0 |  |  | 0 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 0 |  |  | 0 | 0 | 0
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Backfill | Per Lin. m | 8% | 46.4564 | 0 |  |  | 0 | 0 | 0
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Testing | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 665685.893 | 403218.6408 | 1068904.5337
Contractor
Chief Inspector
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2015-12-15
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.67 | 806425.67 | hardwire previous
| Grade ROW | Per Lin. m | 8% | 46.4564 | 25100 | 5300 | 19800 | 919837.44 | 246219.11 | 1166056.55 | hardwire previous | grade | 25100 | 19800
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 16100 | 400 | 15700 | 638195.3 | 16259.75 | 654455.05 | hardwire previous | string | 16100 | 15700
| Bending | Per Lin. m | 7% | 40.6494 | 12000 |  | 12000 | 487792.58 | 0 | 487792.58 | hardwire previous | bend | 12000 | 12000
| Welding | Per Lin. m | 17% | 98.7199 | 9500 |  | 9500 | 937839.31 | 0 | 937839.31 | hardwire previous | weld | 9500 | 9500
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 3700 |  | 3700 | 171888.82 | 0 | 171888.82 | hardwire previous | ditch | 3700 | 3700
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 3700 |  | 3700 | 150402.71 | 0 | 150402.71 | hardwire previous | lower-in | 3700 | 3700
| Backfill | Per Lin. m | 8% | 46.4564 | 2800 |  | 2800 | 130078.02 | 0 | 130078.02 | hardwire previous | backfill | 2800 | 2800
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 1500 |  | 1500 | 60974.07 | 0 | 60974.07 | hardwire previous | tie-ins | 1500 | 1500
| Testing | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 3497008.25 | 1068904.53 | 4565912.78
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2015-12-31
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.67 | 806425.67
| Grade ROW | Per Lin. m | 8% | 46.4564 | 32600 | 25100 | 7500 | 348423.2739 | 1166056.55 | 1514479.8239 |  | grade | 32600 | 7500
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 24400 | 16100 | 8300 | 337389.8702 | 654455.05 | 991844.9202 |  | string | 24400 | 8300
| Bending | Per Lin. m | 7% | 40.6494 | 16100 | 12000 | 4100 | 166662.466 | 487792.58 | 654455.046 |  | bend | 16100 | 4100
| Welding | Per Lin. m | 17% | 98.7199 | 12800 | 9500 | 3300 | 325775.7611 | 937839.31 | 1263615.0711 |  | weld | 12800 | 3300
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 6900 | 3700 | 3200 | 148660.5969 | 171888.82 | 320549.4169 |  | ditch | 6900 | 3200
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 6900 | 3700 | 3200 | 130078.0222 | 150402.71 | 280480.7322 |  | lower-in | 6900 | 3200
| Backfill | Per Lin. m | 8% | 46.4564 | 6900 | 2800 | 4100 | 190471.3897 | 130078.02 | 320549.4097 |  | backfill | 6900 | 4100
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 3700 | 1500 | 2200 | 89428.6403 | 60974.07 | 150402.7103 |  | tie-ins | 3700 | 2200
| Testing | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 1736890.0203 | 4565912.78 | 6302802.8003
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2016-01-15
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.67 | 806425.67
| Grade ROW | Per Lin. m | 8% | 46.4564 | 48600 | 32600 | 16000 | 743302.9843 | 1514479.82 | 2257782.8043 |  | grade | 48600 | 16000
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 40800 | 24400 | 16400 | 666649.864 | 991844.92 | 1658494.784 |  | string | 40800 | 16400
| Bending | Per Lin. m | 7% | 40.6494 | 32200 | 16100 | 16100 | 654455.0494 | 654455.05 | 1308910.0994 |  | bend | 32200 | 16100
| Welding | Per Lin. m | 17% | 98.7199 | 29100 | 12800 | 16300 | 1609134.8199 | 1263615.07 | 2872749.8899 |  | weld | 29100 | 16300
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 21200 | 6900 | 14300 | 664327.0422 | 320549.42 | 984876.4622 |  | ditch | 21200 | 14300
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 20400 | 6900 | 13500 | 548766.6564 | 280480.73 | 829247.3864 |  | lower-in | 20400 | 13500
| Backfill | Per Lin. m | 8% | 46.4564 | 20200 | 6900 | 13300 | 617870.6057 | 320549.41 | 938420.0157 |  | backfill | 20200 | 13300
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 7600 | 3700 | 3900 | 158532.5896 | 150402.71 | 308935.2996 |  | tie-ins | 7600 | 3900
| Testing | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 5663039.6115 | 6302802.8 | 11965842.4115
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2016-01-31
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.6674 | 806425.6674
| Grade ROW | Per Lin. m | 8% | 46.4564 | 59700 | 48600 | 11100 | 515666.4453 | 2257782.8148 | 2773449.2601 |  | grade | 59700 | 11100
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 51600 | 40800 | 10800 | 439013.3251 | 1658494.7837 | 2097508.1088 |  | string | 51600 | 10800
| Bending | Per Lin. m | 7% | 40.6494 | 47600 | 32200 | 15400 | 626000.4821 | 1308910.0989 | 1934910.581 |  | bend | 47600 | 15400
| Welding | Per Lin. m | 17% | 98.7199 | 41900 | 29100 | 12800 | 1263615.0733 | 2872749.8932 | 4136364.9664 |  | weld | 41900 | 12800
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 36000 | 21200 | 14800 | 687555.2605 | 984876.4542 | 1672431.7146 |  | ditch | 36000 | 14800
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 36000 | 20400 | 15600 | 634130.3585 | 829247.3918 | 1463377.7503 |  | lower-in | 36000 | 15600
| Backfill | Per Lin. m | 8% | 46.4564 | 35900 | 20200 | 15700 | 729366.0533 | 938420.0177 | 1667786.071 |  | backfill | 35900 | 15700
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 14600 | 7600 | 7000 | 284545.6737 | 308935.3028 | 593480.9765 |  | tie-ins | 14600 | 7000
| Testing | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 5179892.6717 | 11965842.4244 | 17145735.0961
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2016-02-15
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.6674 | 806425.6674
| Grade ROW | Per Lin. m | 8% | 46.4564 | 69435 | 59700 | 9735 | 452253.4095 | 2773449.2601 | 3225702.6696 |  | grade | 69435 | 9735 | 0
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 64400 | 51600 | 12800 | 520312.089 | 2097508.1088 | 2617820.1978 |  | string | 64400 | 12800 | 0
| Bending | Per Lin. m | 7% | 40.6494 | 58600 | 47600 | 11000 | 447143.2015 | 1934910.581 | 2382053.7824 |  | bend | 58600 | 11000 | 0
| Welding | Per Lin. m | 17% | 98.7199 | 55900 | 41900 | 14000 | 1382078.9864 | 4136364.9664 | 5518443.9528 |  | weld | 55900 | 14000 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 51800 | 36000 | 15800 | 734011.697 | 1672431.7146 | 2406443.4116 |  | ditch | 51800 | 15800 | 0
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 51800 | 36000 | 15800 | 642260.2349 | 1463377.7503 | 2105637.9852 |  | lower-in | 51800 | 15800 | 0
| Backfill | Per Lin. m | 8% | 46.4564 | 51800 | 35900 | 15900 | 738657.3406 | 1667786.071 | 2406443.4116 |  | backfill | 51800 | 15900 | 0
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 31800 | 14600 | 17200 | 699169.3696 | 593480.9765 | 1292650.3461 |  | tie-ins | 31800 | 17200 | 0
| Testing | Per Lin. m | 7% | 40.6494 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 2500 |  | 2500 | 130658.7277 | 0 | 130658.7277 |  | Clean Up | 2500 | 2500 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 5746545.0561 | 17145735.0961 | 22892280.1522
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2016-02-29
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.6674 | 806425.6674
| Grade ROW | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 64400 | 5035 | 204669.6381 | 2617820.1978 | 2822489.8359
| Bending | Per Lin. m | 7% | 40.6494 | 69435 | 58600 | 10835 | 440436.0535 | 2382053.7824 | 2822489.8359 |  | bend | 69435 | 10835 | 0
| Welding | Per Lin. m | 17% | 98.7199 | 69435 | 55900 | 13535 | 1336174.2201 | 5518443.9528 | 6854618.1729 |  | weld | 69435 | 13535 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 67400 | 51800 | 15600 | 724720.4097 | 2406443.4116 | 3131163.8213 |  | ditch | 67400 | 15600 | 0
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 66900 | 51800 | 15100 | 613805.6675 | 2105637.9852 | 2719443.6526 |  | lower-in | 66900 | 15100 | 0
| Backfill | Per Lin. m | 8% | 46.4564 | 66500 | 51800 | 14700 | 682909.6168 | 2406443.4116 | 3089353.0284 |  | backfill | 66500 | 14700 | 0
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 37700 | 31800 | 5900 | 239831.3535 | 1292650.3461 | 1532481.6996 |  | tie-ins | 37700 | 5900 | 0
| Testing | Per Lin. m | 7% | 40.6494 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 10700 | 2500 | 8200 | 428560.6269 | 130658.7277 | 559219.3546 |  | Clean Up | 10700 | 8200 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 4671107.586 | 22892280.1522 | 27563387.7383
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2016-03-15
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.6674 | 806425.6674
| Grade ROW | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359
| Bending | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | bend | 69435 | 0 | 0
| Welding | Per Lin. m | 17% | 98.7199 | 69435 | 69435 |  | 0 | 6854618.1729 | 6854618.1729 |  | weld | 69435 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 69435 | 67400 | 2035 | 94538.8483 | 3131163.8213 | 3225702.6696 |  | ditch | 69435 | 2035 | 0
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 66900 | 2535 | 103046.1833 | 2719443.6526 | 2822489.8359 |  | lower-in | 69435 | 2535 | 0
| Backfill | Per Lin. m | 8% | 46.4564 | 69435 | 66500 | 2935 | 136349.6412 | 3089353.0284 | 3225702.6696 |  | backfill | 69435 | 2935 | 0
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 48200 | 37700 | 10500 | 426818.5105 | 1532481.6996 | 1959300.2101 |  | tie-ins | 48200 | 10500 | 0
| Testing | Per Lin. m | 7% | 40.6494 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 17000 | 10700 | 6300 | 329259.9938 | 559219.3546 | 888479.3484 |  | Clean Up | 17000 | 6300 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 1090013.1771 | 27563387.7383 | 28653400.9153
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2016-03-31
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.6674 | 806425.6674
| Grade ROW | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359
| Bending | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | bend | 69435 | 0 | 0
| Welding | Per Lin. m | 17% | 98.7199 | 69435 | 69435 |  | 0 | 6854618.1729 | 6854618.1729 |  | weld | 69435 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696 |  | ditch | 69435 | 0 | 0
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | lower-in | 69435 | 0 | 0
| Backfill | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696 |  | backfill | 69435 | 0 | 0
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 65700 | 48200 | 17500 | 711364.1842 | 1959300.2101 | 2670664.3943 |  | tie-ins | 65700 | 17500 | 0
| Testing | Per Lin. m | 7% | 40.6494 | 18100 | 0 | 18100 | 735753.8133 | 0 | 735753.8133 |  | testing | 18100 | 18100 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 28600 | 17000 | 11600 | 606256.4966 | 888479.3484 | 1494735.845 |  | Clean Up | 28600 | 11600 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 | 0 |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 2053374.4941 | 28653400.9153 | 30706775.4094
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2016-04-15
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.6674 | 806425.6674
| Grade ROW | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359
| Bending | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | bend | 69435 | 0 | 0
| Welding | Per Lin. m | 17% | 98.7199 | 69435 | 69435 |  | 0 | 6854618.1729 | 6854618.1729 |  | weld | 69435 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696 |  | ditch | 69435 | 0 | 0
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | lower-in | 69435 | 0 | 0
| Backfill | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696 |  | backfill | 69435 | 0 | 0
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 69335 | 65700 | 3635 | 147760.5034 | 2670664.3943 | 2818424.8977 |  | tie-ins | 69335 | 3635 | 0
| Testing | Per Lin. m | 7% | 40.6494 | 41000 | 18100 | 22900 | 930870.8467 | 735753.8133 | 1666624.6601 |  | testing | 41000 | 22900 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 47900 | 28600 | 19300 | 1008685.3779 | 1494735.845 | 2503421.2228 |  | Clean Up | 47900 | 19300 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 | 0 |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 2087316.728 | 30706775.4094 | 32794092.1374
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2016-04-30
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.6674 | 806425.6674
| Grade ROW | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359
| Bending | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | bend | 69435 | 0 | 0
| Welding | Per Lin. m | 17% | 98.7199 | 69435 | 69435 |  | 0 | 6854618.1729 | 6854618.1729 |  | weld | 69435 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696 |  | ditch | 69435 | 0 | 0
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | lower-in | 69435 | 0 | 0
| Backfill | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696 |  | backfill | 69435 | 0 | 0
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 69435 | 69335 | 100 | 4064.9382 | 2818424.8977 | 2822489.8359 |  | tie-ins | 69435 | 100 | 0
| Testing | Per Lin. m | 7% | 40.6494 | 69435 | 41000 | 28435 | 1155865.1758 | 1666624.6601 | 2822489.8359 |  | testing | 69435 | 28435 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 69435 | 0 | 69435 | 2016064.1685 | 0 | 2016064.1685 |  | Final Tie ins | 69435 | 69435 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 58300 | 47900 | 10400 | 543540.3073 | 2503421.2228 | 3046961.5301 |  | Clean Up | 58300 | 10400 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 34418 | 0 | 34418 | 399734.408 | 0 | 399734.408 |  |  |  |  | 34418
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 | 0 |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 4119268.9978 | 32794092.1374 | 36913361.1352
Contractor
Construction Manager
PIPELINE PROJECT
Schedule C
1.0 - BASE LAY PRICE
[8 empty] | Billing Date: | 2016-05-15
|  | 69435 | % | 580.7055 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($) |  |  | Current | New
1.1 | Mobilization | Per Lin. m | 2% | 11.6141 | 69435 | 69435 |  | 0 | 806425.6674 | 806425.6674
| Grade ROW | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696
| Haul and String Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359
| Bending | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | bend | 69435 | 0 | 0
| Welding | Per Lin. m | 17% | 98.7199 | 69435 | 69435 |  | 0 | 6854618.1729 | 6854618.1729 |  | weld | 69435 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696 |  | ditch | 69435 | 0 | 0
| Lower-In Pipe | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | lower-in | 69435 | 0 | 0
| Backfill | Per Lin. m | 8% | 46.4564 | 69435 | 69435 |  | 0 | 3225702.6696 | 3225702.6696 |  | backfill | 69435 | 0 | 0
| Tie-Ins | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | tie-ins | 69435 | 0 | 0
| Testing | Per Lin. m | 7% | 40.6494 | 69435 | 69435 |  | 0 | 2822489.8359 | 2822489.8359 |  | testing | 69435 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 29.0353 | 69435 | 69435 |  | 0 | 2016064.1685 | 2016064.1685 |  | Final Tie ins | 69435 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 52.2635 | 58300 | 58300 |  | 0 | 3046961.5301 | 3046961.5301 |  | Clean Up | 58300 | 0 | 0
| Demobilization | Per Lin. m | 2% | 11.6141 | 52077 | 34418 | 17659 | 205093.5531 | 399734.408 | 604827.9611 |  |  |  |  | 52077
| Final Clean Up (one year later) | Per Lin. m | 6% | 34.8423 | 0 | 0 |  | 0 | 0 | 0
|  |  | 100% | 580.7055 |  |  | Total For Base Lay Price: | 205093.5531 | 36913361.1352 | 37118454.6883
Contractor
Construction Manager

## 2.1
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C | Commercial Terms |  | Date: | 2015-12-15
Item | 2.1 Rock Trench
Description |  | per |  | Amount
2.1 | Rock Trench
| a) by mechanical methods, when requested by Company | Cost Plus |  | 36802.67
| b) by drill and blasting methods, when requestd by Company | Cost Plus
| c) within the wetted perimeter of named watercourses in accordance with the Contract Documents, when requested by Company | Cost Plus
|  |  | Total | 36802.67
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C | Commercial Terms |  | Date: | 2016-01-15
Item | 2.1 Rock Trench
Description |  | per |  | Amount
2.1 | Rock Trench
| a) by mechanical methods, when requested by Company | Cost Plus |  | 19134.69
| b) by drill and blasting methods, when requestd by Company | Cost Plus
| c) within the wetted perimeter of named watercourses in accordance with the Contract Documents, when requested by Company | Cost Plus
|  |  | Total | 19134.69
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C | Commercial Terms |  | Date: | 2016-01-31
Item | 2.1 Rock Trench
Description |  | per |  | Amount
2.1 | Rock Trench
| a) by mechanical methods, when requested by Company | Cost Plus |  | 1914.8
| b) by drill and blasting methods, when requestd by Company | Cost Plus
| c) within the wetted perimeter of named watercourses in accordance with the Contract Documents, when requested by Company | Cost Plus
|  |  | Total | 1914.8
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C | Commercial Terms |  | Date: | 2016-02-15
Item | 2.1 Rock Trench
Description |  | per |  | Amount
2.1 | Rock Trench
| a) by mechanical methods, when requested by Company | Cost Plus |  | 4031.8
| b) by drill and blasting methods, when requestd by Company | Cost Plus
| c) within the wetted perimeter of named watercourses in accordance with the Contract Documents, when requested by Company | Cost Plus
|  |  | Total | 4031.8
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C | Commercial Terms |  | Date: | 2016-02-29
Item | 2.1 Rock Trench
Description |  | per |  | Amount
2.1 | Rock Trench
| a) by mechanical methods, when requested by Company | Cost Plus |  | 35207.68
| b) by drill and blasting methods, when requestd by Company | Cost Plus
| c) within the wetted perimeter of named watercourses in accordance with the Contract Documents, when requested by Company | Cost Plus
|  |  | Total | 35207.68
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C | Commercial Terms |  | Date: | 2016-03-15
Item | 2.1 Rock Trench
Description |  | per |  | Amount
2.1 | Rock Trench
| a) by mechanical methods, when requested by Company | Cost Plus |  | 3361.32
| b) by drill and blasting methods, when requestd by Company | Cost Plus
| c) within the wetted perimeter of named watercourses in accordance with the Contract Documents, when requested by Company | Cost Plus
|  |  | Total | 3361.32
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C | Commercial Terms |  | Date: | 2016-05-15
Item | 2.1 Rock Trench
Description |  | per |  | Amount
2.1 | Rock Trench
| a) by mechanical methods, when requested by Company | Cost Plus |  | 3271.42
| b) by drill and blasting methods, when requestd by Company | Cost Plus
| c) within the wetted perimeter of named watercourses in accordance with the Contract Documents, when requested by Company | Cost Plus
|  |  | Total | 3271.42
Contractor
Construction Manager

## 2.2
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2015-12-15
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 318.98 | 22800.6904
|  |  |  | Total | 22800.6904
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres
| SITE UPI Report 0552 Dec. 9: | 51804 | 51835 | 31
|  | 51967.5 | 51978 | 10.5
|  | 52144.4 | 52154.7 | 10.3
|  | 52233.1 | 52269.3 | 36.2
|  | 52269.3 | 52280 | 10.7
|  | 52307 | 52338.2 | 31.2
|  | 52746.9 | 52756.3 | 9.4
|  | 52904.6 | 52923 | 18.4 | 157.7
| SITE UPI Report 0552 Dec 13: | 53113 | 53166 | 53
|  | 52545 | 52617 | 72 | 125
| SITE UPI Report 0554 Dec 15: | 54697.62 | 54724.37 | 26.75
|  | 54229.8 | 54239.33 | 9.53 | 36.28
|  |  | Total: | 318.98 | 318.98
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2015-12-31
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 292.61 | 20915.7628
|  |  |  | Total | 20915.7628
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres |  |  | LEM
| 2016-12-19 | 54463 | 54538 | 75 | 75 | Tim Lay | 0326 |  | should be 54+539
| 2016-12-18 | 57556 | 57574.84 | 18.84 | 18.84 | Dwayne P | 0555
| 2016-12-18 | 57595.16 | 57604.41 | 9.25 | 9.25 | Dwayne P | 0555
| 2016-12-18 | 57622.16 | 57631.44 | 9.28 | 9.28 | Dwayne P | 0555
| 2016-12-20 | 65267 | 65411 | 144 | 144 | Dwayne P | 0555
| 2016-12-19 | 60007.19 | 60043.43 | 36.24 | 36.24 | Dwayne P | 0556
|  |  | Total: | 292.61 | 292.61
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-01-15
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 298.7 | 21351.076
|  |  |  | Total | 21351.076
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres | Survey |  | LEM
| 2016-01-07 | 60496 | 60536 | 39 | 33.4 | Tim/Jerome | 0328 | off by 6m too much compared to survey
| 2016-01-08 | 61258 | 61213 | 44.4 | 44.4 | Jerome | 0329 | survey had in the other direction 61+257.5 to 61+301.9
| 2016-01-11 | 67299 | 67471 | 172 | 172.3 | Dwayne | 0557
| 2016-01-12 | 67562.7 | 67606 | 43.3 | 44 | Dwayne | 0558
0
|  |  | Total: | 298.7 | 294.1
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-01-31
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 319.2 | 22816.416
|  |  |  | Total | 22816.416
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres | Survey |  | LEM
| 2016-01-19 | 6564 | 6600 | 35 | 35.4 | Dwayne | 559
|  | 6749 | 6802 | 53.7 | 53.7 | Dwayne | 559 | 88.7
| 2016-01-19 | 64946 | 64964 | 17 | 18 | Clint | 1176
| 2016-01-20 | 67477 | 67519 | 42 | 42.6 | Jerome | 331
| 2016-01-21 | 10848 | 10902.4 | 54.4 | 54.4 | Dwayne | 560
|  | 11031 | 11040.3 | 9.3 | 9.3 | Dwayne | 560
|  | 11132.4 | 11141.7 | 9.3 | 9.3 | Dwayne | 560
|  | 11687.8 | 11731.9 | 44.1 | 44.1 | Dwayne | 560 | 117.1
| 2016-01-28 | 16901.6 | 16929 | 27.4 | 27.5 | Dwayne | 561
| 2016-01-29 | 14747 | 14774 | 27 | 27.1 | Clint | 1177
0
|  |  | Total: | 319.2 | 321.4
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-02-15
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 1117.7 | 79893.196
|  |  |  | Total | 79893.196
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres | Survey |  | LEM
| 2016-02-02 | 22241.3 | 22303.86 | 62.6 | 62.6 | Dwayne | 0562
| 2016-02-03 | 6425 | 6507 | 83 | 82.1 | Jerome | 0335
| 2016-02-04 | 8232 | 8290 | 59 | 57.8 | Jerome | 0336
| 2016-02-05 | 56706 | 56861 | 155 | 155 | Dwayne | 0564
|  | 56890 | 57083 | 193 | 193 | Dwayne | 0564
| 2016-02-07 | 56661 | 56706 | 45 | 45 | Dwayne | 0529
| 2016-02-11 | 27856 | 27883 | 27 | 27 | Dwayne | 0565
| 2016-02-11 | 32016 | 32052 | 54 | 36.4 | Dwayne | 0566
| 2016-02-11 | 32080 | 32098 |  | 18.3 | Dwayne | 0566
| 2016-02-12 | 32311 | 32544.3 | 233.3 | 233.3 | Dwayne | 0567
| 2016-02-12 | 32572 | 32607.7 | 35.7 | 35.5 | Dwayne | 0567
| 2016-02-12 | 32765.5 | 32784 | 18.5 | 18.5 | Dwayne | 0567 | overlap with Feb 29
| 2016-02-12 | 32899 | 32961.3 | 62.3 | 62.3 | Dwayne | 0567
| 2016-02-12 | 32991 | 33018 | 27 | 27 | Dwayne | 0567
| 2016-02-12 | 33030 | 33056.8 | 26.8 | 26.8 | Dwayne | 0567
| 2016-02-12 | 33056.8 | 33092.3 | 35.5 | 35.5 | Dwayne | 0567
0
|  |  | Total: | 1117.7 | 1116.1
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-02-29
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 6436.2 | 460059.576
|  |  |  | Total | 460059.576
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres |  | Survey |  | LEM
| 2016-02-13 | 25942 | 25979 | 37 |  | 37 | Jerome | 0339
| 2016-02-14 | 25900 | 25920 | 20 | 57 | 20 | Jerome | 0339
| 2016-02-13 | 33142 | 33334 | 192 |  | 192 | Dwayne | 0568
|  | 33460 | 33696 | 236 |  | 236 | Dwayne | 0568
|  | 33110 | 33133.8 | 23.8 | 451.8 | 23.8 | Dwayne | 0568
| 2016-02-16 | 25762 | 25853 | 91 | 91 | 91 | Jerome | 0340
| 2016-02-16 | 32963.9 | 32994.4 | 30.5 |  | 30.5 | Thomas | 0140
|  | 33093.2 | 33110.8 | 17.6 |  | 17.6 | Thomas | 0140
|  | 33136.8 | 33147.3 | 10.5 |  | 10.5 | Thomas | 0140
|  | 33018 | 33030 | 12 | 70.6 | 12 | Thomas | 0140
| 2016-02-17 | 25683 | 25710 | 27 |  | 26.9 | Jerome | 0341
|  | 25720 | 25746 | 26 | 53 | 26.3 | Jerome | 0341
| 2016-02-17 | 29220 | 29237.7 | 17 |  | 17.7 | Clint | 1178
|  | 29309 | 29380 | 71 | 88 | 71 | Clint | 1178
| 2016-02-17 | 34328 | 34399.9 | 71.9 |  | 71.9 | Dwayne | 0569
|  | 34469.5 | 34657.1 | 187.6 |  | 187.6 | Dwayne | 0569
|  | 34821.8 | 34830.9 | 9.1 |  | 9.1 | Dwayne | 0569
|  | 34830.9 | 34876.4 | 45.5 |  | 45.5 | Dwayne | 0569
|  | 34933.8 | 34996.9 | 63.1 |  | 63.1 | Dwayne | 0569
|  | 34996.9 | 35005.9 | 9 | 386.2 | 9 | Dwayne | 0569
| 2016-02-17 | 25488 | 25513 | 25 | 25 | 26.3 | Jerome | 0342
| 2016-02-18 | 35475.4 | 35520.6 | 45.2 |  | 45.2 | Dwayne | 0570
|  | 36312.1 | 36472.7 | 160.6 |  | 160.6 | Dwayne | 0570
|  | 36101 | 36172.8 | 71.8 | 277.6 | 71.8 | Dwayne | 0570
| 2016-02-19 | 36670.5 | 36965.8 | 295.3 |  | 295.3 | Dwayne | 0571
|  | 37213.9 | 37356.8 | 142.9 |  | 142.9 | Dwayne | 0571
|  | 37062.6 | 37133.9 | 71.3 | 509.5 | 71.3 | Dwayne | 0571
| 2016-02-20 | 37491.8 | 37634.5 | 142.7 |  | 142.7 | Dwayne | 0572
|  | 37802.2 | 37965 | 162.8 |  | 162.8 | Dwayne | 0572
|  | 37965 | 38055 | 90 |  | 90 | Dwayne | 0572
|  | 38130.7 | 38185 | 54.3 |  | 54.3 | Dwayne | 0572
|  | 38225.6 | 38351.6 | 126 |  | 126 | Dwayne | 0572
|  | 38770.6 | 38842.8 | 72.2 |  | 72.2 | Dwayne | 0572
|  | 38921.4 | 38984.3 | 62.9 | 710.9 | 62.9 | Dwayne | 0572
| 2016-02-20 | 25606 | 25633 | 27 | 27 | 26.5 | Jerome | 0343
| 2016-02-21 | 39043.6 | 39099.8 | 56.2 |  | 56.2 | Dwayne | 0575
|  | 39102.1 | 39182.9 | 80.8 |  | 80.8 | Dwayne | 0575
|  | 39588.6 | 39633.6 | 45 |  | 45 | Dwayne | 0575
|  | 39741.9 | 39804.9 | 63 |  | 63 | Dwayne | 0575 | 1.1 m overlap with below
|  | 39882.5 | 39900.5 | 18 |  | 18 | Dwayne | 0575 | 3 m overlap with below
|  | 40079.5 | 40115.5 | 36 | 299 | 36 | Dwayne | 0575
| 2016-02-22 | 40303 | 40526 | 223 |  | 223 | Dwayne | 0573
|  | 40922 | 40982.5 | 60.5 |  | 60.5 | Dwayne | 0573
|  | 41089 | 41106 | 18 | 301.5 | 18 | Dwayne | 0573
| 2016-02-23 | 41359 | 41475.3 | 116.3 |  | 116.3 | Dwayne | 1301
|  | 41194 | 41274 | 80 |  | 80 | Dwayne | 1301 | 4 m overlap with below
|  | 41569 | 41587 | 18 |  | 18 | Dwayne | 1301
|  | 41666 | 41692.6 | 26.6 |  | 26.6 | Dwayne | 1301
|  | 42021 | 42066 | 45 |  | 45 | Dwayne | 1301
|  | 42079 | 42106.3 | 27.3 |  | 27.3 | Dwayne | 1301
|  | 42504 | 42522.2 | 18.2 |  | 18.2 | Dwayne | 1301
|  | 42474 | 42483.2 | 9.2 |  | 9.2 | Dwayne | 1301
|  | 42629.8 | 42639 | 9.2 | 349.8 | 9.2 | Dwayne | 1301
| 2016-02-23 | 39008.2 | 38990 | 18.2 |  | 18.2 | Thomas | 0143
|  | 39026.7 | 39035.7 | 9 | 27.2 | 9 | Thomas | 0143
| 2016-02-24 | 32540 | 32567 | 27 |  | 27 | Clint | 1177/1179
|  | 32738 | 32796 | 58 |  | 58 | Clint | 1177/1179 | 18.5 m overlap taken off as previously surveyed and billed on Feb 15
|  | 32858 | 32898 | 40 | 125 | 39 | Clint | 1177/1179
| 2016-02-12 | 32765.5 | 32784 | -18.5 | -18.5 | -18.5 | Dwayne | 0567
| 2016-02-25 | 35006 | 35072 | 66 |  | 66.3 | Jerome | 0344
|  | 34407 | 34468 | 61 | 127 | 60.9 | Jerome | 0344
| 2016-02-25 | 42925.7 | 43023.9 | 98.2 |  | 98.2 | Dwayne | 1303 | 3.9 m overlap with below
|  | 43140 | 43701.6 | 561.6 |  | 561.6 | Dwayne | 1303
|  | 43845 | 44068 | 223 |  | 223 | Dwayne | 1303
|  | 44109 | 44261.7 | 152.7 |  | 152.7 | Dwayne | 1303
|  | 44283 | 44371.9 | 88.9 | 1124.4 | 88.9 | Dwayne | 1303
| 2016-02-26 | 44590 | 44661.6 | 71.6 |  | 71.6 | Dwayne | 1304
|  | 44692.7 | 44763.7 | 71 |  | 71 | Dwayne | 1304 | 2.7 m overlap with below
|  | 44834 | 44959 | 125 |  | 125 | Dwayne | 1304
|  | 45446 | 45464.2 | 18.2 |  | 18.2 | Dwayne | 1304
|  | 45475 | 45528.8 | 53.8 |  | 53.8 | Dwayne | 1304
|  | 45565.8 | 45601.7 | 35.9 | 375.5 | 35.9 | Dwayne | 1304
| 2016-02-27 | 45725.6 | 45867.3 | 141.7 |  | 141.7 | Dwayne | 1305
|  | 45926 | 46188.4 | 262.4 |  | 262.4 | Dwayne | 1305
|  | 46236.2 | 46245.4 | 9.2 |  | 9.2 | Dwayne | 1305
|  | 46377 | 46422.3 | 45.4 |  | 45.4 | Dwayne | 1305
|  | 46454.6 | 46722.3 | 267.7 |  | 267.7 | Dwayne | 1305
|  | 46752.7 | 46815.5 | 62.8 |  | 62.8 | Dwayne | 1305
|  | 47055.4 | 47109 | 53.6 |  | 53.6 | Dwayne | 1305
|  | 47237.4 | 47372.3 | 134.9 | 977.7 | 134.9 | Dwayne | 1305
0
0
|  |  | Total: | 6436.2 | 6436.2 | 6437.1
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-03-15
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 3404.5 | 243353.66
|  |  |  | Total | 243353.66
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres | Survey |  | LEM
| 2016-02-29 | 47622 | 47658.6 | 36.6 | 36.6 | Dwayne/Thomas |  | 1308
|  | 47758.6 | 47785.6 | 27 | 27 | Dwayne/Thomas |  | 1308
|  | 47810 | 47890.6 | 80.6 | 80.6 | Dwayne/Thomas |  | 1308
|  | 47825.8 | 47942.5 | 116.7 | 116.7 | Dwayne/Thomas |  | 1308
|  | 47988.7 | 48015.7 | 27 | 27 | Dwayne/Thomas |  | 1308
|  | 48196.1 | 48286.4 | 90.3 | 90.3 | Dwayne/Thomas |  | 1308
|  | 48478 | 48514.2 | 36.2 | 36.2 | Dwayne/Thomas |  | 1308
| 2016-02-29 | 35183 | 35236 | 53 | 52.7 | Jerome |  | 0345
| 2016-03-01 | 49095.4 | 49122.6 | 27.2 | 27.2 | Dwayne/Thomas |  | 1306
|  | 49149.6 | 49186 | 36.4 | 36.4 | Dwayne/Thomas |  | 1306
|  | 49210.8 | 49238.6 | 27.8 | 27.8 | Dwayne/Thomas |  | 1306
|  | 49354.4 | 49417.8 | 63.4 | 63.4 | Dwayne/Thomas |  | 1306
|  | 49455.8 | 49815.4 | 359.6 | 359.6 | Dwayne/Thomas |  | 1306
|  | 49826 | 49853.2 | 27.2 | 27.2 | Dwayne/Thomas |  | 1306
|  | 49880.7 | 49916.7 | 36 | 36 | Dwayne/Thomas |  | 1306
-0.6
| 2016-03-02 | 37031 | 37064 | 33 | 34 | Jerome |  | 0346
| 2016-03-02 | 37112 | 37201 | 89 | 89 | Jerome |  | 0347
|  | 36472 | 36530 | 58 | 58 | Jerome |  | 0347
| 2016-03-02 | 49923 | 50048.7 | 125.7 | 125.7 | Dwayne/Thomas |  | 1307
|  | 50157 | 50220.1 | 63.1 | 63.1 | Dwayne/Thomas |  | 1307
|  | 50286.9 | 50323.1 | 36.2 | 36.2 | Dwayne/Thomas |  | 1307
|  | 50373.5 | 50526.4 | 152.9 | 152.9 | Dwayne/Thomas |  | 1307
| 2016-03-03 | 39633 | 39647 | 14 | 14 | Clint |  | 1180
|  | 39728 | 39743 | 15 | 15 | Clint |  | 1180 | 1.1 m overlap with above
| 2016-03-04 | 39805 | 39879 | 74 | 74 | Clint |  | 1181
|  | 39897 | 40029 | 132 | 132 | Clint |  | 1181 | 3 m of overlap with above
| 2016-03-04 | 37456 | 37494 | 38 | 38 | Jerome |  | 0348
|  | 37635 | 37706 | 71 | 71.2 | Jerome |  | 0348
|  | 37356 | 37408 | 52 | 51.4 | Jerome |  | 0348
|  | 41064 | 41074 | 10 | 10 | Jerome |  | 0348
|  | 41006 | 41055 | 41 | 49 | Jerome |  | 0348 | 8 m missed
| 2016-03-04 | 49815 | 49829.4 | 14.4 | 14.4 | Thomas |  | 1309 | 3.4m of overlap with above
|  | 49916 | 49919.8 | 3.8 | 3.8 | Thomas |  | 1309
| 2016-03-05 | 50048 | 50087.2 | 39.2 | 39.2 | Thomas |  | 1310
|  | 50110.9 | 50156 | 45.1 | 45.1 | Thomas |  | 1310
| 2016-03-06 | 57238.3 | 57315.7 | 77.4 | 77.4 | Dwayne |  | 0537
|  | 57120.3 | 57179.8 | 59.5 | 59.5 | Dwayne |  | 0537
|  | 59699 | 59743.8 | 44.8 | 44.8 | Dwayne |  | 0537
|  | 59614.8 | 59641.8 | 27 | 27 | Dwayne |  | 0537
| 2016-03-09 | 41270 | 41292 | 22 | 22.5 | Jerome |  | 0349 | 4 m overlap with above
|  | 41542 | 41568 | 26 | 25.7 | Jerome |  | 0349
|  | 41444 | 41486 | 42 | 42 | Jerome |  | 0349
|  | 43020 | 43137 | 117 | 117 | Jerome |  | 0349 | 3 m overlap with above
| 2016-03-09 | 33789.8 | 34031.5 | 242 | 241.6 | Josh |  | 0444
| 2016-03-12 | 44377 | 44460 | 83 | 83 | Jerome |  | 1326
|  | 43705 | 43775 | 70 | 70 | Jerome |  | 1326
| 2016-03-13 | 51215 | 51317 | 102 | 102 | Clint |  | 1182
| 2016-03-15 | 42021 | 42096 | 75 | 75 | Jerome |  | 1327
|  | 42722 | 42927 | 205 | 205 | Jerome |  | 1327
|  | 44465 | 44525 | 60 | 60 | Jerome |  | 1327
|  |  | Total: | 3404.5 | 3413.2 |  |  |  | 14.5 m extra due to overlap; 8.6 m missed= 5.9 m extra on this billing
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-03-31
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 836.07 | 59762.2836
|  |  |  | Total | 59762.2836
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres | Survey |  | LEM
| 2016-03-17 | 47108 | 47233 | 125 | 125.2 | Clint |  | 1183 |  |  | survey has 47233.2 | UPI may be wrong
| 2016-03-17 | 44761 | 44834 | 73 | 73 | Jerome |  | 1328 | 2.7 m overlap with above
|  | 45127 | 45149 | 22 | 22 | Jerome |  | 1328
|  | 45221 | 45465 | 244 | 244 | Jerome |  | 1328
| 2016-03-19 | 45600 | 45705 | 105 | 105 | Jerome |  | 1329
| 2016-03-20 | 48275 | 48318 | 43 | 43 | Ron/Clint |  | 1184
| 2016-03-15 | 67255.43 | 67301.5 | 46.07 | 46.1 | Ron |  | 0145
| 2016-03-25 | 35531 | 35652 | 121 | 121 | Jerome |  | 1330
| 2016-03-26 | 35652 | 35709 | 57 | 57 | Jerome |  | 1330
|  |  | Total: | 836.07 | 836.3
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-04-15
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 552 | 39456.96
|  |  |  | Total | 39456.96
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres | Survey |  | LEM
| 2016-03-29 | 35875 | 35937 | 62 | 62 | Jerome | 1332
| 2016-04-02 | 42568 | 42647 | 79 | 79 | Jerome | 1332
| 2016-04-02 | 42484 | 42541 | 57 | 57 | Jerome | 1332 | 198
| 2016-04-03 | 41971 | 42021 | 50 | 49.5 | Jerome | 1333
|  | 41700 | 41744 | 44 | 44 | Jerome | 1333 | 94
| 2016-04-03 | 38725 | 38768 | 43 | 43 | John Hummel | 1313 | 43
| 2016-04-07 | 48932 | 49014 | 82 | 81.4 | Jerome | 1335
|  | 48514 | 48628 | 114 | 114 | Jerome | 1335 | 196
| 2016-04-14 | 39165 | 39186 | 21 | 40 | Doug Clark | 1609 | 21 |  | some rockshield missing
0
0
|  |  | Total: | 552 | 569.9
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-05-15
Item | 2.2 Rockshield
Description |  | per | Unit Price | Units | Amount
2.2 | Rockshield (NPS 16)
| a) Owner supply rockshield material | per lin. M | 51.48
| b) Contractor supply rockshield material | per lin. M | 71.48 | 708 | 50607.84
|  |  |  | Total | 50607.84
Contractor
Construction Manager
| Locations (KPs): | From | To | Metres | Survey |  | LEM
| 2016-12-09 | 52181 | 52191 | 10 | 10 | Clint
| 2016-12-12 | 54558 | 54585 | 27 | 27 | Clint
| 2016-12-18 | 52526.5 | 52586.4 | 59.9 | 59.9 | Meridian |  | No UPI from Dwayne
| 2016-12-18 | 52693.8 | 52782.6 | 88.8 | 88.8 | Meridian |  | No UPI from Dwayne
| 2016-01-16 | 64932 | 64954 | 22 | 18 | Clint
| 2016-03-01 | 39689 | 39741 | 52 | 80 | Clint |  | No UPI from Clint |  | Clint has to 39+769 but there is overlap with Feb 29 billing
|  | 37740 | 37784 | 44 | 44 | Clint |  | No UPI from Clint
| 2016-03-17 | 47108 | 47233.2 | 125.2 | 125.2 | Clint | no Lem/UPI
| 2016-03-17 | 11835.6 | 11853.9 | 18.3 | 18.3 | Terry | no Lem/UPI
| 2016-03-17 | 11885.8 | 11895.2 | 9.4 | 9.4 | Terry | no Lem/UPI
| 2016-04-04 | 38353 | 38376 | 23 |  | John Hummel | UPI
| 2016-04-04 | 48514 | 48628 | 114 | 114 |  | no Lem/UPI
| 2016-04-05 | 48933.3 | 49014.7 | 81.4 | 81.4 |  | no Lem/UPI
| 2016-04-13 | 39173 | 39206 | 33 | 33 |  | no Lem/UPI
0
0
0
0
0
0
|  |  | Total: | 708 | 709

## 2.3
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Sand Bedding/Padding
Schedule C |  |  |  | Date: | 2015-12-15
Item | 2.3 Sand Bedding/Padding From Borrow Pits
Description |  | per | Unit Price | Units | Amount
2.3 | Sand Bedding/Padding From Borrow Pits (Supply, load, haul, unload, place) | [7 empty] | LEM | From | To
| a) Bedding | Per Lin. m | 89.6 | 80 | 7168 |  |  |  | #0165 | 54+380 | 54+460 | 80 m |  |  | 18.89 | 18.99
| b) Padding (Top) | Per Lin. m | 114.67 |  | 0 | [9 empty] | 18.9 | 19.03
| c) Bedding and Padding Placed As One Operation | Per Lin. m | 166.57 | 180 | 29982.6 |  |  |  | #0167 | 54+200 | 54+380 | 180 m |  |  | 18.95 | 19.27
| d) Hauling (The cost of hauling to the ROW) | m3/km | 2.8 | 15430.75 | 43206.1 | [9 empty] | 9.6
19.19
18.88
|  |  |  | Total | 80356.7 | [9 empty] | 19.51
[15 empty] | 123.92 | 57.29
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Sand Bedding/Padding
Schedule C |  |  |  | Date: | 2016-01-15
Item | 2.3 Sand Bedding/Padding From Borrow Pits
Description |  | per | Unit Price | Units | Amount
2.3 | Sand Bedding/Padding From Borrow Pits (Supply, load, haul, unload, place)
| a) Bedding | Per Lin. m | 89.6 | 10 | 896
| b) Padding (Top) | Per Lin. m | 114.67 |  | 0
| c) Bedding and Padding Placed As One Operation | Per Lin. m | 166.57 |  | 0
| d) Hauling (The cost of hauling to the ROW) | m3/km | 2.8 | 3360 | 9408
|  |  |  | Total | 10304
Contractor
Construction Manager
LEM
| 2016-01-04 | 21 | km one way |  | Josh | Haul sand | 0456
| 2016-01-14 | 21 |  |  | Harvey | Haul sand | 0465
|  | 42 | 80 | 3360
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Sand Bedding/Padding
Schedule C |  |  |  | Date: | 2016-01-31
Item | 2.3 Sand Bedding/Padding From Borrow Pits
Description |  | per | Unit Price | Units | Amount
2.3 | Sand Bedding/Padding From Borrow Pits (Supply, load, haul, unload, place)
| a) Bedding | Per Lin. m | 89.6 | 10 | 896
| b) Padding (Top) | Per Lin. m | 114.67 |  | 0
| c) Bedding and Padding Placed As One Operation | Per Lin. m | 166.57 |  | 0
| d) Hauling (The cost of hauling to the ROW) | m3/km | 2.8 | 5920 | 16576
|  |  |  | Total | 17472
Contractor
Construction Manager
|  | Cubes |  |  |  |  | LEM
| 2016-01-19 | 11 |  | 10 | Clint | Bedding | 1176
| 2016-01-22 | 21 |  |  | Doug | Haul sand | 0466
| 2016-01-30 | 42 |  |  | Shawn | Haul Sand
km 1 way
|  | 74 | 80 | 5920
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Sand Bedding/Padding
Schedule C |  |  |  | Date: | 2016-02-15
Item | 2.3 Sand Bedding/Padding From Borrow Pits
Description |  | per | Unit Price | Units | Amount
2.3 | Sand Bedding/Padding From Borrow Pits (Supply, load, haul, unload, place)
| a) Bedding | Per Lin. m | 89.6 |  | 0
| b) Padding (Top) | Per Lin. m | 114.67 |  | 0
| c) Bedding and Padding Placed As One Operation | Per Lin. m | 166.57 |  | 0
| d) Hauling (The cost of hauling to the ROW) | m3/km | 2.8 | 9760 | 27328
|  |  |  | Total | 27328
Contractor
Construction Manager
|  | Cubes |  |  |  |  | LEM
| 2016-01-31 | 21 |  | 80 | Shawn | Haul Sand | 0704 | missing Shawn's signature
| 2016-02-04 | 11 |  | 80 | Jerome | Haul Sand | 0337
|  | 32 | 80 | 2560
| 2016-02-03 | 15 |  | 96 | Shawn | Haul Sand | 0705
| 2016-02-03 | 15 |  | 96 | Shawn | Haul Sand | 0706
| 2016-02-01 | 15 |  | 96 | Jerome | Haul Sand | 0334
| 2016-02-12 | 30 | 2 loads | 96 | Jerome | Haul Sand | 0338
km 1 way
|  | 75 | 96 | 7200 | Total: | 9760
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Sand Bedding/Padding
Schedule C |  |  |  | Date: | 2016-02-29
Item | 2.3 Sand Bedding/Padding From Borrow Pits
Description |  | per | Unit Price | Units | Amount
2.3 | Sand Bedding/Padding From Borrow Pits (Supply, load, haul, unload, place)
| a) Bedding | Per Lin. m | 89.6 | 269 | 24102.4
| b) Padding (Top) | Per Lin. m | 114.67 | 233.4 | 26763.978
| c) Bedding and Padding Placed As One Operation | Per Lin. m | 166.57 |  | 0
| d) Hauling (The cost of hauling to the ROW) | m3/km | 2.8 | 27072 | 75801.6
|  |  |  | Total | 126667.978
Contractor
Construction Manager
| d) | Cubes | Haul Sand |  |  |  | LEM |  | a) | Bedding | [6 empty] | b) | Padding (Top)
[13 empty] | Survey | [7 empty] | Survey
| 2016-02-17 | 100 |  |  | Dwayne |  | 0531 |  | 2016-02-17 | 34654.9 | 34830.9 | 200 | 176 | Dwayne | 0531 |  | 2016-02-18 | 34654.9 | 34830.9 | 176 | 176 | Thomas | 0141
| 2016-02-18 | 145 |  |  | Thomas |  | 0141 |  |  | 34876.4 | 34933.8 |  | 57.4 | Dwayne | 0531 |  |  | 34876.4 | 34933.8 | 57.4 | 57.4 | Thomas | 0141
| 2016-02-19 | 37 |  |  | Thomas |  | 0142 |  | 2016-02-24 | 32750 | 32787 | 37 | 37 | Clint | 1179 |  |  |  |  | 0
[10 empty] | 32861 | 32893 | 32 | 32 | Clint | 1179 |  |  |  |  | 0
[12 empty] | 0 | [7 empty] | 0
[12 empty] | 0 | [7 empty] | 0
[12 empty] | 0 | [7 empty] | 0
[12 empty] | 0 | [7 empty] | 0
[12 empty] | 0 | [7 empty] | 0
[12 empty] | 0 | [7 empty] | 0
[12 empty] | 0 | [7 empty] | 0
|  |  | km 1 way | [7 empty] | Total: | 269 | [6 empty] | Total: | 233.4
|  | 282 | 96 | 27072 | Total: | 27072
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Sand Bedding/Padding
Schedule C |  |  |  | Date: | 2016-03-15
Item | 2.3 Sand Bedding/Padding From Borrow Pits
Description |  | per | Unit Price | Units | Amount
2.3 | Sand Bedding/Padding From Borrow Pits (Supply, load, haul, unload, place)
| a) Bedding | Per Lin. m | 89.6 |  | 0
| b) Padding (Top) | Per Lin. m | 114.67 |  | 0
| c) Bedding and Padding Placed As One Operation | Per Lin. m | 166.57 |  | 0
| d) Hauling (The cost of hauling to the ROW) | m3/km | 2.8 | 2100 | 5880
|  |  |  | Total | 5880
Contractor
Construction Manager
|  | Cubes | Haul Sand |  |  |  | LEM |  |  | Bedding | [7 empty] | Padding
| 2016-03-02 | 30 |  |  | Darwin Wiebe | Haul Sand | 0716 | 70 km
|  |  | km 1 way | [7 empty] | Total: | 0 | [6 empty] | Total: | 0
|  | 30 | 70 | 2100 | Total: | 2100
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Sand Bedding/Padding
Schedule C |  |  |  | Date: | 2016-04-15
Item | 2.3 Sand Bedding/Padding From Borrow Pits
Description |  | per | Unit Price | Units | Amount
2.3 | Sand Bedding/Padding From Borrow Pits (Supply, load, haul, unload, place)
| a) Bedding | Per Lin. m | 89.6 |  | 0
| b) Padding (Top) | Per Lin. m | 114.67 |  | 0
| c) Bedding and Padding Placed As One Operation | Per Lin. m | 166.57 |  | 0
| d) Hauling (The cost of hauling to the ROW) | m3/km | 2.8 | 36131.7 | 101168.76
|  |  |  | Total | 101168.76
Contractor
Construction Manager
|  |  |  | Haul Sand |  |  |  | LEM/Ticket/Company |  |  |  |  | Bedding & Padding | [5 empty] | Padding
|  | Cubes | Tonnes | KP To | KP | Inspector | UPI
| 2016-12-16 | 9 | 13.8 | 13800 | 9100 | Tyler | Haul Sand
| 2016-12-16 | 72 | 27 | 54234 | 54491 | Thomas | Haul Sand
| 2016-01-15 | 9 |  | 65538 | & 66+514 | Tyler | Haul Sand
| 2016-01-16 | 18 | 29 | 64950 |  | Clint | Haul Sand | Sureway
| 2016-01-15 | 11 |  | 65538 | 65540 | Mark | Haul Sand | Kenelson
| 2016-01-26 | 18 | Tri Drive & Tandem | 67180 | 67220 | Tyler | Haul Sand
| 2016-01-27 | 18 | Tri Drive & Tandem | 66831 | 67220 | Tyler | Haul Sand
| 2016-01-31 | 17 | 21 | 14166 | 14170 | Shawn | Haul Sand
| 2016-02-03 | 15 | 16 | 33361 | 33397 | Shawn | Haul Sand | 0705- Jersey Developments
| 2016-02-08 | 18 | 32 | 5701 |  | Jerome | Haul Sand | 141994
| 2016-02-09 | 18 |  | 68615 |  | Dennis | Haul Sand
| 2016-02-11 | 10.5 | 16 | 6159 |  | Shawn | Haul Sand | 141933 | Jersey Developments unit 400
| 2016-02-12 | 10.5 |  | 31309 | 31289 | Dennis | Haul Sand | Jersey Developments
| 2016-02-15 | 10.5 | 16 | 17067 |  | Shawn | Haul Sand | 141701 | Jersey Developments
| 2016-02-16 | 10.5 | 16 | 50102 |  | Shawn | Haul Sand | 141702 | Jersey Developments
| 2016-02-18 | 10.5 |  | 57205 |  | Dennis | Haul Sand
| 2016-02-18 | 10.5 |  | 57205 |  | Dennis | Haul Sand
| 2016-02-24 | 10.5 | 16 | 47473 |  | Dennis | Haul Sand
| 2016-02-24 | 10.5 | 16 | 47473 |  | Dennis | Haul Sand
| 2016-03-01 | 10.5 | 16 | 42715 | 42709 | Shawn | Haul Sand |  | Jersey Developments
| 2016-03-02 | 10.5 | 16 | 42715 | 42709 | Shawn | Haul Sand |  | Jersey Developments
| 2016-03-02 | 10.5 | 16 | 40173 | 40211 | Shawn | Haul Sand |  | Jersey Developments unit 400
| 2016-04-02 | 18 |  | 24750 | 24943 | Clint | 2 loads sand to Rd 9 (22+846 for KP 24+750-24+943 sight holes
|  |  |  | km 1 way | Total: | [7 empty] | 0 | [6 empty] | Total: | 0
|  | 356.5 |  | 90 | 32085 | Total
| 2016-04-12 | 11 | 16 | 39228 |  | Jerome | 1 load sand
| 2016-04-14 | 39.5838 | 57 | 39165 | 39206 | Doug | 4 loads sand | 1609 |  |  |  |  | 41 | 39165 | 39206 |  | missed on last billing
|  |  |  | km 1 way | Total: | [7 empty] | 41 | [6 empty] | Total: | 0
|  | 50.5838 |  | 80 | 4046.7 | Total
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Sand Bedding/Padding
Schedule C |  |  |  | Date: | 2016-04-30
Item | 2.3 Sand Bedding/Padding From Borrow Pits
Description |  | per | Unit Price | Units | Amount
2.3 | Sand Bedding/Padding From Borrow Pits (Supply, load, haul, unload, place)
| a) Bedding | Per Lin. m | 89.6 |  | 0
| b) Padding (Top) | Per Lin. m | 114.67 |  | 0
| c) Bedding and Padding Placed As One Operation | Per Lin. m | 166.57 | 228 | 37977.96
| d) Hauling (The cost of hauling to the ROW) | m3/km | 2.8 | 13520 | 37856
|  |  |  | Total | 75833.96
Contractor
Construction Manager
|  |  |  | Haul Sand |  |  |  | LEM/Ticket/Company |  |  |  |  | Bedding & Padding | [6 empty] | Padding
|  | Cubes | Tonnes | KP To | KP | Inspector | UPI | [5 empty] | KP To | KP |  | Survey | Inspector | UPI
| 2016-04-24 | 169 |  | 69318 | 69432 | Dwayne | 1611 |  |  | Volume doubled as per Pembina Integrity request |  | 2016-04-24 | 69318 | 69432 | 114 |  | Dwayne | 1611
[12 empty] | 2016-04-24 | 69318 | 69432 | 114 |  | Dwayne | 1611
|  |  |  | km 1 way | Total: | [8 empty] | Total: | 228 | [5 empty] | Total: | 0
|  | 169 |  | 80 | 13520 | Total
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Sand Bedding/Padding
Schedule C |  |  |  | Date: | 2016-05-15
Item | 2.3 Sand Bedding/Padding From Borrow Pits
Description |  | per | Unit Price | Units | Amount
2.3 | Sand Bedding/Padding From Borrow Pits (Supply, load, haul, unload, place)
| a) Bedding | Per Lin. m | 89.6 | 88 | 7884.8
| b) Padding (Top) | Per Lin. m | 114.67 | 48 | 5504.16
| c) Bedding and Padding Placed As One Operation | Per Lin. m | 166.57 | 20 | 3331.4
| d) Hauling (The cost of hauling to the ROW) | m3/km | 2.8 | 17888 | 50086.4
|  |  |  | Total | 66806.76
Contractor
Construction Manager
|  |  |  | Haul Sand |  |  |  | LEM/Ticket/Company |  |  |  |  | Bedding & Padding c) | [6 empty] | Padding b) | [6 empty] | Bedding a)
[30 empty] | Survey | Inspector | UPI
|  | Cubes | Tonnes | KP To | KP | Inspector | UPI | [5 empty] | KP To | KP |  | Survey | Inspector | UPI |  |  |  |  | Survey | Inspector | UPI
| 2016-03-21 | 11 |  | 46270 |  |  | 1929 | [7 empty] | 0
| 2016-03-23 | 11 |  | 69425 |  |  | 1927 | [7 empty] | 0
| 2016-03-23 | 18 |  | 39+300 |  |  | 1930 | [7 empty] | 0 | [10 empty] | 2016-03-23 | 39300 | 39360 | 60 | no back up | Jason | 1930
| 2016-04-01 | 58 |  | 25038 |  |  | 1928 | [7 empty] | 0
| 2016-04-29 | 125.6 | 180.8 | 67396 | 67665 |  | 1932 | back up is good | [6 empty] | 0 | [13 empty] | 0
| 2016-05-01 | [10 empty] | 2016-05-01 | 67638 | 67643 | 5 |  | Dwayne | 1652 | 2016-05-01 | 67388 | 67400 | 12 |  | Dwayne | 1652 | 2016-05-01 | 67391 | 67399 | 8 |  | Dwayne | 1652
[13 empty] | 67653 | 67668 | 15 |  | Dwayne | 1652 |  | 67418 | 67431 | 13 |  | Dwayne | 1652 |  | 67418 | 67426 | 8 |  | Dwayne | 1652
[20 empty] | 67512 | 67526 | 14 |  | Dwayne | 1652 |  | 67520 | 67526 | 6 |  | Dwayne | 1652
[20 empty] | 67566 | 67575 | 9 |  | Dwayne | 1652 |  | 67566 | 67572 | 6 |  | Dwayne | 1652
[15 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[15 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[15 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[14 empty] | Total: | 20 | [5 empty] | Total: | 48 | [5 empty] | Total: | 88
|  |  |  | km 1 way | Total:
|  | 223.6 |  | 80 | 17888 | Total
| Checker |  |  | Haul Sand |  |  |  | LEM/Ticket/Company |  |  |  |  | Bedding & Padding | [6 empty] | Padding | [6 empty] | Bedding
[30 empty] | Survey | Inspector | UPI
|  | Cubes | Tonnes | KP To | KP | Inspector | UPI | [5 empty] | KP To | KP |  | Survey | Inspector | UPI |  |  |  |  | Survey | Inspector | UPI
| 2016-05-07 | 45 | ?? |  |  | Tim | 1828 |  |  |  |  | 2016-05-07 | 8245.4 | 8251.9 | 6.5 | 6.5 | Tim | 1828 | 2016-05-07 | 8163.5 | 8175.5 | 12 | 20.5 | Tim | 1828 | 2016-05-07 | 8251.9 | 8256.9 | 5 | None | Tim | 1828
[13 empty] | 8175.5 | 8184 | 8.5 | 8.5 | Tim | 1828 |  |  |  | 0 | [6 empty] | 5
| 2016-05-10 | 220 | 20 loads | 6428 | 6478 | Tim | 1653 |  |  |  |  | 2016-05-10 | 6428 | 6478 | 50 | 59 | Tim | 1653 |  |  |  | 0 | [6 empty] | 0
| 2016-05-13 | 22 | 2 tri-drives | 37751 | 37761 | [6 empty] | 2016-05-13 | 37751 | 37761 | 10 |  | Tyler |  |  |  |  | 0 | [6 empty] | 0
[12 empty] | 2016-05-13 | 37679 | 37694 | 15 | 15
| 2016-05-14 | 11 |  | 29375 | 29391 | [6 empty] | 2016-05-14 | 29375 | 29391 | 16 |  | Tyler |  |  |  |  | 0 | [6 empty] | 0
| 2016-05-07 | [13 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[22 empty] | 0 | [6 empty] | 0
[15 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[14 empty] | Total: | 106 | 166.57 |  | 17656.42 |  |  | Total: | 12 | 114.67 |  | 1376.04 |  |  | Total: | 10 | 89.6 |  | 896
|  |  |  | km 1 way | Total:
|  | 298 |  | 80 | 23840 | Total |  | 2.8 |  | 66752
19928.46

## 2.11
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  | Date: | 2016-04-15
Item | 2.11 Clean Washed Gravel
Description |  | Per |  | Amount
2.11 | Clean Washed Gravel
| To supply load and place well graded, clean, washed gravel with particle size between 25 mm and 50 mm from contractor sourced borrow pits and pre-approved by the company, as requested by Company. | Cost Plus |  | 7658.4 | Ticket: 1468, 1469 | 7658.4
| Haul (The cost of hauling to the ROW. Pits and haul distance approved by the Company) | Cost Plus |  | 1218 |  | 8876.4
|  |  | Total | 8876.4
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  | Date: | 2016-05-15
Item | 2.11 Clean Washed Gravel
Description |  | Per |  | Amount
2.11 | Clean Washed Gravel
| To supply load and place well graded, clean, washed gravel with particle size between 25 mm and 50 mm from contractor sourced borrow pits and pre-approved by the company, as requested by Company. | Cost Plus |  | 0 | Ticket:
| Haul (The cost of hauling to the ROW. Pits and haul distance approved by the Company) | Cost Plus |  | 0
|  |  | Total | 0
Contractor
Construction Manager

## 2.14
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Billing Date: | 2015-12-15
Item | 2.14 Install Pipe To Extra Depth
Description |  | per | Unit Price | Units | Billing Amount
2.14 | Install Pipe To Extra Depth
| a) 0.30 m total extra depth | per lin. M. | 10
| b) 0.60 m total extra depth | per lin. M. | 14 | 60 | 840
| C) 0.90 m total extra depth | per lin. M. | 19
| d) 1.20 m total extra depth | per lin. M. | 24
| e) 1.50 m total extra depth | per lin. M. | 39
|  |  |  | Total | 840
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Billing Date: | 2015-12-31
Item | 2.14 Install Pipe To Extra Depth
Description |  | per | Unit Price | Units | Billing Amount
2.14 | Install Pipe To Extra Depth
| a) 0.30 m total extra depth | per lin. M. | 10
| b) 0.60 m total extra depth | per lin. M. | 14
| C) 0.90 m total extra depth | per lin. M. | 19
| d) 1.20 m total extra depth | per lin. M. | 24
| e) 1.50 m total extra depth | per lin. M. | 39 | 12 | 468
|  |  |  | Total | 468
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Billing Date: | 2016-04-30
Item | 2.14 Install Pipe To Extra Depth
Description |  | per | Unit Price | Units | Billing Amount
2.14 | Install Pipe To Extra Depth
| a) 0.30 m total extra depth | per lin. M. | 10 | 23.606 | 236.06 | 5.99 | 10.069 | 3.447 | 4.1 | 23.606
| b) 0.60 m total extra depth | per lin. M. | 14 | 3.449 | 48.286 | 1.259 | 2.19 |  |  | 3.449
| C) 0.90 m total extra depth | per lin. M. | 19
| d) 1.20 m total extra depth | per lin. M. | 24
| e) 1.50 m total extra depth | per lin. M. | 39
|  |  | Total: | 27.055
|  |  |  | Total | 284.346
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Billing Date: | 2016-05-15
Item | 2.14 Install Pipe To Extra Depth
Description |  | per | Unit Price | Units | Billing Amount
2.14 | Install Pipe To Extra Depth
| a) 0.30 m total extra depth | per lin. M. | 10 |  | 0
| b) 0.60 m total extra depth | per lin. M. | 14 |  | 0
| C) 0.90 m total extra depth | per lin. M. | 19
| d) 1.20 m total extra depth | per lin. M. | 24
| e) 1.50 m total extra depth | per lin. M. | 39
|  |  | Total: | 0
|  |  |  | Total | 0
Contractor
Construction Manager

## 2.18
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2015-12-15
Item | 2.18 Vehicle & Equipment Wash Stations
Description |  | per | Unit Price | Units | Amount
2.18 | b) Winter Wash
| i) Operating the wash station (Hot Steamer) | Per Day | 1625 | 5 | 8125
| ii) Installation of wash stations (load, haul, assemble) | Per Station | 7785 | 0.33333 | 2594.9974
| iii) Removal of wash station (load, haul, take down) | Per Station | 3960 |  | 0
|  |  |  | Total | 10719.9974
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-05-15
Item | 2.18 Vehicle & Equipment Wash Stations
Description |  | per | Unit Price | Units | Amount
2.18 | b) Winter Wash
| i) Operating the wash station (Hot Steamer) | Per Day | 1625 |  | 0
| ii) Installation of wash stations (load, haul, assemble) | Per Station | 7785 |  | 0
| iii) Removal of wash station (load, haul, take down) | Per Station | 3960 |  | 0
|  |  |  | Total | 0
Contractor
Construction Manager

## 2.22
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-02-15
Item | 2.22 Cut Out And Replace Welds
Description |  | per | Unit Price | Units | Billing Amount
2.22 | To cut out and replace welds rings, including | per weld | 3890 | 2 | 7780
re-bevelling of two (2) pipe ends at request of
Company
|  |  |  | Total | 7780
Contractor
Construction Manager
UPI Report
|  | KP 26+027 | 0563 | Lorne
|  | KP 54+510 | 1152 | Cliff
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-02-29
Item | 2.22 Cut Out And Replace Welds
Description |  | per | Unit Price | Units | Billing Amount
2.22 | To cut out and replace welds rings, including | per weld | 3890 | 1 | 3890 | KP 46+890- TICKET 1302
re-bevelling of two (2) pipe ends at request of
Company
|  |  |  | Total | 3890
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-05-15
Item | 2.22 Cut Out And Replace Welds
Description |  | per | Unit Price | Units | Billing Amount
2.22 | To cut out and replace welds rings, including | per weld | 3890 |  | 0
re-bevelling of two (2) pipe ends at request of
Company
|  |  |  | Total | 0
Contractor
Construction Manager

## 2.27
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-05-15
Item | 2.27 Erosion Control Mat
Description |  | per | Unit Price | Units | Billing Amount
2.27 | Supply & Install Erosion Control Mat When | per m2 | 13.23 | 208 | 2751.84
Requested By The Company
SITE UPI Report# 0477
|  |  |  | Total | 2751.84
Contractor
Construction Manager

## 2.29
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2015-12-31
Item | 2.29 Rig Mats
Description |  | per | Unit Price | Units | Amount
2.29 | Rig Mats | [5 empty] | 2016-12-31 | 2016-01-10
| Oak Interlocking Mats | per mat | 4.5 | 15876 | 71442 |  | 15876 | 21276
| Rig mats complete with metal frame (appox. 8' x 20') | per mat | 45 |  | 0
|  |  |  | Total | 71442
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-01-15 |  | Need to enter the difference:
Item | 2.29 Rig Mats
Description |  | per | Unit Price | Units | Amount |  | Previous
2.29 | Rig Mats | [5 empty] | 2016-12-31 | 2016-01-15
| Oak Interlocking Mats | per mat | 4.5 | 8100 | 36450 |  | 15876 | 8100
| Rig mats complete with metal frame (appox. 8' x 20') | per mat | 45 |  | 0
|  |  |  | Total | 36450
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-01-31 |  | Need to enter the difference:
Item | 2.29 Rig Mats
Description |  | per | Unit Price | Units | Amount |  | Previous
2.29 | Rig Mats | [5 empty] | 2016-12-31 | 2016-01-15 | 2016-01-31 | 2016-02-15 | To Date:
| Oak Interlocking Mats | per mat | 4.5 | 8640 | 38880 |  | 15876 | 8100 | 8640 |  | 32616
| Rig mats complete with metal frame (appox. 8' x 20') | per mat | 45 |  | 0 |  | 71442 | 36450 | 38880 |  | 146772
|  |  |  | Total | 38880
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-02-15 |  | Need to enter the difference:
Item | 2.29 Rig Mats
Description |  | per | Unit Price | Units | Amount |  | Previous
2.29 | Rig Mats | [5 empty] | 2016-12-31 | 2016-01-15 | 2016-01-31 | 2016-02-15 | To Date:
| Oak Interlocking Mats | per mat | 4.5 | 2700 | 12150 |  | 15876 | 8100 | 8640 | 2700 | 35316
| Rig mats complete with metal frame (appox. 8' x 20') | per mat | 45 |  | 0 |  | 71442 | 36450 | 38880 | 12150 | 158922
Pulled out on the 6th.
|  |  |  | Total | 12150
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-03-31 |  | Need to enter the difference:
Item | 2.29 Rig Mats
2016-03-31
Description |  | per | Unit Price | Units | Amount | CNRL | 1237 & 1238: | 1350
2.29 | Rig Mats
| Oak Interlocking Mats | per mat | 4.5 | 1398 | 6291 | 30+551 Frac | 2980,0982,0984,0986: | 48
| Rig mats complete with metal frame (appox. 8' x 20') | per mat | 45 |  | 0 |  |  | 1398
|  |  |  | Total | 6291
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-04-15
Item | 2.29 Rig Mats
2016-04-15
Description |  | per | Unit Price | Units | Amount | CNRL |  | 1275
2.29 | Rig Mats
| Oak Interlocking Mats | per mat | 4.5 | 1275 | 5737.5
| Rig mats complete with metal frame (appox. 8' x 20') | per mat | 45 |  | 0 |  |  | 1275
|  |  |  | Total | 5737.5
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-04-30
Item | 2.29 Rig Mats
2016-04-30
Description |  | per | Unit Price | Units | Amount | CNRL
2.29 | Rig Mats
| Oak Interlocking Mats | per mat | 4.5 | 340 | 1530
| Rig mats complete with metal frame (appox. 8' x 20') | per mat | 45 |  | 0 |  |  | 0
|  |  |  | Total | 1530
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-05-15
Item | 2.29 Rig Mats
2016-04-30
Description |  | per | Unit Price | Units | Amount | CNRL
2.29 | Rig Mats
| Oak Interlocking Mats | per mat | 4.5 |  | 0
| Rig mats complete with metal frame (appox. 8' x 20') | per mat | 45 |  | 0 |  |  | 0
|  |  |  | Total | 0
Contractor
Construction Manager

## 2.31
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-01-31
Item | 2.31 Move Around
Description |  | per | Unit Price | Units | Amount
2.31 | Move Around- Bending
| a) Within 10 km of ROW | Crew | 4500 | 1 | 4500 | 2016-12-12 | 56+109- Bending Part crew move around so within 10 km of ROW used
| b) 10 to -25 km of ROW | Crew | 8200 |  |  |  | KP 51+500 to 61+800 area
|  |  |  | Total | 4500
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-02-29
Item | 2.31 Move Around
[6 empty] | 2016-02-09 | 48+800-Grade- Move Around Bear Den |  |  | 0763 | 3400
Description |  | per | Unit Price | Units | Amount | 2016-02-24 | 48+800-Bending- Move Around Bear Den |  |  | 0229/0229 | 4500 | 4500
2.31 | Move Around- Bending |  |  |  |  | 2016-02-25 | 48+800-Welding- Move Around Bear Den |  |  |  | 11050 | 11050
| a) Within 10 km of ROW | Crew | 4500 | 1 | 4500 | 2016-02-26 | 48+800-Coating- Move Around Bear Den |  |  | 0281 | 4500 | 4500
| b) 10 to -25 km of ROW | Crew | 8200 |  | 0 | 2016-02-29 | 48+800-Ditching- Move Around Bear Den |  |  | 0765 | 10500
| Move Around- Welding |  |  |  |  | 2016-02-29 | 48+800-Lower-In- Move Around Bear Den |  |  | 0766 | 9000
| a) Within 10 km of ROW | Crew | 11050 | 1 | 11050 | 2016-03-01 | 48+800-Backfill- Move Around Bear Den |  |  | 0144 | 9000
| b) 10 to -25 km of ROW | Crew | 17600 |  | 0 |  |  | test |  |  | 4500
| Move Around- Coating | [6 empty] | Tie-ins | 4 crew- 9,000 |  | 27000
| a) Within 10 km of ROW | Crew | 4500 | 1 | 4500 |  |  | Initial clean up |  |  | 12000
| b) 10 to -25 km of ROW | Crew | 8200 |  | 0 |  |  | final Clean up |  |  | 12000
|  |  |  | Total | 20050 | [5 empty] | 107450 | 20050
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-03-15
Item | 2.31 Move Around
[6 empty] | 2016-02-09 | 48+800-Grade- Move Around Bear Den |  |  | 0763 | 3400 | 3400
Description |  | per | Unit Price | Units | Amount | 2016-02-24 | 48+800-Bending- Move Around Bear Den |  |  | 0229/0229 | 4500 |  | paid Feb 29
2.31 | Move Around- Grading |  |  |  |  | 2016-02-25 | 48+800-Welding- Move Around Bear Den |  |  |  | 11050 |  | paid Feb 29
| a) Within 10 km of ROW | Crew | 10500 | 0.32381 | 3399.9987 | 2016-02-26 | 48+800-Coating- Move Around Bear Den |  |  | 0281 | 4500 |  | paid Feb 29
| b) 10 to -25 km of ROW | Crew | 16400 |  | 0 | 2016-02-29 | 48+800-Ditching- Move Around Bear Den |  |  | 0765 | 10500 | 10500
| Move Around- Trenching |  |  |  |  | 2016-02-29 | 48+800-Lower-In- Move Around Bear Den |  |  | 0766 | 9000 | 9000
| a) Within 10 km of ROW | Crew | 10500 | 1 | 10500 | 2016-03-01 | 48+800-Backfill- Move Around Bear Den |  |  | 0144 | 9000 | 9000
| b) 10 to -25 km of ROW | Crew | 16400 |  | 0 |  |  | test |  |  | 4500
| Move Around- Lower-In | [6 empty] | Tie-ins | 4 crew- 9,000 |  | 27000
| a) Within 10 km of ROW | Crew | 9000 | 1 | 9000 |  |  | Initial clean up |  |  | 12000
| b) 10 to -25 km of ROW | Crew | 15200 |  | 0 |  |  | final Clean up |  |  | 12000
| Move Around- Backfill | [9 empty] | 107450 | 31900
| a) Within 10 km of ROW | Crew | 9000 | 1 | 9000
| b) 10 to -25 km of ROW | Crew | 15200 |  | 0
|  |  |  | Total | 31899.9987
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-04-30
Item | 2.31 Move Around
[6 empty] | 2016-02-09 | 48+800-Grade- Move Around Bear Den |  |  | 0763 | 3400 | 3400 | paid Mar 15
Description |  | per | Unit Price | Units | Amount | 2016-02-24 | 48+800-Bending- Move Around Bear Den |  |  | 0229/0229 | 4500 |  | paid Feb 29
2.31 | Move Around- Tie-Ins |  |  |  |  | 2016-02-25 | 48+800-Welding- Move Around Bear Den |  |  |  | 11050 |  | paid Feb 29
| a) Within 10 km of ROW | Crew | 9000 | 2 | 18000 | 2016-02-26 | 48+800-Coating- Move Around Bear Den |  |  | 0281 | 4500 |  | paid Feb 29
| b) 10 to -25 km of ROW | Crew | 15200 |  | 0 | 2016-02-29 | 48+800-Ditching- Move Around Bear Den |  |  | 0765 | 10500 | 10500 | paid Mar 15
[6 empty] | 2016-02-29 | 48+800-Lower-In- Move Around Bear Den |  |  | 0766 | 9000 | 9000 | paid Mar 15
[6 empty] | 2016-03-01 | 48+800-Backfill- Move Around Bear Den |  |  | 0144 | 9000 | 9000 | paid Mar 15
[8 empty] | test |  |  | 4500
[6 empty] | 2016-03-13 |  | Tie-ins | 4 crew- 9,000 | 1454 | 27000 | 18000
[8 empty] | Initial clean up |  |  | 12000
[8 empty] | final Clean up |  |  | 12000
[11 empty] | 107450 | 49900
|  |  |  | Total | 18000
Contractor
Construction Manager
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-05-15
Item | 2.31 Move Around
[6 empty] | 2016-02-09 | 48+800-Grade- Move Around Bear Den |  |  | 0763 | 3400 | 3400 | paid Mar 15
Description |  | per | Unit Price | Units | Amount | 2016-02-24 | 48+800-Bending- Move Around Bear Den |  |  | 0229/0229 | 4500 |  | paid Feb 29
2.31 | Move Around- Tie-Ins |  |  |  |  | 2016-02-25 | 48+800-Welding- Move Around Bear Den |  |  |  | 11050 |  | paid Feb 29
| a) Within 10 km of ROW | Crew | 9000 |  | 0 | 2016-02-26 | 48+800-Coating- Move Around Bear Den |  |  | 0281 | 4500 |  | paid Feb 29
| b) 10 to -25 km of ROW | Crew | 15200 |  | 0 | 2016-02-29 | 48+800-Ditching- Move Around Bear Den |  |  | 0765 | 10500 | 10500 | paid Mar 15
[6 empty] | 2016-02-29 | 48+800-Lower-In- Move Around Bear Den |  |  | 0766 | 9000 | 9000 | paid Mar 15
[6 empty] | 2016-03-01 | 48+800-Backfill- Move Around Bear Den |  |  | 0144 | 9000 | 9000 | paid Mar 15
[8 empty] | test |  |  | 4500
[6 empty] | 2016-03-13 |  | Tie-ins | 4 crew- 9,000 | 1454 | 27000 | 18000
[8 empty] | Initial clean up |  |  | 12000
[8 empty] | final Clean up |  |  | 12000
[11 empty] | 107450 | 49900
|  |  |  | Total | 0
Contractor
Construction Manager

## 2.35
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Schedule C |  |  |  | Date: | 2016-05-15
Item | 2.35 Crossings Under Existing Buried Pipelines
Description |  | per | Unit Price | Units | Amount
2.35 | Crossings Under Existing Buried Pipelines
| Add per crossing | Crossing | 18360 | 3 | 55080
|  |  |  | Total | 55080
Contractor
Construction Manager

## 3.2.2-2A
PIPELINE PROJECT
3.0 INCREMENTAL LUMP SUM
Schedule C |  |  |  |  | Billing Date: | 2016-05-15
Item | HDD and Brored Crossing Lump Sum Prices for 12" Oil Line Segment
Description |  | per | Unit Price | Previous | Units | Billing Amount
2A-C.1 | NPS 12 HDD Crossing Installation- Bow River | Lump Sum | 344650 | 1 |  | 0
2A-C.2 | NPS 12 HDD Crossing Installation- Irrigation Canal & Reservoir | Lump Sum | 286300 | 1
2A-C.3 | NPS 12 HDD Crossing Installation- Secondary Hwy 524 | Lump Sum | 18000 | 1
2A-C.4 | NPS 12 HDD Crossing Installation- Secondary Hwy 875 | Lump Sum | 18000 | 1
2A-C.5 | NPS 12 HDD Crossing Installation- Old Man River | Lump Sum | 386350 | 1
[5 empty] | Total | 0
Contractor
Construction Manager

## 3.1.2-2A
PIPELINE PROJECT
3.0 INCREMENTAL LUMP SUM
Schedule C |  |  |  | Billing Date: | 2016-05-15
Item | Fabricated Assembly Lump Sum Prices For 12" Oil Line Segment
Description |  | per | Unit Price | Previous | Units | Billing Amount
2A-B.1 | Fabricate Test & Install NPS 12 Mainline Block Valve Assembly | Lump Sum | 25050 | 1 |  | 0
2A-B.2 | Fabricate Test & Install NPS 12 Mainline Block Valve & Check Valve Assembly | Lump Sum | 28650 | 1 |  | 0
[5 empty] | Total | 0
Contractor
Construction Manager

## 4.1
PIPELINE PROJECT
UNIT PRICE ITEM SUMMARY
Topsoil Stripping & Replacement
Schedule C | [5 empty] | Billing Date: | 2016-05-15
Item | 4.1
Description |  | per | Unit Price | Units Stripped | Units Replaced | Total Units | Amount This Period
4.1 | Topsoil Stripping And Replacement
4.1.1 | Removal and restoration of topsoil over trench area (blade width stripping)
| a) 0 to 40 cm in depth | Per Lin. m | 3.5 |  |  | 0 | 0
| b) 40 cm and greater | Per Lin. m | 4.5 |  |  | 0 | 0
4.1.2 | Removal and restoration of topsoil over trench and spoil side area
| a) 0 to 40 cm in depth | Per Lin. m | 6.5 |  |  | 0 | 0
| b) 40 cm and greater | Per Lin. m | 9.5 |  |  | 0 | 0
4.1.3 | Removal and restoration of topsoil over the entire Construction Right of Way
| a) 0 to 40 cm in depth | Per Lin. m | 9.5 |  |  | 0 | 0
| b) 40 cm and greater | Per Lin. m | 12.5 |  |  | 0 | 0
|  |  |  | Total |  | 0 | 0
Contractor
Construction Manager

## RFI's
RFI Log
Expansion Pipeline Project |  |  |  |  | Date: | 2016-05-15
Request for Information (RFI)
RFI # | Description | Originator | Date Issued | Reply Date Required | Status | Cost Impact | Change Order Request | Change Order (if applicable) | RFI Complete
W2K-RFI-0001 | Additional HDD Location | Mark Ringrose | 2015-11-03 | 2015-11-03 | Approved |  |  |  | Complete
W2K-RFI-0002 | Harvest Crossing and Road Use Agreements | Mark Ringrose | 2015-11-03 | 2015-11-09 | Approved |  |  |  | Complete
W2K-RFI-0003 | Road Allowance Workspace | Mark Ringrose | 2015-11-04 | 2015-11-10 | Approved |  |  |  | Complete
W2K-RFI-0004 | Corinthian Access Roads & Pipeline Crossings- Crossing & Proximity Agreements | Mark Ringrose | 2015-11-04 | 2015-11-16 | Approved |  |  |  | Complete
W2K-RFI-0005 | Depth of Cover at Ephemeral Draws and Intermittent Creek Crossings | Mark Ringrose | 2015-11-06 | 2015-11-10 | Approved |  |  |  | Complete
W2K-RFI-0006 | Slashing Standby | Kendall O'Regan | 2015-11-06 | 2015-11-09 | N/A | 12805 |  |  | Complete
W2K-RFI-0007 | Purchase Of Two-Way Radios | Kendall O'Regan | 2015-11-06 | 2015-11-09 | Approved | 6751 |  | CO2 | Complete
W2K-RFI-0008 | Weather Conditions & Winter Welding | Andrew Elash | 2015-11-06 | 2015-11-10 | Not Approved |  |  |  | Complete
W2K-RFI-0009 | Typical Construction Drawings | Andrew Elash | 2015-11-06 | 2015-11-10 | Approved |  |  |  | Complete
W2K-RFI-0010 | Additional TFA For ROW Access | Mark Ringrose | 2015-11-06 | 2015-11-10 | Approved |  |  |  | Complete
W2K-RFI-0011 | Welder Testing- Line Up Clamps | Andrew Elash | 2015-11-06 | 2015-11-10 | Approved |  |  |  | Complete
W2K-RFI-0012R1 | Removal Of Pipe Clamps During Hot Pass | Andrew Elash | 2015-12-23 | 2015-12-31 | Responded |  |  |  | Complete
W2K-RFI-0013 | Minimum Tie Install Temperature | Andrew Elash | 2015-11-06 | 2015-11-10 | Approved |  |  |  | Complete
W2K-RFI-0014 | Pipe & Bend MTRs | Andrew Elash | 2015-11-06 | 2015-11-10 | Approved |  |  |  | Complete
W2K-RFI-0015R3 | Project Delay Indirect Costs, Equipment Costs & Foremen Retention | Kendall O'Regan | 2015-11-10 | 2015-11-12 | Approved | 555229.22 |  | CO5 | Complete
W2K-RFI-0016 | Combine Typical Drills #6 (38+390) & #7 (38+606) | Andrew Elash | 2015-11-11 | 2015-11-16 | Approved |  |  |  | Complete
W2K-RFI-0017R1 | Extend Bore At KP 22+821 | Andrew Elash | 2015-11-11 | 2015-11-16 | Approved |  |  |  | Complete
W2K-RFI-0018 | Extra Work Space Required For HDD At KP 26+759 | Andrew Elash | 2015-11-11 | 2015-11-16 | Approved |  |  |  | Complete
W2K-RFI-0019R1 | Husky Road Use Agreement Required For Husky Roads | Andrew Elash | 2015-11-12 | 2015-11-16 | Approved |  |  |  | Complete
W2K-RFI-0020 | Clearing Support: Change Request CR-0001 Proposal | Mark Ringrose | 2015-11-19 | 2015-11-21 | Approved |  |  | CO3 | Complete
W2K-RFI-0021 | Sand Blasting Abrasive | Andrew Elash | 2015-11-19 | 2015-11-20 | Approved |  |  |  | Complete
W2K-RFI-0022 | Hydro Test Pressure | Andrew Elash | 2015-11-19 | 2015-11-20 | Approved |  |  |  | Complete
W2K-RFI-0023 | CNRL Pipeline Crossings | Kristen Jones | 2015-11-19 | 2015-11-24 | Approved |  |  |  | Complete
W2K-RFI-0024 | Hauling Of Stripped Topsoil | Mark Ringrose | 2015-11-20 | 2015-11-24 | Not Approved | 34974.24 |  |  | Complete
W2K-RFI-0025 | Extended Bore KP 57+204 | Mark Ringrose | 2015-11-20 | 2015-11-24 | Approved |  |  |  | Complete
W2K-RFI-0026R1 | 24Hr Medic Coverage | Mark Ringrose | 2015-11-23 | 2015-11-25 | Approved | 103635 |  | CO4 | Complete
W2K-RFI-0027
W2K-RFI-0028 | River Pull Back (Over Bend Radius) | Mark Ringrose | 2015-11-23 | 2015-11-25 | Approved |  |  |  | Complete
W2K-RFI-0029 | Approval To Use Methanol For HDD Pre-Tests | Mark Ringrose | 2015-11-23 | 2015-11-25 | Approved |  |  |  | Complete
W2K-RFI-0030R1 | Atco Power Pole At 8+221 | Mark Ringrose | 2015-11-23 | 2015-11-25 | Approved |  |  |  | Complete
W2K-RFI-0031 | Removal Of USM & Topsoil | Mark Ringrose | 2015-11-23 | 2015-11-25 | Approved |  |  |  | Complete
W2K-RFI-0032 | Sump Pit Excavation- Test Holes | Mark Ringrose | 2015-11-26 | 2015-11-27 | Approved | 20000 |  | CO9 | Complete
W2K-RFI-0033 | Minimum Separation During HDD | Mark Ringrose | 2015-11-30 | 2015-12-01 | Reviewed |  |  |  | Complete
W2K-RFI-0034 | Trucking Mats To Cutbank HDD | Mark Ringrose | 2015-12-01 | 2015-12-03 | Approved | 76820 |  | CO10 | Complete
W2K-RFI-0035 | Atco Power Pole At 14+157 | Mark Ringrose | 2015-12-01 | 2015-12-04 | Approved |  |  |  | Complete
W2K-RFI-0036 | Proposed Ditch Line KP 52+445 | Mark Ringrose | 2015-12-02 | 2015-12-03 | Approved |  |  |  | Complete
W2K-RFI-0037 | HD Bore Live Line Separations | Mark Ringrose | 2015-12-03 | 2015-12-05 | Approved |  |  |  | Complete
W2K-RFI-0038R2 | NuVista Riser | Mark Ringrose | 2015-12-01 | 2015-12-04 | No Response | 9586.06 |  |  | Complete
W2K-RFI-0039 | Red One Rock Shield In Lieu of Tuff-N-Nuff | Mark Ringrose | 2015-12-03 | 2015-12-07 | Approved |  |  |  | Complete
W2K-RFI-0040 | Crossing Agreement SE-11-68-8 W6M | Mark Ringrose | 2015-12-05 | 2015-12-05 | Approved |  |  |  | Complete
W2K-RFI-0041 | Direct Drilling Support (440 Rig) | Mark Ringrose | 2015-12-07 | 2015-12-14 | Not Approved |  |  |  | Complete
W2K-RFI-0042 | Digging Sumps | Mark Ringrose | 2016-12-08 | 2016-12-11 | Approved |  |  | CO11 & CO43 | Complete
W2K-RFI-0043 | Lowering In Deviation | Mark Ringrose | 2015-12-08 | 2015-12-10 | Approved |  |  |  | Complete
W2K-RFI-0044 | Unload Pembina Owned Mats | Mark Ringrose | 2016-01-19 | 2016-01-20 | Approved | 19408 |  | CO17 | Complete | 19.41/mat
W2K-RFI-0045 | Bentonite | Mark Ringrose | 2015-12-08 | 2015-12-10 | Not Approved |  |  |  | Complete
W2K-RFI-0046 | Performance Vac- Mud Disposal | Mark Ringrose | 2015-12-10 | 2015-12-12 | Not Approved | 50000 |  | CO12 | Complete
W2K-RFI-0047
W2K-RFI-0048 | Rework Due To Survey Error | Mark Ringrose | 2015-12-12 | 2015-12-13 | Approved | 4250.2 |  | CO13 | Complete
W2K-RFI-0049 | Cost Estimate Holiday Support | Mark Ringrose | 2015-12-21 | 2015-12-23 | No Response From SITE | 175603.32 |  |  | Complete
W2K-RFI-0050 | Miscellaneous Extra Works | Mark Ringrose | 2015-12-16 | 2015-12-18 | Approved |  |  | CO14 | Ongoing
W2K-RFI-0051 | New Weld Procedure | Mark Ringrose | 2015-12-16 | 2015-12-18 | Approved |  |  |  | Complete
W2K-RFI-0052 | Extended Bore KP 67+800 | Mark Ringrose | 2015-12-17 | 2015-12-21 | Approved |  |  |  | Complete
W2K-RFI-0053R2 | Extended Bore KP 24+539 to 24+942 | Mark Ringrose | 2015-12-18 | 2015-12-21 | Partly Approved |  |  |  | Complete
W2K-RFI-0054 | Grade Crew Delays | Mark Ringrose | 2016-01-06 | 2016-01-08 | Approved |  |  |  | Complete
W2K-RFI-0055R1 | Replace 8.4 mm Bore Pipe With 9.5 mm | Mark Ringrose | 2016-01-06 | 2016-01-07 | Approved | 42835.64 |  |  | Complete
W2K-RFI-0056 | Coating No-Productive Time | Mark Ringrose | 2016-01-07 | 2016-01-09 | Not Approved |  |  |  | Complete
W2K-RFI-0057 | Access Around Beaver Dam (KP 17+772) | Mark Ringrose | 2016-01-07 | 2016-01-08 | Not Approved |  |  |  | Complete
W2K-RFI-0058 | Remob to HDD | Mark Ringrose | 2016-01-09 | 2016-01-10 | Approved |  |  |  | Complete
W2K-RFI-0059 | Haul Water ROW Freezing | Mark Ringrose | 2016-01-08 | 2016-01-09 | Approved | 23684.06 |  | CO18 | Complete
W2K-RFI-0060
W2K-RFI-0061 | Crossing Agreement- Station (Conoco Phillips) | Mark Ringrose | 2016-01-13 | 2016-01-14 | Approved |  |  |  | Complete
W2K-RFI-0062 | Long Run Exploration Rep | Mark Ringrose | 2016-01-14 | 2016-01-15 | Approved | 5040 |  | CO19 | Complete
W2K-RFI-0063 | Hydrovac Truck Supply | Mark Ringrose | 2016-01-14 | 2016-01-15 | Not Approved | 15000 |  |  | Complete
W2K-RFI-0064 | Additional RT Trucks | Mark Ringrose | 2016-01-14 | 2016-01-15 | Approved |  |  |  | Complete
W2K-RFI-0065 | Combine Bore 15+920 to 16+010/16+043 to 16+097 | Mark Ringrose | 2016-01-14 | 2016-01-18 | Approved |  |  |  | Complete
W2K-RFI-0066 | Bore @ 69+397 | Mark Ringrose | 2016-01-14 | 2016-01-18 | Approved |  |  |  | Complete
W2K-RFI-0067 | River Additional Rig Support | Mark Ringrose | 2016-01-14 | 2016-01-15 | Approved | 66500.64 |  | CO20 | Complete
W2K-RFI-0068 | Addition Of 60 m On Drag Section At KP 0+000 | Mark Ringrose | 2016-01-15 | 2016-01-18 | Approved |  |  |  | Complete
W2K-RFI-0069 | Nova Line Crossing At 39+400 | Mark Ringrose | 2016-01-16 | 2016-01-18 | Not Approved |  |  |  | Complete
W2K-RFI-0070R1 | Hydrovac Support | Mark Ringrose | 2016-01-20 | 2016-01-22 | Approved | 359953.32 |  | CO23 | Complete
W2K-RFI-0071 | Additional Tie-In Support | Mark Ringrose | 2016-01-27 | 2016-01-29 | Approved | 763439.04 |  | CO24 | Complete
W2K-RFI-0072 | HDD Support Crews | Mark Ringrose | 2016-01-28 | 2016-01-31 | Approved | 1201072.32 |  | CO24 | Complete
W2K-RFI-0073 | Deviation From Pre Testing Drag Sections | Mark Ringrose | 2016-01-21 | 2016-01-24 | Not Approved |  |  |  | Complete
W2K-RFI-0074 | Deviation From Pre Testing Drag Sections- Cleaning Pig Tech. Info | Mark Ringrose | 2016-01-22 | 2016-01-26 | Approved |  |  |  | Complete
W2K-RFI-0075 | Tracked HydroVac Truck Supply | Mark Ringrose | 2016-01-22 | 2016-01-23 | Approved | 118900 |  | C044 | Complete
W2K-RFI-0076 | Husky Crossing At 28+221 | Mark Ringrose | 2016-01-23 | 2016-01-26 | Replied |  |  |  | Complete
W2K-RFI-0077 | Hot Bend @ 10+711 | Mark Ringrose | 2016-01-23 | 2016-01-26 | Approved |  |  |  | Complete
W2K-RFI-0078 | Combine Bores 34+139 & 34+228 | Mark Ringrose | 2016-01-26 | 2016-01-30 | Not Approved |  |  |  | Complete
W2K-RFI-0079R1 | Extend Bore 35+273 To 35+327 | Mark Ringrose | 2016-01-26 | 2016-01-30 | Approved |  |  |  | Complete
W2K-RFI-0080 | Extend HDD 35+668 To 35+886 | Mark Ringrose | 2016-01-26 | 2016-01-30 | Approved |  |  |  | Complete
W2K-RFI-0081R1 | Open Cut To Trenchless Crossings | Mark Ringrose | 2016-01-26 | 2016-01-30 | Partly Approved |  |  |  | Complete
W2K-RFI-0082 | Hydrotest Water Source | Mark Ringrose | 2016-01-27 | 2016-01-30 | Responded |  |  |  | Complete
W2K-RFI-0083 | Additional Grade Through Crossings | Mark Ringrose | 2016-01-29 | 2016-02-01 | Responded |  |  |  | Complete
W2K-RFI-0084 | Safety Stand Down Jan 18th | Mark Ringrose | 2016-01-30 | 2016-02-01 | Approved | 215855.08 |  | CO22 | Complete
W2K-RFI-0085 | Clean Up Release | Mark Ringrose | 2016-01-30 | 2016-02-01 | Approved | 60808.38 |  | CO21 | Complete
W2K-RFI-0086 | Miscellaneous Extra Works | Mark Ringrose | 2016-01-30 | 2016-02-01 | Not Approved |  |  |  | Complete
W2K-RFI-0087R1 | Open Cut To Trenchless Crossings | Mark Ringrose | 2016-01-31 | 2016-02-04 | Approved |  |  |  | Complete
W2K-RFI-0088 | Drag Section At KP 63+700 To Be Tested In Two Sections | Mark Ringrose | 2016-02-06 | 2016-02-10 | Approved |  |  |  | Complete
W2K-RFI-0089 | Drag Section At KP 12+500 To Be Tested In Two Sections | Mark Ringrose | 2016-02-11 | 2016-02-15 | Approved |  |  |  | Complete
W2K-RFI-0090 | Drag Sections At KP 30+115 & 10+608- Add Tested Pipe To Section | Mark Ringrose | 2016-02-16 | 2016-02-18 | Not Approved |  |  |  | Complete
W2K-RFI-0091 | Water Trucks To Support HDD Rigs | Mark Ringrose | 2016-02-16 | 2016-02-18 | Approved | 38750 |  | CO36 | Complete
W2K-RFI-0092 | Backfill Sumps Along ROW | Mark Ringrose | 2016-02-17 | 2016-02-19 | Approved | 165080.96 |  | CO33 | Complete
W2K-RFI-0093 | 24Hr Medic Coverage | Mark Ringrose | 2016-02-19 | 2016-02-21 | Approved | 151000 |  | CO30 | Complete
W2K-RFI-0094 | Stumping & Grubbing Support | Mark Ringrose | 2016-02-19 | 2016-02-21 | Approved | 22069.31 |  | CO29 | Complete
W2K-RFI-0095 | Move Around Bear Den At KP 48+800 | Mark Ringrose | 2016-02-20 | 2016-02-23 | Approved |  |  | UPI | Complete
W2K-RFI-0096 | Clean Up Crew Move Around HDD Drills | Jeremy Manning | 2016-02-20 | 2016-02-23 | Not Approved |  |  |  | Complete
W2K-RFI-0097 | Drag Section At KP 30+551 To Be Tested In Two Sections | Mark Ringrose | 2016-02-23 | 2016-02-25 | Approved |  |  |  | Complete
W2K-RFI-0098 | Drag Section At KP 26+759 And 48+756 Tested In Two Sections | Jeremy Manning | 2016-02-24 | 2016-02-26 | Accepted/Not Accepted |  |  |  | Complete
W2K-RFI-0099 | Cross Above Harvest Line At Road 23, KP 51+264 | Jeremy Manning | 2016-02-25 | 2016-02-28 | Not Approved |  |  |  | Complete
W2K-RFI-0100 | Two Section Hydro Tests For HDDs | Jeremy Manning | 2016-02-25 | 2016-02-27 | Partly Approved | 15560 |  |  | Complete
W2K-RFI-0101 | Tow Equipment To Access Drilling Rigs | Jeremy Manning | 2016-02-26 | 2016-02-28 | Partly Approved | 393404 |  | C058 | Complete
W2K-RFI-0102 | Bore Extension- KP 42+647 To 42+737 | Jeremy Manning | 2016-02-26 | 2016-02-28 | Lochlan Checking Jarrett
W2K-RFI-0103R1 | Move Backs Due To Improper Agreements/ CNRL/NuVista Change In Crossing Type | Jeremy Manning | 2016-03-21 | 2016-03-24 | Responded | 55080 |  | UPI | Complete
W2K-RFI-0104 | KP 24+539 Daylighting Support | Jeremy Manning | 2016-03-04 | 2016-03-07 | Approved | 32248.4 |  | C044 | Complete
W2K-RFI-0105R1 | Joint Length Impact | Jeremy Manning | 2016-03-07 | 2016-03-09 | Rejected | 615000 |  |  | Complete
W2K-RFI-0106 | HDD Clean-Up Impact | Jeremy Manning | 2016-03-21 | 2016-03-24 | Not Approved |  |  |  | Complete
W2K-RFI-0107 | Fill Void In Bore At KP 42+709 With Foam | Jeremy Manning | 2016-03-05 | 2016-03-07 | N/A |  |  |  | Complete
W2K-RFI-0108 | PVC Pipe For Temperature Probes | Jeremy Manning | 2016-03-09 | 2016-03-11 | Accepted |  |  |  | Complete
W2K-RFI-0109 | Additional Drill Support | Jeremy Manning | 2016-03-12 | 2016-03-14 | Accepted | 169946.08 |  | CO47 | Complete
W2K-RFI-0110 | Clean Up Environmental Concerns | Jeremy Manning | 2016-03-15 | 2016-03-16 | Accepted | 182366.91 |  | CO37 | Complete
W2K-RFI-0111 | Miscellaneous Stand By | Jeremy Manning | 2016-03-17 | 2016-03-18 | Accepted | 84077.7 |  | CO40 | Complete
W2K-RFI-0112 | Bore Extension- KP 38+390 To 38+731 | Jeremy Manning | 2016-03-17 | 2016-03-18 | Accepted |  |  |  | Complete
W2K-RFI-0113 | Bear Den HDD Extra Work | Jeremy Manning | 2016-03-17 | 2016-03-20 | Accepted | 366773.29 |  | C052 | Complete
W2K-RFI-0114 | X Ray Auditor Callbacks | Jeremy Manning | 2016-03-17 | 2016-03-19 | Approved | 9810.78 |  | CO39 | Complete
W2K-RFI-0115 | HDD Rig Foot Print 39+239 | Jeremy Manning | 2016-03-19 | 2016-03-21 | N/A |  |  |  | Complete
W2K-RFI-0116 | Hydrotest Medium Change | Jeremy Manning | 2016-03-24 | 2016-03-28 | Approved | 440014.76 |  | Need CO | Complete
W2K-RFI-0117 | Indirect Support For Extension | Jeremy Manning | 2016-03-31 | 2016-04-04 |  | 1023136.2 |  | CO???
W2K-RFI-0118 | Sump Light Towers | Jeremy Manning | 2016-03-31 | 2016-04-02 | Approved | 62260 |  | CO46 | Complete
W2K-RFI-0119 | Access Road Repair | Jeremy Manning | 2016-03-31 | 2016-04-02 | Partially Approved | 100000 |  | C054
W2K-RFI-0120 | Extension of HDD Support | Jeremy Manning | 2016-04-01 | 2016-04-05 | Rejected | 216860.28 |  |  | Complete
W2K-RFI-0121 | Purchase Of ROW Seed | Jeremy Manning | 2016-04-02 | 2016-04-05 | Accepted | 8411.63 |  | CO41 | Complete
W2K-RFI-0122 | Electronic Inspection Tool Support | Jeremy Manning | 2016-04-06 | 2016-04-08 | Rejected | 123580.44
W2K-RFI-0123 | HD Bore Tie-Ins | Jeremy Manning | 2016-04-12 | 2016-04-15 | Rejected | 680132.93 |  |  | Complete
W2K-RFI-0124 | HDD Tie-In Impact | Jeremy Manning | 2016-04-13 | 2016-04-15 | Rejected | 715929.4 |  |  | Complete
W2K-RFI-0125 | Test Lead Extension | Jeremy Manning | 2016-04-14 | 2016-04-16 | Approved | 7870.42 |  | Misc. CO | Complete
W2K-RFI-0126 | Typical HDD Hydrotesting | Jeremy Manning | 2016-04-14 | 2016-04-18 |  | 202650 |  | Need CO | Complete
W2K-RFI-0127 | All Conditions Equipment Usage | Jeremy Manning | 2016-04-18 | 2016-04-21 | Approved | 69770.04 |  | C055 | Complete
W2K-RFI-0128 | Second Season Clean Up Clarifications | Jeremy Manning | 2016-04-18 | 2016-04-21 | Responded |  |  |  | Complete
W2K-RFI-0129 | Access Matting Swap/Replacement | Jeremy Manning | 2016-04-18 | 2016-04-22 |  | 271724.25
W2K-RFI-0130
W2K-RFI-0131 | Line Rep Delays | Jeremy Manning | 2016-04-21 | 2016-04-23 |  | 28049.96
W2K-RFI-0132 | Road Ban Cost Impact | Jeremy Manning | 2016-05-02 | 2016-05-05 |  | 438387.8
W2K-RFI-0133 | Integrity Dig Ups | Jeremy Manning | 2016-05-04 | 2016-05-06 | Rejected | 359544
W2K-RFI-0134 | Caliper Pig Contractor Change | Jeremy Manning | 2016-05-04 | 2016-05-06 | Accepted | 55529.92 |  | C057
W2K-RFI-0135 | Access Matting Dig-ups | Jeremy Manning | 2016-05-13 | 2016-05-16 | Rejected | TBD
W2K-RFI-0136 | Inspection Tool Measurement Discrepancies | Jeremy Manning | 2016-05-13 | 2016-05-16 | Rejected | TBD
[5 empty] | Total Cost Impact | 11047169.98

## SI Log
SI Log
Expansion Pipeline Project |  |  | Energy Services |  |  |  |  | Progress Period | 2016-05-01 | To | 2016-05-15
| CO | Description | Type | Approved | Forecast | Date | Change | Work
SI | Number |  | SI | Value | Value | Approved | Order | Status
Number | If Applic. |  | Change Request | $ | $ |  | Status |  | This | Previous | To Date
|  |  | Change Order | [5 empty] | Period
1 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
2 |  | Overnight Hold on Welds | SI | 0 | 0 |  |  |  | 0 | 0 | 0
3 |  | Theoretical Road Crossing Depth | SI | 0 | 0 |  |  |  | 0 | 0 | 0
4 |  | Minimum Depth Of Cover For Watercourses | SI | 0 | 0 |  |  |  | 0 | 0 | 0
5 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
6 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
7 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
8 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
9 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
10 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
11 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
12 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
13 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
14 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
15 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
16 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
17 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
18 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
19 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
20 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
21 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
22 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
23 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
24 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
25 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
26 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
27 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
28 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
29 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
30 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
|  | Accumulated Value |  | 0 | 0 |  |  | Subtotal: | 0 | 0 | 0
[8 empty] | Total: | 0 | 0 | 0

## CO Log
Change Order Log
Expansion Pipeline Project |  |  | Contractor |  |  |  |  | Progress Period | 2016-05-01 | To | 2016-05-15
Change | RFI | Description | Type | Approved | Forecast | Date | Change | Work
Order | Number |  | RFI | Value | Value | Approved | Order | Status
Number | If Applic. |  | Change Request | $ | $ |  | Status |  | This | Previous | To Date
|  |  | Change Order | [5 empty] | Period |  |  | 40321283.37 |  |  | If Negative then CO is Over | Pending | Difference
1 | N/A | Additional Right-of-Way Stripping (Add $12.44 To Base Lay Price) | Change Order | 863980 | 863980 | 2015-11-05 | Executed | Ongoing | 4394.62 | 790957.11 | 795351.73 | 41185263.37 |  |  | 68628.27
2 | 007 | Additional Two Way Radios For Inspection | Change Order | 7088.55 | 7088.55 | 2015-11-09 | Executed | Ongoing | 0 | 0 | 0 | 41192351.92 |  |  | 7088.55
3 | 020 | Clearing Support | Change Order | 670085.52 | 438132.84 | 2015-12-02 | Executed | Complete | 0 | 438132.84 | 438132.84 | 41862437.44 |  |  | 0
4 | 026R1 | 24Hr Medic Coverage | Change Order | 103635 | 103635 | 2015-12-02 | Executed | Complete | 0 | 103635 | 103635 | 41966072.44 |  |  | 0
5 | 015R3 | Delayed Start Due To Weather- Cost Impacts | Change Order | 555229.22 | 555229.22 | 2015-12-07 | Executed | Complete | 0 | 555229.22 | 555229.22 | 42521301.66 |  |  | 0
6 | N/A | UPIs For Progress Payments Dec 15 & Dec 31 2015 | Change Order | 244345.82 | 244345.82 | 2016-01-04 | Executed | Complete | 0 | 244345.82 | 244345.82 | 42765647.48 | PO added 3 cents On CO 6. |  | 0
7 | N/A | UPIs For Progress Payment Jan 15 2016 | Change Order | 86343.77 | 86343.77 | 2016-01-19 | Executed | Complete | 0 | 86343.77 | 86343.77 | 42851991.25 |  |  | 0
8 | N/A | VOID | VOID | 0 | 0 |  |  | Complete | 0 | 0 | 0 | 42851991.25 |  |  | 0
9 | 032 | Digging Test Holes | Change Order | 20000 | 18809.25 | 2016-01-21 | Executed | Complete | 0 | 18809.25 | 18809.25 | 42871991.25 |  |  | 0
10 | 034 | Installation/Removal & Trucking Of Access Mats To The River | Change Order | 80000 | 80000 | 2016-01-21 | Executed | Complete | 0 | 80000 | 80000 | 42951991.25 |  |  | 0
11 | 042 | Digging Sumps | Change Order | 60000 | 59756.38 | 2016-01-21 | Executed | Complete | 0 | 59756.38 | 59756.38 | 43011991.25 |  |  | 0
12 | 046 | Performance Vac- Mud Disposal | Change Order | 25000 | 25000 | 2016-01-21 | Executed | Ongoing | 0 | 0 | 0 | 43036991.25 |  |  | 25000
13 | 048 | Rework Due To Survey Error | Change Order | 4250.2 | 3397.2 | 2016-01-21 | Executed | Complete | 0 | 3397.2 | 3397.2 | 43041241.45 |  |  | 0
14 | 050 | Paragon Soils Test Holes & Repair Factory Holidays | Change Order | 2070.78 | 686.9 | 2016-01-21 | Executed | Complete | 0 | 686.9 | 686.9 | 43043312.23 |  |  | 0
15 | N/A | Miscellaneous Additional Costs | Change Order | 50000 | 50000 | 2016-01-21 | Executed | Ongoing | 2238.76 | 29808.89 | 32047.65 | 43093312.23 |  |  | 17952.35
16 | N/A | Damage To Irrigation Pipe | Change Order | 5991.3 | 5991.3 | 2016-01-21 | Executed | Complete | 0 | 5991.3 | 5991.3 | 43099303.53 |  |  | 0
17 | 044 | Unloading Mats | Change Order | 19408 | 19410 | 2016-01-26 | Executed | Ongoing | 0 | 5958.87 | 5958.87 | 43118711.53 |  |  | 13451.13
18 | 059 | Haul Water For ROW Freezing | Change Order | 23684.06 | 23684.06 | 2016-01-27 | Executed | Complete | 0 | 23684.06 | 23684.06 | 43142395.59 |  |  | 0
19 | 062 | Consultant For Long Run Crossing | Change Order | 5040 | 4410 | 2016-01-27 | Executed | Complete | 0 | 4410 | 4410 | 43147435.59 |  |  | 0
20 | 067 | Drilling Support- Extended Schedule At River | Change Order | 88667.52 | 88667.52 | 2016-01-27 | Executed | Complete | 0 | 88667.52 | 88667.52 | 43236103.11 |  |  | 0
21 | 085 | IMR Clean Up | Change Order | 65808.38 | 60232.38 | 2016-02-03 | Executed | Complete | 0 | 60232.38 | 60232.38 | 43301911.49 |  |  | 0
22 | 084 | Safety Stand Down | Change Order | 215855.08 | 215562.16 | 2016-02-03 | Executed | Complete | 0 | 215562.16 | 215562.16 | 43517766.57 |  |  | 0
23 | 070R1 | Additional Hydrovac Support | Change Order | 359953.32 | 359893.28 | 2016-02-03 | Executed | Complete | 0 | 359893.28 | 359893.28 | 43877719.89 |  |  | 0
24 | 071 & 072 | Additional Tie-In Support And HDD Support Crews | Change Order | 1964511.36 | 1964511.36 | 2016-02-03 | Executed | Complete | 0 | 1964511.36 | 1964511.36 | 45842231.25 |  |  | 0
25 | N/A | VOID | VOID | 0 | 0 |  |  | Complete | 0 | 0 | 0 | 45842231.25 |  |  | 0
26 | N/A | UPIs For Progress Payment Jan 31 2016 | Change Order | 85583.22 | 85583.22 | 2016-02-03 | Executed | Complete | 0 | 85583.22 | 85583.22 | 45927814.47 |  |  | 0
27 | N/A | Existing Piping Removal At Station | Change Order | 200000 | 85020.86 | 2016-02-16 | Executed | Complete | 0 | 85020.86 | 85020.86 | 46127814.47 |  |  | 0
28 | N/A | UPIs For Progress Payment Feb 15 2016 | Change Order | 131183 | 131183 | 2016-02-22 | Executed | Complete | 0 | 131183 | 131183 | 46258997.47 |  |  | 0
29 | 094 | Stumping & Grubbing Not Completed By Clearing Contractor | Change Order | 22069.31 | 22059.31 | 2016-02-24 | Executed | Complete | 0 | 22059.31 | 22059.31 | 46281066.78 |  |  | 0
30 | 093 | 24Hr Medic Coverage (Additional To C004) | Change Order | 150785.25 | 137550 | 2016-02-24 | Executed | Complete | 0 | 137550 | 137550 | 46431852.03 |  |  | 0
31 | 034 | Installation/Removal & Trucking Of Access Mats To The Cutbank River (Addit. To C010) | Change Order | 2965.6 | 2965.6 | 2016-02-24 | Executed | Complete | 0 | 2965.6 | 2965.6 | 46434817.63 |  |  | 0
32 | N/A | Additional Force Account Equipment Rates | Change Order | 0 | 0 | 2016-02-24 | Executed | Complete | 0 | 0 | 0 | 46434817.63 |  |  | 0
33 | 092 | Mix And Backfill HDD Mud Sump Pits | Change Order | 165080.96 | 165041.2 | 2016-02-24 | Executed | Complete | 0 | 165041.2 | 165041.2 | 46599898.59 |  |  | 0 | 137519.85 | 137519.85
34 | N/A | Remove Merchantable Timber When Mills Were Closed | Change Order | 5512.5 | 5512.5 | 2016-03-09 | Executed | Complete | 0 | 5512.5 | 5512.5 | 46605411.09 |  |  | 0
35 | N/A | UPIs For Progress Payment Feb 29 2016 | Change Order | 645875.24 | 645875.24 | 2016-03-09 | Executed | Complete | 0 | 645875.24 | 645875.24 | 47251286.33 |  |  | 0
36 | N/A | UPIs For Progress Payment Mar 15 2016 | Change Order | 284494.98 | 284494.98 | 2016-03-23 | Executed | Complete | 0 | 284494.98 | 284494.98 | 47535781.31 |  |  | 0
37 | 091 | Water Trucks To Support HDD Rigs | Change Order | 67500 | 42875.6 | 2016-03-23 | Executed | Complete | 0 | 42875.6 | 42875.6 | 47603281.31 |  |  | 0
38 | 110 | Other Drill IMR Clean Up | Change Order | 197366.91 | 197366.91 | 2016-03-23 | Executed | Ongoing | 1480.14 | 195710.53 | 197190.67 | 47800648.22 |  | 176.24 | 176.24 | 14188.92 | 14012.68
39 | 114 | X-Ray Auditor Call Backs | Change Order | 9805.78 | 9805.78 | 2016-03-23 | Executed | Ongoing | 0 | 5805.78 | 5805.78 | 47810454 |  |  | 4000
40 | 111 | Delays Due To Clearing, Reps & Miscellaneous Causes | Change Order | 104077.7 | 104077.7 | 2016-04-14 | Executed | Ongoing | 0 | 84077.7 | 84077.7 | 47914531.7 |  |  | 20000
41 | 121 | Purchase Of Seed Mix | Change Order | 10000 | 10000 | 2016-04-14 | Executed | Ongoing | 0 | 8923.6 | 8923.6 | 47924531.7 |  |  | 1076.4
42 | N/A | UPIs For Progress Payment Mar 31 2016 | Change Order | 66053.28 | 66053.28 | 2016-04-14 | Executed | Complete | 0 | 66053.28 | 66053.28 | 47990584.98 |  |  | 0
43 | 042 | Digging Sumps Additional To C011 | Change Order | 80000 | 66369.92 | 2016-04-14 | Executed | Complete | 0 | 66369.92 | 66369.92 | 48070584.98 |  |  | 0 |  | 0
44 | 075 & 104 | Daylighting CNRL Pipelines At KP 24+804 | Change Order | 122491.4 | 101151.91 | 2016-04-14 | Executed | Ongoing | 0 | 101151.91 | 101151.91 | 48193076.38 |  |  | 0
45 | 070R1 | Hydrovac Support Additional to C023 | Change Order | 54750.6 | 32090.76 | 2016-04-14 | Executed | Complete | 0 | 32090.76 | 32090.76 | 48247826.98 |  |  | 0 | 8670.08 | 8670.08
46 | N/A | UPIs For Progress Payment Apr 15 2016 | Change Order | 155239.62 | 155239.62 | 2016-04-22 | Executed | Complete | 0 | 155239.62 | 155239.62 | 48403066.6 |  |  | 0
47 | 118 | Light Towers For HDD Sumps | Change Order | 62260 | 62260 | 2016-04-22 | Executed | Complete | 0 | 62260 | 62260 | 48465326.6 |  |  | 0
48 | 067 | Drilling Support- Extended Schedule At River Additional To C020 | Change Order | 169946.08 | 169946.08 | 2016-04-22 | Executed | Complete | 0 | 169946.08 | 169946.08 | 48635272.68 |  |  | 0
49 | N/A | UPIs For Progress Payment Apr 30 2016 | Change Order | 95648.31 | 95648.31 | 2016-05-11 | Executed | Complete | 0 | 95648.31 | 95648.31 | 48730920.99 |  |  | 0
50 | 062 | Consultant For Long Run Exploration Crossing Additional To C019 | Change Order | 5040 | 5040 | 2016-05-11 | Executed | Complete | 0 | 5040 | 5040 | 48735960.99 |  |  | 0
51 | 092 | Mix And Backfill HDD Mud Sump Pits Additional To C033 | Change Order | 143330.98 | 143330.98 | 2016-05-11 | Executed | Complete | 0 | 143330.98 | 143330.98 | 48879291.97 |  |  | 0
52 | 113 | Additional Work Associated With Bear Den At KP 48+800 | Change Order | 366773.29 | 366773.29 |  |  | Complete | 325639.92 | 0 | 325639.92 | 49246065.26 |  |  | 41133.37
53 | 110 | Inadvertent Mud Release Clean Up In Addition To C038 | Change Order | 13198.84 | 13198.84 |  |  | Complete | 13198.84 | 0 | 13198.84 | 49259264.1 |  |  | 0
54 | 119 | Access Road Repairs & Maintenance | Change Order | 100000 | 100000 |  |  | Ongoing | 5195.45 | 0 | 5195.45 | 49359264.1 |  |  | 94804.55
55 | 127 | All Conditions Equipment Use During Spring Break Up | Change Order | 69770.04 | 69770.04 |  |  | Complete | 69770.04 | 0 | 69770.04 | 49429034.14 |  |  | 0
56 | N/A | UPIs For Progress Payment May 15 2016 | Change Order | 125158.18 | 125158.18 |  |  | Complete | 125158.18 | 0 | 125158.18 | 49554192.32 |  |  | 0
57 | 134 | Caliper Pig Contractor Change | Change Order | 55529.82 | 55529.82 |  |  |  | 0 | 0 | 0 | 49609722.14 |  |  | 55529.82
58 | 101 | Tow Equipment To Access Drilling Rigs | Change Order | 155203.98 | 155203.98 |  |  |  | 0 | 0 | 0 | 49764926.12 |  |  | 155203.98
59 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 49764926.12 | CO total should be 3 cents more |  | 0
|  | Accumulated Value |  | 9443642.75 | 8990943.9 |  |  | Subtotal: | 547075.95 | 7939823.29 | 8486899.24
[8 empty] | Total: | 547075.95 | 7939823.29 | 8486899.24

## CO001
WAPITI EXPANSION PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | 001
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2015-11-15
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 34718 |  | 34718 | 8639.9244 | 0 | 8639.9244
| Grade ROW | Per Lin. m | 8% | 0.99544 | 0 |  |  | 0 | 0 | 0
| Haul and String Ppipe | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Bending | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Welding | Per Lin. m | 17% | 2.1153 | 0 |  |  | 0 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 0 |  |  | 0 | 0 | 0
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Backfill | Per Lin. m | 8% | 0.99544 | 0 |  |  | 0 | 0 | 0
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Testing | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 8639.9244 | 0 | 8639.9244
Contractor
Chief Inspector
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 8639.9244
WAPITI EXPANSION PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | 001
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2015-11-30
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 34718 | 34717 | 8639.6756 | 8639.9244 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 5300 |  | 5300 | 5275.8338 | 0 | 5275.83
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 400 |  | 400 | 348.4041 | 0 | 348.4
| Bending | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Welding | Per Lin. m | 17% | 2.1153 | 0 |  |  | 0 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 0 |  |  | 0 | 0 | 0
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Backfill | Per Lin. m | 8% | 0.99544 | 0 |  |  | 0 | 0 | 0
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Testing | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 14263.9135 | 8639.9244 | 22903.83
Contractor
Chief Inspector
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 22903.83
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | 001
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2015-12-15
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 25100 | 5300 | 19800 | 19709.72 | 5275.83 | 24985.55
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 16100 | 400 | 15700 | 13674.86 | 348.4 | 14023.26
| Bending | Per Lin. m | 7% | 0.87101 | 12000 |  | 12000 | 10452.12 | 0 | 10452.12
| Welding | Per Lin. m | 17% | 2.1153 | 9500 |  | 9500 | 20095.45 | 0 | 20095.45
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 3700 |  | 3700 | 3683.13 | 0 | 3683.13
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 3700 |  | 3700 | 3222.74 | 0 | 3222.74
| Backfill | Per Lin. m | 8% | 0.99544 | 2800 |  | 2800 | 2787.23 | 0 | 2787.23
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 1500 |  | 1500 | 1306.52 | 0 | 1306.52
| Testing | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 74931.77 | 22903.83 | 97835.6
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 97835.6
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2015-12-31
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 32600 | 25100 | 7500 | 7465.8025 | 24985.55 | 32451.3525
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 24400 | 16100 | 8300 | 7229.3855 | 14023.26 | 21252.6455
| Bending | Per Lin. m | 7% | 0.87101 | 16100 | 12000 | 4100 | 3571.1422 | 10452.12 | 14023.2622
| Welding | Per Lin. m | 17% | 2.1153 | 12800 | 9500 | 3300 | 6980.5254 | 20095.45 | 27075.9754
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 6900 | 3700 | 3200 | 3185.4091 | 3683.13 | 6868.5391
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 6900 | 3700 | 3200 | 2787.233 | 3222.74 | 6009.973
| Backfill | Per Lin. m | 8% | 0.99544 | 6900 | 2800 | 4100 | 4081.3054 | 2787.23 | 6868.5354
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 3700 | 1500 | 2200 | 1916.2227 | 1306.52 | 3222.7427
| Testing | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 37217.0257 | 97835.6 | 135052.6257
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 135052.6257
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2016-01-15
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 48600 | 32600 | 16000 | 15927.0454 | 32451.35 | 48378.3954
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 40800 | 24400 | 16400 | 14284.5689 | 21252.65 | 35537.2189
| Bending | Per Lin. m | 7% | 0.87101 | 32200 | 16100 | 16100 | 14023.2658 | 14023.26 | 28046.5258
| Welding | Per Lin. m | 17% | 2.1153 | 29100 | 12800 | 16300 | 34479.5648 | 27075.98 | 61555.5448
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 21200 | 6900 | 14300 | 14234.7969 | 6868.54 | 21103.3369
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 20400 | 6900 | 13500 | 11758.639 | 6009.97 | 17768.609
| Backfill | Per Lin. m | 8% | 0.99544 | 20200 | 6900 | 13300 | 13239.3565 | 6868.54 | 20107.8965
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 7600 | 3700 | 3900 | 3396.9402 | 3222.74 | 6619.6802
| Testing | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 121344.1774 | 135052.63 | 256396.8074
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 256396.8074
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2016-01-31
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 59700 | 48600 | 11100 | 11049.3878 | 48378.395 | 59427.7828
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 51600 | 40800 | 10800 | 9406.9112 | 35537.22 | 44944.1312
| Bending | Per Lin. m | 7% | 0.87101 | 47600 | 32200 | 15400 | 13413.5586 | 28046.5257 | 41460.0843
| Welding | Per Lin. m | 17% | 2.1153 | 41900 | 29100 | 12800 | 27075.9772 | 61555.54 | 88631.5172
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 36000 | 21200 | 14800 | 14732.517 | 21103.34 | 35835.857
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 36000 | 20400 | 15600 | 13587.7606 | 17768.61 | 31356.3706
| Backfill | Per Lin. m | 8% | 0.99544 | 35900 | 20200 | 15700 | 15628.4133 | 20107.9 | 35736.3133
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 14600 | 7600 | 7000 | 6097.0721 | 6619.68 | 12716.7521
| Testing | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 110991.5979 | 256396.8107 | 367388.4086
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 367388.4086
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2016-02-15
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 69435 | 59700 | 9735 | 9690.6117 | 59427.7828 | 69118.3945
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 64400 | 51600 | 12800 | 11148.9318 | 44944.1312 | 56093.063
| Bending | Per Lin. m | 7% | 0.87101 | 58600 | 47600 | 11000 | 9581.1133 | 41460.0843 | 51041.1976
| Welding | Per Lin. m | 17% | 2.1153 | 55900 | 41900 | 14000 | 29614.3501 | 88631.5172 | 118245.8674
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 51800 | 36000 | 15800 | 15727.9574 | 35835.857 | 51563.8144
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 51800 | 36000 | 15800 | 13761.9627 | 31356.3706 | 45118.3333
| Backfill | Per Lin. m | 8% | 0.99544 | 51800 | 35900 | 15900 | 15827.5014 | 35736.3133 | 51563.8147
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 31800 | 14600 | 17200 | 14981.3771 | 12716.7521 | 27698.1292
| Testing | Per Lin. m | 7% | 0.87101 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 |  |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 2500 |  | 2500 | 2799.676 | 0 | 2799.676
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 123133.4814 | 367388.4086 | 490521.89
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 490521.89
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2016-02-29
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.3945 | 69118.3945
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 64400 | 5035 | 4385.5368 | 56093.063 | 60478.5999
| Bending | Per Lin. m | 7% | 0.87101 | 69435 | 58600 | 10835 | 9437.3966 | 51041.1976 | 60478.5941
| Welding | Per Lin. m | 17% | 2.1153 | 69435 | 55900 | 13535 | 28630.7306 | 118245.8674 | 146876.598
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 67400 | 51800 | 15600 | 15528.8693 | 51563.8144 | 67092.6837
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 66900 | 51800 | 15100 | 13152.2555 | 45118.3333 | 58270.5888
| Backfill | Per Lin. m | 8% | 0.99544 | 66500 | 51800 | 14700 | 14632.973 | 51563.8147 | 66196.7877
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 37700 | 31800 | 5900 | 5138.9608 | 27698.1292 | 32837.09
| Testing | Per Lin. m | 7% | 0.87101 | 0 | 0 |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 | 0 |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 10700 | 2500 | 8200 | 9182.9371 | 2799.676 | 11982.6131
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 100089.6597 | 490521.89 | 590611.5498
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 590611.5498
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2016-03-15
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.3945 | 69118.3945
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5999 | 60478.5999
| Bending | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5941 | 60478.5941
| Welding | Per Lin. m | 17% | 2.1153 | 69435 | 69435 |  | 0 | 146876.598 | 146876.598
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 69435 | 67400 | 2035 | 2025.7211 | 67092.6837 | 69118.4048
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 66900 | 2535 | 2208.0111 | 58270.5888 | 60478.5999
| Backfill | Per Lin. m | 8% | 0.99544 | 69435 | 66500 | 2935 | 2921.6174 | 66196.7877 | 69118.4051
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 48200 | 37700 | 10500 | 9145.6081 | 32837.09 | 41982.6981
| Testing | Per Lin. m | 7% | 0.87101 | 0 | 0 |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 | 0 |  | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 17000 | 10700 | 6300 | 7055.1834 | 11982.6131 | 19037.7965
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 23356.1411 | 590611.5498 | 613967.6909
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 613967.6909
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2016-03-31
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.3945 | 69118.3945
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5999 | 60478.5999
| Bending | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5941 | 60478.5941
| Welding | Per Lin. m | 17% | 2.1153 | 69435 | 69435 |  | 0 | 146876.598 | 146876.598
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.4048 | 69118.4048
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5999 | 60478.5999
| Backfill | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.4051 | 69118.4051
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 65700 | 48200 | 17500 | 15242.6802 | 41982.6981 | 57225.3783
| Testing | Per Lin. m | 7% | 0.87101 | 18100 | 0 | 18100 | 15765.2864 | 0 | 15765.2864
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 | 0 | 0 | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 28600 | 17000 | 11600 | 12990.4964 | 19037.7965 | 32028.2929
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 43998.463 | 613967.6909 | 657966.1539
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 657966.1539
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2016-04-15
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.3945 | 69118.3945
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5999 | 60478.5999
| Bending | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5941 | 60478.5941
| Welding | Per Lin. m | 17% | 2.1153 | 69435 | 69435 |  | 0 | 146876.598 | 146876.598
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.4048 | 69118.4048
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5999 | 60478.5999
| Backfill | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.4051 | 69118.4051
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 69335 | 65700 | 3635 | 3166.1224 | 57225.3783 | 60391.5007 | changed as previous was wrong
| Testing | Per Lin. m | 7% | 0.87101 | 41000 | 18100 | 22900 | 19946.1358 | 0 | 19946.1358
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 0 | 0 | 0 | 0 | 0 | 0
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 47900 | 28600 | 19300 | 21613.4984 | 19037.7965 | 40651.2949
| Demobilization | Per Lin. m | 2% | 0.24886 | 0 |  |  | 0 | 0 | 0
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 44725.7566 | 629210.3711 | 673936.1277
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 673936.1277
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2016-04-30
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.3945 | 69118.3945
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5999 | 60478.5999
| Bending | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5941 | 60478.5941
| Welding | Per Lin. m | 17% | 2.1153 | 69435 | 69435 |  | 0 | 146876.598 | 146876.598
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.4048 | 69118.4048
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.5999 | 60478.5999
| Backfill | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.4051 | 69118.4051
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 69435 | 69335 | 100 | 87.101 | 60391.5007 | 60478.6017 | changed as previous was wrong
| Testing | Per Lin. m | 7% | 0.87101 | 69435 | 41000 | 28435 | 24767.1778 | 19946.1358 | 44713.3136
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 69435 | 0 | 69435 | 43199 | 0 | 43199
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 58300 | 47900 | 10400 | 11646.652 | 40651.2949 | 52297.9469
| Demobilization | Per Lin. m | 2% | 0.24886 | 34418 |  | 34418 | 8565.2664 | 0 | 8565.2664
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 88265.1972 | 673936.1277 | 762201.3249
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 762201.3249
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C01
Item | Additional Right-Of-Way Stripping: Add $12.44/m To Base Lay Price
[8 empty] | Billing Date: | 2016-05-15
|  | 69435 | % | 12.443 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
1.1 | Mobilization | Per Lin. m | 2% | 0.24886 | 69435 | 69435 |  | 0 | 17279.6 | 17279.6
| Grade ROW | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.4 | 69118.4
| Haul and String Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.6 | 60478.6
| Bending | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.6 | 60478.6
| Welding | Per Lin. m | 17% | 2.1153 | 69435 | 69435 |  | 0 | 146876.6 | 146876.6
| Excavate Pipe Trench | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.4 | 69118.4
| Lower-In Pipe | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.6 | 60478.6
| Backfill | Per Lin. m | 8% | 0.99544 | 69435 | 69435 |  | 0 | 69118.4 | 69118.4
| Tie-Ins | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.6 | 60478.6
| Testing | Per Lin. m | 7% | 0.87101 | 69435 | 69435 |  | 0 | 60478.6 | 60478.6
| Final Tie-Ins | Per Lin. m | 5% | 0.62215 | 69435 | 69435 |  | 0 | 43199 | 43199
| Cleanup/Reclamation/Seeding | Per Lin. m | 9% | 1.1199 | 58300 | 58300 |  | 0 | 65288.4433 | 65288.4433
| Demobilization | Per Lin. m | 2% | 0.24886 | 52077 | 34418 | 17659 | 4394.6202 | 8565.2664 | 12959.8866
| Final Clean Up (one year later) | Per Lin. m | 6% | 0.74658 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 12.443 |  |  | Total For Base Lay Price: | 4394.6202 | 790957.1097 | 795351.7299
Contractor
Construction Manager
[7 empty] | Approved CO Value ($) |  | CO To Date ($)
[7 empty] | 863980 |  | 795351.7299

## CO002
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | 002
|  |  | Billing Date: | 2016-05-15
Item | Additional Two Way Radios For Inspection
Date | Description | This Period | Previous | Total To Date
0
|  | 25000 |  | 25000
|  | 25000 |  | 25000
0
0
0
0
0
0
0
0
| Total | 50000 | 0 | 50000
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 7088.55 | 50000

## CO003
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C03
|  |  | Date: | 2016-01-15
Item | Clearing Support
Date | Description | This Period | Previous | Total To Date | Dec 4- Dec 15 | 8590.84 | 12 | 103090.08
Nov 25- Dec 15 | Support Crew #2 & #3 (30 Days) | 257725.2 |  | 257725.2 | Nov 25-Dec 13 | 8590.84 | 18 | 154635.12
Dec 16- Dec 21 | Support Crew #2 (6 Days) | 51545.04 |  | 51545.04 | Dec 16- Dec 21 | 8590.84 | 6 | 51545.04
Jan 3- Jan 12 | Support Crew (9 Days) | 77317.56 |  | 77317.56 | Jan 3- Jan 12 | 8590.84 | 9 | 77317.56
386587.8
| Total | 386587.8 | 0 | 386587.8
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 670085.52 | 386587.8
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C03
|  |  | Date: | 2016-01-31
Item | Clearing Support
Date | Description | This Period | Previous | Total To Date | Dec 4- Dec 15 | 8590.84 | 12 | 103090.08
Nov 25- Dec 15 | Support Crew #2 & #3 (30 Days) |  | 257725.2 | 257725.2 | Nov 25-Dec 13 | 8590.84 | 18 | 154635.12
Dec 16- Dec 21 | Support Crew #2 (6 Days) |  | 51545.04 | 51545.04 | Dec 16- Dec 21 | 8590.84 | 6 | 51545.04
Jan 3- Jan 12 | Support Crew (9 Days) |  | 77317.56 | 77317.56 | Jan 3- Jan 12 | 8590.84 | 9 | 77317.56
Jan 14- Jan 21 | Support Crew (6 Days) | 51545.04 |  | 51545.04 | Jan 14- Jan 21 | 8590.84 | 6 | 51545.04
438132.84
| Total | 51545.04 | 386587.8 | 438132.84
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 670085.52 | 438132.84
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C03
|  |  | Date: | 2016-05-15
Item | Clearing Support
Date | Description | This Period | Previous | Total To Date
Nov 25- Dec 15 | Support Crew #2 & #3 (30 Days) |  | 257725.2 | 257725.2
Dec 16- Dec 21 | Support Crew #2 (6 Days) |  | 51545.04 | 51545.04
Jan 3- Jan 12 | Support Crew (9 Days) |  | 77317.56 | 77317.56
Jan 14- Jan 21 | Support Crew (6 Days) |  | 51545.04 | 51545.04
| Total | 0 | 438132.84 | 438132.84
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 670085.52 | 438132.84
Complete

## CO004
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C04
|  |  | Date: | 2015-12-15
Item | 24 Hour Medic Coverage
Date | Description | This Period | Previous | Total To Date
2015-12-15 | 24 Hour Medic for HDD & Burning Crew | 25357.5 |  | 25357.5
| Total | 25357.5 | 0 | 25357.5
Contractor
Construction Manager
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C04
|  |  | Date: | 2015-12-31
Item | 24 Hour Medic Coverage
Date | Description | This Period | Previous | Total To Date
2015-12-15 | 24 Hour Medic for HDD & Burning Crew |  | 25357.5 | 25357.5
2015-12-31 | 25 Hour Medic for HDD & Burning Crew | 8820 |  | 8820
| Total | 8820 | 25357.5 | 34177.5
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 103635 | 34177.5
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C04
|  |  | Date: | 2016-01-15
Item | 24 Hour Medic Coverage
Date | Description | This Period | Previous | Total To Date
2015-12-15 | 24 Hour Medic for HDD & Burning Crew (Nov 25-Dec 15) |  | 25357.5 | 25357.5
2015-12-31 | 25 Hour Medic for HDD & Burning Crew (Dec 16-31) |  | 8820 | 8820
2016-01-15 | 26 Hour Medic for HDD & Burning Crew (Jan 1-14) | 23152.5 |  | 23152.5
| Total | 23152.5 | 34177.5 | 57330
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 103635 | 57330
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C04
|  |  | Date: | 2016-01-31
Item | 24 Hour Medic Coverage
Date | Description | This Period | Previous | Total To Date
2015-12-15 | 24 Hour Medic for HDD & Burning Crew (Nov 25-Dec 15) |  | 25357.5 | 25357.5
2015-12-31 | 24 Hour Medic for HDD & Burning Crew (Dec 16-31) |  | 8820 | 8820
2016-01-15 | 24 Hour Medic for HDD & Burning Crew (Jan 1-14) |  | 23152.5 | 23152.5
2016-01-24 | 24 Hour Medic for HDD & Burning Crew (Jan 14-24) | 31972.5 |  | 31972.5
| Total | 31972.5 | 57330 | 89302.5
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 103635 | 89302.5
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C04
|  |  | Date: | 2016-02-15
Item | 24 Hour Medic Coverage
Date | Description | This Period | Previous | Total To Date
2015-12-15 | 24 Hour Medic for HDD & Burning Crew (Nov 25-Dec 15) |  | 25357.5 | 25357.5
2015-12-31 | 24 Hour Medic for HDD & Burning Crew (Dec 16-31) |  | 8820 | 8820
2016-01-15 | 24 Hour Medic for HDD & Burning Crew (Jan 1-14) |  | 23152.5 | 23152.5
2016-01-24 | 24 Hour Medic for HDD & Burning Crew (Jan 14-24) |  | 31972.5 | 31972.5
2016-02-15 | 25 Hour Medic for HDD & Burning Crew (Jan 30-Feb 4) | 14332.5 |  | 14332.5
| Total | 14332.5 | 89302.5 | 103635
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 103635 | 103635
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C04
|  |  | Date: | 2016-05-15
Item | 24 Hour Medic Coverage
Date | Description | This Period | Previous | Total To Date
2015-12-15 | 24 Hour Medic for HDD & Burning Crew (Nov 25-Dec 15) |  | 25357.5 | 25357.5
2015-12-31 | 24 Hour Medic for HDD & Burning Crew (Dec 16-31) |  | 8820 | 8820
2016-01-15 | 24 Hour Medic for HDD & Burning Crew (Jan 1-14) |  | 23152.5 | 23152.5
2016-01-24 | 24 Hour Medic for HDD & Burning Crew (Jan 14-24) |  | 31972.5 | 31972.5
2016-02-15 | 25 Hour Medic for HDD & Burning Crew (Jan 30-Feb 4) |  | 14332.5 | 14332.5
| Total | 0 | 103635 | 103635
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 103635 | 103635
Complete

## CO005
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO5
|  |  | Billing Date: | 2015-12-15
Item | RFI-015-R3 Cost Impacts
Date | Description | This Period | Previous | Total To Date
2015-12-15 | Cost Impacts Due To Start Delay | 555229.22 |  | 555229.22
| Total | 555229.22 | 0 | 555229.22
Contractor
Construction Manager
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO5
|  |  | Billing Date: | 2016-05-15
Item | W2K-RFI-015-R3 Cost Impacts
Date | Description | This Period | Previous | Total To Date
2015-12-31 | Cost Impacts Due To Start Delay |  | 555229.22 | 555229.22
| Total | 0 | 555229.22 | 555229.22
Contractor
Construction Manager
Complete

## CO006
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO6
|  |  |  | Billing Date: | 2016-05-15
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
0
2015-12-15 | 2.1 a) | Rock Trench | 36802.67 |  | 36802.67
| 2.2 b) | Rockshield | 22800.6904 |  | 22800.6904
| 2.3 a) c) d) | Sand Bedding/Padding From Borrow Pits | 80356.7 |  | 80356.7
| 2.14 b) | Install Pipe To Extra Depth | 840 |  | 840
| 2.18 b) | Vehicle & Equipment Wash Stations | 10720 |  | 10720
0
0
0
0
0
0
0
0
0
|  | Total | 151520.0604 | 0 | 151520.0604
Contractor
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO6
|  |  |  | Billing Date: | 2015-12-31
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
0
2015-12-31 | 2.1 a) | Rock Trench |  | 36802.67 | 36802.67
| 2.2 b) | Rockshield | 20915.7628 | 22800.6904 | 43716.4532
| 2.3 a) c) d) | Sand Bedding/Padding From Borrow Pits |  | 80356.7 | 80356.7
| 2.14 b) | Install Pipe To Extra Depth | 468 | 840 | 1308
| 2.18 b) | Vehicle & Equipment Wash Stations |  | 10720 | 10720
| 2.29 | Rig Mats | 71442 |  | 71442
0
0
0
0
0
0
0
0
|  | Total | 92825.7628 | 151520.0604 | 244345.8232
Contractor

## CO007
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO7
|  |  |  | Billing Date: | 2016-01-15
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
2016-01-15 | 2.1 a) | Rock Trench | 19134.69 |  | 19134.69
| 2.2 b) | Rockshield | 21351.076 |  | 21351.076
| 2.3 a) c) d) | Sand Bedding/Padding From Borrow Pits | 9408 |  | 9408
| 2.14 b) | Install Pipe To Extra Depth |  |  | 0
| 2.18 b) | Vehicle & Equipment Wash Stations |  |  | 0
| 2.29 | Rig Mats | 36450 |  | 36450
0
0
0
0
0
0
0
0
|  | Total | 86343.766 | 0 | 86343.766
Contractor

## CO009
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO9
|  |  | Billing Date: | 2016-01-31
Item | Digging Test Holes For Sump Suitability
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Digging Test Holes | 4889.75 |  | 4889.75
Tickets 0153, 0401, 0426, 0430, 0431, 0432
| Total | 4889.75 | 0 | 4889.75
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 20000 | 4889.75
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO9
|  |  | Billing Date: | 2016-02-15
Item | Digging Test Holes For Sump Suitability
Date | Description | This Period | Previous | Total To Date
2016-02-15 | Digging Test Holes |  | 4889.75 | 4889.75
| Tickets 0677, 0678 | 10369.43 |  | 10369.43
| Total | 10369.43 | 4889.75 | 15259.18
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 20000 | 15259.18
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO9
|  |  | Billing Date: | 2016-03-31
Item | Digging Test Holes For Sump Suitability
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Digging Test Holes |  | 4889.75 | 4889.75
Tickets 0153, 0401, 0426, 0430, 0431, 0432
2016-02-29 | Digging Test Holes |  | 10369.43 | 10369.43
Tickets 0677, 0678
2016-03-31 | Digging Test Holes | 3550.07 |  | 3550.07
Ticket 1439
| Total | 3550.07 | 15259.18 | 18809.25
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 20000 | 18809.25
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO9
|  |  | Billing Date: | 2016-05-15
Item | Digging Test Holes For Sump Suitability
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Digging Test Holes |  | 4889.75 | 4889.75
Tickets 0153, 0401, 0426, 0430, 0431, 0432
2016-02-29 | Digging Test Holes |  | 10369.43 | 10369.43
Tickets 0677, 0678
2016-03-31 | Digging Test Holes |  | 3550.07 | 3550.07
Ticket 1439
| Total | 0 | 18809.25 | 18809.25
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 20000 | 18809.25
Complete

## CO010
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO10
|  |  | Billing Date: | 2016-01-31
Item | Installation & Removal Of Access Mats At River 56+109
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Installation & Trucking Of Mats For HDD Pad | 41482.8 |  | 41482.8
Total is 540 mats @ $153.64 per mat:
50% For Installation; Remaining 50% Upon Removal
| Total | 41482.8 | 0 | 41482.8
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 80000 | 41482.8
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO10
|  |  | Billing Date: | 2016-02-15
Item | Installation & Removal Of Access Mats At River 56+109
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Installation & Trucking Of Mats For HDD Pad |  | 41482.8 | 41482.8
Total is 540 mats @ $153.64 per mat:
50% For Installation; Remaining 50% Upon Removal
2016-02-15 | Installation & Trucking Of Mats For HDD Pad | 38517.2 |  | 38517.2
50% For Removal
Note: Balance of work ($2,965.60) to be issued in
another Change Order
| Total | 38517.2 | 41482.8 | 80000
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 80000 | 80000
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO10
|  |  | Billing Date: | 2016-05-15
Item | Installation & Removal Of Access Mats At River 56+109
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Installation & Trucking Of Mats For HDD Pad |  | 41482.8 | 41482.8
Total is 540 mats @ $153.64 per mat:
50% For Installation; Remaining 50% Upon Removal
2016-02-15 | Installation & Trucking Of Mats For HDD Pad |  | 38517.2 | 38517.2
50% For Removal
Note: Balance of work ($2,965.60) to be issued in
another Change Order
| Total | 0 | 80000 | 80000
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 80000 | 80000
Complete

## CO011
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO11
|  |  | Billing Date: | 2016-01-31
Item | Digging Sumps For Mud Containment
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Digging Sumps | 18307.84 |  | 18307.84
Tickets 0157, 0168, 0169
| Total | 18307.84 | 0 | 18307.84
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 60000 | 18307.84
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO11
|  |  | Billing Date: | 2016-02-15
Item | Digging Sumps For Mud Containment
Date | Description | This Period | Previous | Total To Date
2016-02-15 | Digging Sumps |  | 18307.84 | 18307.84
| Tickets 0679, 0680, 0681, 0682, 0683, 0684, 0685, | 28369.24 |  | 28369.24
0686, 0688
| Total | 28369.24 | 18307.84 | 46677.08
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 60000 | 46677.08
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO11
|  |  | Billing Date: | 2016-02-29
Item | Digging Sumps For Mud Containment
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Digging Sumps- Tickets 0157, 0168, 0169 |  | 18307.84 | 18307.84
2016-02-15 | Digging Sumps- Tickets 0679, 0680, 0681, 0682, |  | 28369.24 | 28369.24
0683, 0684, 0685,0686, 0688
2016-02-29 | Digging Sumps- Tickets 0687, 0689, 0699, 1426 | 13079.3 |  | 13079.3
| Total | 13079.3 | 46677.08 | 59756.38
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 60000 | 59756.38
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO11
|  |  | Billing Date: | 2016-05-15
Item | Digging Sumps For Mud Containment
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Digging Sumps- Tickets 0157, 0168, 0169 |  | 18307.84 | 18307.84
2016-02-15 | Digging Sumps- Tickets 0679, 0680, 0681, 0682, |  | 28369.24 | 28369.24
0683, 0684, 0685,0686, 0688
2016-02-29 | Digging Sumps- Tickets 0687, 0689, 0699, 1426 |  | 13079.3 | 13079.3
| Total | 0 | 59756.38 | 59756.38
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 60000 | 59756.38
Complete

## CO012
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C012
|  |  | Billing Date: | 2016-05-15
Item | Performance Vac- Mud Disposal
Date | Description | This Period | Previous | Total To Date
0
| Total | 0 | 0 | 0
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 25000 | 0

## CO013
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO13
|  |  | Billing Date: | 2016-01-31
Item | Rework Due To Survey Error
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Rework Due To Survey Error (Estimate Revised) | 3397.2 |  | 3397.2
Ticket 0226
| Total | 3397.2 | 0 | 3397.2
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 4250.2 | 3397.2
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO-13
|  |  | Billing Date: | 2016-05-15
Item | Rework Due To Survey Error
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Rework Due To Survey Error (Estimate Revised) |  | 3397.2 | 3397.2
Ticket 0226
| Total | 0 | 3397.2 | 3397.2
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 4250.2 | 3397.2
Complete

## CO014
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO14
|  |  | Billing Date: | 2016-01-31
Item | Paragon Soil Test Holes & Sandblast Defective Repairs
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Paragon Test Holes Ticket 0437 | 686.9 |  | 686.9
| Total | 686.9 | 0 | 686.9
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 2070.78 | 686.9
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO14
|  |  | Billing Date: | 2016-05-15
Item | Paragon Soil Test Holes & Sandblast Defective Repairs
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Paragon Test Holes Ticket 0437 |  | 686.9 | 686.9
Sandblast Defective Repairs Ticket 0176
| (Ticket 0176 was $483.30 over the CO so I put it in | 1867.18
the Miscellaneous CO15)
| Total | 1867.18 | 686.9 | 686.9
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 2070.78 | 686.9
Complete

## CO015
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C015
|  |  | Billing Date: | 2016-02-15
Item | Miscellaneous Additional Costs
Date | Description | This Period | Previous | Total To Date
2016-01-13 | 0128- Pull Out Badger Hydrovac | 1985.36 |  | 1985.36
2015-12-21 | TKT00160522- Badger Water Haul- No TDL Available | 1978.2 |  | 1978.2
2015-12-20 | TKT00160521- Badger Water Haul- No TDL Available | 2167.2 |  | 2167.2
2015-12-20 | TKT00226429- Badger Water Haul- No TDL Available | 2167.2 |  | 2167.2
2016-02-11 | 0181-Repair Coating After Buffing Due To Defect | 231.94 |  | 231.94
2015-12-03 | Badger Hydrovac Mud Disposal To Secure | 945 |  | 945
| Total | 9474.9 | 0 | 9474.9
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 50000 | 9474.9
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C015
|  |  | Billing Date: | 2016-03-15
Item | Miscellaneous Additional Costs
Date | Description | This Period | Previous | Total To Date
2016-01-13 | 0128- Pull Out Badger Hydrovac |  | 1985.36 | 1985.36
2015-12-21 | TKT00160522- Badger Water Haul- No TDL Available |  | 1978.2 | 1978.2
2015-12-20 | TKT00160521- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2015-12-20 | TKT00226429- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2016-02-11 | 0181-Repair Coating After Buffing Due To Defect |  | 231.94 | 231.94
2015-12-03 | Badger Hydrovac Mud Disposal To Secure 0618 |  | 945 | 945
TKT00210800
2016-03-15 | Sandblast Defective Repairs Ticket 0176 | 1867.18 |  | 1867.18
(Ticket 0176 was $483.30 over the C014 limit so it
will be placed in C015)
| Total | 1867.18 | 9474.9 | 11342.08
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 50000 | 11342.08
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO#
C015
|  |  | Billing Date: | 2016-03-31
Item | Miscellaneous Additional Costs
Date | Description | This Period | Previous | Total To Date
2016-01-13 | 0128- Pull Out Badger Hydrovac |  | 1985.36 | 1985.36
2015-12-21 | TKT00160522- Badger Water Haul- No TDL Available |  | 1978.2 | 1978.2
2015-12-20 | TKT00160521- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2015-12-20 | TKT00226429- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2016-02-11 | 0181-Repair Coating After Buffing Due To Defect |  | 231.94 | 231.94
2015-12-03 | Badger Hydrovac Mud Disposal To Secure 0618 |  | 945 | 945
TKT00210800
2016-03-15 | Sandblast Defective Repairs Ticket 0176 |  | 1867.18 | 1867.18
2016-03-31 | Digging Test Holes- 0697 | 3195.16 |  | 3195.16
(Would have put C009 over by $2,004.41 so it will be
placed in C015)
| Total | 3195.16 | 11342.08 | 14537.24
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 50000 | 14537.24
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C015
|  |  | Billing Date: | 2016-04-15
Item | Miscellaneous Additional Costs
Date | Description | This Period | Previous | Total To Date
2016-01-13 | 0128- Pull Out Badger Hydrovac |  | 1985.36 | 1985.36
2015-12-21 | TKT00160522- Badger Water Haul- No TDL Available |  | 1978.2 | 1978.2
2015-12-20 | TKT00160521- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2015-12-20 | TKT00226429- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2016-02-11 | 0181-Repair Coating After Buffing Due To Defect |  | 231.94 | 231.94
2015-12-03 | Badger Hydrovac Mud Disposal To Secure 0618 |  | 945 | 945
TKT00210800
2016-03-15 | Sandblast Defective Repairs Ticket 0176 |  | 1867.18 | 1867.18
2016-03-31 | Digging Test Holes- 0697 |  | 3195.16 | 3195.16
(Would have put C009 over by $2,004.41 so it will be
placed in C015)
2016-04-15 | Badger Hydrovac Expose For Secure TKT00228896 | 1829.63 |  | 1829.63
| Conoco Rep Request Invoice #16-0089 | 850.5 |  | 850.5
| Remove Ribbons From Cutbank- 1470 | 1639.92 |  | 1639.92
| Total | 4320.05 | 14537.24 | 18857.29
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 50000 | 18857.29
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C015
|  |  | Billing Date: | 2016-04-30
Item | Miscellaneous Additional Costs
Date | Description | This Period | Previous | Total To Date
2016-01-13 | 0128- Pull Out Badger Hydrovac |  | 1985.36 | 1985.36
2015-12-21 | TKT00160522- Badger Water Haul- No TDL Available |  | 1978.2 | 1978.2
2015-12-20 | TKT00160521- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2015-12-20 | TKT00226429- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2016-02-11 | 0181-Repair Coating After Buffing Due To Defect |  | 231.94 | 231.94
2015-12-03 | Badger Hydrovac Mud Disposal To Secure 0618 |  | 945 | 945
TKT00210800
2016-03-15 | Sandblast Defective Repairs Ticket 0176 |  | 1867.18 | 1867.18
2016-03-31 | Digging Test Holes- 0697 |  | 3195.16 | 3195.16
(Would have put C009 over by $2,004.41 so it will be
placed in C015)
2016-04-15 | Badger Hydrovac Expose For Secure TKT00228896 |  | 1829.63 | 1829.63
| Conoco Rep Request Invoice #16-0089 |  | 850.5 | 850.5
| Remove Ribbons From Cutbank- 1470 |  | 1639.92 | 1639.92
2016-04-30 | Hydrovac Support For Cathodic Protection- 0129 | 924 |  | 924
| TCR Vac For Bore Support- 0715 | 924 |  | 924
| Inspect Mainline- 1311 | 4784.76 |  | 4784.76
| NuVista Road Maintenance- 1931 | 2817.88 |  | 2817.88
| Install Nipple For Bleed At Kakwa Station- 1851 | 1500.96 |  | 1500.96
| Total | 10951.6 | 18857.29 | 29808.89
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 50000 | 29808.89
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C015
|  |  | Billing Date: | 2016-05-15
Item | Miscellaneous Additional Costs
Date | Description | This Period | Previous | Total To Date
2016-01-13 | 0128- Pull Out Badger Hydrovac |  | 1985.36 | 1985.36
2015-12-21 | TKT00160522- Badger Water Haul- No TDL Available |  | 1978.2 | 1978.2
2015-12-20 | TKT00160521- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2015-12-20 | TKT00226429- Badger Water Haul- No TDL Available |  | 2167.2 | 2167.2
2016-02-11 | 0181-Repair Coating After Buffing Due To Defect |  | 231.94 | 231.94
2015-12-03 | Badger Hydrovac Mud Disposal To Secure 0618 |  | 945 | 945
TKT00210800
2016-03-15 | Sandblast Defective Repairs Ticket 0176 |  | 1867.18 | 1867.18
2016-03-31 | Digging Test Holes- 0697 |  | 3195.16 | 3195.16
(Would have put C009 over by $2,004.41 so it will be
placed in C015)
2016-04-15 | Badger Hydrovac Expose For Secure TKT00228896 |  | 1829.63 | 1829.63
| Conoco Rep Request Invoice #16-0089 |  | 850.5 | 850.5
| Remove Ribbons From Cutbank- 1470 |  | 1639.92 | 1639.92
2016-04-30 | Hydrovac Support For Cathodic Protection- 0129 |  | 924 | 924
| TCR Vac For Bore Support- 0715 |  | 924 | 924
| Inspect Mainline- 1311 |  | 4784.76 | 4784.76
| NuVista Road Maintenance- 1931 |  | 2817.88 | 2817.88
| Install Nipple For Bleed At Kakwa Station- 1851 |  | 1500.96 | 1500.96
2016-05-15 | Test Leads: Tickets 1645, 0709 | 939.4 |  | 939.4
| Test Leads: Tickets 1331, 1648 | 829.66 |  | 829.66
| Test Leads: Tickets 1473, 1649 | 469.7 |  | 469.7
| Total | 2238.76 | 29808.89 | 32047.65
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 50000 | 32047.65

## CO016
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO16
|  |  | Billing Date: | 2016-01-31
Item | Damage To Irrigation Pipe
Date | Description | This Period | Previous | Total To Date
2015-12-12 | Energy Fluid Service: Invoice #2015-0032 | 5706 |  | 5706
| Handling Fee/Mark Up @ 5%: | 285.3 |  | 285.3
| Total | 5991.3 | 0 | 5991.3
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 5991.3 | 5991.3
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO16
|  |  | Billing Date: | 2016-05-15
Item | Damage To Irrigation Pipe
Date | Description | This Period | Previous | Total To Date
2015-12-12 | Energy Fluid Service: Invoice #2015-0032 |  | 5706 | 5706
| Handling Fee/Mark Up @ 5%: |  | 285.3 | 285.3
| Total | 0 | 5991.3 | 5991.3
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 5991.3 | 5991.3
Complete

## CO017
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO17
|  |  | Billing Date: | 2016-01-31
Item | Unloading Mats- $19.41 Per Mat
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Offload Company Supplied Mats | 5027.19 |  | 5027.19
259 Mats @ $19.41/mat To Dec 19, 2015
| Total | 5027.19 | 0 | 5027.19
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 19408 | 5027.19
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO17
|  |  | Billing Date: | 2016-02-29
Item | Unloading Mats- $19.41 Per Mat
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Offload Company Supplied Mats |  | 5027.19 | 5027.19
259 Mats @ $19.41/mat To Dec 19, 2015
2016-02-24 | Offload Company Supplied Mats- NTL 6826 | 562.89 |  | 562.89
29 Mats @ $19.41/mat
2016-02-25 | Offload Company Supplied Mats- NTL 6826 | 368.79 |  | 368.79
19 Mats @ $19.41/mat
Total: 307 Mats To Date
| Total | 931.68 | 5027.19 | 5958.87
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 19408 | 5958.87
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO17
|  |  | Billing Date: | 2016-05-15
Item | Unloading Mats- $19.41 Per Mat
Date | Description | This Period | Previous | Total To Date
2016-01-31 | Offload Company Supplied Mats |  | 5027.19 | 5027.19
259 Mats @ $19.41/mat To Dec 19, 2015
2016-02-24 | Offload Company Supplied Mats- NTL 6826 |  | 562.89 | 562.89
29 Mats @ $19.41/mat
2016-02-25 | Offload Company Supplied Mats- NTL 6826 |  | 368.79 | 368.79
19 Mats @ $19.41/mat
Total: 307 Mats To Date
| Total | 0 | 5958.87 | 5958.87
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 19408 | 5958.87

## CO018
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO18
|  |  | Billing Date: | 2016-02-29
Item | Water Haul- ROW Freezing
Date | Description | This Period | Previous | Total To Date
2016-01-07 | Haul Water For ROW Freezing (No TDLs In Place) | 23684.06 |  | 23684.06
| Total | 23684.06 | 0 | 23684.06
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 23684.06 | 23684.06
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO18
|  |  | Billing Date: | 2016-05-15
Item | Water Haul- ROW Freezing
Date | Description | This Period | Previous | Total To Date
2016-01-07 | Haul Water For ROW Freezing (No TDLs In Place) |  | 23684.06 | 23684.06
| Total | 0 | 23684.06 | 23684.06
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 23684.06 | 23684.06
Complete

## CO019
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO19
|  |  | Billing Date: | 2016-03-15
Item | Consultant For Long Run Crossing
Date | Description | This Period | Previous | Total To Date
2016-03-15 | Avid Resource Management Jan 11-14 | 4410 |  | 4410
Invoices 1362, 1363, 1366, 1367
| Total | 4410 | 0 | 4410
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 5040 | 4410
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO19
|  |  | Billing Date: | 2016-05-15
Item | Consultant For Long Run Crossing
Date | Description | This Period | Previous | Total To Date
2016-03-15 | Avid Resource Management Jan 11-14 |  | 4410 | 4410
| Invoices 1362, 1363, 1366, 1367 |  |  | 0
| Total | 0 | 4410 | 4410
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 5040 | 4410

## CO020
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO20
|  |  | Billing Date: | 2016-01-31
Item | Drilling Support- Extended Schedule At River
Date | Description | This Period | Previous | Total To Date
2016-01-31 | 24 Additional Shifts @ $3,694.48 | 88667.52 |  | 88667.52
12 Days: Jan 10 to Jan 21, 2016
| Total | 88667.52 | 0 | 88667.52
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 88667.52 | 88667.52
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO20
|  |  | Billing Date: | 2016-05-15
Item | Drilling Support- Extended Schedule At River
Date | Description | This Period | Previous | Total To Date
2016-01-31 | 24 Additional Shifts @ $3,694.48 |  | 88667.52 | 88667.52
12 Days: Jan 10 to Jan 21, 2016
| Total | 0 | 88667.52 | 88667.52
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 88667.52 | 88667.52
Complete

## CO021
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO21
|  |  | Billing Date: | 2016-02-15
Item | Inadvertant Mud Release Clean Up
Date | Description | This Period | Previous | Total To Date
2015-12-19 | 0580- IMR Clean Up | 21412.1 |  | 21412.1
2015-12-20 | 0276- IMR Clean Up | 32413.12 |  | 32413.12
2015-12-21 | 0277- IMR Clean Up | 6407.16 |  | 6407.16
| Total | 60232.38 | 0 | 60232.38
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 65808.36 | 60232.38
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO21
|  |  | Billing Date: | 2016-05-15
Item | Inadvertant Mud Release Clean Up
Date | Description | This Period | Previous | Total To Date
2015-12-19 | 0580- IMR Clean Up |  | 21412.1 | 21412.1
2015-12-20 | 0276- IMR Clean Up |  | 32413.12 | 32413.12
2015-12-21 | 0277- IMR Clean Up |  | 6407.16 | 6407.16
| Total | 0 | 60232.38 | 60232.38
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 65808.36 | 60232.38
Complete

## CO022
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO22
|  |  | Billing Date: | 2016-02-15
Item | Safety Stand Down
Date | Description | This Period | Previous | Total To Date
2016-01-18 | Safety Stand Down | 215562.16 |  | 215562.16
| Total | 215562.16 | 0 | 215562.16
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 215855.08 | 215562.16
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO22
|  |  | Billing Date: | 2016-05-15
Item | Safety Stand Down
Date | Description | This Period | Previous | Total To Date
2016-01-18 | Safety Stand Down |  | 215562.16 | 215562.16
| Total | 0 | 215562.16 | 215562.16
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 215855.08 | 215562.16
Complete

## CO023
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO23
|  |  | Billing Date: | 2016-03-15
Item | Additional Hydrovac Support
Date | Description | This Period | Previous | Total To Date
2016-03-15 | Additional Hydrovac Support | 76263.46 |  | 76263.46
| Total | 76263.46 | 0 | 76263.46
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 359953.32 | 76263.46
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO23
|  |  | Billing Date: | 2016-03-31
Item | Additional Hydrovac Support
Date | Description | This Period | Previous | Total To Date
2016-03-15 | Additional Hydrovac Support |  | 76263.46 | 76263.46
2016-03-31 | Additional Hydrovac Support | 283629.82 |  | 283629.82
| Total | 283629.82 | 76263.46 | 359893.28
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 359953.32 | 359893.28
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO23
|  |  | Billing Date: | 2016-05-15
Item | Additional Hydrovac Support
Date | Description | This Period | Previous | Total To Date
2016-03-15 | Additional Hydrovac Support |  | 76263.46 | 76263.46
2016-03-31 | Additional Hydrovac Support |  | 283629.82 | 283629.82
| Total | 0 | 359893.28 | 359893.28
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 359953.32 | 359893.28
Complete

## CO024
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO-24
|  |  | Billing Date: | 2016-03-31
Item | Additional Tie-In Support & HDD Crews
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Additional Tie-In Support: W2K-RFI-071
| March 31 Payment (25% of $763,439.04) | 190859.76 |  | 190859.76
| April 15 Payment (50% of $763,439.04) |  |  | 0
| April 31 Payment (25% of $763,439.04) |  |  | 0
2016-03-31 | HDD Support Crews To March 31: W2K-RFI-072 | 1201072.32 |  | 1201072.32
March 31 Payment (100% of $1,201,072.32)
| Total | 1391932.08 | 0 | 1391932.08
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 1964511.36 | 1391932.08
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO-24
|  |  | Billing Date: | 2016-04-15
Item | Additional Tie-In Support & HDD Crews
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Additional Tie-In Support: W2K-RFI-071
| March 31 Payment (25% of $763,439.04) |  | 190859.76 | 190859.76
April 31 Payment (25% of $763,439.04)
2016-03-31 | HDD Support Crews To March 31: W2K-RFI-072 |  | 1201072.32 | 1201072.32
March 31 Payment (100% of $1,201,072.32)
2016-04-15 | Additional Tie-In Support: W2K-RFI-071
| April 15 Payment (50% of $763,439.04) | 381719.52 |  | 381719.52
| Total | 381719.52 | 1391932.08 | 1773651.6
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 1964511.36 | 1773651.6
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO-24
|  |  | Billing Date: | 2016-04-30
Item | Additional Tie-In Support & HDD Crews
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Additional Tie-In Support: W2K-RFI-071
| March 31 Payment (25% of $763,439.04) |  | 190859.76 | 190859.76
2016-03-31 | HDD Support Crews To March 31: W2K-RFI-072
| March 31 Payment (100% of $1,201,072.32) |  | 1201072.32 | 1201072.32
2016-04-15 | Additional Tie-In Support: W2K-RFI-071
| April 15 Payment (50% of $763,439.04) |  | 381719.52 | 381719.52
2016-04-30 | Additional Tie-In Support: W2K-RFI-071 | 190859.76 |  | 190859.76
April 30 Payment (25% of $763,439.04)
| Total | 190859.76 | 1773651.6 | 1964511.36
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 1964511.36 | 1964511.36
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO-24
|  |  | Billing Date: | 2016-05-15
Item | Additional Tie-In Support & HDD Crews
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Additional Tie-In Support: W2K-RFI-071
| March 31 Payment (25% of $763,439.04) |  | 190859.76 | 190859.76
2016-03-31 | HDD Support Crews To March 31: W2K-RFI-072
| March 31 Payment (100% of $1,201,072.32) |  | 1201072.32 | 1201072.32
2016-04-15 | Additional Tie-In Support: W2K-RFI-071
| April 15 Payment (50% of $763,439.04) |  | 381719.52 | 381719.52
2016-04-30 | Additional Tie-In Support: W2K-RFI-071 |  | 190859.76 | 190859.76
April 30 Payment (25% of $763,439.04)
| Total | 0 | 1964511.36 | 1964511.36
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 1964511.36 | 1964511.36
Complete

## CO026UPI
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO26
|  |  |  | Billing Date: | 2016-01-31
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
2016-01-31 | 2.1 a) | Rock Trench | 1914.8 |  | 1914.8
| 2.2 b) | Rockshield | 22816.42 |  | 22816.42
| 2.3 a) b) c) d) | Sand Bedding/Padding From Borrow Pits | 17472 |  | 17472
| 2.29 | Rig Mats | 38880 |  | 38880
| 2.31 | Move Around | 4500 |  | 4500
0
0
0
0
0
0
0
0
0
|  | Total | 85583.22 | 0 | 85583.22
Contractor

## CO027
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO027
|  |  | Billing Date: | 2016-02-29
Item | Existing Piping Removal At Station
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Existing Piping Removal At Bald Mountain Station
| Tickets 0753 to 0760 | 78334.63 |  | 78334.63
| Total | 78334.63 | 0 | 78334.63
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 200000 | 78334.63
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO027
|  |  | Billing Date: | 2016-03-15
Item | Existing Piping Removal At Station
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Existing Piping Removal At Station |  | 78334.63 | 78334.63
2016-03-15 | Badger Ticket: TKT00232464 plus 5% mark up | 3649.1 |  | 3649.1
| Badger Ticket: TKT00233225 plus 5% mark up | 3037.13 |  | 3037.13
| Total | 6686.23 | 78334.63 | 85020.86
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 200000 | 85020.86
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO027
|  |  | Billing Date: | 2016-05-15
Item | Existing Piping Removal At Station
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Existing Piping Removal At Station |  | 78334.63 | 78334.63
2016-03-15 | Badger Ticket: TKT00232464 plus 5% mark up |  | 3649.1 | 3649.1
| Badger Ticket: TKT00233225 plus 5% mark up |  | 3037.13 | 3037.13
| Total | 0 | 85020.86 | 85020.86
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 200000 | 85020.86
Complete

## CO028UPI
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO028
|  |  |  | Billing Date: | 2016-02-15
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
2016-02-15 | 2.1 a) | Rock Trench | 4031.8 |  | 4031.8
| 2.2 b) | Rockshield | 79893.2 |  | 79893.2
| 2.3 d) | Sand Bedding/Padding From Borrow Pits | 27328 |  | 27328
| 2.22 | Cut Out And Replace Welds | 7780 |  | 7780
| 2.29 | Rig Mats | 12150 |  | 12150
0
0
0
0
0
0
0
0
0
|  | Total | 131183 | 0 | 131183
Contractor

## CO029
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO029
|  |  | Billing Date: | 2016-02-29
Item | Stumping & Grubbing Not Completed By Clearing Contractor
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Stumping & Grubbing Not Completed By Clearing
| Tickets 0601, 0602 | 22059.31 |  | 22059.31
| Total | 22059.31 | 0 | 22059.31
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 22069.31 | 22059.31
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO029
|  |  | Billing Date: | 2016-05-15
Item | Stumping & Grubbing Not Completed By Clearing Contractor
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Stumping & Grubbing Not Completed By Clearing
| Tickets 0601, 0602 |  | 22059.31 | 22059.31
| Total | 0 | 22059.31 | 22059.31
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 22069.31 | 22059.31
Complete

## CO030
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO030
|  |  | Billing Date: | 2016-02-29
Item | 24 Hr Medic Coverage Additional To C004
Date | Description | This Period | Previous | Total To Date
2016-02-29 | 24 Hr Medic Coverage Additional To C004
| (Feb 5-Feb 29) | 55125 |  | 55125
| Total | 55125 | 0 | 55125
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 150785.25 | 55125
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO030
|  |  | Billing Date: | 2016-03-15
Item | 24 Hr Medic Coverage Additional To C004
Date | Description | This Period | Previous | Total To Date
2016-02-29 | 24 Hr Medic Coverage Additional To C004 |  | 55125 | 55125
(Feb 5-Feb 29)
2016-03-15 | 24 Hr Medic Coverage Additional To C004 | 34177.5 |  | 34177.5
(Mar 1-15)
| Total | 34177.5 | 55125 | 89302.5
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 150785.25 | 89302.5
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO030
|  |  | Billing Date: | 2016-03-31
Item | 24 Hr Medic Coverage Additional To C004
Date | Description | This Period | Previous | Total To Date
2016-02-29 | 24 Hr Medic Coverage Additional To C004 |  | 55125 | 55125
(Feb 5-Feb 29)
2016-03-15 | 24 Hr Medic Coverage Additional To C004 |  | 34177.5 | 34177.5
(Mar 1-15)
2016-03-31 | 24 Hr Medic Coverage Additional To C004 | 31710 |  | 31710
(Mar 16-31)
| Total | 31710 | 89302.5 | 121012.5
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 150785.25 | 121012.5
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO030
|  |  | Billing Date: | 2016-04-15
Item | 24 Hr Medic Coverage Additional To C004
Date | Description | This Period | Previous | Total To Date
2016-02-29 | 24 Hr Medic Coverage Additional To C004 |  | 55125 | 55125
(Feb 5-Feb 29)
2016-03-15 | 24 Hr Medic Coverage Additional To C004 |  | 34177.5 | 34177.5
(Mar 1-15)
2016-03-31 | 24 Hr Medic Coverage Additional To C004 |  | 31710 | 31710
(Mar 16-31)
2016-04-15 | 24 Hr Medic Coverage Additional To C004 | 16537.5 |  | 16537.5
(Mar 1-8)
| Total | 16537.5 | 121012.5 | 137550
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 150785.25 | 137550
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO030
|  |  | Billing Date: | 2016-05-15
Item | 24 Hr Medic Coverage Additional To C004
Date | Description | This Period | Previous | Total To Date
2016-02-29 | 24 Hr Medic Coverage Additional To C004 |  | 55125 | 55125
(Feb 5-Feb 29)
2016-03-15 | 24 Hr Medic Coverage Additional To C004 |  | 34177.5 | 34177.5
(Mar 1-15)
2016-03-31 | 24 Hr Medic Coverage Additional To C004 |  | 31710 | 31710
(Mar 16-31)
2016-04-15 | 24 Hr Medic Coverage Additional To C004 |  | 16537.5 | 16537.5
(Mar 1-8)
2016-04-30 | 24 Hr Medic Coverage Additional To C004 |  |  | 0
(Mar ?-?)
| Total | 0 | 137550 | 137550
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 150785.25 | 137550
Complete

## CO031
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO031
|  |  | Billing Date: | 2016-02-29
Item | Install/Remove/Truck Access Mats- Addit. To C010
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Install/Remove/Truck Access Mats- Addit. To C010
| Note: This is balance of work ($2,965.60) from | 2965.6 |  | 2965.6
Change Order C010
| Total | 2965.6 | 0 | 2965.6
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 2965.6 | 2965.6
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO031
|  |  | Billing Date: | 2016-05-15
Item | Install/Remove/Truck Access Mats- Addit. To C010
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Install/Remove/Truck Access Mats- Addit. To C010
| Note: This is balance of work ($2,965.60) from |  | 2965.6 | 2965.6
Change Order C010
| Total | 0 | 2965.6 | 2965.6
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 2965.6 | 2965.6
Complete

## CO033
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO033
|  |  | Billing Date: | 2016-02-29
Item | Mix & Backfill HDD Mud Sump Pits
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Mix & Backfill HDD Mud Sump Pits
| Tickets 0436, 0437, 0438, 0439 | 14188.83 |  | 14188.83
| Total | 14188.83 | 0 | 14188.83
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 165080.96 | 14188.83
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO033
|  |  | Billing Date: | 2016-03-31
Item | Mix & Backfill HDD Mud Sump Pits
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Mix & Backfill HDD Mud Sump Pits
| Tickets: 0436, 0437, 0438, 0439 |  | 14188.83 | 14188.83
2016-03-31 | Mix & Backfill HDD Mud Sump Pits | 66930.13 |  | 66930.13
Tickets: 0446, 0449, 0450, 1455, 1456, 1458, 1457,
1459, 1462, 0150, 1463, 1026, 1464, 1443, 1027,
1444, 1445
| Total | 66930.13 | 14188.83 | 81118.96
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 165080.96 | 81118.96
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO033
|  |  | Billing Date: | 2016-04-15
Item | Mix & Backfill HDD Mud Sump Pits
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Mix & Backfill HDD Mud Sump Pits |  | 14188.83 | 14188.83
Tickets: 0436, 0437, 0438, 0439
2016-03-31 | Mix & Backfill HDD Mud Sump Pits |  | 66930.13 | 66930.13
Tickets: 0446, 0449, 0450, 1455, 1456, 1458, 1457,
1459, 1462, 0150, 1463, 1026, 1464, 1443, 1027,
1444, 1445
2016-04-15 | Mix & Backfill HDD Mud Sump Pits | 47362.37 |  | 47362.37
Tickets: 1031, 0539, 1446, 0953, 0540, 0541, 0954,
1447, 1467, 0957, 1450
| Total | 47362.37 | 81118.96 | 128481.33
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 165080.96 | 128481.33
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO033
|  |  | Billing Date: | 2016-04-30
Item | Mix & Backfill HDD Mud Sump Pits
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Mix & Backfill HDD Mud Sump Pits |  | 14188.83 | 14188.83
Tickets: 0436, 0437, 0438, 0439
2016-03-31 | Mix & Backfill HDD Mud Sump Pits |  | 66930.13 | 66930.13
Tickets: 0446, 0449, 0450, 1455, 1456, 1458, 1457,
1459, 1462, 0150, 1463, 1026, 1464, 1443, 1027,
1444, 1445
2016-04-15 | Mix & Backfill HDD Mud Sump Pits |  | 47362.37 | 47362.37
Tickets: 1031, 0539, 1446, 0953, 0540, 0541, 0954,
1447, 1467, 0957, 1450
2016-04-30 | Mix & Backfill HDD Mud Sump Pits | 36559.87 |  | 36559.87
Tickets: 0964, 0965, 0969, 0970, 0973
| Total | 36559.87 | 128481.33 | 165041.2
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 165080.96 | 165041.2
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO033
|  |  | Billing Date: | 2016-05-15
Item | Mix & Backfill HDD Mud Sump Pits
Date | Description | This Period | Previous | Total To Date
2016-02-29 | Mix & Backfill HDD Mud Sump Pits |  | 14188.83 | 14188.83
Tickets: 0436, 0437, 0438, 0439
2016-03-31 | Mix & Backfill HDD Mud Sump Pits |  | 66930.13 | 66930.13
Tickets: 0446, 0449, 0450, 1455, 1456, 1458, 1457,
1459, 1462, 0150, 1463, 1026, 1464, 1443, 1027,
1444, 1445
2016-04-15 | Mix & Backfill HDD Mud Sump Pits |  | 47362.37 | 47362.37
Tickets: 1031, 0539, 1446, 0953, 0540, 0541, 0954,
1447, 1467, 0957, 1450
2016-04-30 | Mix & Backfill HDD Mud Sump Pits |  | 36559.87 | 36559.87
Tickets: 0964, 0965, 0969, 0970, 0973
| Total | 0 | 165041.2 | 165041.2
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 165080.96 | 165041.2
Complete

## CO034
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO034
|  |  | Billing Date: | 2016-03-15
Item | Remove Merchantable Timber When Mills Were Closed
Date | Description | This Period | Previous | Total To Date
2016-03-15 | Remove Merchatable Timber
| 1701747 Alberta Ltd Invoice: #242 | 5512.5 |  | 5512.5
| Total | 5512.5 | 0 | 5512.5
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 5512.5 | 5512.5
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO034
|  |  | Billing Date: | 2016-05-15
Item | Remove Merchantable Timber When Mills Were Closed
Date | Description | This Period | Previous | Total To Date
2016-03-15 | Remove Merchatable Timber
| 1701747 Alberta Ltd Invoice: #242 |  | 5512.5 | 5512.5
| Total | 0 | 5512.5 | 5512.5
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 5512.5 | 5512.5
Complete

## CO035UPI
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO035
|  |  |  | Billing Date: | 2016-02-29
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
2016-02-29 | 2.1 a) | Rock Trench | 35207.68 |  | 35207.68
| 2.2 b) | Rockshield | 460059.58 |  | 460059.58
| 2.3 a) | Sand Bedding From Borrow Pits | 24102.4 |  | 24102.4
| 2.3 b) | Sand Padding (Top) From Borrow Pits | 26763.98 |  | 26763.98
| 2.3 d) | Sand Hauling From Borrow Pits | 75801.6 |  | 75801.6
| 2.22 | Cut Out And Replace Welds | 3890 |  | 3890
| 2.31 | Move Around (Bear Den At KP 48+800) | 20050 |  | 20050
|  | (Bending, Welding, Coating) |  |  | 0
0
0
0
0
0
0
|  | Total | 645875.24 | 0 | 645875.24
Contractor

## CO036UPI
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO036
|  |  |  | Billing Date: | 2016-03-15
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
2016-03-15 | 2.1 a) | Rock Trench | 3361.32 |  | 3361.32
| 2.2 b) | Rockshield | 243353.66 |  | 243353.66
| 2.3 d) | Sand Hauling From Borrow Pits | 5880 |  | 5880
| 2.31 | Move Around (Bear Den At KP 48+800) | 31899.9987 |  | 31899.9987
|  | (Part of Grade, Trenching, Lower-In & Backfill) |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Total | 284494.9787 | 0 | 284494.9787
Contractor

## CO037
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO037
|  |  | Billing Date: | 2016-03-15
Item | Water Trucks To Support HDD Rigs
Date | Description | This Period | Previous | Total To Date
2016-03-15 | Water Trucks (Feb 16-23) | 42875.6 |  | 42875.6
| Total | 42875.6 | 0 | 42875.6
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 67500 | 42875.6
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO037
|  |  | Billing Date: | 2016-05-15
Item | Water Trucks To Support HDD Rigs
Date | Description | This Period | Previous | Total To Date
2016-03-15 | Water Trucks (Feb 16-23) |  | 42875.6 | 42875.6
| Total | 0 | 42875.6 | 42875.6
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 67500 | 42875.6
Complete

## CO038
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO038
|  |  | Billing Date: | 2016-03-15
Item | Other Drill IMR Clean Up
Date | Description | This Period | Previous | Total To Date
2016-03-15 | River & KP 64+445 IMR Clean Up | 122366.91 |  | 122366.91
| Total | 122366.91 | 0 | 122366.91
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 197366.91 | 122366.91
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO038
|  |  | Billing Date: | 2016-03-31
Item | Other Drill IMR Clean Up
Date | Description | This Period | Previous | Total To Date
2016-03-15 | River & KP 64+445 IMR Clean Up |  | 122366.91 | 122366.91
2016-03-31 | KP 30+551 IMR Clean Up | 67863.74 |  | 67863.74
| Total | 67863.74 | 122366.91 | 190230.65
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 197366.91 | 190230.65
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO038
|  |  | Billing Date: | 2016-04-15
Item | Other Drill IMR Clean Up
Date | Description | This Period | Previous | Total To Date
2016-03-15 | River & KP 64+445 IMR Clean Up |  | 122366.91 | 122366.91
2016-03-31 | KP 30+551 IMR Clean Up |  | 67863.74 | 67863.74
2016-04-15 | River IMR Clean Up | 5479.88 |  | 5479.88
| Total | 5479.88 | 190230.65 | 195710.53
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 197366.91 | 195710.53
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO038
|  |  | Billing Date: | 2016-05-15
Item | Other Drill IMR Clean Up
Date | Description | This Period | Previous | Total To Date
2016-03-15 | River & KP 64+445 IMR Clean Up |  | 122366.91 | 122366.91
2016-03-31 | KP 30+551 IMR Clean Up |  | 67863.74 | 67863.74
2016-04-15 | River IMR Clean Up |  | 5479.88 | 5479.88
2016-05-15 | KP 39+600 Mud Clean Up | 1480.14 |  | 1480.14
| Total | 1480.14 | 195710.53 | 197190.67
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 197366.91 | 197190.67

## CO039
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO039
|  |  | Billing Date: | 2016-03-15
Item | X-Ray Auditor Call Backs
Date | Description | This Period | Previous | Total To Date
2016-03-15 | X-Ray Auditor Call Back | 5805.78 |  | 5805.78
Tickets: 0178, 0332, 0179, 0180, 0278
| Total | 5805.78 | 0 | 5805.78
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 9805.78 | 5805.78
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO039
|  |  | Billing Date: | 2016-05-15
Item | X-Ray Auditor Call Backs
Date | Description | This Period | Previous | Total To Date
2016-03-15 | X-Ray Auditor Call Back |  | 5805.78 | 5805.78
Tickets: 0178, 0332, 0179, 0180, 0278
| Total | 0 | 5805.78 | 5805.78
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 9805.78 | 5805.78

## CO040
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO040
|  |  | Billing Date: | 2016-03-31
Item | Delays Due To Clearing, Reps & Misc. Causes
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Delays Due to Clearing, Reps & Misc. Causes | 84077.7 |  | 84077.7
Tickets: 0604, 0617, 0606, 0330, 0613, 0707, 0708
0710, 0712
| Total | 84077.7 | 0 | 84077.7
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 104077.7 | 84077.7
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | C0040
|  |  | Billing Date: | 2016-05-15
Item | Delays Due To Clearing, Reps & Misc. Causes
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Delays Due to Clearing, Reps & Misc. Causes |  | 84077.7 | 84077.7
Tickets: 0604, 0617, 0606, 0330, 0613, 0707, 0708
0710, 0712
| Total | 0 | 84077.7 | 84077.7
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 104077.7 | 84077.7

## CO041
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO041
|  |  | Billing Date: | 2016-03-31
Item | Purchase Of Seed Mix
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Purchase of Seed Mix | 8411.63 |  | 8411.63
Invoice: Foster's Seed & Feed #230164
| Total | 8411.63 | 0 | 8411.63
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 10000 | 8411.63
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO041
|  |  | Billing Date: | 2016-04-30
Item | Purchase Of Seed Mix
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Purchase of Seed Mix |  | 8411.63 | 8411.63
Invoice: Foster's Seed & Feed #230164
2016-04-30 | Purchase of Seed Mix | 511.97 |  | 511.97
Invoice: Foster's Seed & Feed #230295
| Total | 511.97 | 8411.63 | 8923.6
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 10000 | 8923.6
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO041
|  |  | Billing Date: | 2016-05-15
Item | Purchase Of Seed Mix
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Purchase of Seed Mix |  | 8411.63 | 8411.63
Invoice: Foster's Seed & Feed #230164
2016-04-30 | Purchase of Seed Mix |  | 511.97 | 511.97
Invoice: Foster's Seed & Feed #230295
| Total | 0 | 8923.6 | 8923.6
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 10000 | 8923.6

## CO042UPI
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO042
|  |  |  | Billing Date: | 2016-03-31
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
2016-03-31 | 2.2 b) | Rockshield | 59762.28 |  | 59762.28
| 2.29 | Rig Mats | 6291 |  | 6291
0
0
0
0
0
0
0
0
0
0
0
0
|  | Total | 66053.28 | 0 | 66053.28
Contractor

## CO043
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO043
|  |  | Billing Date: | 2016-03-31
Item | Digging Sumps Additional To C011
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Digging Sumps Additional To C011 | 9370.55 |  | 9370.55
Tickets: 1440, 1441, 1442
| Total | 9370.55 | 0 | 9370.55
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 80000 | 9370.55
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO043
|  |  | Billing Date: | 2016-04-15
Item | Digging Sumps Additional To C011
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Digging Sumps Additional To C011 |  | 9370.55 | 9370.55
2016-04-15 | Digging Sumps Additional To C011 | 56999.37 |  | 56999.37
| Total | 56999.37 | 9370.55 | 66369.92
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 80000 | 66369.92
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO043
|  |  | Billing Date: | 2016-05-15
Item | Digging Sumps Additional To C011
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Digging Sumps Additional To C011 |  | 9370.55 | 9370.55
2016-04-15 | Digging Sumps Additional To C011 |  | 56999.37 | 56999.37
| Total | 0 | 66369.92 | 66369.92
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 80000 | 66369.92
Complete

## CO044
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO044
|  |  | Billing Date: | 2016-03-31
Item | Daylighting CNRL Pipelines At KP 24+804
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Daylighting CNRL Pipelines At KP 24+804 | 94936.83 |  | 94936.83
Tickets: 2010062, 0634, 0635, 0636, 0637, 0638
| Total | 94936.83 | 0 | 94936.83
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 122491.4 | 94936.83
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO044
|  |  | Billing Date: | 2016-04-15
Item | Daylighting CNRL Pipelines At KP 24+804
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Daylighting CNRL Pipelines At KP 24+804 |  | 94936.83 | 94936.83
Tickets: 2010062, 0634, 0635, 0636, 0637, 0638
2016-04-15 | Daylighting CNRL Pipelines At KP 24+804 | 6215.08 |  | 6215.08
Tickets: 0768, 0220, 0219
| Total | 6215.08 | 94936.83 | 101151.91
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 122491.4 | 101151.91
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO044
|  |  | Billing Date: | 2016-05-15
Item | Daylighting CNRL Pipelines At KP 24+804
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Daylighting CNRL Pipelines At KP 24+804 |  | 94936.83 | 94936.83
Tickets: 2010062, 0634, 0635, 0636, 0637, 0638
2016-04-15 | Daylighting CNRL Pipelines At KP 24+804 |  | 6215.08 | 6215.08
Tickets: 0768, 0220, 0219
| Total | 0 | 101151.91 | 101151.91
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 122491.4 | 101151.91
Complete

## CO045
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO045
|  |  | Billing Date: | 2016-03-31
Item | Hydrovac Support Additional To C023
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Hydrovac Support Additional To C023 | 23420.68 |  | 23420.68
Tickets: 0807, 0808, 1242, 0809, 0810, 0772, 0771
| Total | 23420.68 | 0 | 23420.68
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 54750.6 | 23420.68
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO045
|  |  | Billing Date: | 2016-04-15
Item | Hydrovac Support Additional To C023
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Hydrovac Support Additional To C023 |  | 23420.68 | 23420.68
Tickets: 0807, 0808, 1242, 0809, 0810, 0772, 0771
2016-04-15 | Hydrovac Support Additional To C023 | 8670.08 |  | 8670.08
Tickets: 0770, 0769
| Total | 8670.08 | 23420.68 | 32090.76
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 54750.6 | 32090.76
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO045
|  |  | Billing Date: | 2016-05-15
Item | Hydrovac Support Additional To C023
Date | Description | This Period | Previous | Total To Date
2016-03-31 | Hydrovac Support Additional To C023 |  | 23420.68 | 23420.68
Tickets: 0807, 0808, 1242, 0809, 0810, 0772, 0771
2016-04-15 | Hydrovac Support Additional To C023 |  | 8670.08 | 8670.08
Tickets: 0770, 0769
| Total | 0 | 32090.76 | 32090.76
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 54750.6 | 32090.76

## CO046UPI
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO046
|  |  |  | Billing Date: | 2016-04-15
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
2016-04-15 | 2.2 b) | Rockshield | 39456.96 |  | 39456.96
| 2.3 d) | Sand Hauling From Borrow Pits | 101168.76 |  | 101168.76
| 2.11 | Clean Washed Gravel | 8876.4 |  | 8876.4
| 2.29 | Rig Mats | 5737.5 |  | 5737.5
0
0
0
0
0
0
0
0
0
0
|  | Total | 155239.62 | 0 | 155239.62
Contractor

## CO047
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO047
|  |  | Billing Date: | 2016-04-15
Item | Light Towers For HDD Sumps
Date | Description | This Period | Previous | Total To Date
2016-04-15 | Light Towers For HDD Sumps | 62260 |  | 62260
| Total | 62260 | 0 | 62260
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 62260 | 62260
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO047
|  |  | Billing Date: | 2016-05-15
Item | Light Towers For HDD Sumps
Date | Description | This Period | Previous | Total To Date
2016-04-15 | Light Towers For HDD Sumps |  | 62260 | 62260
| Total | 0 | 62260 | 62260
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 62260 | 62260
Complete

## CO048
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO-048
|  |  | Billing Date: | 2016-04-15
Item | Drilling Support- Extended Schedule At River Additional To C020
Date | Description | This Period | Previous | Total To Date
2016-04-15 | Drilling Support At River | 169946.08 |  | 169946.08
| Total | 169946.08 | 0 | 169946.08
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 169946.08 | 169946.08
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO048
|  |  | Billing Date: | 2016-05-15
Item | Drilling Support- Extended Schedule AtRiver Additional To C020
Date | Description | This Period | Previous | Total To Date
2016-04-15 | Drilling Support At River |  | 169946.08 | 169946.08
| Total | 0 | 169946.08 | 169946.08
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 169946.08 | 169946.08
Complete

## CO049UPIs
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO049
|  |  |  | Billing Date: | 2016-04-30
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
2016-04-30 | 2.3 c), d) | Sand Bedding, Padding and Hauling | 75833.96 |  | 75833.96
| 2.14 | Extra Depth Ditch | 284.346 |  | 284.346
| 2.29 | Rig Mats | 1530 |  | 1530
| 2.31 | Move Arounds | 18000 |  | 18000
0
0
0
0
0
0
0
0
0
0
|  | Total | 95648.306 | 0 | 95648.306
Contractor

## CO050
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO050
|  |  | Billing Date: | 2016-04-30
Item | Consultant For Long Run Crossing Additional To C019
Date | Description | This Period | Previous | Total To Date
2016-04-30 | Avid Resource Management Ltd. Feb 15-19 | 5040 |  | 5040
Invoices 1371, 1372, 1373, 1374
| Total | 5040 | 0 | 5040
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 5040 | 5040
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO050
|  |  | Billing Date: | 2016-05-15
Item | Consultant For Long Run Crossing Additional To C019
Date | Description | This Period | Previous | Total To Date
2016-04-30 | Avid Resource Management Ltd. Feb 15-19 |  | 5040 | 5040
Invoices 1371, 1372, 1373, 1374
| Total | 0 | 5040 | 5040
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 5040 | 5040
Complete

## CO051
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO051
|  |  | Billing Date: | 2016-04-30
Item | Mix & Backfill HDD Mud Sump Pits Additional To C033
Date | Description | This Period | Previous | Total To Date
2016-04-30 | Mix & Backfill HDD Mud Sump Pits | 143330.98 |  | 143330.98
| Total | 143330.98 | 0 | 143330.98
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 143330.98 | 143330.98
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO051
|  |  | Billing Date: | 2016-05-15
Item | Mix & Backfill HDD Mud Sump Pits Additional To C033
Date | Description | This Period | Previous | Total To Date
2016-04-30 | Mix & Backfill HDD Mud Sump Pits |  | 143330.98 | 143330.98
| Total | 0 | 143330.98 | 143330.98
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 143330.98 | 143330.98
Complete

## CO052
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO052
|  |  | Billing Date: | 2016-05-15
Item | Additional Work Associated With Bear Den At KP 48+800
Date | Description | This Period | Previous | Total To Date
2016-05-15 | Additional Work Associated With The Bear Den | 325639.92 |  | 325639.92
| Total | 325639.92 | 0 | 325639.92
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 366773.29 | 325639.92

## CO053
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO053
|  |  | Billing Date: | 2016-05-15
Item | Inadvertent Mud Release Clean Up In Addition To C038
Date | Description | This Period | Previous | Total To Date
2016-05-15 | IMR Clean Up In Addition To C038 | 13198.84 |  | 13198.84
| Total | 13198.84 | 0 | 13198.84
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 13198.84 | 13198.84

## CO054
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO054
|  |  | Billing Date: | 2016-05-15
Item | Access Road Repairs & Maintenance
Date | Description | This Period | Previous | Total To Date
2016-05-15 | Access Road Repairs:
| Deep Basin Contracting Ltd. MGMISC020 | 2630.25 |  | 2630.25
| Supply/Deliver 1.5" Gravel To Rd 5: (MK 194, MK198) | 2565.2 |  | 2565.2
| Total | 5195.45 | 0 | 5195.45
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 100000 | 5195.45

## CO055
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO055
|  |  | Billing Date: | 2016-05-15
Item | All Conditions Equipment Use During Spring Break Up
Date | Description | This Period | Previous | Total To Date
2016-05-15 | All Conditions Equipment Use During Spring Break Up | 69770.04 |  | 69770.04
| Total | 69770.04 | 0 | 69770.04
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 69770.04 | 69770.04

## CO056UPIs
PIPELINE PROJECT
UNIT PRICE SUMMARY
CO# | CO056
|  |  |  | Billing Date: | 2016-05-15
Item | UPI SUMMARY
Date | UPI | Description | This Period | Previous | Total To Date
2016-04-30 | 2.1 | Rock Trench | 3271.42 |  | 3271.42
| 2.3 c), d) | Sand Bedding, Padding and Hauling | 66806.76 |  | 66806.76
| 2.35 | Crossings Under Existing Buried Pipelines | 55080 |  | 55080
0
0
0
0
0
0
0
0
0
0
0
|  | Total | 125158.18 | 0 | 125158.18
Contractor

## CO057
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO057
|  |  | Billing Date: | 2016-05-15
Item | Caliper Pig Contractor Change
Date | Description | This Period | Previous | Total To Date
2016-05-15 | Caliper Pig Contractor Change |  |  | 0
| Total | 0 | 0 | 0
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 55529.82 | 0

## CO058
PIPELINE PROJECT
EXTRA WORK SUMMARY
CO# | CO058
|  |  | Billing Date: | 2016-05-15
Item | Tow Equipment To Access Drilling Rigs
Date | Description | This Period | Previous | Total To Date
2016-05-15 | Tow Equipment To Access Drilling Rigs |  |  | 0
| Total | 0 | 0 | 0
Contractor
Construction Manager
|  |  | Approved CO Value ($) | CO To Date ($)
|  |  | 155203.98 | 0

## Mats
540 in Total | 2015-12-02 | 2015-12-03 | 2015-12-04 | 2015-12-05 | 2015-12-06 | 2015-12-07 | 2015-12-08 | 2015-12-09 | 2015-12-10 | 2015-12-11 | 2015-12-12 | 2015-12-13 | 2015-12-14 | 2015-12-15 | 2015-12-16 | 2015-12-17 | 2015-12-18 | 2015-12-19 | 2015-12-20 | 2015-12-21 | 2015-12-22 | 2015-12-23 | 2015-12-24 | 2015-12-25 | 2015-12-26 | 2015-12-27 | 2015-12-28 | 2015-12-29 | 2015-12-30 | 2015-12-31 | [5 empty] | Total Mat Days
| 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | [5 empty] | 6480 | 4.5 | 29160
|  | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | [5 empty] | 9396 | 4.5 | 42282 | 71442
[35 empty] | December: | 15876 | 4.5 | 71442
Previous | 2016-01-01 | 2016-01-02 | 2016-01-03 | 2016-01-04 | 2016-01-05 | 2016-01-06 | 2016-01-07 | 2016-01-08 | 2016-01-09 | 2016-01-10 | 2016-01-11 | 2016-01-12 | 2016-01-13 | 2016-01-14 | 2016-01-15 | 2016-01-16 | 2016-01-17 | 2016-01-18 | 2016-01-19 | 2016-01-20 | 2016-01-21 | 2016-01-22 | 2016-01-23 | 2016-01-24 | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-28 | 2016-01-29 | 2016-01-30 | 2016-01-31
| 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 |  |  |  |  | 6696 | 4.5 | 30132
| 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 |  |  |  |  | 10044 | 4.5 | 45198 | 75330
| 2015-12-02: 2016-02-01; 2015-12-03: 2016-02-02; 2015-12-04: 2016-02-03; 2015-12-05: 2016-02-04; 2015-12-06: 2016-02-05; 2015-12-07: 2016-02-06 |  |  |  |  | January: | 16740 | 4.5 | 75330
| 2015-12-02: 216; 2015-12-03: 216; 2015-12-04: 216; 2015-12-05: 216; 2015-12-06: 216 | [5 empty] | 1080 | 4.5 | 4860
| 2015-12-02: 324; 2015-12-03: 324; 2015-12-04: 324; 2015-12-05: 324; 2015-12-06: 324 | [5 empty] | 1620 | 4.5 | 7290 | 12150
[35 empty] | February: | 2700 | 4.5 | 12150
[32 empty] | Cutbank Mats |  |  | Dec, Jan & Feb To Date: | 35316 | 4.5 | 158922
[34 empty] | Billing: | Feb 15: | 1080
1620
[36 empty] | 2700 | 4.5 | 12150
Access Mats For CNRL 24+804
| 2016-03-02 | 2016-03-03 | 2016-03-04 | 2016-03-05 | 2016-03-06 | 2016-03-07 | 2016-03-08 | 2016-03-09 | 2016-03-10 | 2016-03-11 | 2016-03-12 | 2016-03-13 | 2016-03-14 | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-18 | 2016-03-19 | 2016-03-20 | 2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25 | 2016-03-26 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01
| 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 1240
|  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  | 900
Access Mats For CNRL 24+804
| 2016-04-02 | 2016-04-03 | 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08 | 2016-04-09 | 2016-04-10 | 2016-04-11 | 2016-04-12 | 2016-04-13 | 2016-04-14 | 2016-04-15 | 2016-04-16 | 2016-04-17 | 2016-04-18 | 2016-04-19 | 2016-04-20 | 2016-04-21 | 2016-04-22 | 2016-04-23 | 2016-04-24 | 2016-04-25 | 2016-04-26 | 2016-04-27 | 2016-04-28 | 2016-04-29 | 2016-04-30 | 2016-05-01 | 2016-05-02
| 2016-04-02: 40; 2016-04-03: 40 |  | 80
| 2016-04-02: 30; 2016-04-03: 30 |  | 60
[32 empty] | Previous: | 2140
[32 empty] | Total: | 2280
Access Mats For Drill ShooFly 24+722 | bar: 2016-04-02 to 2016-04-03
| 2016-03-16 | 2016-03-17 | 2016-03-18 | 2016-03-19 | 2016-03-20 | 2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25 | 2016-03-26 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01 | 2016-04-02 | 2016-04-03 | 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08 | 2016-04-09 | 2016-04-10 | 2016-04-11 | 2016-04-12 | 2016-04-13 | 2016-04-14 | 2016-04-15
| 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |  | 1125
|  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 150
[32 empty] | Total: | 1275 | 4.5 | 5737.5
KP 30+551 Frac
| 2016-03-11 | 2016-03-12 | 2016-03-13 | 2016-03-14 | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-18 | 2016-03-19 | 2016-03-20 | 2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25 | 2016-03-26 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01 | 2016-04-02 | 2016-04-03 | 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08 | 2016-04-09 | 2016-04-10
| 2016-03-11: 12; 2016-03-12: 12; 2016-03-13: 12; 2016-03-14: 12 |  | 48
0
[32 empty] | Total: | 48
[32 empty] | Grand Total Mats: | 3603 | bar: 2016-04-10

## Standby
PIPELINE PROJECT
Standby or Days of Non-Productivity
Date: | Who: | Reason: | Cost:
2015-11-03 | Slashing | Wet Weather- Road Use Agreements only allowed trucking during frozen/dry conditions | Slashing- 8 hrs Standby | Indirect Support Costs
2015-11-04 | Slashing | Wet Weather- Road Use Agreements only allowed trucking during frozen/dry conditions | Slashing- 8 hrs Standby | Indirect Support Costs