# Pipe-Up Administrator Handbook

## Complete Outline

### Pipeline Construction Office Administrator

“The Cost Control Guru”

The essential bridge between field operations and the project’s financial integrity

## PART 1: INTRODUCTION & ROLE OVERVIEW

### Chapter 1: Welcome to Your Role

1.1 Purpose of This Handbook 1.2 The Administrator as the “Cost Control Guru” 1.3 Your Place in the Organization - Field Operations ↔ You ↔ Finance/Accounting - How you protect the company’s financial integrity

1.4 The Four Pillars of Your Role - Financial Reconciliation & Billing - Project Personnel & Access Control - Regulatory Compliance & Audit Readiness - Reporting & Stakeholder Communication

1.5 Key Relationships - Field Inspectors (your team in the field) - Contractors & Foremen (your verification counterparts) - Project Managers & CMT (your reporting stakeholders) - Finance/Accounts Payable (your downstream partners) - Executives & Chiefs (your dashboard consumers)

1.6 Systems Overview - Pipe-Up Platform (app.pipe-up.ca) - Email & Communication Tools - Document Storage - Banking/HR Systems (for onboarding)

## PART 2: PROJECT PERSONNEL & ACCESS CONTROL

“The Gatekeeper”

### Chapter 2: The Secure Invitation Workflow

2.1 Understanding User Roles in Pipe-Up | Role | Access Level | Can See | |——|————–|———| | Field Inspector | Truncated | Daily tickets, photo upload, their assigned spreads | | NDT Auditor | Specialized | Weld inspection, NDE reports, audit functions | | Contractor User | Limited | LEM submission portal, their own tickets only | | CMT Member | Dashboard | Construction progress, EVM data | | Executive/Chief | Executive | Photo gallery, high-level dashboards, project overview | | Administrator | Full | Everything - user management, billing, compliance |

2.2 Inviting New Users - Step-by-step: The Invitation System - Composing the invitation email - Setting initial role assignment - Project assignment during invitation - What the new user receives

2.3 Role Assignment Best Practices - Principle of Least Privilege (only what they need) - When to grant elevated access - Temporary vs. permanent access

2.4 Managing Existing Users - Viewing user roster - Modifying role assignments - Transferring users between projects - Deactivating users (offboarding) - Password reset procedures

### Chapter 3: Inspector Onboarding - The Hire-On Package

3.1 Pre-Arrival Checklist - [ ] User account created in Pipe-Up - [ ] Role assigned (Field Inspector / NDT Auditor) - [ ] Project(s) assigned - [ ] Spread/crew assignment confirmed

3.2 Credential Verification - Required Certifications by Role: - General Inspector: API 1169, First Aid, H2S Alive - NDT Auditor: CGSB Level II/III, specific method certifications - Welding Inspector: CWB certification, procedure qualifications - Document collection and filing - Expiry date tracking - Renewal reminders

3.3 HR & Administrative Requirements - Banking information collection (direct deposit setup) - Insurance verification - WCB/Workers Compensation - Professional liability (if required) - Vehicle insurance (if using personal vehicle) - Emergency contact information - Tax forms (TD1, etc.)

3.4 Equipment & Access Provisioning - Mobile device requirements - Pipe-Up app installation guide - Login credential distribution (secure method) - PPE requirements confirmation

3.5 First Day Orientation Checklist - [ ] System login successful - [ ] Mobile app working - [ ] Test photo upload completed - [ ] Voice input configured (if using) - [ ] Daily ticket workflow demonstrated - [ ] Reporting chain confirmed - [ ] Emergency procedures reviewed

3.6 Inspector-Specific Training - Daily ticket submission workflow - Photo requirements (geotagging, metadata) - Activity block documentation - Timesheet photo capture - Weather logging - Voice-to-text features

### Chapter 4: Contractor User Onboarding

4.1 Contractor Account Setup - Creating contractor organization - Inviting contractor admin users - LEM submission portal walkthrough

4.2 Documentation Requirements - Rate schedule communication - LEM format requirements - Photo/document upload standards - Submission deadlines

4.3 Contractor Training Topics - Digital LEM entry - Physical LEM photo upload - Understanding the reconciliation process - Dispute resolution procedures

## PART 3: PROJECT SETUP & CONFIGURATION

### Chapter 5: Creating & Configuring Projects

5.1 New Project Setup - Project information entry - Pipeline specifications - Geographic boundaries - Start/end dates

5.2 Organizational Structure - Spreads and crews - Work fronts - Kilometer/station references

### Chapter 6: Rate Table Management

6.1 Labour Rate Tables - Classifications (Foreman, Journeyman, Operator, Labourer, etc.) - Straight time (ST) rates - Overtime (OT) rates - Double time (DT) rates - Effective dates and versioning

6.2 Equipment Rate Tables - Equipment types (Sideboom, Excavator, Welding Rig, etc.) - Hourly rates - Standby rates - Mobilization/demobilization rates

6.3 Rate Table Best Practices - Aligning with contractor agreements - Handling rate changes mid-project - Auditing rate accuracy

### Chapter 7: Inspection Module Configuration

7.1 Available Inspection Modules - Clearing & Grading - Stringing - Bending - Welding (Pre-heat, Fit-up, Root, Fill, Cap) - Coating (Field Joint, Mainline) - Lowering-In - Backfill - Hydrostatic Testing - Tie-ins & Final Connections - Cleanup & Restoration

7.2 Module Assignment - Assigning modules to projects - Inspector module permissions - Custom parameters per module

## PART 4: FINANCIAL RECONCILIATION & BILLING

“The Money”

### Chapter 8: Understanding the Three-Way Match

8.1 The Three Sources of Truth 1. Contractor LEM (Digital) - What the contractor claims 2. Physical LEM/Timesheet (Scanned) - Paper backup proof 3. Inspector Report - Independent verification of work performed

8.2 Why Three-Way Matching Matters - Preventing overbilling - Catching data entry errors - Building audit-proof records - Maintaining contractor accountability

8.3 The “Money Up Front” Principle - Verify before you pay - No invoice without verification - Document everything

### Chapter 9: The No-Talk Verification Process

9.1 Accessing the Verification Dashboard - Navigating to Billing tab - Understanding status cards - Filter toggles explained

9.2 The Four-Panel Verification View | Panel | Color | Source | What to Check | |——-|——-|——–|—————| | Contractor LEM | Dark Blue | Digital submission | Names, hours, classifications, rates | | Physical LEM | Light Blue | Scanned document | Matches digital? Signatures present? | | Inspector Report | Orange | Field inspector | Independent hour verification, calculated costs | | OCR’d Daily Ticket | Light Orange | Foreman signature | Proof of work acknowledgment |

9.3 The Money Banner - Labour Cost - Equipment Cost - Total Contractor Billed - LEM Hours vs Inspector Hours - Variance indicator (Red = mismatch, Green = aligned)

9.4 Variance Analysis - Clicking to highlight mismatches - Red rows = contractor discrepancies - Green rows = inspector verification - Common variance causes

9.5 Making Verification Decisions Option A: Verify Matched - When to use - What happens in the system - Audit trail created

Option B: Keep Open with Discrepancy Note - Required: Discrepancy note - Examples of good notes - What happens next

### Chapter 10: Billing Status Workflow

10.1 Status Definitions | Status | Meaning | Your Action | |——–|———|————-| | Open | New, unreviewed | Verify | | Matched | Verified, aligned | Add to batch | | Disputed | Discrepancy found | Investigate/resolve | | Ready for Billing | Approved | Await contractor invoice | | Invoiced | Swiped clean | Complete (archived) |

10.2 Moving Tickets Through the Pipeline - Individual status changes - Bulk status updates - Status change audit trail

### Chapter 11: Invoice Finalization - The Swipe Clean

11.1 Preparing for Invoice Batching - Gathering matched tickets - Verifying contractor invoice received - Comparing totals

11.2 The Invoice Assignment Modal - Selecting tickets for batch - Entering contractor invoice number - Total verification (MUST MATCH physical invoice) - Notes and documentation

11.3 The Swipe Clean Action - What happens when you confirm: 1. Invoice record created 2. Tickets linked via invoice_id 3. Status updated to “Invoiced” 4. Tickets removed from active view 5. Audit trail logged

11.4 Post-Invoice Verification - Confirming batch in Invoices tab - Verifying all tickets assigned correctly - Communicating to Finance/AP

### Chapter 12: Dispute Management & Troubleshooting

12.1 When to Create a Dispute - Hours variance beyond tolerance - Missing documentation - Classification disagreements - Equipment discrepancies

12.2 The Disputes Tab - Viewing open disputes - Dispute statuses (Open, Disputed, Resolved) - Filtering and sorting

12.3 Communicating with Contractors - Email single dispute - Batch email all open disputes - Professional communication templates - Following up on responses

12.4 Resolving Disputes - Contractor provides documentation - Adjusting values - Accepting contractor explanation - Escalation procedures

12.5 Troubleshooting View - Finding Archived Records - Enabling “View Archived/Invoiced” filter - Searching by invoice number - Researching historical tickets - Supporting audit requests

### Chapter 13: Third-Party Billing Management

13.1 What are Third-Party Tickets? - Subcontractor work - Rental equipment - Specialized services

13.2 Third-Party Workflow Differences - Later arrival timing - Different documentation - Using the “Third-Party Only” filter

13.3 Reconciling Third-Party Invoices - Matching to original work dates - Verification without inspector overlap - Documentation requirements

## PART 5: REGULATORY COMPLIANCE & AUDIT READINESS

“Bulletproof for CER/BCER”

### Chapter 14: The Polymorphic Audit Log

14.1 Understanding the Audit Trail - Every change is recorded - Old Value vs. New Value - Who changed it and when - Change reason/justification

14.2 Critical Fields Under Audit Scrutiny - Wall thickness measurements - GPS coordinates (6-decimal precision) - Weld identification numbers - NDE results - Financial corrections

14.3 Monitoring the Audit Log - Accessing the Corrections tab - Filtering by change type - Identifying unusual patterns - Generating audit reports

### Chapter 15: Photo & Metadata Integrity

15.1 Photo Requirements for Compliance - Geotagging with 6-decimal GPS precision - Direction/bearing metadata - Accuracy indicators - Timestamp verification

15.2 Supporting the Chief’s Photo Gallery - Photo organization - Quality standards - Missing photo follow-up

15.3 Common Photo Issues - Missing geotag (GPS disabled) - Incorrect timestamp (device clock) - Poor image quality - Missing required angles

### Chapter 16: Legacy Data Management

16.1 Ingesting Historical Data - Look-Ahead schedules - Construction Summary reports - Previous project records

16.2 Data Archiving - Retention requirements - Archive procedures - Retrieval processes

16.3 Maintaining Project Continuity - Bridging legacy and current systems - Data migration verification - Historical reference access

## PART 6: REPORTING & STAKEHOLDER COMMUNICATION

“Translating Data into Action”

### Chapter 17: Dashboard Overview

17.1 Executive Dashboard - High-level project metrics - Cost performance indicators - Schedule status

17.2 CMT (Construction Management Team) Dashboard - Field progress tracking - Linear meters completed vs. planned - Earned Value Management (EVM) data - Contractor performance metrics

17.3 Billing Dashboard - Outstanding tickets summary - Variance totals - Invoice status overview

### Chapter 18: Standard Reports

18.1 Daily Reports - Tickets submitted - Verification status - Outstanding items

18.2 Weekly Reports - Billing summary - Dispute status - Progress metrics

18.3 Monthly Reports - Invoice reconciliation summary - Contractor performance - Compliance status

18.4 Exporting Data - CSV exports - PDF generation - Custom report requests

### Chapter 19: Contractor Meeting Support

19.1 Preparing for Weekly Meetings - Pulling the “Discrepancy/Outstanding” view - Summarizing floating tickets - Identifying trends

19.2 Meeting Data Package - Tickets pending verification - Open disputes by age - Resolution required items - Financial impact summary

19.3 Action Item Tracking - Documenting commitments - Following up - Escalation triggers

## PART 7: DAILY OPERATIONS & BEST PRACTICES

### Chapter 20: The Administrator’s Daily Routine

20.1 Morning Checklist - [ ] Review overnight ticket submissions - [ ] Check for missing inspector reports - [ ] Process verification queue - [ ] Review open disputes for responses - [ ] Check user access requests

20.2 Midday Activities - [ ] Follow up on outstanding items - [ ] Process contractor communications - [ ] Prepare for any scheduled meetings - [ ] Monitor field activity

20.3 End of Day - [ ] Final verification pass - [ ] Update status reports - [ ] Queue items for next day - [ ] Document any escalations

### Chapter 21: Weekly Responsibilities

21.1 Monday: Week Kickoff - Review previous week’s outstanding items - Set priorities for the week

21.2 Wednesday: Mid-Week Check - Contractor meeting preparation - Progress assessment

21.3 Friday: Week Closeout - Invoice batch processing - Weekly reporting - Status updates to management

### Chapter 22: Monthly Responsibilities

22.1 Invoice Reconciliation Review - All batches processed - Outstanding aging report - Variance analysis

22.2 Compliance Check - Audit log review - Certification expiry monitoring - Insurance renewals

22.3 Reporting - Monthly summary to management - KPI updates - Trend analysis

## PART 8: TROUBLESHOOTING & SUPPORT

### Chapter 23: Common Issues & Solutions

23.1 User Issues | Issue | Cause | Solution | |——-|——-|———-| | Can’t log in | Password expired | Reset via admin | | Missing tickets | Wrong date range | Adjust filter | | App not syncing | Connectivity | Check internet, force sync | | Photos not uploading | Storage full | Clear device storage |

23.2 Data Issues | Issue | Cause | Solution | |——-|——-|———-| | $0 calculated costs | Missing rate | Add to rate table | | Variance shows incorrectly | Name mismatch | Standardize naming | | Missing inspector match | Date/foreman mismatch | Manual investigation |

23.3 Process Issues | Issue | Cause | Solution | |——-|——-|———-| | Invoice total doesn’t match | Missing/extra tickets | Reconcile before finalizing | | Can’t find archived ticket | Wrong search | Use invoice number search | | Dispute not resolving | Missing info | Request specific documentation |

### Chapter 24: Escalation Procedures

24.1 When to Escalate - Repeated contractor non-compliance - Suspected fraud or manipulation - System technical issues - Compliance concerns

24.2 Escalation Contacts - Technical Support: [Contact info] - Project Manager: [Contact info] - Finance Manager: [Contact info] - Compliance Officer: [Contact info]

24.3 Documentation for Escalation - Screenshots - Audit log excerpts - Communication history - Timeline of events

## APPENDICES

### Appendix A: Glossary of Terms

- API 1169

- BCER (British Columbia Energy Regulator)

- CER (Canada Energy Regulator)

- CMT (Construction Management Team)

- EVM (Earned Value Management)

- LEM (Labour Equipment Materials)

- NDE/NDT (Non-Destructive Examination/Testing)

- OT (Overtime)

- RT/ST (Regular Time/Straight Time)

- WCB (Workers Compensation Board)

### Appendix B: Status Definitions Quick Reference

### Appendix C: Color Code Reference

### Appendix D: Checklists

- New Inspector Onboarding Checklist

- New Contractor Onboarding Checklist

- Daily Operations Checklist

- Weekly Close Checklist

- Monthly Review Checklist

- Audit Preparation Checklist

### Appendix E: Document Templates

- Invitation Email Templates

- Dispute Communication Templates

- Weekly Meeting Agenda Template

- Monthly Report Template

### Appendix F: Contact Directory

### Appendix G: System Navigation Quick Reference

- Screenshot guides for common tasks

- Keyboard shortcuts (if applicable)

- Mobile app vs. desktop differences

## Document Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | January 2026 | [Name] | Initial release |

This handbook is a living document and will be updated as the Pipe-Up platform evolves.