Path of an Extra Work/UPI Ticket

1-Field ticket and or discussion of pending extra work is presented by Contractor to Inspector

Inspector Role

To verify the following:

- Manpower- type and hours

- Equipment- type and hours

- Location- KP

- Description- describe the work that took place so it can be interpreted in the context of the contract

- Date

- Sign that above is valid

Inspector should be aware of contract obligations and be able to phone a contact (Assistant Chief or Chief Inspector) to discuss the ticket or extra work for clarification if required. Inspector does not guarantee payment- that will be vetted by the Chief and/or Construction Manager and Project Manager.

2-Ticket reaches field office via Contractor or Inspector’s copy (usually a yellow duplicate)

If received by Office Manager, the ticket should be presented to the Chief Inspector for review to determine validity and discuss context to contract with the Construction Manager.  He may also provide any missing information not already on the ticket via discussions with Inspector or Contractor.  He should provide a means or direction for determining overall validity (survey numbers, engineering back up) so the Office Manager is not completely responsible to interpret the ticket as valid for payment.

Chief Inspector’s Role

- Determine whether the ticket is valid for payment by discussing with on site Inspector the context of the ticket.  Discuss if necessary with Construction Manager for context regarding “in or out” of scope.

- Fill in any information he may know about why the work took place since he is likely to have discussed the extra work with the Superintendent or Construction Manager.

- Notify the Construction Manager of the extra work if not discussed with the CM.  Notify the Superintendent/Contractor that a Change Request is necessary if one does not exist.

- Support the Office Manager with back up/information regarding the ticket

- Sign the ticket so the Office Manager knows he agrees the work is “extra” or “out of scope”

Construction Manager’s Role

- Discusses the work on the ticket and determines whether “in or out” of scope

- Relays information about the work and pending costs to the Project Manager so he is aware of the change and that a Change Request is on the way if not done so already

3-Once signed by the Chief Inspector, ticket goes back to the Contractor (if presented by Contractor) and a copy goes to the Office Manager for input into their systems for final LEM.  If not valid within context of the contract, then ticket goes back to Contractor (either by the Chief Inspector or Office Manager) with a written explanation on the ticket explaining why.  This will provide back up as to why a ticket was rejected should the Contractor choose to put the ticket in a future claim or simply re-submit the ticket at a later date.

Chief Inspector’s Role

- Provide an explanation as to why the charges are not to be billed

4-All valid and rejected tickets go into CMT database for recording.  Valid tickets are submitted into weekly scorecard and/or accruals. If not in weekly scorecard the value is kept to compile total value pending in the weekly accruals until put through on the scorecard.  Rejected ticket totals should be kept in a separate column from the scorecard/accruals, but the ticket is recorded should it be submitted after the project is complete.

The valid/signed ticket will have a value applied and “lemmed” out.

Office Manager’s Role- Enter/validate LEMs received FROM the Contractor but do not submit tickets, spreadsheets and LEMs on behalf of the contractor!

- Enter the signed ticket “blind” into the database so errors/omissions may be determined when the LEM is presented by the Contractor to the Office Manager.

- Once LEM is received from Contractor- Ensure the correct hours are being charged

- Ensure the correct labour and equipment rates are being charged

- Ensure the correct mark up (if applicable) is being charged on 3rd party tickets/invoices

- Ensure the total is correct.

- Ensure the ticket is being assigned to the correct Change Order or Change Request.

- Present the LEM to the Chief Inspector for sign off if above is correct

- Return signed copy of LEM (with back up) to the Contractor for billing through Scorecard.

- Update Change Order/Request Log to keep charges to each CO up to date.

- Ensure Scorecard summaries of LEMs, UPIs, Progress, etc. match with what has been signed off and the math is correct and all back up is attached.

5-Final signed tickets and accompanying LEM summaries as well as UPI summaries are signed off by the Chief Inspector and itemized in the Contractor’s Scorecard.  The complete Scorecard is then reviewed and signed off by Construction Manager.