7/3/2019

Rick Judson

AREION VENTURES INC.

CONSTRUCTION MANAGEMENT PLAN

TABLE OF CONTENTS

Overview - Detailed Outline of Inspection Team……………………………………………………………………………………………………2 - Construction Manager…………………………………………………………………………………………………………………………4 - Chief Inspector…………………………………………………………………………………………………………………………………….4 - Assistant Chief Inspector……………………………………………………………………………………………………………………..5 - Field Office Administrator……………………………………………………………………………………………………………………6 - Senior Welding Inspector…………………………………………………………………………………………………………………….6 - Lead Coating Inspector………………………………………………………………………………………………………………………..7 - Activity Inspectors……………………………………………………………………………………………………………………………….8 2.1 Non Inspection Tasks…………………………………………………………………………………………………………………………..10 2.2 Field Reporting and Communications………………………………………………………………………………………………….11 2.2.2 Contract Administration………………………………………………………………………………………………………………………13 2.2.3 Statements………………………………………………………………………………………………………………………………………….13 2.2.4 Change Requests and Requests for Information………………………………………………………………………………….14 2.2.5 Inspector Role……………………………………………………………………………………………………………………………………..15 2.2.6 Chief Inspector Role…………………………………………………………………………………………………………………………….15 2.2.7 Construction Manager Role…………………………………………………………………………………………………………………15 2.2.8 Field Office Administrator Role……………………………………………………………………………………………………………16 2.2.9 Invoicing………………………………………………………………………………………………………………………………………………17 3.1 Safety and Environment………………………………………………………………………………………………………………………17 4.1 Schedule……………………………………………………………………………………………………………………………………………..17 5.1 Turnover Package……………………………………………………………………………………………………………………………….18

AREION VENTURES RESPONSIBILITIES

Areion shall be responsible for inspection during the installation of the pipeline, and all associated services.

Overview

The following is a summary of the various types of personnel required to monitor, and question the performance of the Mainline Contractor, and administer the Contract Documents between the Mainline Contractor and the Company.

- Construction Manager

- Chief Inspector

- Assistant Chief Inspector

- Field Office Administrators

- Project Controls/Scheduler

- Senior Welding Inspector

- Lead Coating Inspector

- Activity Inspectors

Areion will provide field inspection serviced and administration of any and all Contract Documents.  Areion will not be responsible for directing any of the work on the Pipeline ort the Mainline Contractor.

All inspection services provided by Areion will report to Areion’s Construction Manager (or to their designate) while operating in the field.

The Chief Inspector will report directly to Areion’s Construction Manager, and he/she will consult with the Company’s Project Manager (or their designate) for issues regarding engineering, land, environment, etc.

The Company shall approve the Inspection Team prior to mobilizing personnel to the field.  The total number of field inspection personnel required will be approved by the Company and be a direct function of the Mainline Contractor’s work plan, schedule, and the number of crews deployed to the field.

  - Detailed Outline Of Inspection Team

The following roles are expected to be provided by Areion:

    - Construction Manager

The Construction Manager will be responsible for overseeing all aspects of construction and communicate regularly with Company personnel.  The Construction Manager will be responsible for ensuring that all facets of the inspection, engineering, and survey are carried out in a consistent manner.

The roles for the Construction Manager will include but not limited to:

- Representing Company interests

- Overseeing construction activities and contractors

- Coordinating Company safety representatives

- Reporting to the Project Manager

- Managing the Inspection Team

- Reviewing commercial changes

- Reviewing commercial statements and back up

- Interpreting the Contract Documents

- Ensuring effective communication is occurring between all stakeholders

- Communicating with senior Contractor representatives

    - Chief Inspector

The Chief Inspector will coordinate all Activity Inspectors, and others as required.  The Chief Inspector will report directly to the Construction Manager.  The Chief Inspector will be considered the senior representative for the Project and will direct all efforts of the Inspection Team including the Company supplied safety inspectors, environmental inspectors, the Assistant Chief’s, Field Office Administrators, Project Controls personnel, Senior Welding Inspector as well as Company supplied survey contractor and foreign line locators.

The role of the Chief Inspector will include, but is not limited to:

- Ensure all Activity Inspectors and Mainline Contractor’s supervisors are thoroughly familiar with the Contract Documents and any Special Conditions that may apply

- Give guidance to and assist Activity Inspectors with issues as they occur

- Ensure the quality assurance is to the level specified in the Contract Documents, and all operations under the surveillance of the Inspectors runs smoothly and orderly

- Review and sign all Daily Inspection Reports; address and resolve any issues identified by the Inspection Team

- After consultation with a Company Representative, advise the MCC of any work shutdowns due to ROW conditions or inclement weather. The direction to shut down all the work, or portions thereof, will be given verbally to the MCC, then followed up with written confirmation

- Resolve issues that have arisen between the MCC and the Inspection Team

- Work with the appropriate Activity Inspector to ensure that any concerns identified by a regulatory agency, or by their own personnel, are resolved satisfactorily

- Monitor construction progress and track against MCC's projected schedules. Discuss with MCC any schedule or milestone deficiencies and work toward a solution for achieving project schedules

- Provide adequate supervision and discipline to the Activity Inspector and audit them daily for accuracy and consistency by reviewing workmanship and Daily Inspection Reports

- Ensure that proper action takes place with respect to all non-compliances, in addition, that all necessary reports associated with non-compliances have been properly completed, filed and distributed

Qualifications (Training and Experience)

Contractor shall submit reasonable justification if any qualifications are not met.

- Required: Completion of an API 1169 pipeline inspector certification

- Minimum Grade 12 or equivalent, technical college or Professional Engineer preferred and 15 to 20 years inspection/construction experience

- Familiar with and experienced in interpreting construction contracts

- Working knowledge of project management principles

- Familiar with the fundamentals of project accounting

- Able to handle large volumes of paperwork efficiently

- Tact and diplomacy in dealing with people

1.1.3    	Assistant Chief Inspector

An Assistant Chief Inspector will be assigned to each construction spread and will report to and support the Chief Inspector. Their duties and responsibilities shall include but not be limited to the following:

      - Provide support, assistance, and backup to the Chief Inspector on all facets of construction and, as such, assure that all the work performed on the spread is carried out in accordance with the Contract Documents and in an orderly fashion

      - Liaise closely with the appropriate Activity Inspector to ensure, to the extent practical, that environmental guidelines are being implemented into the work

      - Work closely with the Company-supplied Land Agent to ensure landowner restrictions are adhered to

      - Assist the Chief Inspector in handling all on-site logistical planning associated with the assigning of Inspection Team to Work tasks and Work areas

      - Support the Chief Inspector in ensuring that the MCC expeditiously undertakes to rectify any identified Contract deficiencies

      - Monitor MCC compliance with the requirements of the contract

      - Interface with MCC’s supervisory staff on a daily basis and assist in resolving issues that arise between the Inspection Team and the MCC

      - Prepare and assist Inspectors in the preparation of Daily Inspection Reports

      - Assist the Chief Inspector in determining if the MCC is deficient in any area of the mainline construction contract

      - Be consistently available on the ROW and assist the Senior Welding Inspector and the Lead Coating Inspector in the verification of the effectiveness of the quality control system that has been developed for the Project

      - Provide back-up inspection on activities that may be temporarily undermanned from time to time

      - Attend project management and safety meetings as requested by the Chief Inspector

# Qualifications (Training and Experience)

Contractor shall submit reasonable justification if any qualifications are not met.

Required: Completion of an API 1169 pipeline inspector certification

Minimum Grade 12 or technical college preferred and 10 to 15 years inspection/construction experience

Ability to deal with people

Experience in interpreting construction contracts

1.1.4	Field Office Administrator

The Field Office Administrator performs an important role within the Inspection Team. The Field Office Administrator shall contribute toward the smooth and timely flow of data between Company and the MCC as well as the Field Office and the Head Office. Although the Field Office Administrator is rarely directly involved with any inspection duties, they must be completely conversant in general terms with all aspects of the Project. The Field Office Administrator will report directly to the Chief Inspector.

The normal duties of the Field Office Administrator include but are not limited to the following:

- Set up the field office(s)

- Establish and maintain the field office filing system

- Prepare Daily Progress Reports based on information compiled from the Inspectors' Daily Inspection Reports

- Assist the Chief Inspector with the interpretation and administration of non-technical aspects of the Contract and perform clerical duties required on a daily or otherwise regular basis

- Manage correspondence under the direction of the Chief Inspector

- Perform cost monitoring, cost estimates and cost breakdowns

- Administration of third-party contractor service contracts

- Preparation of progress payment estimates of work

- Recording of minutes at meetings

- Document MCC’s actual progress for each key construction activity against their stated progress and record in meeting minutes any lags or concerns

- Maintaining stationery inventory levels

- Administration of blanket purchase orders for miscellaneous items such as office services (cleaning), coffee supplies and office stationery

- Assist with the preparation of the Contractor Evaluation Report

- Preparation of the Contractor’s Clearance and Close-out Reports

- Assist with field material procurement/receiving documentation. Field Office Administrator shall maintain copies of packing slips and invoices on site and forward the originals to Company

- Direct the activities of any field clerks or secretaries who may be assigned to the field office

- Demobilize field office(s), including the transfer of field files to Company

# Qualifications (Training and Experience)

Contractor shall submit reasonable justification if any qualifications are not met.

- 15 to 20 years experience in field office supervision and practices particularly with pipeline construction

- Construction accounting and contract administration experience

- Must handle paperwork efficiently

- Knowledge of construction agreements and contracts

1.1.5        Senior Welding Inspector

The Senior Welding Inspector will be assigned to the Project and will report daily to the Chief Inspector to coordinate all welding activities throughout the Project. The Senior Welding Inspector shall be responsible for ensuring consistency of inspection procedures, consistency among NDT contractors (if applicable), and welding consistency between all spreads. Duties of the Senior Welding Inspector include but are not limited to the following:

      - Ensure NDT contractor’s employees are qualified and maintain records of those qualifications

      - Provide quality assurance audits to ensure field inspection and reporting is consistent within all spreads

      - Provide technical welding support to assist in any required problem solving during the welding operations

      - Confirm that Welding Qualification Tests are completed in accordance with the Contract Documents and ensure that the MCC maintains an ongoing log of welders and their respective qualifications

      - Ensure that all welders working on the job are qualified in accordance with the Construction Specifications, CSA Z662, ASME Codes, and that they can carry out work only on pipes of the diameter and wall thickness for which they are qualified

      - Ensure that all Welding Inspectors are familiar with their roles, levels of responsibility and authority

      - Ensure that Welding Inspectors are deployed in accordance with MCC’s daily work plan

      - Review all Daily Welding Reports to ensure that they are both accurate and comprehensive

      - Evaluate and communicate welding-related information to the Chief Inspector for their action where necessary

      - Prepare Daily Welding and NDT Production Reports and ascertain that the information used to formulate these reports is both accurate and comprehensive

      - Work with the MCC’s welding foremen to confirm they are all familiar with Project Welding Specifications, Drawings, welding procedures, and any special requirements necessary to obtain the desired quality of final product

      - Review daily repair welding data, in conjunction with the NDT contractor, prior to submitting a repair list to the MCC each morning prior to 7:00 a.m.

      - Ensure that all welding is carried out in accordance with the approved welding procedures

      - Ensure that all NDT work carried out is in accordance with the qualified NDT procedures

      - Ensure that the storage of film and ultrasonic reports meets Project requirements

      - Ensure that radiographic film is available for each completed weld and is properly recorded and stored

      - Visit all welding locations on a regular basis to check with the Inspectors on problem areas, quality of work, and generally auditing the Inspectors for accuracy and consistency

      - Prepare, in conjunction with the Senior NDT technician, the daily NDT diagnosis of repair and cut- out welds and ensure that all cut-out and repaired welds are tracked until a satisfactory weld is obtained and recorded

      - Coordinate with the Field Office Administrator to ensure Project document control and field records are maintained in an orderly fashion during the Project to ensure documents and records generated in the field are incorporated into the Project document control system upon completion of the Project

      - Coordinate with the NDT contractor or MCC regarding the maintenance of NDT records throughout the Project and arrange for the transfer of this information/data to Company- specified delivery location upon completion of the Project

      - Coordinate with the NDT contractor or MCC regarding the maintenance of NDT records throughout the Project and arrange for the transfer of this information/data to Company- specified delivery location upon completion of the Project

      - Assist with the preparation of the final welding as-built package and compiling the welding reports from each spread into a consolidated binder

# Qualifications (Training and Experience)

Contractor shall submit reasonable justification if any qualifications are not met.

- Required: Completion of an API 1169 pipeline inspector certification

- Required: Completion of an API 1104 or AWS Certified Welding Inspector certification

- Minimum Grade 12 or equivalent, technical college or Professional Engineer preferred and 15 to 20 years inspection/construction experience

- Familiar with and experienced in interpreting construction contracts

- Able to handle large volumes of paperwork efficiently

- Tact and diplomacy in dealing with people

1.1.6     Lead Coating Inspector

The Lead Coating Inspector will be assigned to the Project and will report daily to the Chief Inspector to coordinate all coating activities throughout the Project. The Lead Coating Inspector shall be responsible for ensuring consistency of inspection procedures, consistency among NDT contractors (if applicable), and coating consistency between all spreads. Duties of the Lead Coating Inspector include but are not limited to the following:

Tasks to be performed:

a)	Conduct visual inspection for jeeps and ensure they are repaired as per Specifications;

b)	Ensure only approved coating materials/sleeves on site and being used by Contractor;

c)	Check that appropriate MSDSs are on site and proper PPE being used/worn by workers;

d)	Check that coating materials/sleeves are properly stored (e.g., dry, warm);

e)	Ensure that sandblasting and pre-heating are as per Contract or manufacturer's specifications;

f)	Ensure proper application of coating material/sleeves as per Specifications;

g)	Ensure 'induced voltage' mitigation measures are employed and

h)	Ensure proper grounding techniques are observed.

Quality Checks:

•	blast profiles of metal surfaces to be coated;

•	pre-heat temperatures;

•	coating thickness and

visual inspection to ensure integrity of sleeve installation. Other Requirements:

•	Ensure that the Contractor has the necessary equipment and that regular testing of breathing                            air is conducted to ensure its safety and Ensure that coating equipment crosses existing pipelines in accordance with the Specifications.

1.1.7	Activity Inspectors

Contractor shall be required to provide a dedicated Inspector for each construction activity including but not limited to:

•	Welding

•	NDE

•	NDE auditing

•	Hydrovac

•	Stripping

•	Grading

•	Trenching

•	Lowering In

•	Stringing

•	Clearing

•	Crossings

•	Horizontal Directional Drills

•	Mud Disposal

•	Bending

•	Ditch Plugs

•	Backfill

•	Hydrostatic Testing

•	Pipeline Drying

•	Corrosion Inhibitor Run

•	Inline Inspection Survey

•	Facilities and Tie-ins

•	Cathodic Protection

•	Clean-up and Reclamation

The Activity Inspectors play a leading role in ensuring that construction and installation of the Project is carried out correctly and that all construction activities comply with the undertakings to which Company and, therefore, the Inspectors are committed. The intent of all the inspection activities is to monitor, control, and ensure the minimization of construction practices or procedures that could have adverse effects on the safety of the work areas, the environment or the final technical performance requirements of the Pipeline. This involves foresight and quick communicative action by all the Inspectors involved. Such action must be conveyed to the Inspector's immediate supervisor and to the MCC’s immediate supervisor on-site. The recognition of the need for the early implementation of mitigative and corrective measures is a key function and responsibility of all Inspectors.

All Activity Inspectors will report directly to the Chief Inspector, although daily instructions will be through the Assistant Chief Inspector or assigned Senior/Lead Inspector. Activity Inspectors will also have direct contact with the field engineers, safety inspectors, environmental inspectors and survey coordinator for appropriate input from these disciplines.

Prior to the commencement of the construction activities and during the orientation process, all Inspectors will be thoroughly briefed on their duties and responsibilities and on the environmental, safety and technical requirements associated with each activity.

The general responsibilities of Activity Inspectors include but are not limited to the following:

a)	Prepare a Daily Inspection Report for their specific activity. If an Inspector is monitoring more than one activity, they shall prepare a Daily Inspection Report for each respective activity. The Daily Inspection Reports shall include:

a.	Photographs

b.	Problems encountered

c.	General comments relating to the work

d.	Quantity of manpower and equipment as well as conditions of the equipment

e.	Weather conditions

f.	Progress obtained

g.	Comments on the MCC’s attitude toward the work as it affects quality

h.	Reference to tickets completed/received that day (see Section 3.4.2.4).

b)	Display effective communication skills and be prepared to develop a rapport with other Activity Inspectors, the MCC’s personnel and the public, the field engineer, safety inspector, environmental inspector, Field Office Administrator, and Company

c)	Use and wear all necessary protective equipment and clothing as required by government regulations and company policy.

d)	Ensure that they have the necessary tools and equipment readily available to check and test      quantities, lengths, diameters, thicknesses, pressures and other items affecting the quality of construction, where appropriate, to their monitoring function. Consultants may be employed from time to time to provide specialized inspection tests.

e)	Each Activity Inspector shall be thoroughly familiar with their assigned area of responsibility, including the Specifications and Contract Documents and any special, local, municipal, or regional requirements. Verbal and written reporting shall be used as methods of communicating and both shall be employed daily.

f)	Cross-communicate between related and sequential activities of the entire construction function, as communication is essential to minimize conflicts arising between phases of construction.

All Activity Inspectors will have the authority to prevent work from continuing when a significant non- compliance has occurred. If the non-compliance is not life threatening, the Activity Inspector shall contact the Chief Inspector or the Assistant Chief Inspector immediately to confirm course of action. If the situation is life threatening, the Activity Inspector shall request the MCC to stop work, then contact the Chief Inspector or the Assistant Chief Inspector for follow-up action. The safety inspector or environmental inspector shall be contacted if the non-compliance relates to either safety or environmental matters

Qualifications (Training and Experience)

- Required: Completion of an API 1169 pipeline inspector certification

- Minimum Grade 12 preferred with 8 to 10 years of pipeline inspection construction experience

- Ability to deal with people

# 2.1	Outline of Non-Inspection Tasks

The Inspection Team shall be responsible for providing inspection services for the Project, as well as other non-inspection tasks such as administering the Contract Documents in the manner specified in this Schedule A – Scope of Work.

# Field Reporting and Communication

FIGURE 1: COMMUNICATION FLOW CHART

Frequent communication between the Construction Manager and Company’s Project Manager is expected; approximately each day, a meeting will occur between the Project Manager and the Construction Manager. Additional meetings or other communications between Company and the Construction Manager, Chief Inspector or other members of the Inspection Team will occur as required. It is expected that communications within the Inspection Team will generally follow the sample hierarchy provided in FIGURE 1. Changes to this hierarchy shall be communicated to and reviewed by Company before implementation.

There shall be daily communications, reporting, and resolutions of potential environmental problems between the environmental inspectors and the Chief Inspector. In the event of more difficult situations, the communications shall be elevated to Company environmental representative and the Construction Manager for resolution.

The following disciplines shall receive direction from the Inspection Team directly only for coordination purposes. The Inspection Team shall be required to ensure the MCC’s daily work plan and changes to the daily work plan are communicated to these disciplines:

      - Environmental field inspection

      - Field engineers

      - Survey crews

      - NDE crews

      - Field Land Agents

      - Timber Salvage Coordinators

      - Caliper/Smart Pig Crews

2.2	Reporting and Communications

Potential changes to the scope of the Contract and all Trends will be reported to the Project Manager and field engineer prior to commencement of any extra work.

The Construction Manager through the Inspection team shall meet the minimum field reporting guidelines as outlined in this document. This reporting includes the following:

        - A weekly roll up of man hours for the Inspection Team (including NDT, survey, environmental and other third-party contractors)

        - Daily Progress Report – a daily progress summary outlining the MCC’s daily progress for each significant operation

        - Weekly Construction Summary – a weekly progress summary outlining the MCC’s weekly progress for each significant operation

        - Unit Price Items (UPI) Register – the Field Office Administrator will summarize from the Inspectors’ Daily Inspection Reports and track on a daily basis the various Unit Price Item quantities installed

        - Progress Payments - the Field Office Administrator in consultation with the Chief Inspector, the surveyor and the Construction Manager shall prepare an estimate of production completed for comparison against the MCC’s progress statements. Large variations in progress shall be reported to the Project Manager by the Construction Manager if they cannot be resolved with the MCC.

        - Support services - tracking of daily progress, man hours and equipment for other third-party contractors (NDT contractor, survey contractor, caliper pig contractor etc.) shall be completed in a similar fashion to that described above for the MCC

# 2.2.1	Reporting Daily Progress

The Activity Inspectors will each prepare a Daily Inspection Report for the previous day’s activities that will be submitted to the Field Office Administrator prior to the start of each day.

The Field Office Administrator and Chief Inspector shall collect the Activity Inspectors’ daily reports and generate the Daily Construction Summary Report using information from the Activity Inspectors’ reports. Additional comments from the field engineer may be made as they relate to technical items and materials.

Once the Daily Construction Summary Report is finalized it shall be transmitted to the Construction Manager and the Project Manager.

The Daily Construction Summary Report shall include the following as a minimum:

        - Daily production figures and the percentage completions for each major item of construction

        - A written report covering the following items:

          - Summary of construction activities for the previous day, including if the construction activities were within the scope of the mainline construction contract or were extra work

          - Significant visitors to site (name and company represented)

          - Significant environmental concerns (spills or other environmental infractions)

          - Potential material shortages

          - Identification if a weather delay occurred

          - Significant landowner or stakeholder problems

          - Non-compliances served by any authority having jurisdiction

          - Key milestones on lump sum work

          - Significant safety incidents, positive safety reports or near misses

          - Summary of major safety or progress meetings

# 2.2.2	Contract Administration

Tickets

- All unpriced and priced tickets will be submitted to the Field Office Administrator by all onsite contractors

- Daily, all unpriced tickets shall be reviewed for accuracy and acknowledged by the onsite Inspector by signing and dating the ticket

  - Work shall not be considered for compensation if unpriced tickets are not signed and dated by the Inspector on the day that the work was completed by the MCC

  - Acknowledgment does not constitute approval of additional costs

  - Acknowledgment confirms to the contractor and Company that the ticket accurately describes the work that occurred

- Priced and unpriced tickets from all onsite contractors shall be inputted on the ticket log daily

- Priced tickets will generally be received from contractors within 48 hours of the work occurring

- Priced tickets shall be verified by the Field Office Administrator by signing and dating each priced ticket

  - Verification includes cross-checking the ticket quantities to the unpriced ticket as well as cross-checking the rates included on the ticket to the rates included in the Contract Documents

- Priced tickets shall be accepted or rejected by the Chief Inspector or Construction Manager

  - Acceptance confirms that the ticket has the appropriate signatures, is associated with a valid purchase order or change request and that the incurred cost associated with the ticket is valid

# 2.2.3	Statements

- All onsite contractors are required to submit weekly statements

  - A statement will consist of a list of tickets, timesheets, third-party invoices, progress reports for base lay quantities, and field office verification summary that are planned to be submitted on an invoice

- Statements shall be reviewed and accepted by the Construction Manager within 48 hours of receiving the statement

  - The Construction Manager is required to confirm that all tickets included on the statement are properly signed, are valid, and that no changes have been made to the tickets

  - The Construction Manager is required to confirm that progress included on the statement is consistent with the terms of the Contract Documents and the actual progress of the contractor

- All statements with signed tickets are forwarded to the Project Coordinator, Contract Administrator and contractor (for inclusion with invoice)

  - Statement will be signed by Field Office Administrator and Construction Manager to acknowledge review and accuracy of charges to the Company

  - Statement to include: PO#, PO line item or Change Order to which the work is applicable, contractor’s name, AFE, Statement number (consecutive), and date

# One statement per contractor shall be issued per week

2.2.4	Change Requests and Requests for Information

# If Work must me performed that is not within Contractor’s scope, a Change Request can be generated.  If more information is required to perform Work, a Request for Information can be initiated.  FIGURE 2 illustrates the process of how to initiate a Change Request or and RFI:

FIGURE 2: CHANGE ORDER MANAGEMENT FLOW CHART

- The Field Office Administrator will be copied on all Change Requests sent by onsite contractors

- All Change Requests for all onsite contractors shall be input daily into the Company-supplied Change Request log

- All contractor Change Requests shall be signed by the Construction Manager

# 2.2.5	Inspector Role

        - Verify the following items on tickets:

          - Manpower – type and hours

          - Equipment – type and hours

          - Quantity of unit price items (“UPI”)

          - Materials

          - Location (Kilometre point must be identified)

          - Description – describe the work that took place so it can be interpreted in the context of the Contract (extra work or UPI)

          - Date

          - Sign acknowledging work, hours, manpower, equipment listed is valid on the day the work took place

        - Contact Assistant Chief Inspector or Chief Inspector if extra work clarification is required

        - Ensure that contractors shall not attempt to get tickets signed more than 48 hours after the work occurred

# 2.2.6	Chief Inspector Role

- Determine whether the ticket is valid for payment by discussing the context of the ticket with the onsite Inspector. Discuss if necessary with Construction Manager for context regarding “in or out” of scope

- Fill in any information about why the work took place since the contractor is likely to have discussed the extra work with the Superintendent or Construction Manager

- Notify the Construction Manager of the extra work if not already discussed. Notify the Superintendent/Contractor that a Change Request is necessary if one does not exist and work was approved

- Support the Field Office Administrator with back up/information regarding the ticket

- Sign the ticket so the Field Office Administrator knows that the Chief Inspector agrees the work is “extra” or “out of scope”

- Provide an explanation if charges are not to be billed because work is determined to be “out of scope”

- Sign off on costed tickets/LEMs and summaries

- Ensure costs are for approved work

- Ensure all relevant information is in place and any changes have been identified/initialed off

# 2.2.7	Construction Manager Role

        - Discuss the work on the ticket and determine whether the work is “in or out” of scope

        - Notify the Superintendent/Contractor that a Change Request is necessary if one does not exist and work was approved

        - Relay information about the work and pending costs to the Project Manager so he or she is aware of the change and that a Change Request is required

        - Sign off on statement and any costed tickets/LEMs and summaries if applicable

Ensure costs are for approved work and Change Requests are in place

# 2.2.8	Field Office Administrator Role

        - Discuss tickets with the Chief Inspector

        - Enter tickets on the LEM log or cost tracker spreadsheet for accruing costs

        - Enter status of tickets as “pending” or “rejected” on the LEM Log/Cost Tracker spreadsheet. Rejected ticket totals should be kept in a separate column from the scorecard/accruals, but the rejected ticket and record should be submitted after the project is complete

        - Hold Inspector tickets (yellow copies) until costed LEMs and billing packages are presented by the contractor (the Field Office Administrator does not prepare or present tickets/billing packages on behalf of the contractor)

        - Ensure survey measurements are included as back up in the event of “measured quantities” or UPIs

        - Enter LEMs received from the contractor into LEM Log/Cost Tracker but do not submit tickets, spreadsheets and LEMs on behalf of the contractor

        - Enter the signed field ticket into the checking spreadsheet/cost tracker so errors, ommissions, and additions may be identified.

        - When the costed LEM is received from the Contractor, the Filed Office Administrator will:

- Ensure the correct hours on the ticket are being charged on the LEM

- Ensure the correct labour and equipment rates are being charged (watch for changes in labour classifications, equipment sizes/age e.g. D6R vs D6T)

- Ensure the correct mark up (if applicable) is being charged on third-party tickets/invoices

- Ensure quantities are validated with survey measurements and a copy of the survey measurements accompany billing documents where applicable

- Ensure the ticket is being assigned to the correct Change Order and/or Change Request if applicable

- Ensure the totals are reconciled with the contractor (all LEMs and summaries)

        - Ensure statement package (tickets, LEMs, summaries of LEMs, UPIs, Progress Reports, change order logs, etc.) is complete

        - Ensure their field office summaries are included to provide validation they checked the charges

        - Update Change Order/Request Log to keep charges to each CO up to date

        - Present statement package to the Construction Manager for sign off

        - Return statement package to contractor for their sign off

        - Send copy of signed statement to contractor, Project Coordinator and Contract Specialist

# 2.2.9	Invoicing

        - Invoices shall be accompanied by signed statements (with Project Manager, Construction Manager and Field Office Administrator signatures)

        - The correct PO# and correct Company entity (as listed on the PO) shall be displayed on the invoice

        - Invoices with Change Orders shall have the Change Order clearly identified on a separate line item within the invoice or be invoiced individually

        - More than one statement may be submitted with an invoice

        - Contractor to email signed invoices and all back up to accountspayable@pembina.com

Holdback: Contractors with holdback can apply for holdback after submitting a Statutory Declaration and Certificate of Substantial Completion to Pembina once the project is done. Release of holdback is at the discretion of the Project Manager based on acceptance of substantial completion.

3.1       Safety and Environment

With respect to the Project safety, the MCC is the designated Prime Contractor. The Inspection Team shall meet the safety requirements of the MCC in addition to the safety training required by Company. Company safety orientation shall be issued using Complyworks and shall be issued to Contractor upon bid award.

Safety and environmental inspection services will be provided by Company. The Inspection Team will be responsible for understanding and following the safety and environmental requirements of the Project. The Inspection Team shall work with the safety and environmental inspectors to ensure the success of the Project, which may include providing inspection services relating to construction in support of environmental or safety work. If environmental or safety issues are identified, the Inspection Team shall communicate those issues to the Project Manager or the environmental / safety inspectors.

The Construction Manager shall communicate regularly with the Project Manager and safety and environmental inspectors to monitor Project compliance.

4.1	Schedule

The Inspection Team shall comply with the OH&S act regarding work schedule. It is expected that some of the key field personnel will require one field break during each spread. Inspection will work the days of the week that the MCC works, which is currently scheduled to be a 6 and 1 shift. Sunday work may be required from time to time; Contractor shall communicate with the MCC to ensure adequate inspection support is available, which may include mobilization of additional inspection staff to ensure compliance with applicable legislation.

The Construction Manager, through the appropriate Inspection staff, will track Contractor’s actual progress for each of the key activities against their stated progress. The Construction Manager shall discuss Contractor’s progress with Contractor at each of the weekly field management meetings.

The Chief Inspector will also liaise with Construction Manager regarding crewing up to meet the MCC’s schedule and crewing down as various phases of the work is completed.

5.1	Turnover Package

The Inspection Team shall compile a Turnover Package upon completion of the Project, including the following information and documents:

| Item |  | Timeline |  |
| --- | --- | --- | --- |
| Daily Progress Report – including a snapshot of daily activities |  | 9:00 AM Daily |  |
| Management Meeting Minutes – Signed and accepted by contractor within two business days of meeting |  | End of Day |  |
| Daily Contractor Meeting Minutes (if applicable) |  | End of Day |  |
| Signed Contractor Statements & CO Logs |  | Weekly |  |
| Ticket/LEM Checking Spreadsheets |  | As Requested |  |
| Signature Log – ongoing and part of turnover package |  | Monthly |  |
| Contractor Accruals with CO Log Progress |  | Weekly |  |
| Collect 3rd party inspection reports and track progress accordingly i.e. drilling contractor, survey, line sweepers etc. |  | Daily |  |
| Inspector Reports (as applicable): Chief Inspector Assistant Chief Inspector Stockpiling Clearing Foreign Line Crossings Hydrovac Log Access Grade Stringing Bending Senior Welding Inspector Weld Log, Weld Parameters, Welder Tests Mainline Welding Tie-In Welding Tie-In Supplemental Mainline Coating Coating Checklist Tie-In Coating Bores HDDs Ditch Lower-In Mainline Backfill Tie-In Backfill Test Caliper Pigging Machine Clean Up Final Clean Up Pile Driving Indications Valves Test Leads Pictures |  | Project Turn Over Or As Needed |  |