Contract Analyst/Administrator

Interactions with Personnel/Defining Roles- Most item examples are based on the last few days in the Duvernay Office.  In general, I do the same thing on the other projects.

1) Attend Inspector morning meetings where applicable.  Take notes regarding what has taken place in the field the previous day.  Make note of extra works and potential extra works to determine strategy for tracking and make not of potential Change Requests.

Interactions:

-Chief Inspector: Discuss notes on extra works with the Chief Inspector to confirm he is aware of the work and has Inspectors on site to sign for tickets or draw up MP&E/UPI forms/spreadsheets for potential extra work.  Discuss strategy on what tickets to sign (if applicable).

-Assistant Chief Inspector: Discuss extra work with Assistant Chief and Inspector overseeing the work.  Answer questions as to how to track extra work and develop a strategy for cost tracking.

-Answer questions from Inspectors regarding what they need to sign/track in the field.

Deliverables To Myself:

-Send me tracking spreadsheets for archiving or for Pembina files where required.  Example: Crossings where mats have been placed over ramps.  This information could be relevant should Midwest submit a claim for additional mats over previously matted locations.

2) Review Emails regarding the following (this takes up the majority of my time):

- Statements: Review statements from all the projects for CO coverage, correct CO delegation, validity, sign off, commercial terms, organization, accuracy (CO logs), mark ups, properly signed back up, duplicates, omissions, etc.  Email/discuss any issues with the Office Manager to make corrections prior to invoicing or come up with a strategy for credits after invoicing.

- Update Statement/Accrual log as well as Contractor CO logs where required.

- Review/discuss change requests and write change orders for the CRs that have been approved by the team.  Update contractor CO log with new CR information and status.  Discuss CR requirements via verbal or email with Nathan if estimates are missing or if something is unclear.  Ensure changes to the scope of work have been covered off in a Change Order. Send written change orders with relevant back up to the Project Coordinator for PM sign off.

- Review accruals for overages on POs and whether the office manager has the revised POs/COs in possession in case they are holding statements until they receive the revised PO.

- Contact the Project Coordinator or check s-drive for outstanding PO revisions and change order status.

- Discuss Pembina documentation with Office Managers before making changes, additions or deletions.

- Interpret contracts and relay how they should be administered to the Office Manager (ie. deliverables):  tracking, type of back up (ex field ticket or invoice), how the statement should be formatted to accurately reflect how the contract is structured, whether a Change Request/ CO is required, etc.

- Review POs for structure and break down to determine how the statements should be laid out so the Receivers can easily input the charges next to the appropriate line item. Make sure COs are clearly defined on the statements or the CO log displays the correct CO/CR for the charge going through.

- Relay information from the Project Coordinator to the Office Manager as required.

Interactions:

-Relevant Office Managers, Field Engineers, Project Coordinator, Construction Manager, Project Coordinator

Deliverables To Myself:

- Weekly statements, accruals, change requests, emails relating to changes to any accrual/statement documents, revised POs

-Receive CRs as part of the distribution list from the contractors

3) Answer questions/interact with Pembina Contractors, Pembina personnel and KDM personnel regarding contract administration and contract content.  Discuss change request format where applicable.  Ensure they are contacting the right people (ex. Tickets go to the office manager, CRs go to the CM, etc.) and have the contract documents they need to perform the work that Pembina has asked them to do.  Example:  Adam Olson did not have the commercial terms for the drilling contractors yet there were complaints that CCI was not tracking what they needed to track in the field.  Normally, ensuring subcontractors have the proper protocols and documentation falls under the Construction Management team’s umbrella.

Another example: Victor from Midwest wanted to discuss how the base lay was to be broken down in the PO (rates for each phase) because of “receiving” issues encountered on the F2N project.

After interacting with the Contractors, any relevant items will be relayed to the Office Manager so they are all on the same page.

Interactions:

-Pembina Contractors (ex. CCI, Midwest), Office Manager, Chief Inspector, Construction Manager, Field Engineer, Project Manager, Project Coordinator

Deliverables To Myself:

- Responses from Field Engineers, Project Manager to emails requesting clarification of contract documents

-Please include me on any emails or discussions relating to any contract administration and procedures or CR distribution lists.

4) Ensure the Field Office team is delivering what Pembina requires for validations, accruals, LEM logs, statements, etc.  Ensure the Office Manager has the appropriate spreadsheets, forms and documents to properly validate charges and check LEMs.

At the start of each job, I lay out our expectations (ex. The inspectors need to be signing field tickets, the Chief signs the LEMs, the CM signs the statement along with the person validating the tickets (Office Admin)).  I spend a lot of time “training” KDM office personnel on what Pembina requires as far as deliverables pertaining to the aforementioned.

Some groups are better than others at getting tickets signed in the field. This is often related to a) Signature philosophy ie. the CM/Chief feel they can sign for charges even though they are not validated by an inspector

b) Commercial philosophy ie. the inspectors do not need to know about commercial aspects in the field so the inspectors are reluctant to ask the foreman any questions regarding what they are signing or they tend to not step forward and look to validate the extra work taking place

c) CM/Chief relationship ie. the Chief does not provide adequate inspector coverage for field sign off since he is not aware of what he needs to have covered for extra work.

Interactions:

- Office Manager, Chief Inspector, Construction Manager

Deliverables To Myself:

- Correct statements, ensure charges are going against the proper CO, review invoices, accruals, LEM logs, tickets, etc.

5) Offer suggestions/solutions based on my personal experience as an inspector and Office Manager on how to deal with poorly written field tickets.  Example:  Remind inspectors to write down the 5 W’s (who, what, when, where, why) to make sure the ticket can “stand alone” in an audit and does not require back up from other sources (ex. Inspector reports).  The other sources/inspector reports do not get put in with the billing documents sent in to accounts payable by the Contractor so they are not part of the audit.  The 5 Ws also eliminates extra work for the field office as they do not have to look for information on reports or other documents (thus save time, thus eliminate overhead at Pembina’s cost).

Interactions:

-Inspectors, Office Manager, Chief Inspector, Construction Manager

Deliverables To Myself:

- Tickets that can stand alone in an audit with all relevant information to make a sound decision that the work took place and is in or out of scope (can tell what change request it belongs to).

6) Make observations as to what is not working with a particular Construction Management Team.  Consistency in the paperwork/team interactions is all based on how the team functions.  It is not enough to “teach” the Office Manager because she takes direction from the Construction Manager or Chief and does what they say. If the proper information is funneling from the field, the rest (accurate accruals, proper tracking, sign off and efficiency) tends to take care of itself.

Interactions:

-Arms Length: Inspectors, Pembina Contractors (ex. CCI, Midwest), Office Manager, Chief Inspector, Construction Manager

Deliverables To Myself:

- N/A

7) Attend the weekly management meeting to keep abreast of relevant issues/contract items that require immediate attention (ex. Status of CRs/COs, invoice payment, etc.)

Interactions:

- Pembina Contractors (ex. CCI, Midwest), Office Manager, Chief Inspector, Construction Manager

Deliverables To Myself:

- Management meeting minutes, CO logs, Two Week Look Ahead, etc.