Contract Analyst/Administrator

Interactions with Personnel/Defining Roles- Most item examples are based on the last few days in the Duvernay Office so there are specifics.  In general, I do the same thing on the other projects.

1) Attend Inspector morning meetings where applicable.  Take notes regarding what has taken place in the field the previous day.  Make note of extra works and potential extra works to determine strategy for tracking.

Interactions:

-Chief Inspector: Discuss notes on extra works with the Chief Inspector to confirm he is aware of the work and has Inspectors on site to sign for tickets or draw up UPI forms for potential extra work.  Discuss strategy on what tickets to sign (if applicable).

-Assistant Chief Inspector: Discuss extra work with Assistant Chief and Inspector (if in the office).  Answer questions as to how to track extra work and develop a strategy for cost tracking.

-Answer questions from Inspectors regarding what they need to sign/track in the field.

Deliverables To Myself:

-Send me tracking spreadsheets for archiving or for Pembina files where required.  Example: Crossings where mats have been placed over ramps.  This information could be relevant should Midwest submit a claim for additional mats over previously matted locations.

2) Review Emails regarding the following (this takes up the majority of my time):

- Statements: Review statements from all the projects for CO coverage, validity, sign off, commercial terms, organization, accuracy (CO logs), mark ups, properly signed back up, duplicates, omissions, etc.  Email/discuss any issues with the Office Manager in charge to make corrections prior to invoicing or come up with a strategy for credits.

- Update Contractor CO logs where required.

- Review/discuss change requests and write change orders for the CRs that have been approved by the team.  Update contractor CO log with new CRs and status.  Discuss CR requirements via verbal or email with Nathan if estimates are missing or if something is unclear.  Ensure changes to the scope of work have been covered off in a Change Order. Send written change orders with relevant back up to the Project Coordinator for PM sign off.

- Review accruals for overages on POs and whether the office manager has the revised POs/COs in possession in case they are holding statements until they receive the revised PO.

- Contact the Project Coordinator or check s-drive for outstanding PO revisions and change order status.

- Discuss Pembina documentation with office managers for making changes, additions or deletions.

Interactions:

-Relevant office managers, field engineers, Project Coordinator, Construction Manager (example: Questioned the CM whether Pembina knew we were paying final clean up despite mat piles left on the ROW.,

Deliverables To Myself:

- Weekly statements, accruals, change requests, emails relating to changes to any accrual/statement documents, revised POs,

3) Answer questions from contractors, Pembina and KDM personnel regarding contract administration and contract content.  Example: Riley asked whether Shaw’s trailer electricity falls under Pembina’s scope or whether Shaw needs their own generator.  I did not see any reference to their trailer hookups/electrical in the contract.  I found out there are conflicting references to overall payment for the trailer in the contract so I asked for Nathan’s opinion and he would look into it further.  He also said Pembina agreed to pay for the trailer.

Because the contracts can be conflicting, I “go up the ladder” to further clarify what/what is not to be paid.  I have sent out emails for clarification and try to figure the best way to the contract administration based on past experience and “what is written in the contract”.

I try to avoid writing responses to contract questions in emails- I will generally phone the person or speak to them in person because:

- they (usually the Office Manager) often has not given the full picture/context of the contract question

- they take my response out of context

- they take my response and use it for other contractors or do not adapt the response to new situations

- they send my email response directly to the contractor as back up to their arguments.  If the question was not worded correctly, the answer is wrong and we have issues with the contractor and they end up contacting me directly

- they ask my opinion about how to handle a situation without first asking the Chief Inspector or the Construction Manager for their expertise.  This is part of the heartburn with the emails that were sent to Sherry.  If the Office manager would ask their superiors for their opinion, most of the answers would be answered before they get to the “Calgary” level.  If the CM does not have the answer, he has the opportunity to go directly to the PM for an answer since the PM was involved in contract negotiations. This has caused much of the static with the Crooked Lake crew.

Interactions:

-Pembina Contractors (ex. CCI, Midwest), Office Manager, Chief Inspector, Construction Manager

Deliverables To Myself:

- If I send out emails/make phone calls to Pembina staff for clarifications, responses would be appreciated (this has not always happened – included other projects).

-Please include me on any emails or discussions relating to contract administration and procedures. Example: Office Manager obtained signing authority without my knowledge on one project.  This undermined the processes I had outlined to the field team throughout the project.  As a result, Contract Administration questions are no longer going through me, but to others.

4) Ensure the Field Office team is delivering on what Pembina requires for accruals, LEM logs, statements, etc.  Ensure the Office Manager has the appropriate spreadsheets, forms and documents to properly validate charges and check LEMs.  At the start of each job, I lay out our expectations (ex. The inspectors need to be signing field tickets, the Chief signs the LEMs, the CM signs the statement along with the person validating the tickets (Office Admin).  I spend a lot of time “training” KDM office personnel on what Pembina requires as far as deliverables pertaining to the aforementioned.

There is NOT a 100% success rate (but a good success rate!) in getting consistency between the field management teams because:

- Each Construction Manager has an opinion on what their team has been hired to do

For example: Field tickets (for M/L Contractor and subcontractors) are not getting signed by inspectors in the field partly because of a philosophy of “no commercial in the field” and “the CM’s signature should be enough”.  This has created a large gap between what appears to be validated in the field vs what was an afterthought.  I have seen pages and pages of 3rd party invoices with no contractor or inspector sign off (only a ticket written by the contractor 5 months after the work took place that gets signed off by the Chief or CM).   I believe the Chief has not been directed by the CM to have extra works covered off in the field because of two things: 1) the “no commercial in the field policy” and 2) the Chief Inspector needs more guidance on inspector management so the proper items are tracked and signed for in the field.

Because the field is not being directed to be involved with the day to day tracking/commercial sign off, accruals and weekly statement regularity suffers.  Costs cannot be tallied because the Office Manager has not received a ticket immediately after it was signed (including third party tickets where a scan can be made)- thus no accrual and no ability to push the contractor for finalized invoices since he/she does not know the cost exists. In this type of situation, the CMs or Chiefs feel their signature is good enough to justify the costs even though no one was in the field to check on what was being charged.  In the end the Chief, CM and OM are not looked upon favourably and do not appear to be in control.

- The Office Manager changes the forms to suit their personal needs

- They do what they want anyway (ex. Work off of scans from the contractor and submit yellow carbon copies on behalf of the contractor even though they have been told to get hard copies from the contractor package (so a physical “tick” can be placed on the paper to show it was checked); Or the CM overrules my suggestions)

Interactions:

-Pembina Contractors (ex. CCI, Midwest), Office Manager, Chief Inspector, Construction Manager, Project Coordinator

Deliverables To Myself:

- Respond to emails when requesting clarification on contract questions as I am not sure if a Statement needs to be retracted.

5) Offer suggestions/solutions based on my personal experience as an inspector and Office Manager on how to deal with poorly written field tickets.  Ie- I have reminded inspectors to write down the 5 W’s (who, what, when, where, why) to make sure the ticket can “stand alone” in an audit and does not require back up from other sources (ex. Inspector reports).  The other sources/inspector reports do not get put in with the billing documents sent in to AP by the Contractor for payment so is not part of the audit.  The 5 Ws also eliminates extra work for the field office as they do not have to look for information on reports or other documents (thus save time, thus eliminate overhead at Pembina’s cost).

This is a current issue on Lator as the CM wishes to follow the old “no commercial in the field” policy or “the contractor has to do that work” policy.  He is concerned this will cause issues between inspectors and foremen in the field.  After administering contracts in this manner for the past 5 years (since the IPL target price project), we have not had an issue with inspectors/foremen not getting along.  The inspectors learn to “own the costs” they are signing for and pay attention to tracking better.  The foremen become better at writing accurate tickets since they see what the Client requires on the ticket as well as the fact that the inspector is “watching”.  If commercial items are not handled directly in the field, the resulting product is poor (incorrect snapshot of what took place or no sign off), the majority of the tickets get signed by the Chief or CM at a later date and there are extra people in the field office having to deal with the poor product or put reports with the tickets.

Interactions:

-Inspectors, Pembina Contractors (ex. CCI, Midwest), Office Manager, Chief Inspector, Construction Manager

Deliverables To Myself:

- N/A

6) Make observations as to what is not working with a particular Construction Management Team and offer suggestions (when asked) without stepping on toes.  This is not something I make a point of doing, however, consistency in the paperwork/team interactions is all based on how the team functions.  It is not enough to “teach” the Office Manager because she takes direction from the Construction Manager or Chief and does what they say. If the proper information is funneling from the field, the rest (accurate accruals, proper tracking, sign off and efficiency) tends to take care of itself.

Interactions:

-Arms Length: Inspectors, Pembina Contractors (ex. CCI, Midwest), Office Manager, Chief Inspector, Construction Manager

Deliverables To Myself:

- N/A

7) Answer questions from Pembina’s contractors ex. Midwest, CCI, etc.  Ensure they are contacting the right people (ex. Tickets go to the office manager, CRs go to the CM, etc.) and have the contract documents they need to perform the work that Pembina has asked them to do.  Example:  Adam Olson did not have the commercial terms for the drilling contractors yet there were complaints that CCI was not tracking what they needed to track in the field.  Normally, ensuring subcontractors have the proper protocols and documentation falls under the Construction Management team’s umbrella (especially the Chief Inspector and Construction Manager and to a lesser degree, the Office Manager).  However, I believe no one followed through with providing a copy of the Commercial Terms to Adam because of the “no commercial in the field” policy.  As a result, the office manager is sending out emails to try and interpret the drilling contract (which is CCI’s scope) and has heartburn when she is not receiving the appropriate documentation.

After interacting with the Contractors, any relevant items will be relayed to the Office Manager so they are on the same page.

Interactions:

- Pembina Contractors (ex. CCI, Midwest), Office Manager, Chief Inspector, Construction Manager

Deliverables To Myself:

- N/A

8) Attend the weekly management meeting to keep abreast of relevant issues/contract items that require immediate attention (ex. Status of CRs/COs, invoice payment, etc.)

Interactions:

- Pembina Contractors (ex. CCI, Midwest), Office Manager, Chief Inspector, Construction Manager

Deliverables To Myself:

- Management meeting minutes, CO logs, Two Week Look Ahead, etc.