Summaries/Statements

Do not prepopulate cells. Only use rates in the contract. Only display units charged

Summaries should match the PO lines. Refer to both the PO and the contract

Keep a co log to show status of cos

Summary date is when signed

Period can be put on summary

Ticket revisions can take place on next statement at bottom of the page referencing original ticket and stmt?

Tickets should be entered daily and not in a lump just before the progress payment

Spreadsheet and OM hold the contractor accountable to the contract. If not in contract the charge is not valid. If valid but not in contract then CR is needed

PO how to read

Statement display and naming convention and email title

Enter in rejected tickets and add comment whether on “statement #4” or “rejected”

Statements and back up:

-Contractor presents signed off UPI/LEM for review by office manager.

- “approved” tickets are signed off by the chief or CM and sent back to the contractor for formal submission into a statement.  The package should have a summary and the office manager should submit their summary and/or spreadsheet as proof of validation

-back up should be the field ticket (office manager can include their inspector copy as proof),

-third party charges should be supplemented with invoices, field tickets, bills of ladings and ideally a copy of the contractor’s PO if able-to show proof of request by Contractor, what job it belongs to, etc.

Co management

Contractors send in CR to initiate co and alert cmt to pending extra work

Cm and contractor signs the CR once agreed to. A co is generated and PO updated in Calgary so invoicing for extra work can proceed

Contract analyst flow chart. Cycle for cos to the field. Linda to contractor and me then to field office. Difference between CR and co