Field ticket verified by inspector for Mp&E hours, location, description, date. Inspector should be aware of contract obligations and have a field contact (asst chief or chief) to discuss the ticket for clarification if required. Chief should inform inspection of extra work or UPI if communicated to by the contractor so inspector knows what to look for and vice versa. Inspector does not guarantee payment- that is responsibility of chief, cm and pm.

Morning meetings- inspectors relay previous days work to highlight or raise flags regarding potential reimbursable extra work. Extra work mentioned by contractor can also be relayed from chief to inspection team so they know what to sign.

Ongoing communication between chief and superintendent

Ongoing between inspector and foreman

Ongoing between asst chief, chief, inspector in a circle

Engineering, Land, environment, safety, flow through chief and cm to inspectors and filters through to foremen in the field. Chief and cm have direct lines to contractor. Cm has direct line to Calgary

Chief coordinates survey, land, env, engineering

Ticket goes to chief inspector for review to determine validity and context to contract and provide any missing information

Once signed, ticket goes to contractor and office manager for input into their systems for final lem or billing. If not valid within context of contract then ticket goes back to contractor explaining the issue. Final Lems and UPI summaries with values are signed by the chief inspector for billing.

Valid tickets go into CMT database for submission into weekly scorecard. If not in weekly scorecard the value is kept to compile total value pending in the weekly accruals until put through on the scorecard.

Roles and responsibilities inspector, CM, chief, office manager.

Lem processing:

-enter tickets "blind" into spreadsheet so the OM can see where the errors are when the Lem comes in. Once Lem deemed correct, chief signs off. Lems are the $$ page and the ticket is the back up.

Summaries

Do not prepopulate cells. Only use rates in the contract. Only display units charged

Summaries should match the PO lines. Refer to both the PO and the contract

Keep a colog to show status of cos

Summary date is when signed

Period can be put on summary

Ticket revisions can take place on next statement at bottom of the page referencing original ticket and stmt?

Tickets should be entered daily and not in a lump just before the progress payment

Spreadsheet and OM hold the contractor accountable to the contract. If not in contract the charge is not valid. If valid but not in contract then CR is needed

PO how to read

Statement display and naming convention and email title

Co management

Contractors send in CR to initiate co and alert cmt to pending extra work

Cm and contractor signs the CR once agreed to. A co is generated and PO updated in Calgary so invoicing for extra work can proceed

Contract analyst flow chart. Cycle for cos to the field. Linda to contractor and me then to field office. Difference between CR and co