## 1.0 BaseLay
SUNRISE LATERAL
10102 95th Avenue
Clairmont, AB
T8X 0M6
|  |  | Tel: 780-814-2332 |  | accountsreceivable@ntlpipelines.com
C-2.1. BASELAY INDIVIDUAL SPREADS SEGMENT 1
Date:
|  | 31194 | % | 1559.09 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
2.1 | Mobilization | Per Lin. m | 8% | 124.73 | 81955.6559 |  | 81955.6559 | 10222328.9604 | 0 | 10222328.9604
| Grade ROW | Per Lin. m | 10% | 57.78 | 0 |  |  | 0 | 0 | 0
| Haul and String Ppipe | Per Lin. m | 5% | 28.89 | 0 |  |  | 0 | 0 | 0
| Bending | Per Lin. m | 5% | 28.89 | 0 |  |  | 0 | 0 | 0
| Welding | Per Lin. m | 23% | 132.89 | 0 |  |  | 0 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 5% | 28.89 | 0 |  |  | 0 | 0 | 0
| Lower-In Pipe | Per Lin. m | 4% | 23.11 | 0 |  |  | 0 | 0 | 0
| Backfill | Per Lin. m | 4% | 23.11 | 0 |  |  | 0 | 0 | 0
| Tie-Ins | Per Lin. m | 14% | 80.89 | 0 |  |  | 0 | 0 | 0
| Testing | Per Lin. m | 6% | 34.67 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 3% | 17.33 | 0 |  |  | 0 | 0 | 0
| Machine Clean Up | Per Lin. m | 9% | 52.01 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 11.56 | 0 |  |  | 0 | 0 | 0
| Mechanical Completion/Initial Clean Up | Release Of Holdback
| Final Clean Up Fall 2016 | Per Lin. m | 1% | 17.33 | 0 |  |  | 0 | 0 | 0
| Final Clean Up Summer 2017 | Per Lin. m | 3% | 5.78 | 0 |  |  | 0 | 0 | 0
|  |  | 102% | 667.86 |  |  | Total For Base Lay Price: | 10222328.9604 | 0 | 10222328.9604
C-2.1. BASELAY COMBINED SPREADS SEGMENT 1,3,4
|  | 1151 | % | 1348.2 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
2.1 | Mobilization | Per Lin. m | 6% | 80.89 | 576 |  | 576 | 46592.64 | 0 | 46592.64
| Grade ROW | Per Lin. m | 10% | 134.82 | 0 |  |  | 0 | 0 | 0
| Haul and String Ppipe | Per Lin. m | 5% | 67.41 | 0 |  |  | 0 | 0 | 0
| Bending | Per Lin. m | 5% | 67.41 | 0 |  |  | 0 | 0 | 0
| Welding | Per Lin. m | 23% | 310.09 | 0 |  |  | 0 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 5% | 67.41 | 0 |  |  | 0 | 0 | 0
| Lower-In Pipe | Per Lin. m | 4% | 53.93 | 0 |  |  | 0 | 0 | 0
| Backfill | Per Lin. m | 4% | 53.93 | 0 |  |  | 0 | 0 | 0
| Tie-Ins | Per Lin. m | 14% | 188.75 | 0 |  |  | 0 | 0 | 0
| Testing | Per Lin. m | 6% | 80.89 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 3% | 40.45 | 0 |  |  | 0 | 0 | 0
| Machine Clean Up | Per Lin. m | 9% | 121.33 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 26.96 | 0 |  |  | 0 | 0 | 0
| Mechanical Completion/Initial Clean Up | Release Of Holdback
| Final Clean Up Fall 2016 | Per Lin. m | 1% | 40.45 | 0 |  |  | 0 | 0 | 0
| Final Clean Up Summer 2017 | Per Lin. m | 3% | 13.48 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 1348.2 |  |  | Total For Base Lay Price: | 46592.64 | 0 | 46592.64
C-2.1. BASELAY COMBINED SPREADS SEGMENT 1,2,3
|  | 1695 | % | 1540.8 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
2.1 | Mobilization | Per Lin. m | 6% | 92.45 | 848 |  | 848 | 78397.6 | 0 | 78397.6
| Grade ROW | Per Lin. m | 10% | 154.08 | 0 |  |  | 0 | 0 | 0
| Haul and String Ppipe | Per Lin. m | 5% | 77.04 | 0 |  |  | 0 | 0 | 0
| Bending | Per Lin. m | 5% | 77.04 | 0 |  |  | 0 | 0 | 0
| Welding | Per Lin. m | 23% | 354.38 | 0 |  |  | 0 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 5% | 77.04 | 0 |  |  | 0 | 0 | 0
| Lower-In Pipe | Per Lin. m | 4% | 61.63 | 0 |  |  | 0 | 0 | 0
| Backfill | Per Lin. m | 4% | 61.63 | 0 |  |  | 0 | 0 | 0
| Tie-Ins | Per Lin. m | 14% | 215.71 | 0 |  |  | 0 | 0 | 0
| Testing | Per Lin. m | 6% | 92.45 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 3% | 46.22 | 0 |  |  | 0 | 0 | 0
| Machine Clean Up | Per Lin. m | 9% | 138.68 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 30.82 | 0 |  |  | 0 | 0 | 0
| Mechanical Completion/Initial Clean Up | Release Of Holdback
| Final Clean Up Fall 2016 | Per Lin. m | 1% | 46.22 | 0 |  |  | 0 | 0 | 0
| Final Clean Up Summer 2017 | Per Lin. m | 3% | 15.41 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 1540.8 |  |  | Total For Base Lay Price: | 78397.6 | 0 | 78397.6
Page 1 of 2
C-2.1. BASELAY COMBINED SPREADS SEGMENT 2,4
|  | 832 | % | 963 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
2.1 | Mobilization | Per Lin. m | 6% | 57.78 | 416 |  | 416 | 24036.48 | 0 | 24036.48
| Grade ROW | Per Lin. m | 10% | 96.3 | 0 |  |  | 0 | 0 | 0
| Haul and String Ppipe | Per Lin. m | 5% | 48.15 | 0 |  |  | 0 | 0 | 0
| Bending | Per Lin. m | 5% | 48.15 | 0 |  |  | 0 | 0 | 0
| Welding | Per Lin. m | 23% | 221.49 | 0 |  |  | 0 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 5% | 48.15 | 0 |  |  | 0 | 0 | 0
| Lower-In Pipe | Per Lin. m | 4% | 38.52 | 0 |  |  | 0 | 0 | 0
| Backfill | Per Lin. m | 4% | 38.52 | 0 |  |  | 0 | 0 | 0
| Tie-Ins | Per Lin. m | 14% | 134.82 | 0 |  |  | 0 | 0 | 0
| Testing | Per Lin. m | 6% | 57.78 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 3% | 28.89 | 0 |  |  | 0 | 0 | 0
| Machine Clean Up | Per Lin. m | 9% | 86.67 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 19.26 | 0 |  |  | 0 | 0 | 0
| Mechanical Completion/Initial Clean Up | Release Of Holdback
| Final Clean Up Fall 2016 | Per Lin. m | 1% | 28.89 | 0 |  |  | 0 | 0 | 0
| Final Clean Up Summer 2017 | Per Lin. m | 3% | 9.63 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 963 |  |  | Total For Base Lay Price: | 24036.48 | 0 | 24036.48
C-2.1. BASELAY COMBINED SPREADS SEGMENT 3,4
|  | 598 | % | 770.4 | Total To Date | Previous | This Period | Amount This Period ($) | Total Earned Previously ($) | Amount Earned To Date ($)
2.1 | Mobilization | Per Lin. m | 6% | 46.22 | 299 |  | 299 | 13819.78 | 0 | 13819.78
| Grade ROW | Per Lin. m | 10% | 77.04 | 0 |  |  | 0 | 0 | 0
| Haul and String Ppipe | Per Lin. m | 5% | 38.52 | 0 |  |  | 0 | 0 | 0
| Bending | Per Lin. m | 5% | 38.52 | 0 |  |  | 0 | 0 | 0
| Welding | Per Lin. m | 23% | 177.19 | 0 |  |  | 0 | 0 | 0
| Excavate Pipe Trench | Per Lin. m | 5% | 38.52 | 0 |  |  | 0 | 0 | 0
| Lower-In Pipe | Per Lin. m | 4% | 30.82 | 0 |  |  | 0 | 0 | 0
| Backfill | Per Lin. m | 4% | 30.82 | 0 |  |  | 0 | 0 | 0
| Tie-Ins | Per Lin. m | 14% | 107.86 | 0 |  |  | 0 | 0 | 0
| Testing | Per Lin. m | 6% | 46.224 | 0 |  |  | 0 | 0 | 0
| Final Tie-Ins | Per Lin. m | 3% | 23.11 | 0 |  |  | 0 | 0 | 0
| Machine Clean Up | Per Lin. m | 9% | 69.34 | 0 |  |  | 0 | 0 | 0
| Demobilization | Per Lin. m | 2% | 15.41 | 0 |  |  | 0 | 0 | 0
| Mechanical Completion/Initial Clean Up | Release Of Holdback
| Final Clean Up Fall 2016 | Per Lin. m | 1% | 23.11 | 0 |  |  | 0 | 0 | 0
| Final Clean Up Summer 2017 | Per Lin. m | 3% | 7.7 | 0 |  |  | 0 | 0 | 0
|  |  | 100% | 770.404 |  |  | Total For Base Lay Price: | 13819.78 | 0 | 13819.78
[7 empty] | Total All Segments: | 10385175.4604 | 0 | 10385175.4604
Regan Schafer- Chief Inspector
Page 2 of 2