## Field Office Cost Tracking/Accrual Procedures (Sunrise)

Steven as discussed, below is my understanding of the Pembina requirements with respect to providing accruals, weekly cost information and invoicing support from the field (based on my understanding of what Dawn is doing on Sunrise)

This summary represents the cost tracking and accrual process requirements only – not the support for the inspection requirement

Cost Tracking

- Track and document on a spread sheet the daily cost breakdown for contractors who develop daily time sheets (based on method of compensation) for each Contractor and Sub-Contractor in the field (I have a sample);

  - Sweep contractor

  - NDT contractor

  - Altus

  - Davis safety

  - Survey contractor

  - Progress Land

  - Environment

  - Other 3rd parties

- At the end of each week prepare a Progress Certificate for the pipeline contractor (BLP progress, UPIs, lump sum work and any approved Extra Work), the HDD contractor on contract to Pembina, each of the consultants/contractors summarized above

- The finalized/signed weekly progress certificates plus all backup are submitted to each contractor, Sherry Phillps, and Corrine Barta

- The field office manager will track Unit Price items from contractor Lems/tickets, inspector daily reports and summarize on spread sheet (work with survey to ensure no difference between inspector quantities and as-built quantities. Also on a regular basis compare/share unit price item values with Contractor administration)

- The field Office Manager will develop spreadsheets and enter tickets to ensure Contractor is charging correct rates and hours for approved extra work (as vetted through the Chief Inspector).  The Chief Inspector/CM will identify what is out of scope work and ensure a Change Request has been initiated.

- Contractor extra work will be tracked against the CO/CR log by the Office Manager.

- Weekly accruals required for ALL contractors/consultants will be submitted on Tuesdays by end of day for Pouce Coupe Project

- Weekly progress certificates or statements will be generated for each contractor and submitted to Pembina as soon as possible (day of week may change as required by contractor if necessary)

- Statements/progress certificates and associated invoices will be formatted as per the PO document

- Invoices (based on the statements) will be signed by the CM and sent back to the vendor for submission to Pembina’s accounts payable department.

Question

- Can the smaller value contractor/consultants be accrued on 15th and end of each month – or are they weekly?  All contractors (with daily tickets) are accrued weekly.  KDM/EIs/Safety can be accrued on the 15th

- With some of contractors/consultants the daily tickets being signed at the field level and accrued on spread sheets may not have the overhead and markup included – therefore the contractor/consultant actual invoice could be different than the spread sheet summary generated at the field level A statement can still be sent in based on the daily tickets/invoices.  The mark up can be sent in on a separate statement and signed by the PM if necessary (in the case of KDM).  The invoice would then be for the amount of the two statements.

Change Process

- The Contractor (or Company where Contractor is unable ie. native clearing contractors) fills out a Pembina CR form when they believe work will done out side their scope of work.  An estimate detailing the costs, manpower/equipment and associated rates for the change accompanies the form.

- Change request is sent to the PM, CM, Chief Inspector, Pembina Engineer, Office Manager and Corry.  CM reviews and signs if in agreement.

- Signed package is sent to Corry for CO generation.

- Field Engineer to t

- rack RFIs (request for information) and maintain an RFI log

- Office manager will track CRs and COs on a log

Question

- Can approved LEMS be charged against a COR?  Only approved LEMs can be invoiced against a Change Order.  The PO needs to be increased to accommodate the change and contractors are not getting in change requests in a timely fashion so this helps ensure the documents are in place.  It is up to the CM, Chief Inspector and Office Manager to ensure a Change Request has been written and approved to account for all changes outside the contract.

- Can CORs or Cos be revised if value exceeds original value or does new CO have to be generated Due to SAP limitations, a new change order will have to be generated.  The change request can be revised, but a new change order will be issued to account for the additional amount being requested.