## LEM LOG
522553.77
Date of Time Sheet | Date Received | Time Sheet Reference # | CR# | Description | UPI | Additional SubContractor Tickets | SubCon Ticket Number | Date Given Back to MW | Related LEM # | LEM Amount | Rejected | Statement # | Comments
2016-08-02 | 2016-08-04 | 02082016-LD | 1 | Taqa Bridge Overlap - CR1 |  |  |  | 2016-08-15 | 02082016-LD | 1433.46 |  |  | Approved
2016-08-02 | 2016-08-04 | 02082016-LB | 1 | Taqa Bridge Overlap - CR1 |  | G. Mindus & Sons Holding | 14596 | 2016-08-15 | 02082016-MAT | 2658.5 |  | 4 | Approved
2016-08-02 | 2016-08-04 | 02082016-LB | 1 | Taqa Bridge Overlap - CR1 |  | G. Mindus & Sons Holding | 14512 | 2016-08-15 | 02082016-MAT | 0 |  | 4 | Approved
2016-08-02 | 2016-08-04 | 02082016-LB | 1 | Taqa Bridge Overlap - CR1 |  | Enterprise Truck Haul Card | 5838 | 2016-08-17 | 02082016-LB | 6386.6 |  | 4 | Approved
2016-08-03 | 2016-08-12 | 03082016-GR | 1 | Taqa Bridge Overlap - CR1 |  |  |  | 2016-08-22 | 03082016-GR | 537.06 |  | 4 | Approved
2016-08-03 | 2016-08-12 | 03082016-LB | 1 | Taqa Bridge Overlap - CR1 |  |  |  | 2016-08-22 | 03082016-LB | 2694.54 |  | 4 | Approved
2016-08-05 | 2016-08-04 | TS 3328 | 1 | Taqa Bridge Overlap - CR1 |  | G. Mindus & Sons Holding | 14513 | 2016-08-22 | 03082016-MAT | 1788.98 |  | 4 | Approved
2016-08-05 | 2016-08-04 | TS 3328 | 1 | Taqa Bridge Overlap - CR1 |  | G. Mindus & Sons Holding | 14597 | 2016-08-22 | 03082016-MAT | 0 |  | 4 | Approved
2016-08-05 | 2016-08-12 | 05082016-LB | 2 | LandOwner Request - CR2 |  |  |  | 2016-08-16 | 05082016-LB | 2977.44 |  | 4 | Approved
2016-08-03 | 2016-08-12 | 05082016-LB | 2 | LandOwner Request - CR2 |  | G. Mindus & Sons Holding | 14600-11944 | 2016-08-16 | 05082016-MAT | 1511.13 |  | 4 | Approved
2016-08-03 | 2016-08-13 | 05082016-LB | 2 | LandOwner Request - CR2 |  | Armtrac | 90572536 | 2016-08-16 | 05082016-MAT2 | 822.56 |  | 4 | Approved
2016-08-11 | 2016-08-15 | 12082016-GS | 8 | Stumping |  |  |  | 2016-09-09 | 12082016-GS | 952.08 |  | 7
2016-08-10 | 2016-08-23 | 352 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 110+920 | 110m |  | 20082016-UPI | 0 |  |  | With JS Sept 12
2016-08-10 | 2016-08-23 | 352 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 110+050 | 86m |  | 20082016-UPI | 0 |  |  | With JS Sept 12
2016-08-10 | 2016-08-23 | 352 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 111+310 | 30m |  | 20082016-UPI | 0 |  |  | With JS Sept 12
2016-08-10 | 2016-08-23 | 352 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 111+450 | 70m |  | 20082016-UPI | 0 |  |  | With JS Sept 12
2016-08-09 | 2016-08-13 | 402 |  | Additional Hydrovac | 2.20.1.2 | 111+544 - 111+544 | 7hr | 2016-08-26 | 10082016-UPI1 | 4654 |  | 3 | Approved
2016-08-12 | 2016-09-08 |  | 5 | Additional Hydrovac |  |  |  |  | 09082016-AACR | -408 |  |  | With JS Sept 12
2016-08-12 | 2016-08-13 | 09082017-AA | 5 | Additional Hydrovac |  |  |  |  | 09092016-AA | 4022.4 |  |  | With JS Sept 12
2016-08-13 | 2016-08-13 | 402 |  | Additional Hydrovac | 2.20.1.2 | 111+523 - 111+523 | 2hr | 2016-08-26 | 10082016-UPI1 | 0 |  | 3 | Approved
2016-08-13 | 2016-08-13 | 402 |  | Additional Hydrovac | 2.20.1.2 | 111+800 - 111+800 | 3hr | 2016-08-26 | 10082016-UPI1 | 0 |  | 3 | Approved
2016-08-13 | 2016-08-13 | 402 |  | Additional Hydrovac | 2.20.1.2 | 100+783 - 100+783 | 1hr | 2016-08-26 | 10082016-UPI1 | 0 |  | 3 | Approved
2016-08-13 | 2016-08-18 | 403 |  | Installation of wash station | 2.21.1.2 | Wash Station |  |  | 12082016-UPI3 | 38500 |  | 2 | Approved
2016-08-13 | 2016-08-20 | 404 |  | Operate Wash Station | 2.21.1.1 |  |  |  | 13082016-UPI2 | 21000 |  | 2 | Approved
2016-08-16 | 2016-08-18 | 452 |  | Additional Hydrovac | 2.19.1.1 |  | 140m | 2016-09-06 | 12082016-UPI2 | 0 |  |  | Rejected
2016-08-16 | 2016-08-13 | 453 |  | Up to depth of 20cm (total 35cm USM stripping) | 2.19.2.1 | 100+840; 101+312 |  | 2016-09-06 | 12082016-UPI | 12508 |  |  | Approved
2016-08-12 | 2016-08-17 | 14082016-GS | 8 | Stumping |  | Scott Safety | 11 | 2016-09-09 | 14082016-GS | 5229.8 |  | 7
2016-08-13 | 2016-08-17 | 15082016-GS | 8 | Stumping |  |  |  | 2016-09-09 | 15082016-GS | 448.56 |  | 7
2016-08-13 | 2016-08-18 | 454 |  | Clubroot Affected Land | 2.57.1.1 | 112+476 to 113+258 | 785m |  | 15082016-UPI1 | 192325 |  | 2 | Approved
2016-08-15 | 2016-08-23 | 455 |  | Additional Top soil 10-20cm | 2.19.1.1 | 116+680 to 116+898 | 218m | 2016-09-06 | 19082016-UPI1 | 0 |  |  | With JS Sept 12
2016-08-10 | 2016-08-23 | 455 |  | Club Root affected land | 2.57.1.1 | 118+262 to 118+496 | 234m |  | 19082016-UPI1 | 57330 |  |  | With JS Sept 12
2016-08-12 | 2016-08-17 | 527 |  | VOID | [8 empty] | VOID
2016-08-12 | 2016-08-16 | 476 |  | Barb Wire3 strand Fence | 2.26.1.8 | 114+300-114+550 | 250m |  | 13082016-UPI1 | 14800 |  | 2 | Approved
2016-08-13 | 2016-08-17 |  | 8 | Stumping |  |  |  | 2016-09-09 | 13082016-GS | 6491.24 |  | 7
2016-08-14 | 2016-08-30 |  | 5 | Additional Hydrovac |  | Lone Star | 88826 |  | 10082016-SUB | 472.5 |  |  | With JS Sept 12
2016-08-12 | 2016-08-16 | 476 |  | Barb Wire3 strand Fence | 2.26.1.8 | 114+250 - 114+580 | 330m |  | 13082016-UPI1 | 0 |  | 2 | Approved
2016-08-15 | 2016-08-16 | 476 |  | Vehicle Gate | 2.26.1.12 | Two gates | 8m |  | 13082016-UPI1 | 0 |  | 2 | Approved
2016-08-15 | 2016-08-18 |  | 8 | Stumping |  |  |  | 2016-09-09 | 16082016-GS | 598.08 |  | 7
2016-08-15 | 2016-08-13 | 11082016-AA | 5 | Additional Hydrovac |  |  |  |  | 11082016-AA | 5228.8 |  |  | With JS Sept 12
2016-08-15 | 2016-09-10 |  | 9 | Clubroot Non Continous Work |  |  |  |  | 01092016-LB | 6669.7 |  |  | Waiting for Approval of CR9
2016-08-16 | 2016-08-18 |  | 9 | Clubroot Non Continous Work |  |  |  |  | 15082016-LD | 1029.48 |  |  | Waiting for Approval of CR9
2016-08-12 | 2016-08-16 | 476 |  | Vehicle Gate | 2.26.1.12 | Two gates | 8m |  | 13082016-UPI1 | 0 |  | 2 | Approved
2016-08-16 | 2016-09-08 |  | 5 | Additional Hydrovac |  |  |  |  | 11082016-AACR | -510 |  |  | With JS Sept 12
2016-08-16 | 2016-08-30 |  | 5 | Additional Hydrovac |  | Lone Star | 88827 |  | 11082016-SUB | 2244.38 |  |  | With JS Sept 12
2016-08-17 | 2016-08-19 |  | 10 | Clubroot Green to Green |  |  |  |  | 17082016-CN | 2444.48 |  |  | Waiting for Approval of CR10
2016-08-17 | 2016-08-18 |  | 9 | Clubroot Non Continous Work |  |  |  |  | 16082016-LD | 4415.24 |  |  | Waiting for Approval of CR9
2016-08-17 | 2016-08-19 |  | 8 | Stumping |  |  |  | 2016-09-09 | 17082016-GS | 299.04 |  | 7
2016-08-16 | 2016-08-16 | 476 |  | Barb Wire3 strand Fence | 2.26.1.8 | 117+129 - 117+349 | 220m |  | 13082016-UPI1 | 0 |  | 2 | Approved
2016-08-13 | 2016-08-17 | 477 |  | Barb Wire3 strand Fence | 2.26.1.8 | 111+000 | 160m |  | 16082016-UPI | 3404 |  | 2 | Approved
2016-08-19 | 2016-08-17 | 477 |  | Vehicle Gate | 2.26.1.12 | Alley at 111+000 | 18 |  | 16082016-UPI | 0 |  | 2 | Approved
2016-08-19 | 2016-08-19 | 477 |  | Additional Hydrovac | 2.20.1.2 |  | 3 |  | 16082016-UPI1 | 1074 |  | 2 | Approved
2016-08-19 | 2016-08-17 | 551 |  | Additional Hydrovac | 2.20.1.2 | 101+385 to 101+385 | 1.5 | 2016-08-26 | 10082016-UPI | 537 |  | 3 | Approved
2016-08-19 | 2016-08-17 | 552 |  | Additional Hydrovac | 2.20.1.2 | 114+108; 112+245 | 8.5 | 2016-08-26 | 12082016-UPI1 | 3043 |  | 3 | Approved
2016-08-17 | 2016-08-17 | 553 |  | Additional Hydrovac | 2.20.1.2 | 117+328,117+333,117+335 | 8hr | 2016-08-26 | 13082016-UPI | 2864 |  | 3 | Approved
2016-08-18 | 2016-08-17 | 554 |  | Additional Hydrovac | 2.20.1.2 | 117+328,117+333,117+335,114+430 | 10 | 2016-08-26 | 15082016-UPI | 3580 |  | 3 | Approved
2016-08-18 | 2016-08-20 |  | 8 | Stumping |  |  |  | 2016-09-09 | 18082016-GS | 448.56 |  | 7
2016-08-18 | 2016-08-20 |  | 8 | Stumping |  |  |  | 2016-09-09 | 18082016-BF | 3457.2 |  | 7
2016-08-18 | 2016-08-20 |  | 10 | Clubroot Green to Green |  |  |  |  | 18082016-CN | 916.68 |  |  | Waiting for Approval of CR10
2016-08-20 | 2016-08-20 | 556 |  | Additional Hydrovac | 2.20.1.2 | 112+245 | 8 |  | 17082016-UPI | 2864 |  | 2 | Approved
2016-08-20 | 2016-08-20 | 557 |  | Additional Hydrovac | 2.20.1.2 | 101+384 | 5 |  | 18082016-UPI | 1790 |  | 2 | Approved
2016-08-20 | 2016-08-20 | 558 |  | Additional Hydrovac | 2.20.1.2 | 98+200 | 1 | [5 empty] | Signed by Bart
2016-08-20 | 2016-08-20 | 558 |  | Additional Hydrovac | 2.20.1.2 | 100+136 | 4 |  | 19082016-UPI | 1432 |  | 2 | Approved
2016-08-18 | 2016-08-18 | 12082016-AA | 5 | Additional Hydrovac |  |  |  |  | 12082016-AA | 3099.36 |  |  | With JS Sept 12
2016-08-18 | 2016-08-19 |  | 9 | Clubroot Non Continous Work |  |  |  |  | 17082016-LD | 1029.48 |  |  | Waiting for Approval of CR9
2016-08-19 | 2016-08-22 |  | 9 | Clubroot Non Continous Work |  |  |  |  | 18082016-LELEM | 2058.96 |  |  | Waiting for Approval of CR9
2016-08-19 | 2016-09-08 |  | 5 | Additional Hydrovac |  |  |  |  | 12082016-AACR | -204 |  |  | With JS Sept 12
2016-08-19 | 2016-08-20 | 558 |  | Additional Hydrovac | 2.20.1.2 | 100+138 | 0 |  | 19082016-UPI | 0 |  | 2 | Approved
2016-08-19 | 2016-08-20 | 558 |  | Additional Hydrovac | 2.20.1.2 | 106+139 | 0 |  | 19082016-UPI | 0 |  | 2 | Approved
2016-08-23 | 2016-08-22 | 559 |  | Additional Hydrovac | 2.20.1.2 | 106+805 | 10 |  | 20082016-UPI | 3580 |  |  | With JS Sept 12
2016-08-23 | 2016-08-22 | 559 |  | Additional Hydrovac | 2.20.1.2 | 106+782 | 0 | 2016-09-08 | 20082016-UPI | 0 |  |  | Rejected
2016-08-23 | 2016-08-22 | 559 |  | Additional Hydrovac | 2.20.1.2 | 106+789 | 0 | 2016-09-08 | 20082016-UPI | 0 |  |  | Rejected
2016-08-23 | 2016-08-22 | 559 |  | Additional Hydrovac | 2.20.1.2 | 106+807 | 0 | 2016-09-08 | 20082016-UPI | 0 |  |  | Rejected
2016-08-22 | 2016-08-24 |  | 8 | Stumping |  |  |  | 2016-09-09 | 22082016-GS | 1208 |  | 7
2016-08-22 | 2016-08-24 |  | 4 | Water Storage Athabasca River |  |  |  |  | 22082016-BF | 4204.8 |  |  | Waiting on Approval of CR4
2016-08-23 | 2016-08-24 | 23082016-BF | 4 | Water Storage Athabasca River |  |  |  |  | 23082016-BF | 3457.2 |  |  | Waiting on Approval of CR4
2016-08-20 | 2016-08-25 | 20082016-LD | 13 | HDD Water and Vac Trucks |  |  |  |  | 20082016-LD | 748.64 |  |  | Waiting for Approval of CR13
2016-08-22 | 2016-08-25 | 22082016-LD | 13 | HDD Water and Vac Trucks |  |  |  |  | 22082016-LD | 3743.2 |  |  | Waiting for Approval of CR13
2016-08-23 | 2016-08-27 |  | 13 | HDD Water and Vac Trucks |  |  |  | 2016-08-29 | 22082016-RL | 10577.22 |  |  | Back with MW to review
2016-08-23 | 2016-08-25 |  | 8 | Stumping |  |  |  | 2016-09-09 | 23082016-GS | 1208 |  | 7
2016-08-23 | 2016-09-12 |  | 12 | Weather Mitigation |  |  |  |  | 09092016-LB | 680 |  |  | With JS Sept 13
2016-08-24 | 2016-08-26 |  | 12 | Weather Mitigation |  |  |  | 2016-09-09 | 24082016-LB | 1008.9 |  | 8
2016-08-24 | 2016-09-12 |  | 12 | Weather Mitigation |  |  |  | 2016-09-12 | 09092016-EW | 1107.12 |  |  | With MW to review
2016-08-26 | 2016-09-10 |  | 12 | Weather Mitigation |  |  |  | 2016-09-12 | 08092016-BF | 1140.96 |  |  | With MW to review
2016-08-24 | 2016-08-30 |  | 13 | HDD Water and Vac Trucks |  | Bulldog | 62075 | 2016-08-26 | 22082016-SUB | 1837.5 |  |  | Back with MW to review
2016-08-22 | 2016-08-25 |  | 13 | HDD Water and Vac Trucks |  | Bulldog | 11554 |  | 23082016-KM | 3661.85 |  |  | Waiting for Approval of CR13
2016-08-23 | 2016-08-27 |  | 13 | HDD Water and Vac Trucks |  |  |  | 2016-08-29 | 23082016-RL | 9417.02 |  |  | Back with MW to review
2016-08-25 | 2016-08-30 |  | 5 | Additional Hydrovac |  | Lone Star | 88840 |  | 25082016-AA | 1712.43 |  |  | With JS Sept 12
2016-08-25 | 2016-09-12 |  | 12 | Weather Mitigation |  |  |  |  | 09092016-RL | 1272.08 |  |  | With RM Sept 12
2016-08-25 | 2016-08-29 |  |  | Clearing Contractor Move Around due to Work Space |  |  |  | 2016-08-29 | 25082016-LDLEM | 0 |  |  | VOID - Change CR Not pursuing at this time
2016-08-25 | 2016-08-26 |  | 14 | Hauling of Spoil Material |  |  |  |  | 24082016-RL | 1640.34 |  |  | With AW Sept 13
2016-08-26 | 2016-09-08 |  | 12 | Weather Mitigation |  |  |  | 2016-09-10 | 30082016-KM | 1290.1 |  |  | With MW to review
2016-08-26 | 2016-08-27 |  | 13 | HDD Water and Vac Trucks |  | Bulldog | 11555 |  | 24082016-SUB | 2115.75 |  |  | Waiting for Approval of CR13
2016-08-27 | 2016-08-30 |  | 13 | HDD Water and Vac Trucks |  | Bulldog | 11557 |  | 26082016-SUB | 1627.5 |  |  | Waiting for Approval of CR13
2016-08-27 | 2016-08-30 |  | 13 | HDD Water and Vac Trucks |  |  |  |  | 27082016-KM | 1871.6 |  |  | Waiting for Approval of CR13
2016-08-25 | 2016-08-30 | 560 |  | Additional Hydrovac | 2.20.1.2 |  |  | 2016-09-09 | 26082016-UPI | 2864
2016-08-26 | 2016-08-29 |  | 14 | Hauling of Spoil Material |  |  |  | 2016-09-13 | 25082016-RL | 5625.8 |  |  | With MW to review
2016-08-27 | 2016-08-30 |  | 10 | Clubroot Green to Green |  |  |  |  | 27082016-CN | 305.56 |  |  | Waiting for Approval of CR10
2016-08-27 | 2016-08-27 |  | 12 | Weather Mitigation |  |  |  | 2016-09-10 | 25082016-TH | 1719.48 |  |  | With MW to review
2016-08-10 | 2016-08-30 |  | 5 | Additional Hydrovac |  | Lone Star | 88828 |  | 12082016-SUB | 472.5 |  |  | With JS Sept 12
2016-08-11 | 2016-08-17 | 13082016-AA | 5 | Additional Hydrovac |  | Lone Star | 88829 | 2016-08-30 | 13082016-AA | 3741.3 |  | 6
2016-08-12 | 2016-08-18 |  | 5 | Additional Hydrovac |  | Lone Star | 88830 | 2016-08-30 | 15082016-AA | 3977.55 |  | 6
2016-08-15 | 2016-08-30 |  | 5 | Additional Hydrovac |  | Lone Star | 88830 | 2016-08-30 | 15082016-SUB | 0 |  |  | Void see 15082016AA
2016-08-20 | 2016-08-18 | 16082016-AA | 5 | Additional Hydrovac |  | Lone Star | 88831 |  | 16082016-AA | 5929.83 |  |  | With JS Sept 12
2016-08-20 | 2016-09-08 |  | 5 | Additional Hydrovac |  |  |  |  | 16082016-AACR | -306 |  |  | With JS Sept 12
2016-08-25 | 2016-08-22 |  | 5 | Additional Hydrovac |  | Lone Star | 88833 | 2016-08-22 | 18082016-AA | 2854.05 |  | 6
2016-08-26 | 2016-08-23 |  | 5 | Additional Hydrovac |  | Lone Star | 88834 |  | 19082016-AA | 2008.2 |  |  | With JS Sept 12
2016-08-22 | 2016-08-30 |  | 13 | HDD Water and Vac Trucks |  | Bulldog | 11558 |  | 27082016-SUB | 1302 |  |  | Waiting for Approval of CR13
2016-08-22 | 2016-09-06 | 456 |  | Crossing Ramp | 2.37.1.1 | 2 | [6 empty] | Signed by Brian F
522553.77