## MPI UPI (2)
2442198.72
Date of Time Sheet | Date Received | Time Sheet Reference # | CR# | Description | UPI | Additional SubContractor Tickets | SubCon Ticket Number | Date Given Back to MW | Related LEM # | Batch Number | LEM Amount | Rejected | Statement # | Comments
2016-10-12 | 2016-10-13 | 77 |  | Screened Gravel | 2.12.1.1 | 105+000 | 820
2016-08-19 | 2016-08-18 | 452 |  | Additional Hydrovac | 2.19.1.1 |  | 140m | 2016-09-06 | 12082016-UPI2 |  | 0 |  |  | Rejected
2016-08-20 | 2016-08-23 | 455 |  | Additional Top soil 10-20cm | 2.19.1.1 | 116+680 to 116+898 | 218m
2016-08-27 | 2016-09-07 | 326 |  | Additional Top Soil | 2.19.1.1 | 110+920-111+030 | 110
2016-08-27 | 2016-09-07 | 326 |  | Additional Top Soil | 2.19.1.1 | 111+820-111+995 | 175
2016-08-27 | 2016-09-07 | 326 |  | Additional Top Soil | 2.19.1.1 | 112+050-112+420 | 370
2016-08-27 | 2016-09-07 | 326 |  | Additional Top Soil | 2.19.1.1 | 117+190-117+290 | 100
2016-08-27 | 2016-09-07 | 326 |  | Additional Top Soil | 2.19.1.1 | 117+410-117+630 | 220
2016-08-27 | 2016-09-07 | 326 |  | Additional Top Soil | 2.19.1.1 | 116+920-116+780 | 140
2016-10-07 | 2016-10-15 | 129 |  | Removal & Restoration ove ROW-10cm-20cm | 2.19.1.1 |  |  |  | 22738 |  | 68900
2016-10-07 | 2016-10-15 | 330 |  | Removal & Restoration over ROW-10cm-20cm | 2.19.1.1 |  |  |  | 22766 |  | 71550
2016-10-07 | 2016-10-15 | 331 |  | Removal & Restoration over ROW-10cm-20cm | 2.19.1.1 |  |  |  | 22767 |  | 34450
2016-08-23 | 2016-08-23 | 352 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 110+920 | 110m |  | 20082016-UPI |  | 0 |  |  | With JS Sept 12
2016-08-23 | 2016-08-23 | 352 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 110+050 | 86m |  | 20082016-UPI |  | 0 |  |  | With JS Sept 12
2016-08-23 | 2016-08-23 | 352 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 111+310 | 30m |  | 20082016-UPI |  | 0 |  |  | With JS Sept 12
2016-08-23 | 2016-08-23 | 352 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 111+450 | 70m |  | 20082016-UPI |  | 0 |  |  | With JS Sept 12
2016-08-31 | 2016-09-12 | 457 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 121+879; 122+124 | 250m | 2016-10-11 | 31082016-UPI |  | 11375 |  |  | With MW to review
2016-09-23 | 2016-09-24 | 462 |  | Additional Top Soil Removal and restoration | 2.19.1.2 | 161+350 to 161+425 | 75 | [6 empty] | Signed by Monty S
2016-08-31 | 2016-09-17 | 457 |  | Additional Topsoil clubroot | 2.19.1.8 | 121+879; 122+129 | 250m | 2016-10-11 | 31082016-UPI1 |  | 3937.5 |  |  | Approved
2016-09-20 | 2016-09-22 | 378 |  | Seconds | 2.19.1.8 | 168+500 to 168+300 | 800 | 2016-10-11 | 20092016-UPI3 |  | 12600 |  | 17 | Approved
2016-08-19 | 2016-08-13 | 453 |  | Up to depth of 20cm (total 35cm USM stripping) | 2.19.2.1 | 100+840; 101+312 |  | 2016-09-06 | 12082016-UPI |  | 12508 |  |  | Approved
2016-09-23 | 2016-09-22 | 151 |  | Rock Shield | 2.2.1.3 | 13+569 to 13+609 | 40 |  | 20092016-UPI |  | 2180 |  | 14 | Approved
2016-09-22 | 2016-09-22 | 151 |  | Rock Shield | 2.2.1.4 | 13+569 to 13+609 | 40 |  | 20092016-UPI1 |  | 2580 |  | 14 | Approved
2016-08-13 | 2016-08-17 | 551 |  | Additional Hydrovac | 2.20.1.2 | 101+385 to 101+385 | 1.5 | 2016-08-26 | 10082016-UPI |  | 537 |  | 3 | Approved
2016-08-13 | 2016-08-13 | 402 |  | Additional Hydrovac | 2.20.1.2 | 111+544 - 111+544 | 7hr | 2016-08-26 | 10082016-UPI1 |  | 4654 |  | 3 | Approved
2016-08-13 | 2016-08-13 | 402 |  | Additional Hydrovac | 2.20.1.2 | 111+523 - 111+523 | 2hr | 2016-08-26 | 10082016-UPI1 |  | 0 |  | 3 | Approved
2016-08-14 | 2016-08-13 | 402 |  | Additional Hydrovac | 2.20.1.2 | 111+800 - 111+800 | 3hr | 2016-08-26 | 10082016-UPI1 |  | 0 |  | 3 | Approved
2016-08-19 | 2016-08-13 | 402 |  | Additional Hydrovac | 2.20.1.2 | 100+783 - 100+783 | 1hr | 2016-08-26 | 10082016-UPI1 |  | 0 |  | 3 | Approved
2016-08-17 | 2016-08-17 | 553 |  | Additional Hydrovac | 2.20.1.2 | 117+328,117+333,117+335 | 8hr | 2016-08-26 | 13082016-UPI |  | 2864 |  | 3 | Approved
2016-08-18 | 2016-08-17 | 554 |  | Additional Hydrovac | 2.20.1.2 | 117+328,117+333,117+335,114+430 | 10 | 2016-08-26 | 15082016-UPI |  | 3580 |  | 3 | Approved
2016-08-20 | 2016-08-20 | 556 |  | Additional Hydrovac | 2.20.1.2 | 112+245 | 8 |  | 17082016-UPI |  | 2864 |  | 2 | Approved
2016-08-20 | 2016-08-20 | 557 |  | Additional Hydrovac | 2.20.1.2 | 101+384 | 5 |  | 18082016-UPI |  | 1790 |  | 2 | Approved
2016-08-20 | 2016-08-20 | 558 |  | Additional Hydrovac | 2.20.1.2 | 98+200 | 1 |  | 19082016-UPI |  | 0 |  |  | Approved
2016-08-20 | 2016-08-20 | 558 |  | Additional Hydrovac | 2.20.1.2 | 100+136 | 4 |  | 19082016-UPI |  | 1432 |  | 2 | Approved
2016-08-18 | 2016-08-17 | 552 |  | Additional Hydrovac | 2.20.1.2 | 114+108; 112+245 | 8.5 | 2016-08-26 | 12082016-UPI1 |  | 3043 |  | 3 | Approved
2016-08-19 | 2016-08-20 | 558 |  | Additional Hydrovac | 2.20.1.2 | 100+138 | 0 |  | 19082016-UPI |  | 0 |  | 2 | Approved
2016-08-19 | 2016-08-20 | 558 |  | Additional Hydrovac | 2.20.1.2 | 106+139 | 0 |  | 19082016-UPI |  | 0 |  | 2 | Approved
2016-08-20 | 2016-08-22 | 559 |  | Additional Hydrovac | 2.20.1.2 | 106+805 | 10 |  | 20082016-UPI |  | 3580 |  |  | With JS Sept 30
2016-08-25 | 2016-08-30 | 560 |  | Additional Hydrovac | 2.20.1.2 |  |  | 2016-09-09 | 26082016-UPI |  | 2864
2016-08-20 | 2016-08-19 | 555 |  | Additional Hydrovac | 2.20.1.2 |  | 3 |  | 16082016-UPI1 |  | 1074 |  | 2 | Approved
2016-08-26 | 2016-08-22 | 559 |  | Additional Hydrovac | 2.20.1.2 | 106+782 | 0 |  | 20082016-UPI |  | 0 |  |  | With JS Sept 30
2016-08-16 | 2016-08-22 | 559 |  | Additional Hydrovac | 2.20.1.2 | 106+789 | 0 |  | 20082016-UPI |  | 0 |  |  | With JS Sept 30
2016-08-11 | 2016-08-22 | 559 |  | Additional Hydrovac | 2.20.1.2 | 106+807 | 0 |  | 20082016-UPI |  | 0 |  |  | With JS Sept 30
2016-08-25 | 2016-08-30 | 561 |  | Additional Hydrovac | 2.20.1.2 |  |  | 2016-09-09 | 25082016-UPI |  | 1074
2016-09-14 | 2016-09-19 | 568 |  | Hydrovac | 2.20.1.2 | Lac st Anne 178+389 | 5 |  | 14092016-UPI1 |  | 3580 |  |  | With JS Sept 22
2016-09-14 | 2016-09-19 | 568 |  | Hydrovac | 2.20.1.2 | Lac St Anne 167+377 | 5 |  | 14092016-UPI1 |  | 0 |  |  | With JS Sept 22
2016-09-13 | 2016-09-20 | 567 |  | Hydrovac | 2.20.1.2 | Lac St Anne 178+389 | 4 |  | 13092016-UPI |  | 1432 |  | 14 | Approved
2016-09-17 | 2016-09-19 | 566 |  | Hydrovac | 2.20.1.2 | Telus line | 1.5 |  | 12092016-UPI2 |  | 1074 |  |  | With JS Sept 22
2016-09-17 | 2016-09-19 | 566 |  | Hydrovac | 2.20.1.2 | Telus line | 1.5 |  | 12092016-UPI2 |  | 0 |  |  | With JS Sept 22
2016-08-25 | 2016-09-12 | 562 |  | Additional Hydrovac | 2.20.1.2 | 178+407 | 10hrs | 2016-10-17 | 08092016-UPI |  | 3580 |  | 17 | Approved
2016-08-20 | 2016-09-12 | 565 |  | Additional Hydrovac | 2.20.1.2 | Rd45 | 1.5hrs | 2016-10-17 | 10092016-UPI |  | 537 |  | 17 | Approved
2016-09-21 | 2016-09-24 | 573 |  | Hydrovac | 2.20.1.2 | 160+605 | 5 | 2016-10-17 | 21092016-UPI |  | 1790 |  | 17 | Approved
2016-09-25 | 2016-09-19 | 569 |  | Hydrovac | 2.20.1.2 | Lac St Anne 177+840 | 4 |  | 16092016-UPI1 |  | 5370
2016-09-21 | 2016-09-19 | 570 |  | Hydrovac | 2.20.1.2 | Lac st Anne 167+377 | 3 |  | 15092016-UPI |  | 1074 |  | 14 | Approved
2016-09-25 | 2016-09-19 | 569 |  | Hydrovac | 2.20.1.2 | Pembina 170+686 | 1 |  | 16092016-UPI1 |  | 0
2016-09-16 | 2016-09-19 | 569 |  | Hydrovac | 2.20.1.2 | TRL 117+758 | 10 |  | 16092016-UPI1 |  | 0 |  |  | With JS Sept 22
2016-09-18 | 2016-09-24 | 572 |  | Hydrovac | 2.20.1.2 | 112+743 | 9 | 2016-10-04 | 20092016-UPI4 |  | 3222 |  |  | With MW to review
2016-09-24 | 2016-09-29 | 103 |  |  | 2.20.1.2 | 103+538 | 1.5 |  | 24062016-UPI2 |  | 4654 |  |  | With JS Oct 7
2016-09-24 | 2016-09-29 | 103 |  |  | 2.20.1.2 | 103+529 | 1.5 |  | 24062016-UPI2 |  | 0 |  |  | With JS Oct 7
2016-09-24 | 2016-09-29 | 103 |  |  | 2.20.1.2 | 112+750 | 10 |  | 24062016-UPI2 |  | 0 |  |  | With JS Oct 7
2016-09-22 | 2016-09-24 | 575 |  | Hydrovac | 2.20.1.2 | 170+620 | 1 | 2016-10-04 | 22092016-UPI2 |  | 358 |  |  | With MW to review
2016-09-22 | 2016-09-24 | 574 |  | Hydrovac | 2.20.1.2 | 160+645 | 8 | 2016-10-04 | 22092016-UPI3 |  | 5728 |  |  | With MW to review
2016-09-21 | 2016-09-24 | 574 |  | Hydrovac | 2.20.1.2 | 160+501 | 8 | 2016-10-04 | 22092016-UPI3 |  | 0 |  |  | With MW to review
2016-09-19 | 2016-09-24 | 571 |  | Hydrovac | 2.20.1.2 | 112+743 | 10 |  | 19092016-UPI1 |  | 6802 |  |  | With JS Sep 29
2016-09-19 | 2016-09-24 | 571 |  | Hydrovac | 2.20.1.2 | 112+132 | 9 |  | 19092016-UPI1 |  | 0 |  |  | With JS Sep 29
2016-10-04 | 2016-10-05 | 105 |  | Hydrovac | 2.20.1.2 | 139+917 | 1 | [6 empty] | Signed by Rmueller
2016-09-26 | 2016-09-29 | 102 |  |  | 2.20.1.2 | 1532+219 | 2.5 |  | 26092016-UPi2 |  | 3401 |  |  | With JS Oct 7
2016-09-26 | 2016-09-29 | 102 |  |  | 2.20.1.2 | 130+144 | 3 |  | 26092016-UPi2 |  | 0 |  |  | With JS Oct 7
2016-09-26 | 2016-09-29 | 102 |  |  | 2.20.1.2 | 160+644 | 4 |  | 26092016-UPi2 |  | 0 |  |  | With JS Oct 7
2016-09-26 | 2016-09-29 | 340 |  | Additional Hydrovac | 2.20.1.2 | 105+692 | 1.5 |  | 26092016-UPI4 |  | 2864 |  |  | With JS Oct 7
2016-10-07 | 2016-10-11 | 107 |  | Hydrovac less than 3m | 2.20.1.2 | 135+306 | 6
2016-09-26 | 2016-09-29 | 340 |  | Additional Hydrovac | 2.20.1.2 | 117+728 | 1.5 |  | 26092016-UPI4 |  | 0 |  |  | With JS Oct 7
2016-09-26 | 2016-09-29 | 340 |  | Additional Hydrovac | 2.20.1.2 | 117+732 | 1 |  | 26092016-UPI4 |  | 0 |  |  | With JS Oct 7
2016-09-26 | 2016-09-29 | 340 |  | Additional Hydrovac | 2.20.1.2 | 123+704 | 1 |  | 26092016-UPI4 |  | 0 |  |  | With JS Oct 7
2016-09-26 | 2016-09-29 | 340 |  | Additional Hydrovac | 2.20.1.2 | 166+175 | 1 |  | 26092016-UPI4 |  | 0 |  |  | With JS Oct 7
2016-09-26 | 2016-09-29 | 340 |  | Additional Hydrovac | 2.20.1.2 | 172+869 | 2 |  | 26092016-UPI4 |  | 0 |  |  | With JS Oct 7
2016-10-07 | 2016-10-15 | 105 |  | Hydro-vac Facilities less than 3m | 2.20.1.2 |  |  |  | 22755 |  | 358 |  |  | With JS Oct 15
2016-10-08 | 2016-10-15 | 107 |  | Hydro-vac Facilities less than 3m | 2.20.1.2 |  |  |  | 22779 |  | 5370 |  |  | With JS Oct 15
2016-09-19 | 2016-09-29 | 101 |  |  | 2.20.1.4 | 160+645 to 160+501 | 16 |  | 23092016-UPI |  | 5728 |  |  | With JS Sept 29
2016-10-06 | 2016-10-11 | 106 |  | Hydrovac Greater than 3m | 2.20.1.4 | 135+306 | 7
2016-09-26 | 2016-09-29 | 340 |  | Additional Hydrovac | 2.20.1.4 | 115+815 | 2 | 2016-10-11 | 26092016-UPI5 |  | 1432 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 340 |  | Additional Hydrovac | 2.20.1.4 | 118+407 | 2 | 2016-10-11 | 26092016-UPI5 |  | 0 |  | 17 | Approved
2016-10-08 | 2016-10-15 | 106 |  | Hydro-vac Facilities greater than 3m | 2.20.1.4 |  |  |  | 22778 |  | 4296 |  |  | With JS Oct 15
2016-08-13 | 2016-08-20 | 404 |  | Operate Wash Station | 2.21.1.1 |  |  |  | 13082016-UPI2 |  | 21000 |  | 2 | Approved
2016-09-06 | 2016-09-17 | 327 |  |  | 2.21.1.1 | Wash Station |  |  | 06092016-UPI |  | 3500 |  | 11 | Approved
2016-09-08 | 2016-09-17 | 327 |  |  | 2.21.1.1 | Wash Station |  |  | 08092016-UPI1 |  | 3500 |  | 11 | Approved
2016-09-09 | 2016-09-17 | 327 |  |  | 2.21.1.1 | Wash Station |  |  | 09092016-UPI1 |  | 3500 |  | 11 | Approved
2016-09-12 | 2016-09-17 | 327 |  |  | 2.21.1.1 | Wash Station |  |  | 12092016-UPI |  | 3500 |  | 11 | Approved
2016-09-20 | 2016-09-22 | 328 |  | Vehicle and Equipment Wash Stations | 2.21.1.1 | Sept 13-14-15-16-17 |  |  | 19092016-UPI |  | 17500 |  | 15 | Approved
2016-10-03 | 2016-10-03 | 342 |  | Clubroot Wash Station | 2.21.1.1 | Yard | 1 | [6 empty] | Signed by CH
2016-10-10 | 2016-10-13 | 138 |  | Clubroot Wash Station | 2.21.1.1 | Stripping Crew | 2
2016-09-26 | 2016-09-29 | 337 |  | Clubroot Wash Station | 2.21.1.1 | Yard | 6 | 2016-10-11 | 26092016-UPI3 |  | 21000 |  | 17 | Approved
2016-09-28 | 2016-09-29 | 341 |  | Clubroot Wash Station | 2.21.1.1 | Yard | 3 | 2016-10-17 | 28092016-UPI |  | 10500 |  | 17 | Approved
2016-10-17 | 2016-10-17 | 143 |  | Clubroot Wash Station | 2.21.1.1 | [8 empty] | Signed by CH
2016-10-10 | 2016-10-19 | 138 |  | Vehicle & Equipment Wash Station | 2.21.1.1 |  |  |  | 23153 |  | 7000 |  |  | With JS Oct 19
2016-08-25 | 2016-08-18 | 403 |  | Installation of wash station | 2.21.1.2 | Wash Station |  |  | 12082016-UPI3 |  | 38500 |  | 2 | Approved
2016-10-06 | 2016-10-11 | 152 |  | Cut and Re-bevel Pipe Ends | 2.23.1.1 | 105+605 | 1
2016-10-08 | 2016-10-15 | 152 |  | Cut & Re Bevel Pipe Ends-Spread 2 NPS 16 | 2.23.1.1 |  |  |  | 22771 |  | 380 |  |  | With JS Oct 15
2016-10-06 | 2016-10-11 | 152 |  | Pipe Ends | 2.23.1.2 | 105+616 | 1
2016-10-08 | 2016-10-15 | 152 |  | Cut & Re Bevel Pipe Ends-Spread 2 NPS 24 | 2.23.1.2 |  |  |  | 22777 |  | 515 |  |  | With JS Oct 15
2016-09-22 | 2016-10-03 | 228 |  | Cut and Re-bevel Pipe Ends | 2.23.1.3 | 115+190 to 115+193 | 1 | 2016-10-04 | 20092016-UPI5 |  | 350 |  |  | With MW to review
2016-09-14 | 2016-10-03 | 228 |  | Cut and Re-bevel Pipe Ends | 2.23.1.4 | 115+190 to 115+193 | 1 | 2016-10-04 | 20092016-UPI6 |  | 465 |  |  | With MW to review
2016-10-15 | 2016-10-19 | 598 |  | Snow Fence-Spread 2 | 2.26.1.1 |  |  |  | 23167 |  | 2142 |  |  | With JS Oct 19
2016-10-05 | 2016-10-07 | 489 |  | Barbwire 4 strand | 2.26.1.10 | 158+904 | 804 | 2016-10-13 | 22742 | 22742 | 86466.6 |  | 17 | Approved
2016-10-05 | 2016-10-07 | 489 |  | Barbwire 4 strand | 2.26.1.10 | 137+000 | 422 | 2016-10-13 | 22742 | 22742 | 0 |  | 17 | Approved
2016-10-05 | 2016-10-07 | 489 |  | Barbwire 4 strand | 2.26.1.10 | 156+750 | 1046 | 2016-10-13 | 22742 | 22742 | 0 |  | 17 | Approved
2016-10-05 | 2016-10-07 | 489 |  | Barbwire 4 strand | 2.26.1.10 | 156+680 | 916 | 2016-10-13 | 22742 | 22742 | 0 |  | 17 | Approved
2016-10-05 | 2016-10-07 | 489 |  | Barbwire 4 strand | 2.26.1.10 | 158+150 | 488 | 2016-10-13 | 22742 | 22742 | 0 |  | 17 | Approved
2016-10-05 | 2016-10-07 | 489 |  | Barbwire 4 strand | 2.26.1.10 | 158+150 | 680 | 2016-10-13 | 22742 | 22742 | 0 |  | 17 | Approved
2016-10-05 | 2016-10-13 | 493 |  | Barbwire 4 strand | 2.26.1.10 | 150+370 | 420 | 2016-10-13 | 22744 | 22744 | 8337 |  | 17 | Approved
2016-09-12 | 2016-09-17 | 480 |  | Barbwire 4 strand | 2.26.1.10 | 107+650 to 105+500 | 874m | 2016-10-13 | 12092016-UPI1 |  |  |  |  | Redo
2016-09-19 | 2016-09-20 | 484 |  |  | 2.26.1.10 | 4 Barb Wire Fence | [7 empty] | Signed by Monty S
2016-10-05 | 2016-10-13 | 494 |  | Barbwire 4 strand | 2.26.1.10 | 109+600 | 625 | 2016-10-13 | 22773 | 22773 | 12406.25 |  | 17 | Approved
2016-08-25 | 2016-09-17 | 481 |  | Barbwire 4 strand | 2.26.1.10 | 165+948 to 166+700 | 890m | 2016-10-13 | 14092016-UPI |  | 17666.5 |  | 17 | Approved
2016-09-14 | 2016-09-23 | 482 |  | Barbwire 4 strand | 2.26.1.10 | 166+780 to 167+000 | 220 | 2016-10-13 | 22092016-UPI |  | 8515.65 |  | 17 | Approved
2016-09-20 | 2016-09-23 | 482 |  | Barbwire 4 strand | 2.26.1.10 | 166+790 to 166+999 | 209 | 2016-10-13 | 22092016-UPI |  | 0 |  |  | Approved
2016-09-22 | 2016-09-23 | 482 |  | Vehicle Gate | 2.26.1.10 | 166+790 to 166+999 | 10 | 2016-10-13 | 22092016-UPI1 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 490 |  | Barbwire 4 strand | 2.26.1.10 | RD46 | 328 |  | 26092016-UPI |  | 0 |  |  | Void
2016-09-26 | 2016-09-29 | 490 |  | Barbwire 4 strand | 2.26.1.10 | RD46 East Side | 711 |  | 26092016-UPI |  | 0 |  |  | Void
2016-10-06 | 2016-10-17 | 495 |  | Barbwire 5 strand | 2.26.1.10 | 161+375 | 240
| 2016-10-17 | 493 |  | Barbwire 4 strand | 2.26.1.10 | 150+370 | 420
| 2016-10-17 | 494 |  | Barbwire 4 strand | 2.26.1.10 | 169+600 | 625
| 2016-10-17 | 499 |  | Barbwire 4 strand | 2.26.1.10 | 131+280 | 640
| 2016-10-17 | 499 |  | Barbwire 4 strand | 2.26.1.10 | 131+260 | 730
| 2016-10-17 | 498 |  | Barbwire 4 strand | 2.26.1.10 | 131+900 | 460
| 2016-10-17 | 498 |  | Barbwire 4 strand | 2.26.1.10 | 131+975 | 325
| 2016-10-17 | 498 |  | Aelly | 2.26.1.10 | 132+150 | 100
| 2016-10-17 | 497 |  | Barbwire 4 strand | 2.26.1.10 | 139+145 | 105
2016-08-15 | 2016-08-16 | 476 |  | Vehicle Gate | 2.26.1.12 | Two gates | 8m |  | 13082016-UPI1 |  | 0 |  | 2 | Approved
2016-08-12 | 2016-08-16 | 476 |  | Vehicle Gate | 2.26.1.12 | Two gates | 8m |  | 13082016-UPI1 |  | 0 |  | 2 | Approved
2016-08-12 | 2016-08-17 | 477 |  | Vehicle Gate | 2.26.1.12 | Alley at 111+000 | 18 |  | 16082016-UPI |  | 0 |  | 2 | Approved
2016-09-10 | 2016-09-15 | 480 |  | Vehicle Gate | 2.26.1.12 | 172+864 to 172+041 | 900m | [6 empty] | Signed by Don Durda
| 2016-10-07 | 487 |  | Vehicle Gate | 2.26.1.12 | 163+100 | 32 | 2016-10-13 | 22746 | 22746 | 1920 |  | 17 | Approved
| 2016-10-07 | 487 |  | Vehicle Gate | 2.26.1.12 | 163+800 | 32 | 2016-10-13 | 22746 | 22746 | 0 |  | 17 | Approved
2016-10-05 | 2016-10-13 | 493 |  | Vehicle Gate | 2.26.1.12 | 150+790 | 30 | 2016-10-13 | 22748 | 22748 | 900 |  | 17 | Approved
2016-09-08 | 2016-09-17 | 480 |  | Vehicle Gate | 2.26.1.12 | 172+864 to 172+041 | 10 | 2016-10-04 | 10092016-UPI2 |  | 300 |  |  | With MW to review
2016-09-21 | 2016-09-29 | 486 |  | Vehicle Gate | 2.26.1.12 | 164+260 | 8 | 2016-10-13 | 21092016-UPI2 |  | 240 |  | 17 | Approved
2016-09-20 | 2016-09-23 | 482 |  | Vehicle Gate | 2.26.1.12 | 166+999 | 8 | 2016-10-13 | 22092016-UPI1 |  | 540 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 490 |  | Vehicle Gate | 2.26.1.12 |  | 9 | [6 empty] | Signed by Monty S
2016-09-20 | 2016-09-15 | 478 |  | Vehicle Gate | 2.26.1.12 | 178+850 to 178+860 | 10m | 2016-10-13 | 25082016-UPI2 |  | 300 |  | 17 | Approved
2016-10-11 | 2016-10-14 | 492 |  | Barbwire 4 strand | 2.26.1.12 | 147+780 | 10
2016-10-11 | 2016-10-14 | 492 |  | Barbwire 4 strand | 2.26.1.12 | 147+780 | 10
2016-10-11 | 2016-10-14 | 491 |  | Vehicle Gate | 2.26.1.12 | 145+536 | 9
2016-10-11 | 2016-10-14 | 491 |  | Vehicle Gate | 2.26.1.12 | 145+536 | 9
| 2016-10-17 | 493 |  | Vehicle Gate | 2.26.1.12 | 150+790 | 30
| 2016-10-17 | 499 |  | Vehicle Gate | 2.26.1.12 | Northside | 12
| 2016-10-17 | 499 |  | Vehicle Gate | 2.26.1.12 | Southside | 12
| 2016-10-17 | 498 |  | Vehicle Gate | 2.26.1.12 | 132+150 | 12
| 2016-10-17 | 498 |  | Vehicle Gate | 2.26.1.12 | 132+150 | 12
| 2016-10-17 | 498 |  | Vehicle Gate | 2.26.1.12 | 132+150 | 9
| 2016-10-17 | 498 |  | Vehicle Gate | 2.26.1.12 | 132+150 | 9
2016-10-13 | 2016-10-14 | 598 |  | Snow fence | 2.26.1.2 | Rd14 | 120
2016-10-11 | 2016-10-14 | 492 |  | Electric Fence | 2.26.1.4 | 147+800 | 634
2016-10-11 | 2016-10-14 | 492 |  | Electric Fence | 2.26.1.4 | 147+800 | 641
2016-08-12 | 2016-08-16 | 476 |  | Barb Wire3 strand Fence | 2.26.1.8 | 114+300-114+550 | 250m |  | 13082016-UPI1 |  | 14800 |  | 2 | Approved
2016-08-12 | 2016-08-16 | 476 |  | Barb Wire3 strand Fence | 2.26.1.8 | 114+250 - 114+580 | 330m |  | 13082016-UPI1 |  | 0 |  | 2 | Approved
2016-08-16 | 2016-08-16 | 476 |  | Barb Wire3 strand Fence | 2.26.1.8 | 117+129 - 117+349 | 220m |  | 13082016-UPI1 |  | 0 |  | 2 | Approved
2016-08-19 | 2016-08-17 | 477 |  | Barb Wire3 strand Fence | 2.26.1.8 | 111+000 | 160m |  | 16082016-UPI |  | 3404 |  | 2 | Approved
2016-09-20 | 2016-09-17 | 480 |  | Barb Wire3 strand Fence | 2.26.1.8 | 172+864 to 172+041 | 900 |  | 10092016-UPI1 |  | 0 |  |  | Void
2016-09-16 | 2016-09-29 | 483 |  | Barb Wire3 strand Fence | 2.26.1.8 | 165+929 to 164+964 | 1090 | 2016-10-13 | 16092016-UPI2 |  | 19511 |  | 17 | Approved
2016-09-21 | 2016-09-29 | 486 |  | Barb Wire3 strand Fence | 2.26.1.8 | 164+160 to 164+964 | 860 | 2016-10-13 | 21092016-UPI1 |  | 15394 |  | 17 | Approved
2016-09-22 | 2016-09-29 | 488 |  | Barb Wire3 strand Fence | 2.26.1.8 | 159+700 to 159+780 | 80 | 2016-10-13 | 22092016-UPI5 |  | 1432 |  | 17 | Approved
2016-09-23 | 2016-09-17 | 478 |  | Barb Wire3 strand Fence | 2.26.1.8 | 178+258 to 179+450 | 1200 | 2016-10-13 | 25082016-UPI1 |  | 21480 |  | 17 | Approved
| 2016-10-07 | 487 |  | Barb Wire3 strand Fence | 2.26.1.8 | 163+090 | 937
| 2016-10-07 | 487 |  | Barb Wire3 strand Fence | 2.26.1.8 | 163+120 | 822
| 2016-10-07 | 487 |  | Barb Wire3 strand Fence | 2.26.1.8 | 163+800 | 50
| 2016-10-07 | 487 |  | Barb Wire3 strand Fence | 2.26.1.8 | 163+100 | 50
2016-10-11 | 2016-10-14 | 491 |  | Barb Wire3 strand Fence | 2.26.1.8 | 145+536 | 821
2016-10-11 | 2016-10-14 | 491 |  | Barb Wire3 strand Fence | 2.26.1.8 | 145+536 | 840
2016-10-11 | 2016-10-14 | 491 |  | Alley Gate | 2.26.1.8 | 145+600 | 50
2016-10-11 | 2016-10-14 | 491 |  | Alley Gate | 2.26.1.8 | 145+600 | 50
2016-08-22 | 2016-09-06 | 456 |  | Crossing Ramp | 2.37.1.1 | 2 | [7 empty] | Signed by Brian F
NA | 2016-09-22 | 461 |  | Crossing Ramp | 2.37.1.1 | 166+299 | 1 | [6 empty] | Signed by Monty S
2016-09-24 | 2016-09-24 | 332 |  | Ramp Across Wet Area | 2.37.1.9 | 165+938 to 166+020 | 82 |  | 24092016-UPI |  | 34850 |  |  | With JS Oct 7
2016-10-06 | 2016-10-07 | 208 |  | Install Clay Ramp | 2.37.1.9 | 107+545 to 107+545 | 145 | [6 empty] | Signed By AW
2016-10-07 | 2016-10-15 | 208 |  | Install & Remove per DWG E1.01-16A Sh1028/29 Spread 3 | 2.37.1.9 |  |  |  | 22739 |  | 61625 |  |  | With JS Oct 15
2016-10-13 | 2016-10-19 | 230 |  | Access Mats per DWG E1.01-8-0326 | 2.38.1.1 |  |  |  | 23150 |  | 2400 |  |  | With JS Oct 19
2016-09-14 | 2016-09-22 | 376 |  | Move Around within 10km | 2.41.1.1 | RD 51 to RD45 | [7 empty] | Signed By Blaine
2016-09-20 | 2016-09-23 | 329 |  | Move Around within 10km | 2.41.1.1 | Stripping Crew 162+188 to 158+868 |  | 2016-10-04 | 22092016-UPI4 |  | 27000 |  |  | With MW to review
2016-10-15 | 2016-10-17 | 139 |  | HD Bore Adjustment | 2.42.1.1 | 106+794 | -16
2016-10-15 | 2016-10-17 | 141 |  | HD Bore Adjustment | 2.42.1.2 | 106+794 | -20
2016-10-15 | 2016-10-17 | 140 |  | HD Bore Adjustment | 2.42.1.3 | 111+534 | -9
2016-10-15 | 2016-10-17 | 140 |  | HD Bore Adjustment | 2.42.1.3 | 111+765 | 23
2016-10-15 | 2016-10-17 | 140 |  | HD Bore Adjustment | 2.42.1.3 | 115+128 | 1
2016-10-15 | 2016-10-17 | 140 |  | HD Bore Adjustment | 2.42.1.3 | 117+353 | 0.5
2016-10-15 | 2016-10-17 | 140 |  | HD Bore Adjustment | 2.42.1.3 | 119+674 | -6
2016-10-15 | 2016-10-17 | 140 |  | HD Bore Adjustment | 2.42.1.3 | 167+650 | -4
2016-10-15 | 2016-10-17 | 142 |  | HD Bore Adjustment | 2.42.1.4 | 111+534 | -8
2016-10-15 | 2016-10-17 | 142 |  | HD Bore Adjustment | 2.42.1.4 | 111+765 | 23
2016-10-15 | 2016-10-17 | 142 |  | HD Bore Adjustment | 2.42.1.4 | 115+128 | 0
2016-10-15 | 2016-10-17 | 142 |  | HD Bore Adjustment | 2.42.1.4 | 117+353 | 4
2016-10-15 | 2016-10-17 | 142 |  | HD Bore Adjustment | 2.42.1.4 | 119+674 | -5
2016-10-15 | 2016-10-17 | 142 |  | HD Bore Adjustment | 2.42.1.4 | 167+650 | -3
2016-10-03 | 2016-10-07 | 349 |  | 117+353 | 2.48.1.1 | 117+353 | 583 |  | 22757 | 22757 | 15499.5 |  |  | Holding
2016-10-03 | 2016-10-07 | 350 |  | 106+791 to 119+687 | 2.48.1.1 | HDB | 583 |  | 22756 | 22756 | 98810.55 |  |  | Holding
2016-09-26 | 2016-09-29 | 335 |  | Mud Land Spread | 2.48.1.1 | 100+237.5 | 110 | 2016-10-11 | 26092016-UPI8 |  | 2915 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 335 |  | Mud Land Spread | 2.48.1.2 | 70/5km | 350 | 2016-10-13 | 26092016-UPI9 |  | 3145 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 335 |  | Mud Land Spread | 2.48.1.2 | 10/15km | 150 | 2016-10-13 | 26092016-UPI9 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 335 |  | Mud Land Spread | 2.48.1.2 | 30/40km | 1200 | 2016-10-13 | 26092016-UPI9 |  | 0 |  | 17 | Approved
2016-10-04 | 2016-10-07 | 126 |  | HDD Mud Disposal Prep | 2.52.1.1 | Transfer from sump to sump | 65 | 2016-10-13 | 22749 | 22749 | 3347.5 |  | 17 | Approved
2016-10-03 | 2016-10-07 | 347 |  | HDD Mud Disposal Prep | 2.52.1.1 | 106+300 | 163 | 2016-10-13 | 22759 | 22759 | 8394.5 |  | 17 | Approved
2016-10-03 | 2016-10-07 | 343 |  | HDD Mud Disposal Prep | 2.52.1.1 | Athabasca HDD | 1327.5 | 2016-10-13 | 22763 | 22763 | 68366.25 |  | 17 | Approved
2016-10-03 | 2016-10-07 | 345 |  | HDD Mud Disposal Prep | 2.52.1.1 | Hwy 43 HDD | 291 | 2016-10-13 | 22765 | 22765 | 14986.5 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 333 |  | HDD Mud Disposal Prep | 2.52.1.1 | 100+237.5 | 1507 | 2016-10-13 | 26092016-UPI11 |  | 77610.5 |  | 17 | Approved
2016-10-10 | 2016-10-13 | 135 |  | HDD Mud Disposal Prep | 2.52.1.1 | 106+300 Mink Creek | 208
2016-09-26 | 2016-09-29 | 336 |  | HDD Mud Disposal Prep | 2.52.1.1 | 115+759 | 647 | 2016-10-13 | 26092016-UPI6 |  | 33320.5 |  | 17 | Approved
2016-10-15 | 2016-10-19 | 133 |  | Mix Bury-Cover Non-Frozen Conditions | 2.52.1.1 |  |  |  | 23155 |  | 64478 |  |  | With JS Oct 19
2016-10-15 | 2016-10-19 | 135 |  | Mix Bury-Cover Non-Frozen Conditions | 2.52.1.1 |  |  |  | 23154 |  | 10712 |  |  | With JS Oct 19
2016-10-03 | 2016-10-07 | 348 |  | Mud Hauling | 2.52.1.2 | 16km | 2.608 | 2016-10-13 | 22758 | 22758 | 4824.8 |  | 17 | Approved
2016-10-03 | 2016-10-07 | 346 |  | Mud Hauling | 2.52.1.2 | Hwy 43 HDD | 291
2016-10-04 | 2016-10-07 | 127 |  | Mud Hauling | 2.52.1.2 | HDB | 65
2016-10-03 | 2016-10-07 | 344 |  | Mud Hauling | 2.52.1.2 | Athabasca HDD |  |  | 22762 |  | 137098.88 |  |  | JS Oct 14
2016-10-10 | 2016-10-13 | 137 |  | Mud Hauling | 2.52.1.2 | 106+300 | 992
2016-10-10 | 2016-10-13 | 137 |  | Mud Hauling | 2.52.1.2 | 106+300 | 220
2016-10-10 | 2016-10-13 | 137 |  | Mud Hauling | 2.52.1.2 | 106+300 | 148
2016-10-10 | 2016-10-13 | 137 |  | Mud Hauling | 2.52.1.2 | 106+300 | 300
2016-10-10 | 2016-10-13 | 134 |  | Mud Hauling | 2.52.1.2 | 106+300 | 23498
2016-10-10 | 2016-10-13 | 134 |  | Mud Hauling | 2.52.1.2 | 106+300 | 30396
2016-10-10 | 2016-10-13 | 134 |  | Mud Hauling | 2.52.1.2 | 106+300 | 1722
2016-10-10 | 2016-10-13 | 134 |  | Mud Hauling | 2.52.1.2 | 106+300 | 377
2016-10-10 | 2016-10-13 | 134 |  | Mud Hauling | 2.52.1.2 | 106+300 | 372
2016-10-10 | 2016-10-13 | 134 |  | Mud Hauling | 2.52.1.2 | 106+300 | 7904
2016-10-10 | 2016-10-13 | 134 |  | Mud Hauling | 2.52.1.2 | 106+300 | 2112
2016-10-10 | 2016-10-13 | 134 |  | Mud Hauling | 2.52.1.2 | 106+300 | 850
2016-10-10 | 2016-10-13 | 134 |  | Mud Hauling | 2.52.1.2 | 106+300 | 650
2016-09-26 | 2016-09-29 | 336 |  | Mud Hauling | 2.52.1.2 | 398/11km | 4378 | 2016-10-13 | 26092016-UPI7 |  | 20300.05 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 336 |  | Mud Hauling | 2.52.1.2 | 173/22km | 3806 | 2016-10-13 | 26092016-UPI7 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 336 |  | Mud Hauling | 2.52.1.2 | 36/24km | 864 | 2016-10-13 | 26092016-UPI7 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 336 |  | Mud Hauling | 2.52.1.2 | 25/62km | 1550 | 2016-10-13 | 26092016-UPI7 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 336 |  | Mud Hauling | 2.52.1.2 | 15/25km | 375 | 2016-10-13 | 26092016-UPI7 |  | 0 |  | 17 | Approved
2016-10-15 | 2016-10-19 | 134 |  | Mix Bury Cove Non-Frozen Dondition-Hauling HDD | 2.52.1.2 |  |  |  | 23156 |  | 125579.85 |  |  | With JS Oct 19
2016-10-10 | 2016-10-19 | 137 |  | Mix Bury Cove Non-Frozen Dondition-Hauling HDD | 2.52.1.2 |  |  |  | 23152 |  | 8066 |  |  | With JS Oct 19
2016-08-13 | 2016-08-18 | 454 |  | Clubroot Affected Land | 2.57.1.1 | 112+476 to 113+258 | 785m |  | 15082016-UPI1 |  | 192325 |  | 2 | Approved
2016-09-01 | 2016-08-23 | 455 |  | Clubroot Affected Land | 2.57.1.1 | 118+262 to 118+496 | 234m |  | 19082016-UPI1 |  | 57330 |  | 11 | Approved
2016-09-16 | 2016-09-20 | 460 |  | Clubroot Affected Land | 2.57.1.1 | 165+946 TO 166+780 | 834 |  | 16092016-UPI |  | 204330 |  | 14 | Approved
2016-09-19 | 2016-09-22 | 378 |  | Clubroot Affected Land | 2.57.1.1 | 168+500 to 169+300 | 800 |  | 20092016-UPI2 |  | 196000 |  | 14 | Approved
2016-10-06 | 2016-10-07 | 128 |  | Strip Club root | 2.57.1.1 | 169+300 | 22
2016-10-06 | 2016-10-07 | 128 |  | Strip Club root | 2.57.1.1 | 112+473 | 7
2016-10-06 | 2016-10-07 | 128 |  | Strip Club root | 2.57.1.1 | 113+258 | 8
2016-10-06 | 2016-10-07 | 128 |  | Strip Club root | 2.57.1.1 | 178+513 | 99
2016-10-06 | 2016-10-07 | 128 |  | Strip Club root | 2.57.1.1 | 165+946 | 2
2016-10-07 | 2016-10-15 | 128 |  | Construction through clubroot affected land | 2.57.1.1 |  |  |  | 22737 |  | -19110 |  |  | With JS Oct 15
2016-09-26 | 2016-09-29 | 334 |  | Mud Hauling | 2.57.1.2 | 7/28km | 196 | 2016-10-13 | 26092016-UPI10 |  | 57405.87 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 334 |  | Mud Hauling | 2.57.1.2 | 10/31km | 310 | 2016-10-13 | 26092016-UPI10 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 334 |  | Mud Hauling | 2.57.1.2 | 40/31.5km | 1260 | 2016-10-13 | 26092016-UPI10 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 334 |  | Mud Hauling | 2.57.1.2 | 10/61km | 610 | 2016-10-13 | 26092016-UPI10 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 334 |  | Mud Hauling | 2.57.1.2 | 442/62km | 27404 | 2016-10-13 | 26092016-UPI10 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 334 |  | Mud Hauling | 2.57.1.2 | 14/62.3 | 872.2 | 2016-10-13 | 26092016-UPI10 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 334 |  | Mud Hauling | 2.57.1.2 | 6/6.3km | 378 | 2016-10-13 | 26092016-UPI10 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 333 |  | Mud Hauling | 2.57.1.2 | 895/13.7km | 12261.5 | 2016-10-13 | 26092016-UPI2 |  | 26778.75 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 333 |  | Mud Hauling | 2.57.1.2 | 40/26km | 1040 | 2016-10-13 | 26092016-UPI2 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 333 |  | Mud Hauling | 2.57.1.2 | 18/27km | 486 | 2016-10-13 | 26092016-UPI2 |  | 0 |  | 17 | Approved
2016-09-26 | 2016-09-29 | 333 |  | Mud Hauling | 2.57.1.2 | 25/27.5km | 687.5 | 2016-10-13 | 26092016-UPI2 |  | 0 |  | 17 | Approved
2016-09-09 | 2016-09-12 | 459 |  | Strip Club Root | 2.57.11 | 178+513, 179+513 | 927m |  | 09092016-UPI |  | 227115 |  | 11 | Approved
2016-10-18 | 2016-10-20 | 354 |  | T-Bar& Snow Fence | 2.26.1.1 | Road 51,40,18 | 899m
2016-10-17 | 2016-10-20 | 496 |  | Barbwire 4 strand | 2.26.1.10 | 132+330-1331+137 | 1522m
2016-10-16 | 2016-10-20 | 599 |  | Mat to new sump | 2.38.1.1 | Rd 18 | 42 mats
2016-10-18 | 2016-10-20 | 145 |  | Haul HDD Mud | 2.52.1.2 | 99877.8m
2016-10-18 | 2016-10-20 | 147 |  | Haul HDD Mud | 2.52.1.1 | 273m
2016-10-18 | 2016-10-20 | 148 |  | Haul HDD Mud | 2.52.1.2 | 6366.5m
2016-10-18 | 2016-10-20 | 149 |  | Haul HDD Mud | 2.52.1.1 | 56m |  |  |  |  | 2904.72
2016-10-18 | 2016-10-20 | 26 |  | Haul HDD Mud | 2.52.1.1 | 30mx35km |  |  |  |  | 3487.5
2016-10-18 | 2016-10-20 | 144 |  | Haul HDD Mud | 2.52.1.1 | 1896m
2016-10-18 | 2016-10-20 | 146 |  | Haul HDD Mud | 2.48.1.1 | 39m
2016-10-18 | 2016-10-20 | 27 |  | Haul HDD Mud | 2.52.1.2 | 1050m
2016-10-06 | 2016-10-07 | 131 |  | Ramp Across Wet Area | 2.65.1.1 | EE328 | 21
2016-10-06 | 2016-10-07 | 131 |  | Ramp Across Wet Area | 2.65.1.1 | EE321 | 26
2016-10-06 | 2016-10-07 | 131 |  | Ramp Across Wet Area | 2.65.1.1 | 158+970 Peat Moss | 97
2016-10-06 | 2016-10-07 | 131 |  | Ramp Across Wet Area | 2.65.1.1 | 157+666 | 24
2016-10-06 | 2016-10-07 | 131 |  | Ramp Across Wet Area | 2.65.1.1 | EE323 | 67
2016-10-06 | 2016-10-07 | 132 |  | Ramp Across Wet Area | 2.65.1.2 | EE325A | 30
2016-10-06 | 2016-10-07 | 132 |  | Ramp Across Wet Area | 2.65.1.2 | EE320 | 26
2016-10-06 | 2016-10-07 | 132 |  | Ramp Across Wet Area | 2.65.1.2 | EE319 | 22
2016-10-07 | 2016-10-15 | 207 |  | Diversion Berms | 2.8.1.1 |  |  |  | 22768 |  | 11250 |  |  | With JS Oct 15
2016-09-19 | 2016-09-29 | 485 |  | Barbwire 5 strand | No UPI | 161+580 to 162+179 | 44.7 | [6 empty] | Signed By RM
2442198.72