## Sheet1
Statement #1: | NTL | July 1-7, 2016 |  | Date from- to |  | PO# |  | PO VALUE:$ | 108945
|  | % | Progress | Previous | To Date | Current | Previous | To Date
BASE LAY | Mobilization
Grade
Stringing
Welding
Ditch
Lower-in
Backfill
Clean Up
Demobilization
Final Clean Up
[5 empty] | Base Lay Total: | 0 | 0 | 0
UPIs |  |  |  | Price | Units | Current | Previous | To Date
| 2.1 | Rock Trench
| 2.2 | Bag Weights
| 2.3a | Sand Padding
| 2.3b | Sand Bedding
| 2.3c | Sand Bed/Pad In One Operation
[5 empty] | UPI Total: | 0 | 0 | 0
Change Orders & Change Requests
CO# | CR# | LEM/Ticket # | Value: | Total: |  | Current | Previous | To Date
001 | 1 | 45673 | 1500
|  | 45674 | 1342.7
|  | 45675 | 2325
|  | 45676 | 2354
|  | 45677 | 10055
|  | Inv# 178333 | 46534 | 64110.7 |  | 64110.7 | 0 | 64110.7
002 | 4 | 44886 | 345
|  | 44789 | 688 | 1033 |  | 1033 | 0 | 1033
003 | 5 | Inv# PB-1234 | 12345.98 | 12345.98 |  | 12345.98 | 0 | 12345.98
[5 empty] | CO/CR Total: | 77489.68 | 0 | 77489.68
[5 empty] | Statement Total: | 77489.68 | 0 | 77489.68
71.13%
Office Manager |  |  | Construction Manager |  |  | Contractor |  |  | % PO To Date