## SUMMARY PAGE
PROJECT: | Namao to RFS |  |  |  |  | TOTAL PO. AMOUNT | 10864997.25
A.F.E.# | M/13295 |  |  |  |  | INVOICED | 8106289.0119
PROJECT # | [5 empty] | LEM TOTAL | 7653947.2232
E.W.R. # |  |  |  | Percent Spent |  |  | 70.45%
0
[7 empty] | INVOICED | PO AMOUNT | LEM TOTAL | PO amount remaining from LEM total
Sub Code |  | Sub Description |  | PO number |  | PO AMOUNT (As of October 30th) | TO DATE WITHOUT GST | REMAINING WITHOUT GST
100 | Surerus |  |  | 4500069512 | M/13295.NRFS.S00.S80 | 0 | 0 | 0 |  | 0
103 | RDM Contracting |  |  | 4500071151 | M/13295.NRFS.S00.S90 | 90000 | 87775 | 2225 | 87775 | 2225 | Done
104 | Don Durda Welding Ltd |  |  | 4500071148 | M/13295.NRFS.S00.S90 | 70000 | 36050 | 33950 | 36050 | 33950 | Done
105 | The Ground Hound |  |  | 4500071150 | M/13295.NRFS.S00.S90 | 120000 | 119300 | 700 | 119300 | 700 | Done
106 | QAI Quality Assurance Inc |  |  | 4500067962 | M/13295.NRFS.S00.S90 | 25000 | 15645.9524 | 9354.0476 | 15645.9524 | 9354.0476 | Invoices did not get sent to the field
107 | Golder Associates |  |  | 4500068440 | M/13295.NRFS.M00.M20 | 88800 | 0 | 88800 |  | 88800 | Invoices did not get sent to the field
108 | Joanna Fedoruk |  |  | 4500068445 | M/13295.NRFS.M00.M10 | 32500 | 9675.2381 | 22824.7619 | 9675.2381 | 22824.7619 | Invoices did not get sent to the field
109 | 1687109 Alberta - Kyle Scott |  |  | 4500068465 | M/13295.NRFS.M00.M20 | 210000 | 193842 | 16158 | 193842 | 16158 | Done
110 | Biovision Seed Labs |  |  | 4500068777 | M/13295.NRFS.M00.M10 | 12075 | 9528.5714 | 2546.4286 | 9528.5714 | 2546.4286 | Invoices did not get sent to the field
111 | Warwick Structures |  |  | 4500068833 | M/13295.NRFS.S00.S80 | 74347.94 | 0 | 74347.94 |  | 74347.94 | Invoices did not get sent to the field
112 | Teryx Consulting Ltd |  |  | 4500069175 | M/13295.NRFS.M00.M10 | 50000 | 0 | 50000 |  | 50000 | Invoices did not get sent to the field
113 | Ferner Safety Services |  |  | 4500070235CO1 | M/13295.NRFS.S00.S90 | 200000 | 195250 | 4750 | 195250 | 4750 | done
114 | 1231441 Alberta Ltd - Bear Land |  |  | 4500070543 | M/13295.NRFS.S00.S90 | 66300 | 18245.5 | 48054.5 | 18298 | 48002 | Last invoice not send in the field
115 | Paragon Soil and Environment |  |  | 4500070565 | M/13295.NRFS.M00.M10 | 140239 | 131560.7 | 8678.3 | 131560.7 | 8678.3 | Done
116 | OpusStewart Weir Ltd |  |  | 4500070659 | M/13295.NRFS.S00.S10 | 1374812 | 1224133.52 | 150678.48 | 1224133.505 | 150678.495 | Done
117 | Sacook Remote Project |  |  | 4500070666 | M/13295.NRFS.S00.S90 | 235000 | 216371.74 | 18628.26 | 216371.74 | 18628.26 | Done
118 | Tyrone Enterprises Ltd. |  |  | 4500070667 | M/13295.NRFS.S00.S90 | 180000 | 18308 | 161692 | 72383 | 107617 | Not all invoices get sent to the field
119 | Freeport energy Services |  |  | 4500070836 | M/13295.NRFS.S00.S90 | 1926050 | 1902209 | 23841 | 1902209 | 23841 | Done
120 | X-Calibur |  |  | 4500071064 | M/13295.NRFS.S00.S80 | 94050 | 85981 | 8069 | 89327 | 4723 | Last invoice not send in the field
121 | NorthStar |  |  | 4500071688 | M/13295.NRFS.S00.S80 | 950000 | 848982.64 | 101017.36 | 850360.14 | 99639.86 | Done
122 | Clean Harbors |  |  | 4500071689 | M/13295.NRFS.S00.S80 | 650000 | 615159.5 | 34840.5 | 615159.5 | 34840.5 | Done
123 | Applied Aquatics/Boreal |  |  | 4500035745 | M/13295.NRFS.M00.M10 | 688004 | 0 | 688004 | 228259.5 | 459744.5 | Invoices did not get sent to the field
124 | Davis Safety |  |  | 4500063702 |  | 160736 | 103144 | 57592 | 103144 | 57592 | Done
125 | Surerus - swamp mats |  |  | 4500072397 |  | 117000 | 117000 | 0 | 117000 | 0 | Invoices did not get sent to the field
2 | [5 empty] | 0 | 0 |  |  | 0
126 | Terra HDD solutions |  |  | 4500072601 |  | 338782.74 | 222566.21 | 116216.53 | 222566.21 | 116216.53 | Done
127 | Hawk Enterprise - Paul and Gary |  |  | 4500071568 |  | 133650 | 116045 | 17605 | 116045 | 17605 | Done
128 | Acuren |  |  | 4500071061 |  | 871045 | 832506.4 | 38538.6 | 832404.0163 | 38640.9837 | Done
129 | CORRPRO Canada inc |  |  | 4500074158 |  | 262176.35 | 183409.04 | 78767.31 | 247659.15 | 14517.2 | Last invoice not send in the field
130 | Alberta traffic supply |  |  | 4500072173 |  | 0 | 0 | 0 | 0 | 0 | Invoices did not get sent to the field
131 | Pickseeds |  |  | 4500074600 |  | 19990.9 | 0 | 19990.9 | 0 | 19990.9 | Invoices did not get sent to the field
132 | Pipeworx |  |  | 4500075056 |  | 980000 | 803600 | 176400 |  |  | Done
133 | Rosen |  |  | 4500078076 |  | 75686.3 | 0 | 75686.3 |  |  | Invoices did not get sent to the field
134 | Edgen Murray |  |  | 4500078159 |  | 40835.48 | 0 | 40835.48 |  |  | Invoices did not get sent to the field
135 | CORRPRO Canada inc (AC MITIGATION LUMP SUM PO) |  |  | 4500078250 |  | 587916.54 | 0 | 587916.54 |  |  | Invoices did not get sent to the field
136 | [5 empty] | 0 | 0 | 0
137 | [5 empty] | 0 | 0 | 0
138 | [5 empty] | 0 | 0 | 0
139 | [5 empty] | 0 | 0 | 0
140 | [5 empty] | 0 | 0 | 0
141 | [5 empty] | 0 | 0 | 0
142 | [5 empty] | 0 | 0 | 0
143 | [5 empty] | 0 | 0 | 0
144 | [5 empty] | 0 | 0 | 0
145 | [5 empty] | 0 | 0 | 0
146 | [5 empty] | 0 | 0 | 0
147 | [5 empty] | 0 | 0 | 0
148 | [5 empty] | 0 | 0 | 0
149 | [5 empty] | 0 | 0 | 0
150 | [5 empty] | 0 | 0 | 0
151 | [5 empty] | 0 | 0 | 0
152 | [5 empty] | 0 | 0 | 0
153 | [5 empty] | 0 | 0 | 0
154 | [5 empty] | 0 | 0 | 0
155 | [5 empty] | 0 | 0 | 0
156 | [5 empty] | 0 | 0 | 0
157 | [5 empty] | 0 | 0 | 0
158 | [5 empty] | 0 | 0 | 0
159 | [5 empty] | 0 | 0 | 0
160 | [5 empty] | 0 | 0 | 0
161 | [5 empty] | 0 | 0 | 0
162 | [5 empty] | 0 | 0 | 0
163 | [5 empty] | 0 | 0 | 0
164 | [5 empty] | 0 | 0 | 0
165 | [5 empty] | 0 | 0 | 0
166 | [5 empty] | 0 | 0 | 0
167 | [5 empty] | 0 | 0 | 0
168 | [5 empty] | 0 | 0 | 0
169 | [5 empty] | 0 | 0 | 0
170 | [5 empty] | 0 | 0 | 0
171 | [5 empty] | 0 | 0 | 0
172 | [5 empty] | 0 | 0 | 0
173 | [5 empty] | 0 | 0 | 0
174 | [5 empty] | 0 | 0 | 0
175 | [5 empty] | 0 | 0 | 0
176 | [5 empty] | 0 | 0 | 0
177 | [5 empty] | 0 | 0 | 0
178 | [5 empty] | 0 | 0 | 0
179 | [5 empty] | 0 | 0 | 0
180 | [5 empty] | 0 | 0 | 0
181 | [5 empty] | 0 | 0 | 0
182 | [5 empty] | 0 | 0 | 0
183 | [5 empty] | 0 | 0 | 0
184 | [5 empty] | 0 | 0 | 0
185 | [5 empty] | 0 | 0 | 0
DATE ENTERED | INVOICE # | TYPE | VENDOR # | Vendor |  |  | Sub Code | without GST / Inv Amt.
2015-04-30 | 2015-10 | Apr 16-30 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 1360
2015-05-15 | 2015-12 | May 1-15 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 2980
2015-05-31 | 2015-14 | May 16-31 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 9400
2015-06-24 | 2015-15 | June 1-15 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 14300
2015-07-01 | 2015-17 | June 16-30 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 19050
2015-07-16 | 2015-18 | July 1-15 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 19900
2015-08-03 | 2015-19 | July 16-31 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 22700
2015-08-16 | 2015-20 | August 1-15 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 13700
2015-09-08 | 2015-21 | Aug 16- 31, 2015 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 20100
2015-08-14 | 1219 | July 7-31 |  | Bear Land |  |  | 114 | 1372
2015-08-27 | 1232 | 2015-08-26 |  | Bear Land |  |  | 114 | 2794
2015-08-27 | 1204 | 2015-07-08 |  | Bear Land |  |  | 114 | 1490
2015-08-27 | 1205 | 2015-07-23 |  | Bear Land |  |  | 114 | 3360.5
2015-08-27 | 1209 | 2015-07-23 |  | Bear Land |  |  | 114 | 150
2015-08-27 | 1192 | 2015-06-17 |  | Bear Land |  |  | 114 | 6237
2015-08-27 | 1194 | 2015-06-24 |  | Bear Land |  |  | 114 | 825
2015-06-03 | N/A | PREVIOUS PO SPEND | 112431 | BIOVISION SEED LABS |  |  | 110 | 9528.5714
2015-07-31 | 1001037136 | July 1-31 |  | Clean Harbors |  |  | 122 | 191330
2015-07-27 | 145167 | June 1-15 |  | Davis safety |  |  | 124 | 1575
2015-08-11 | 145750 | 2015-07-19 |  | Davis safety |  |  | 124 | 1050
2015-08-19 | 145931 | July 28-31 |  | Davis safety |  |  | 124 | 16210
2015-08-19 | 145932 | Aug 1-14 |  | Davis safety |  |  | 124 | 5260
2015-09-10 | 146059 | Aug 16- 31, 2015 |  | Davis safety |  |  | 124 | 8404
2015-09-10 | 146060 | Aug 16- 31, 2015 |  | Davis safety |  |  | 124 | 9831
2015-08-17 | 31 | August 1-15 | 110011 | Don Durda Welding LTD. |  |  | 104 | 10475
2015-09-09 | 32 | Aug 16- 31, 2015 |  | Don Durda Welding LTD. |  |  | 104 | 19700
2015-06-11 | 48 | May 1-31 |  | FERNER SERVICES |  |  | 113 | 11250
2015-07-01 | 49 | June 1-30 |  | FERNER SERVICES |  |  | 113 | 38000
2015-08-21 | 50 | July 1-31 |  | FERNER SERVICES |  |  | 113 | 37225
2015-09-10 | 51 | Aug 1- 31, 2015 |  | FERNER SERVICES |  |  | 113 | 32450
2015-06-08 | 2015-047 | May 1-31 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 13200
2015-06-23 | 2015-048 | June 1-15 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 27371
2015-07-22 | 2015-050 | June 16-30 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 76910
2015-08-13 | 2015-052 | July 16-31 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 222638
2015-07-15 | 2015-051 | July 1-15 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 151394
2015-08-25 | 2015-053 | Aug 1-15 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 287577
2015-06-30 | HE-043-15-PPL | June 16-30 |  | Hawk Enterprise |  |  | 127 | 20415
2015-07-17 | HE-044-15-PPL | July 1-15 |  | Hawk Enterprise |  |  | 127 | 23210
2015-08-25 | HE-045-15-PPL | July 16-31 |  | Hawk Enterprise |  |  | 127 | 23260
2015-08-25 | HE-056-15-PPL | Aug 1-15 |  | Hawk Enterprise |  |  | 127 | 18950
2015-09-09 | HE-059-15-PPL | Aug 16- 31, 2015 |  | Hawk Enterprise |  |  | 127 | 21110
2015-06-03 | N/A | PREVIOUS PO SPEND | 112406 | JOANNA FEDORUK |  |  | 108 | 9675.2381
2015-08-06 | 12416 | July 27 - Aug 1 |  | NorthStar |  |  | 121 | 80657.5
2015-08-25 | 12574 | Aug 13-14 |  | NorthStar |  |  | 121 | 30742.5
2015-08-25 | 12545 | Aug 10-12 |  | NorthStar |  |  | 121 | 37785
2015-08-25 | 12503 | Aug 7-8 |  | NorthStar |  |  | 121 | 25822.5
2015-08-25 | 12502 | Aug 3-6 |  | NorthStar |  |  | 121 | 48297.5
2015-08-25 | 12343 | 2015-07-21 |  | NorthStar |  |  | 121 | 1860
2015-08-25 | 12339 | 2015-07-19 |  | NorthStar |  |  | 121 | 3085
2015-08-25 | 12266 | July 10-11 |  | NorthStar |  |  | 121 | 9955
2015-08-25 | 12299 | July 14-20 |  | NorthStar |  |  | 121 | 18770
2015-08-25 | 12194 | July 3-9 |  | NorthStar |  |  | 121 | 42420
2015-08-25 | 12147 | June 29-July 2 |  | NorthStar |  |  | 121 | 13330
2015-08-25 | 12360 | July 21-23 |  | NorthStar |  |  | 121 | 28412.5
2015-08-27 | 12639 | 2015-08-27 |  | NorthStar |  |  | 121 | 111182.5
2015-09-08 | 12739 | Aug 28 - 31 |  | NorthStar |  |  | 121 | 47665
2015-09-08 | 12699 | Aug 25 - 28 |  | NorthStar |  |  | 121 | 54645
2015-09-09 | 12773 | Aug 30- Sept 2 |  | NorthStar |  |  | 121 | 34810
2015-08-25 | 33041 | 2015-06-01 |  | OPUS |  |  | 116 | 202826.7
2015-07-14 | 5420 | June 1-30 |  | Paragon soil and Environment |  |  | 115 | 22468.5
2015-08-14 | 5459 | July 1-31 |  | Paragon Soil and Environment |  |  | 115 | 36213.3
2015-06-03 | N/A | PREVIOUS PO SPEND | 109296 | QAI QUALITY ASSURANCE |  |  | 106 | 15645.9524
2015-07-01 | RDM0032 | June 16-30 | 109998 | RDM Contracting LTD. |  |  | 103 | 13600
2015-07-16 | RMD0033 | July1-15 |  | RDM Contracting LTD. |  |  | 103 | 18225
2015-08-03 | RDM0034 | July 16-31 |  | RDM Contracting LTD. |  |  | 103 | 18400
2015-08-24 | RDM0035 | Aug 1-15 |  | RDM Contracting LTD. |  |  | 103 | 19525
2015-09-09 | RDM0037 | Aug 16- 31, 2015 |  | RDM Contracting LTD. |  |  | 103 | 12150
2015-06-01 | 31052015RFS | May 1-31 |  | SACOOK RPA |  |  | 117 | 2575
2015-06-15 | 15062015RFS | June 1-15 |  | SACOOK RPA |  |  | 117 | 13049.9
2015-06-30 | 30062015RFS | June 16-30 |  | SACOOK RPA |  |  | 117 | 13025
2015-07-18 | 15072015RFS | July 1-15 |  | SACOOK RPA |  |  | 117 | 17275
2015-08-03 | 31072015RFS | July 16-31 |  | SACOOK RPA |  |  | 117 | 14800
2015-08-18 | 15082015RFS | August 1-15 |  | SACOOK RPA |  |  | 117 | 25298.84
2015-09-02 | 31082015RFS | Aug 16- 31, 2015 |  | SACOOK RPA |  |  | 117 | 27200
| Not sure requested copy |  |  | Sureus for Mats |  |  | 125 | 117000
2015-08-25 | 1156 | Aug 1-15 |  | Terra HDD |  |  | 126 | 20412.5
2015-08-25 | 1164 | Aug 5-7 3rd Party |  | Terra HDD |  |  | 126 | 14383.44
2015-08-25 | 1151 | July 16-31 |  | Terra HDD |  |  | 126 | 19793.75
2015-08-25 | 1143 | July 24-Aug 4 3rd Party |  | Terra HDD |  |  | 126 | 5636.06
2015-08-25 | 1131 | June 30 - July 15 |  | Terra HDD |  |  | 126 | 12850
2015-08-25 | 1130 | July 3 - July 17 3rd Party |  | Terra HDD |  |  | 126 | 5620.46
2015-09-09 | 1171 | Aug 16- 31, 2015 |  | Terra HDD |  |  | 126 | 32877.75
2015-07-01 | 13 | May 15-30, 2015 | 1114382 | THE GROUND HOUND |  |  | 105 | 7525
2015-07-01 | 14 | June 1-30, 2015 | 1114382 | THE GROUND HOUND |  |  | 105 | 19175
2015-08-03 | 15 | July 1-31, 2015 |  | THE GROUND HOUND |  |  | 105 | 34025
2015-09-09 | 16 | Aug 1- 31, 2015 |  | THE GROUND HOUND |  |  | 105 | 39225
2015-06-10 | 55J | Apr 15-30 | 107289 | TYRONE ENTERPRISE |  |  | 118 | 2200
2015-06-10 | 56J | May 1-15 | 107289 | TYRONE ENTERPRISE |  |  | 118 | 4089
2015-06-15 | 58J | June 1-15 |  | TYRONE ENTERPRISE |  |  | 118 | 12019
2015-07-27 | 28029 | July 1-15 |  | X-Calibur |  |  | 120 | 16380
2015-07-27 | 27913 | June 15-30 |  | X-Calibur |  |  | 120 | 57660
2015-09-16 | 5502 | Aug 1- 31, 2015 |  | Paragon Soil and Environment |  |  | 115 | 8199.9
2015-09-12 | HE-071 -15-PPL | Sept 1-11, 2015 |  | Hawk Enterprise |  |  | 127 | 9100
2015-09-16 | 2015-22 | Sept 1-15, 2015 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 13850
2015-09-17 | 2015-054 | Aug 16- 31, 2015 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 276996
2015-09-17 | 12816 | 2015-09-16 |  | NorthStar |  |  | 121 | 56107.5
2015-09-17 | 15092015RFS | Sept 1-15, 2015 |  | SACOOK RPA |  |  | 117 | 24100
2015-09-17 | 33 | Sept 1-15, 2015 | 110011 | Don Durda Welding LTD. |  |  | 104 | 5875
2015-09-18 | 1193 | Sept 1-15, 2015 |  | Terra HDD |  |  | 126 | 65908.5
2015-09-18 | 12826 | 2015-09-17 |  | NorthStar |  |  | 121 | 13230
2015-09-04 | 227912 | July 12 - 18 |  | Acuren |  |  | 128 | 20706.67
2015-09-04 | 227911 | July 3-11 |  | Acuren |  |  | 128 | 18320
2015-09-04 | 227914 | July 26-31 |  | Acuren |  |  | 128 | 58864.99
2015-09-04 | 227913 | July 19-26 |  | Acuren |  |  | 128 | 25117
2015-09-04 | 227915 | aug 1-8 |  | Acuren |  |  | 128 | 122538.11
2015-09-04 | 227916 | aug 9-16 |  | Acuren |  |  | 128 | 101402.11
2015-09-04 | 227917 | aug 16-22 |  | Acuren |  |  | 128 | 86628.01
2015-09-24 | 12868 | Sept |  | Northstar |  |  | 121 | 36910
2015-09-24 | 33272 | Jul 1 - 31 |  | OPUS |  |  | 116 | 232485.45
2015-09-15 | 146226 | Sept 1 - 15 |  | Davis Safety |  |  | 124 | 10554
2015-09-25 | 2015-055 | Sep 1 - 15 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 189128
2015-09-30 | 017 | Sep 1 - 30 |  | THE GROUND HOUND |  |  | 105 | 16400
2015-10-01 | 12950 | Sep |  | Northstar |  |  | 121 | 75200
2015-10-01 | 2015-23 | Sep 16-30 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 18200
2015-10-02 | 30092015RFS | Sep 16-30 |  | SACOOK RPA |  |  | 117 | 26050
2015-09-25 | 229624 | Aug 23-31 |  | Acuren |  |  | 128 | 79215.97
2015-09-25 | 229626 | Sep 1-6 |  | Acuren |  |  | 128 | 36582.82
2015-09-26 | 229630 | Sep 7-13 |  | Acuren |  |  | 128 | 62571.64
2015-09-27 | 229632 | Sep 15-20 |  | Acuren |  |  | 128 | 42190.69
2015-09-29 | 1271 | 2015-09-17 |  | Bear Land |  |  | 114 | 105
2015-10-05 | 1001161064 | Aug 1 - 31 |  | Clean Harbors |  |  | 122 | 218370
2015-10-06 | 1212 | Sep 16 - 25 |  | Terra HDD |  |  | 126 | 45083.75
2015-10-13 | RDM0038 | Sep 1-4 |  | RDM Contracting LTD. |  |  | 103 | 5875
2015-10-13 | 5582 | Sep 1-30 |  | Paragon soil and Environment |  |  | 115 | 27775
2015-09-20 | 52 | Sep 1-30 |  | FERNER SERVICES |  |  | 113 | 32450
2015-09-20 | 2015-059 | Sep 16-30 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 200508
2015-10-20 | 15102015RFS | Oct 1-15 |  | SACOOK RPA |  |  | 117 | 22050
2015-10-20 | 1001154781 | Sep 1-30 |  | Clean Harbors |  |  | 122 | 167169.5
2015-10-20 | 28385 | Aug 25 - 28 |  | X-Calibur |  |  | 120 | 3457
2015-10-23 | 2015-062 | Oct 1-15 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 131669
2015-10-23 | 28764 | 2015-10-02 |  | X-Calibur |  |  | 120 | 1498
2015-10-26 | 146463 | Sep 16-30 |  | Davis Safety |  |  | 124 | 13580
2015-10-26 | 146464 | Oct 1-15 |  | Davis Safety |  |  | 124 | 14010
2015-11-02 | 2015-26 | Oct 16-31 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 19695
2015-11-02 | PW2015-232 | 2015-10-31 |  | Pipeworx |  |  | 132 | 803600
2015-11-03 | 349399 | 2015-10-30 |  | Corrpro |  |  | 129 | 183409.04
2015-11-04 | 1301 | 2015-11-04 |  | Bear Land |  |  | 114 | 675
2015-11-04 | 53 | oct 1-31 |  | FERNER SERVICES |  |  | 113 | 10325
2015-11-04 | 33794 | SEPTEMBER |  | OPUS |  |  | 116 | 207511.78
2015-11-06 | 1235 | 2015-08-31 |  | Bear Land |  |  | 114 | 1237
2015-11-07 | 19 | october |  | THE GROUND HOUND |  |  | 105 | 2950
2015-11-07 | 28249 | 2015-08-18 |  | X-Calibur |  |  | 120 | 2450
2015-11-07 | 28274 | 2015-08-24 |  | X-Calibur |  |  | 120 | 1904
2015-11-07 | 28185 | 2015-08-12 |  | X-Calibur |  |  | 120 | 1680
2015-11-07 | 28169 | 2015-08-12 |  | X-Calibur |  |  | 120 | 952
2015-11-09 | 12830 | 2015-09-21 |  | NorthStar |  |  | 121 | 27225
2015-11-09 | 13024 | 2015-10-07 |  | NorthStar |  |  | 121 | 4675
2015-11-09 | 12376 | 2015-07-30 |  | NorthStar |  |  | 121 | 28020
2015-11-09 | 2015-065 | October 16-31 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 42550
2015-11-10 | 146603 | Oct 16-31 |  | Davis Safety |  |  | 124 | 21040
2015-11-18 | 5687 | October |  | Paragon soil and Environment |  |  | 115 | 36904
2015-11-15 | 146729 | nov 1-15 |  | Davis Safety |  |  | 124 | 1630
2015-11-23 | 2015-24 | oct 1-15 | 11117 | 1687109 ALBERTA LTD |  |  | 109 | 18607
2015-11-26 | 2015-071 | Nov 1-15 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 120196
2015-11-26 | 235529 rev 2 | Oct 13 - 31 |  | Acuren |  |  | 128 | 91426.45
2015-11-30 | 1001173212 | 2015-11-02 |  | Clean Harbors |  |  | 122 | 5200
2015-12-03 | 236395 | Nov 2-11 |  | Acuren |  |  | 128 | 18514.47
2015-12-03 | 236335 | sep 21-27 |  | Acuren |  |  | 128 | 29450.3
2015-12-03 | 30112015RFS | Nov 16-nov 30 |  | SACOOK RPA |  |  | 117 | 13025
2015-12-10 | 34210 | October |  | OPUS |  |  | 116 | 128606.05
2015-12-14 | 2015-075 | Nov 16-nov 30 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 82438
2015-12-03 | 232214 | oct 5 - oct 12 |  | Acuren |  |  | 128 | 9797.64
2015-12-03 | 2322195 | Sep 28- oct 4 |  | Acuren |  |  | 128 | 26834.58
2016-01-05 | 2015-081 | dec 1-15 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 56325
2016-01-05 | 57 | December |  | FERNER SERVICES |  |  | 113 | 8475
2016-01-05 | 55 | november |  | FERNER SERVICES |  |  | 113 | 25075
2016-01-05 | 13739 | 2016-12-21 |  | Northstar |  |  | 121 | 4794
2016-01-05 | 13377 | 2016-11-10 |  | Northstar |  |  | 121 | 7545
2016-01-05 | 13395 | 2016-11-10 |  | Northstar |  |  | 121 | 3516.14
2016-01-05 | 13527 | 2016-11-25 |  | Northstar |  |  | 121 | 2320
2016-01-05 | 15122015RFS | dec 1-15 |  | SACOOK RPA |  |  | 117 | 11523
2016-01-05 | 31122015RFS | dec 16-31 |  | SACOOK RPA |  |  | 117 | 800
2016-01-05 | 237756 | 2016-12-08 |  | Acuren |  |  | 128 | 2344.95
2016-01-12 | 34605 | november |  | OPUS |  |  | 116 | 67920.35
2016-01-18 | 2015-084 | dec 16-31 |  | FREEPORT ENERGY SERVICES |  |  | 119 | 23309
2016-01-25 | 1001231770 | october |  | Clean Harbors |  |  | 122 | 33090
2016-02-15 | 34968 | December |  | OPUS |  |  | 116 | 29717.88
2016-03-09 | 33529 | august |  | OPUS |  |  | 116 | 311342.96
2016-03-09 | 31012016RFS | Jan 16-31 |  | SACOOK RPA |  |  | 117 | 1600
| 15012016RFS | jan 1-31 |  | SACOOK RPA |  |  | 117 | 4000
2016-04-13 | 35396 | January |  | OPUS |  |  | 116 | 31062.35
2016-04-13 | 35403 | February |  | OPUS |  |  | 116 | 12660
Note on B9: sacook000: Robert Meidinger at rdm@telus.net 780.835.8072
Note on B10: sacook000: Don Durda at durdawelding@telusmail.net 780.831.6662
Note on B11: sacook000: Gary McIntyre at gary@thegroundhound.ca 780.835.0408
Note on B15: sacook000: Kyle Scott at kylescott1234@hotmail.com 403.391.3188
Note on B19: sacook000: Scott Ferner at fernersafetyservices@gmail.com 780.608.7158
Note on B20: sacook000: Trish Norman accounting@bearlandservices.ca 780.239.5360
Note on B21: sacook000: No name contact email at accounting@paragonsoil.com 780.434.0400
Note on B22: sacook000: Matt Nelson at matthew.nelson@opussw.com 587.987.6283 for Daily Tickets - invoices Andrea Maguire andrea.maguire@opussw.com
Note on B23: sacook000: Shelley Cook at shelley.cook@sacookrpa.com 780.402.4641
Note on B24: sacook000: Jack Slack at jslack@pembina.com 403.809.4656
Note on H24: sacook000: Sent email requesting invoices Aug 24
Note on B25: sacook000: Rebecca Becker at rebecca@loracmanagement.ca 403.652.1100
Note on G25: sacookadmin: Original PO $1146050.00 PO Increased to $1646050.00 Received Sept 12, 2015
Note on B26: sacook000: Robb Sernecky at rsernecky@x-calibur.ca 403.846.1859
Note on G26: sacookadmin: Original PO $81550.00 Increased to $86050.00 Received Sept 12, 2015
Note on B27: sacook000: Debbie Jorgensen at debbie@northstarhydrovac.com 780.532.5703
Note on G27: sacookadmin: PO originally $500000.00 Revised another 150000.00 was added to original amount.
Note on B28: sacook000: Faye Nichole faye.nichole@cleanharbors.com 403.314.3630
Note on G28: sacookadmin: PO Increased to 650000.00 Received Sept 12, 2015
Note on B29: sacook000: Kristen MacPhail at reception@appliedaquatic.com 403.294.0488 for signed tickets invoices come from Borel (contact to follow)
Note on H29: sacook000: Field has not seen invoices for this company. Sent email Aug 25 requesting invoices
Note on B30: sacook000: Inez Purchase at ipurchase@davissafety.ca
Note on H31: sacook000: Requested copy of invoice Aug 20 to Alison
Note on B33: sacook000: Sarah Currie scurrie@terrahdd.com 403.651.5143
Note on B34: sacook000: Grant Huys at grant@hawkhuys.com 780.504.8626
Note on B35: sacook000: Marian Gidzinski at mgidzinski@acuren.com 780.974.4539
Note on H35: sacook000: Sent invoice request to Greg - Aug 24 Field has not received any
Note on B36: sacook000: Levi Blumhagen levi.blumhagen@corrpro.ca
Note on B38: sacook000: Bill Letondre at blentondre@pickseed.com 306.480.9786
Note on B42: sacook000: Levi Blumhagen levi.blumhagen@corrpro.ca
Note on E208: sacook000: Kyle Scott at kylescott1234@hotmail.com 403.391.3188
Note on E228: sacook000: Kyle Scott at kylescott1234@hotmail.com 403.391.3188
Note on E247: sacook000: Kyle Scott at kylescott1234@hotmail.com 403.391.3188

## 1687109 AB - Kyle Scott
1687109 AB
Kyle Scott
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Kyle Scott | Rate | Vehicle | Rate $200 | Quad | Rate $150 | KM Over 180 | Rate $1.00 | Sub | Rate $200 | Labourer class | Rate | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-04-30 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | Invoice from April 16-30 |  | 1360 | 68 | 1428 | 2015-10 |  | 193842
2015-05-15 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | Invoice from May 1-15 |  | 2980 | 149 | 3129 | 2015-12
2015-05-31 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | Invoice from May 16-31 |  | 9400 | 470 | 9870 | 2015-14
2015-06-01 | 12 | 0 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1450 | 12 |  | 0 | 1500 | 75 | 1575 | 2015-15
2015-06-02 | 12 | 0 | 0.5 | 1100 | 0.5 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 6 |  | 0 | 850 | 42.5 | 892.5 | 2015-15
2015-06-03 | 12 | 0 |  | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-15
2015-06-04 | 12 | 0 |  | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-15
2015-06-05 | 12 | 0 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 12 |  | 0 | 1500 | 75 | 1575 | 2015-15
2015-06-08 | 12 | 0 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 12 |  | 0 | 1500 | 75 | 1575 | 2015-15
2015-06-09 | 12 | 0 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 12 |  | 0 | 1500 | 75 | 1575 | 2015-15 | 14300
2015-06-10 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-15
2015-06-11 |  |  | 0.5 | 1100 | 0.5 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 850 | 42.5 | 892.5 | 2015-15
2015-06-12 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-15
2015-06-13 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-15
2015-06-14 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-15
2015-06-15 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-15
2015-06-16 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-17
2015-06-17 |  |  | 1 | 1100 | 1 | 200 | 1 | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1650 | 82.5 | 1732.5 | 2015-17
2015-06-18 |  |  | 1 | 1100 | 1 | 200 | 1 | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1650 | 82.5 | 1732.5 | 2015-17 | 19050
2015-06-19 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-17
2015-06-20 |  |  | 0.5 | 1100 | 0.5 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 850 | 42.5 | 892.5 | 2015-17
2015-06-21 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-17
2015-06-22 |  |  | 1 | 1100 | 1 | 200 | 1 | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1650 | 82.5 | 1732.5 | 2015-17
2015-06-23 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-17
2015-06-24 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-17
2015-06-25 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-17
2015-06-26 |  |  | 0.5 | 1100 | .5 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 850 | 42.5 | 892.5 | 2015-17
2015-06-27 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-17
2015-06-28 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-17
2015-06-29 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-17
2015-06-30 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-17
2015-07-01 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-02 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-03 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-04 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-05 |  |  |  | 1100 |  | 200 |  |  |  |  | 1 | 200 |  | 0 |  | 0 | 1300 | 0 |  | 0 | 200 | 10 | 210 | 2015-18
2015-07-06 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-07 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-08 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-09 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-10 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-11 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-12 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-18
2015-07-13 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-14 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18
2015-07-15 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-18 | 19900
2015-07-16 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-17 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-18 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-19 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-20 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-21 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-22 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-23 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-24 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-25 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-26 |  | 425 |  | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-19
2015-07-27 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-28 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-29 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-30 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19
2015-07-31 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-19 | 22700
2015-08-01 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-20
2015-08-02 |  | 425 |  | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-20
2015-08-03 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-20
2015-08-04 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-20
2015-08-05 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-20
2015-08-06 |  | 425 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 425 |  | 0 | 1500 | 75 | 1575 | 2015-20
2015-08-12 |  | 426 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 426 |  | 0 | 1500 | 75 | 1575 | 2015-20
2015-08-13 |  | 426 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 426 |  | 0 | 1500 | 75 | 1575 | 2015-20
2015-08-14 |  | 426 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 426 |  | 0 | 1500 | 75 | 1575 | 2015-20
2015-08-15 |  | 426 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 426 |  | 0 | 1500 | 75 | 1575 | 2015-20 | 13700 | Invoice#2015-20 | 13700
2015-08-16 |  | 426 | 0 | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-21
2015-08-17 |  | 427 | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 427 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-18 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-19 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-20 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-21 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-22 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  |  |  |  | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-23 |  |  | 0 | 1100 | 0 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-21
2015-08-24 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-25 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-26 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-27 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-28 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-29 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21
2015-08-30 |  |  | 0 | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-21
2015-08-31 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-21 |  | Invoice#2015-21 | 20100
2015-09-01 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-22
2015-09-02 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-22
2015-09-03 |  |  | 1 | 1100 | 1 | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-22
2015-09-04 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 |  | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 0 | 0 | 0 | 2015-22
2015-09-05 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 |  | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 0 | 0 | 0 | 2015-22
2015-09-06 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 |  | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 0 | 0 | 0 | 2015-22
2015-09-07 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 |  | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 0 | 0 | 0 | 2015-22
2015-09-08 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 |  | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 0 | 0 | 0 | 2015-22
2015-09-09 |  |  |  | 1100 |  | 200 |  | 150 |  | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-22
2015-09-10 |  |  | 1 | 1100 | 1 | 200 | 1 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1650 | 82.5 | 1732.5 | 2015-22
2015-09-11 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-22
2015-09-12 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-22
2015-09-13 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-22
2015-09-14 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-22
2015-09-15 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-22 |  | Invoice#2015-22 | 13850
2015-09-16 |  |  | 0 | 1100 | 0 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-23
2015-09-17 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-18 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-19 |  |  | 0 | 1100 | 0 | 200 | 0 | 150 | 0 | 1 | 0 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 0 | 0 | 0 | 2015-23
2015-09-20 |  |  | 0 | 1100 | 0 | 200 | 0 | 150 | 0 | 1 | 0 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 0 | 0 | 0 | 2015-23
2015-09-21 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-22 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-23 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-24 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-25 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-26 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-27 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-28 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-29 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-09-30 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-23
2015-10-01 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-02 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-03 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-04 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-05 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-06 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-07 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-08 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-09 |  |  | 0 | 1100 | 0 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-24
2015-10-10 |  |  | 0 | 1100 | 0 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-24
2015-10-11 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-12 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-13 |  |  | 0 | 1100 | 0 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 200 | 10 | 210 | 2015-24 | Judy creek
2015-10-14 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 7 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 7 | 1507 | 75.35 | 1582.35 | 2015-24
2015-10-15 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-24
2015-10-16 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-26
2015-10-17 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-26
2015-10-18 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-26
2015-10-19 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-26
2015-10-20 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-26
2015-10-21 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-26
2015-10-22 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 10 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1510 | 75.5 | 1585.5 | 2015-26
2015-10-23 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-26
2015-10-24 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-26
2015-10-25 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 0 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1500 | 75 | 1575 | 2015-26
2015-10-26 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 15 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1515 | 75.75 | 1590.75 | 2015-26
2015-10-27 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 3 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1503 | 75.15 | 1578.15 | 2015-26
2015-10-28 |  |  | 1 | 1100 | 1 | 200 | 0 | 150 | 167 | 1 | 1 | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 1667 | 83.35 | 1750.35 | 2015-26
2015-10-29 |  |  |  | 1100 |  | 200 | 0 | 150 |  | 1 |  | 200 |  | 0 |  | 0 | 1451 | 0 |  | 0 | 0 | 0 | 0
2015-10-30
2015-10-31

## Bear Land
Bear Land
Date | LEM # | Straight Hours Charged (ea.) | Manpower | Admin | Rate | Lead | Rate | KM | Rate | Build Spreadsheet | Rate | Titles | Rate | Pad Prep $105 | Rate | Land title spin $32 | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | SUM OF ALL LEM'S (before GST)
2015-05-21 | 5581 | 8 | Craig Burns |  | 75 | 8 | 105 | 70 | 1 |  | 0 |  | 0 |  | 0 |  | 600 |  | 70 | 910 | 45.5 | 955.5 | 1192 | 18298
2015-05-22 | 5582 | 2 | Craig Burns |  | 75 | 2 | 105 | 20 | 1 |  | 0 |  | 0 |  | 0 | 76 | 150 |  | 20 | 230 | 11.5 | 241.5 | 1192
2015-05-25 | 5421 | 2 | Sarah Post | 2 | 75 |  | 105 | 0 | 1 | 0.5 | 75 |  | 0 |  | 0 | 151 | 187.5 |  | 0 | 187.5 | 9.375 | 196.875 | 1192
2015-05-25 | 5584 | 2 | Craig Burns |  | 75 | 2 | 105 | 0 | 1 |  | 0 |  | 0 |  | 0 | 76 | 150 |  | 0 | 210 | 10.5 | 220.5 | 1192
2015-05-26 | 5370 | 6 | ? | 6 | 75 |  | 105 | 0 | 1 |  | 75 |  | 0 |  | 0 | 151 | 450 |  | 0 | 450 | 22.5 | 472.5 | 1192
2015-05-26 | 5372 | 1.5 | ? | 1.5 | 75 |  | 105 | 0 | 1 |  | 75 |  | 0 |  | 0 | 151 | 112.5 |  | 0 | 112.5 | 5.625 | 118.125 | 1192
2015-05-26 | 5426 | 3 | Sarah Post | 3 | 75 |  | 105 |  | 1 | 1.5 | 75 |  | 0 |  | 0 | 151 | 337.5 |  | 0 | 337.5 | 16.875 | 354.375 | 1192
2015-05-27 | 5427 | 6 | Sarah Post | 6 | 75 |  | 105 |  | 1 |  | 75 |  | 0 |  | 0 | 151 | 450 |  | 0 | 450 | 22.5 | 472.5 | 1192
2015-05-27 | 5590 | 6 | Craig Burns |  | 75 | 6 | 105 | 22 | 1 |  | 75 |  | 0 |  | 0 | 151 | 450 |  | 22 | 652 | 32.6 | 684.6 | 1192
2015-05-28 | 5375 | 4 | ? | 4 | 75 |  | 105 |  | 1 |  | 75 |  | 140 |  | 0 | 291 | 300 |  | 0 | 300 | 15 | 315 | 1192
2015-05-29 | 5376 | 1 | ? | 1 | 75 |  | 105 |  | 1 |  | 75 |  | 140 |  | 0 | 291 | 75 |  | 0 | 75 | 3.75 | 78.75 | 1192
2015-06-01 | 5378 | 0.5 | ? | 0.5 | 75 |  | 105 |  | 1 |  | 75 |  | 140 |  | 0 | 291 | 37.5 |  | 0 | 37.5 | 1.875 | 39.375 | 1192
2015-06-02 | 5380 | 2 | ? | 2 | 75 |  | 105 |  | 1 |  | 75 |  | 140 |  | 0 | 291 | 150 |  | 0 | 150 | 7.5 | 157.5 | 1192
2015-06-05 | 5383 | 3 | ? | 3 | 75 |  | 105 |  | 1 |  | 75 |  | 140 |  | 0 | 291 | 225 |  | 0 | 225 | 11.25 | 236.25 | 1192
2015-06-08 | 5386 | 2 | ? | 2 | 75 |  | 105 |  | 1 |  | 75 |  | 140 |  | 0 | 291 | 150 |  | 0 | 150 | 7.5 | 157.5 | 1192
2015-06-08 | 5604 | 5 | Craig Burns |  | 75 | 5 | 105 | 123 | 1 |  | 75 |  | 140 |  | 0 | 291 | 375 |  | 123 | 648 | 32.4 | 680.4 | 1192
2015-06-09 | 5606 | 9 | Craig Burns |  | 75 | 9 | 105 | 167 | 1 |  | 75 |  | 140 |  | 0 | 291 | 675 |  | 167 | 1112 | 55.6 | 1167.6 | 1192
2015-06-10 | 5608 | 4 | Craig Burns |  | 75 | 4 | 105 | 93 | 1 |  | 75 |  | 140 | [6 empty] | 513 | 25.65 | 538.65 | 1205
2015-06-11 | 5390 | 4 | Trish Norman | 4 | 75 |  | 105 |  | 1 |  | 75 |  | 140 |  | 0 | 291 | 300 |  | 0 | 300 | 15 | 315 | 1194
2015-06-12 | 5387 | 4 | Trish Norman | 1 | 75 |  | 105 |  | 1 | 3 | 75 |  | 140 |  | 0 | 291 | 525 |  | 0 | 300 | 15 | 315 | 1194
2015-06-12 | 5444 | 1 | Sarah Post | 1 | 75 |  | 105 |  | 1 |  | 75 |  | 140 |  | 0 | 291 | 75 |  | 0 | 75 | 3.75 | 78.75 | 1194
2015-06-12 | 5613 | 1.5 | Craig Burns |  | 75 | 1.5 | 105 | 11 | 1 |  | 75 |  | 140 | [6 empty] | 168.5 | 8.425 | 176.925 | 1205
2015-06-15 | 5445 | 2 | Sarah Post | 1 | 75 |  | 105 |  | 1 | 1 | 75 |  | 140 |  | 0 | 291 | 225 |  | 0 | 150 | 7.5 | 157.5 | 1194
2015-06-19 | 5393 | 2 | Trish Norman | 2 | 75 |  | 105 |  | 1 |  | 75 | 1 | 140 | [6 empty] | 290 | 14.5 | 304.5 | 1204
2015-06-22 | 5397 |  |  | 3 | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 225 | 11.25 | 236.25 | 1204
2015-06-22 | 5615 | 2 | Craig Burns |  | 75 | 2 | 105 | 28 | 1 |  | 75 |  | 140 | [6 empty] | 238 | 11.9 | 249.9 | 1205
2015-06-23 | 5399 | 2 | Trish Norman | 1 | 75 |  | 105 |  | 1 | 1 | 75 |  | 140 |  | 0 | 291 | 225 |  | 0 | 150 | 7.5 | 157.5 | 1209
2015-06-23 | 5617 | 2 | Craig Burns |  | 75 | 2 | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 210 | 10.5 | 220.5 | 1205
2015-06-24 | 5620 | 2 | Craig Burns |  | 75 | 2 | 105 | 11 | 1 |  | 75 |  | 140 | [6 empty] | 221 | 11.05 | 232.05 | 1205
2015-06-25 | 5622 | 2 | Craig Burns |  | 75 | 2 | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 210 | 10.5 | 220.5 | 1205
2015-06-25 | 5701 | 6 | Trish Norman | 6 | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 450 | 22.5 | 472.5 | 1204
2015-06-26 | 5626 | 2 | Craig Burns |  | 75 | 2 | 105 | 22 | 1 |  | 75 |  | 140 | [6 empty] | 232 | 11.6 | 243.6 | 1205
2015-06-26 | 5702 | 3 | Trish Norman | 3 | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 225 | 11.25 | 236.25 | 1204
2015-06-29 | 5627 | 8 | Craig Burns |  | 75 | 8 | 105 | 56 | 1 |  | 75 |  | 140 | [6 empty] | 896 | 44.8 | 940.8 | 1205
2015-06-29 | 5704 | 4 | Trish Norman | 4 | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 300 | 15 | 315 | 1204
2015-06-30 | 5629 | 2 | Craig Burns |  | 75 | 2 | 105 | 10 | 1 |  | 75 |  | 140 | [6 empty] | 220 | 11 | 231 | 1205
2015-07-06 | 5631 | 4 | Craig Burns |  | 75 | 4 | 105 | 32 | 1 |  | 75 |  | 140 | [6 empty] | 452 | 22.6 | 474.6 | 1205
2015-07-07 | 5633 | 2 | Craig Burns |  | 75 | 2 | 105 | 14 | 1 |  | 75 |  | 140 | [6 empty] | 224 | 11.2 | 235.2 | 1219
2015-07-08 | 5634 | 2 | Craig Burns |  | 75 | 2 | 105 | 0 | 1 |  | 75 |  | 140 | [6 empty] | 210 | 10.5 | 220.5 | 1219
2015-07-09 | 5635 | 3 | Craig Burns |  | 75 | 3 | 105 | 23 | 1 |  | 75 |  | 140 | [6 empty] | 338 | 16.9 | 354.9 | 1219
2015-07-09 | 7055 | 3 |  |  | 75 | 3 | 105 | 26 | 1 |  | 75 |  | 140 | [6 empty] | 341 | 17.05 | 358.05 | 1232
2015-07-13 | 7058 | 3 |  |  | 75 | 3 | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 315 | 15.75 | 330.75 | 1232
2015-07-15 | 7063 | 2 |  |  | 75 | 2 | 105 | 20 | 1 |  | 75 |  | 140 | [6 empty] | 230 | 11.5 | 241.5 | 1232
2015-07-16 | 7066 | 1 |  |  | 75 | 1 | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 105 | 5.25 | 110.25 | 1232
2015-07-20 | 7075 | 2 |  |  | 75 | 2.5 | 105 | 10 | 1 |  | 75 |  | 140 | [6 empty] | 272.5 | 13.625 | 286.125 | 1232
2015-07-21 | 7078 |  |  |  | 75 | 3 | 105 | 63 | 1 |  | 75 |  | 140 | 1 |  |  |  | 1 | 63 | 483 | 24.15 | 507.15 | 1232
2015-08-12 | 7110 |  |  | 1 | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 75 | 3.75 | 78.75 | 1232
2015-07-22 | 7081 | 2 |  |  | 75 | 1.5 | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 157.5 | 7.875 | 165.375 | 1232
2015-07-23 | 7083 | 1 |  |  | 75 | 1 | 105 | 10 | 1 |  | 75 |  | 140 | [6 empty] | 115 | 5.75 | 120.75 | 1232
2015-07-27 | 7089 |  |  |  | 75 | 2 | 105 | 34 | 1 |  | 75 |  | 140 | [6 empty] | 244 | 12.2 | 256.2 | 1232
2015-07-29 | 7098 |  |  |  | 75 |  | 105 | 34 | 1 |  | 75 |  | 140 | 3 |  |  |  |  | 34 | 349 | 17.45 | 366.45 | 1232
2015-07-30 | 7003 | 4 | Trish Norman |  | 75 |  | 105 |  | 1 | 4 | 75 |  | 140 | [6 empty] | 300 | 15 | 315 | 1219
2015-07-30 | 7135 |  |  |  | 75 | 2 | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 210 | 10.5 | 220.5 | 1235
2015-07-31 | 7005 | 4 | Trish Norman |  | 75 |  | 105 |  | 1 | 4 | 75 |  | 140 | [6 empty] | 300 | 15 | 315 | 1219
2015-07-31 | 7136 |  |  |  | 75 | 3 | 105 | 22 | 1 |  | 75 |  | 140 | [6 empty] | 337 | 16.85 | 353.85 | 1235
2015-08-04 | 7139 |  |  |  | 75 | 2 | 105 | 17 | 1 |  | 75 |  | 140 | [6 empty] | 227 | 11.35 | 238.35 | 1235
2015-08-05 | 7144 |  |  |  | 75 | 4 | 105 | 43 | 1 |  | 75 |  | 140 | [6 empty] | 463 | 23.15 | 486.15 | 1235
2015-08-10 | 5481 |  |  |  | 75 |  | 105 |  | 1 |  | 75 |  | 140 |  |  | 1 |  |  |  | 32 | 1.6 | 33.6 | 1232
2015-08-10 | 7027 |  |  | 1 | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 75 | 3.75 | 78.75 | 1232
2015-09-17 | 7314 |  |  |  | 75 | 1 | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 105 | 5.25 | 110.25 | 1271
2015-10-21 | 7558 |  |  |  | 75 |  | 105 |  | 1 | 7 | 75 |  | 140 | [6 empty] | 525 | 26.25 | 551.25 | 1301
2015-10-22 | 7561 |  |  |  | 75 |  | 105 |  | 1 | 2 | 75 |  | 140 | [6 empty] | 150 | 7.5 | 157.5 | 1301
2015-10-27 | 7615 |  |  |  | 75 | 0.5 | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 52.5 | 2.625 | 55.125
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0
[5 empty] | 75 |  | 105 |  | 1 |  | 75 |  | 140 | [6 empty] | 0 | 0 | 0

## Applied Aquatics- Boreal
Applied Aquatics
Date | LEM # | Straight Hours Charged (ea.) | Manpower | Wildlife Lead Chris Fisher | 150 | Biologist Jason Lewis | 130 | Biologist Tanya Debroux | 130 | Field Technician Joe Waler | 75 | Field Technician Joe Prevosy | 75 | Field Technician Anya Weare | 75 | Senior Soil Scientist AL Twardy | 185 | ? Gordon Dunn | 150 | Km's | 0.95 | Hybrid KM's | 0.8 | Water quality probe | rate | Swoffer | rate | Lamotte Turbidity Meter/Day | Rate | Amphibian traps | Rate | Field Kit GPS Kit, Camera, Binoculars, Latoptop | YSI Turbidty Meter | 140 | Boreal Field Kit 78.5 | Fish Sampling Kit | 40 | Minnow Traps | 45 | Backpack Electrofisher | 140 | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-07 | BG13003-1 | 26 | 1 | 4 | 150 | 4 | 130 | 4 | 130 | 5 | 75 | 5 | 75 |  | 75 | 0 | 185 | 4 | 150 | 973 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 924.35 | 3914.35 | 195.7175 | 4110.0675 |  |  | 228259.5
2015-06-08 | BG13003-2 | 50 | 1 | 11 | 150 | 4 | 130 | 11 | 130 | 4 | 75 | 4 | 75 |  | 75 | 5 | 185 | 11 | 150 | 788 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 748.6 | 7523.6 | 376.18 | 7899.78
2015-06-09 | BG13003-3 | 58 | 1 | 12 | 150 | 11.5 | 130 | 11.5 | 130 | 11.5 | 75 | 11.5 | 75 |  | 75 | 0 | 185 | 0 | 150 | 198 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 188.1 | 6860.1 | 343.005 | 7203.105
2015-06-10 | BG13003-4 | 56 | 1 | 12 | 150 | 11.5 | 130 | 11.5 | 130 | 10.5 | 75 | 10.5 | 75 |  | 75 | 0 | 185 | 0 | 150 | 275 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 261.25 | 6704.75 | 335.2375 | 7039.9875
2015-06-11 | BG13003-5 | 24 | 1 | 8 | 150 |  | 130 |  | 130 | 8 | 75 | 8 | 75 |  | 75 |  | 185 |  | 150 | 79 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 0.5 |  |  | 78.5 | [6 empty] | 75.05 | 2514.3 | 125.715 | 2640.015
2015-06-12 | BG13003-6 | 39 | 1 | 13 | 150 |  | 130 |  | 130 | 13 | 75 | 13 | 75 |  | 75 |  | 185 |  | 150 | 121 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 114.95 | 4093.45 | 204.6725 | 4298.1225
2015-06-13 | BG13003-7 | 28 | 3 | 10 | 150 |  | 130 |  | 130 | 9 | 75 | 9 | 75 |  | 75 |  | 185 |  | 150 | 225 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 213.75 | 3142.25 | 157.1125 | 3299.3625
2015-06-14 | BG13003-8 | 32 | 5 | 8 | 150 | 4 | 130 | 4 | 130 | 8 | 75 | 8 | 75 |  | 75 |  | 185 |  | 150 | 102 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 96.9 | 3615.4 | 180.77 | 3796.17
2015-06-15 | BG13003-9 | 62 | 5 | 13 | 150 | 13 | 130 | 13 | 130 | 11.5 | 75 | 11.5 | 75 |  | 75 |  | 185 |  | 150 | 268 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 254.6 | 7466.6 | 373.33 | 7839.93
2015-06-16 | BG13003-10 | 57.5 | 5 | 13 | 150 | 12 | 130 | 12.5 | 130 | 10 | 75 | 10 | 75 |  | 75 |  | 185 |  | 150 | 240 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 228 | 7020 | 351 | 7371
2015-06-17 | BG13003-11 | 54 | 5 | 11 | 150 | 11 | 130 | 11 | 130 | 10.5 | 75 | 10.5 | 75 |  | 75 |  | 185 |  | 150 | 318 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 302.1 | 6544.1 | 327.205 | 6871.305
2015-06-18 | BG13003-12 | 51 | 6 | 10 | 150 | 10 | 130 | 10 | 130 | 8 | 75 | 8 | 75 |  | 75 |  | 185 | 5 | 150 | 501 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 475.95 | 6682.95 | 334.1475 | 7017.0975
2015-06-19 | BG13003-13 | 42 | 5 |  | 150 | 4 | 130 | 10 | 130 | 9 | 75 | 9.5 | 75 |  | 75 |  | 185 | 9.5 | 150 | 355 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 337.25 | 5126.75 | 256.3375 | 5383.0875
2015-06-20 | BG13003-14 | 44 | 4 |  | 150 |  | 130 | 14 | 130 | 12 | 75 | 8 | 75 |  | 75 |  | 185 | 10 | 150 | 606 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 575.7 | 5552.7 | 277.635 | 5830.335
2015-06-21 | BG13003-15 | 32 | 5 | 4 | 150 |  | 130 | 8 | 130 | 8 | 75 | 8 | 75 | 4 | 75 |  | 185 |  | 150 | 326 | 0.95 | 331 | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 574.5 | 3793 | 189.65 | 3982.65
2015-06-22 | BG13003-16 | 22.5 | 4 | 9.5 | 150 |  | 130 | 4 | 130 | 9.5 | 75 | 9.5 | 75 |  | 75 |  | 185 |  | 150 | 385 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 365.75 | 3892.75 | 194.6375 | 4087.3875
2015-06-23 | BG13003-17 | 38 | 4 | 10 | 150 |  | 130 |  | 130 | 9.5 | 75 | 9.5 | 75 | 9 | 75 |  | 185 |  | 150 | 371 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 352.45 | 4109.45 | 205.4725 | 4314.9225
2015-06-24 | BG1300318 | 42 | 4 | 11 | 150 |  | 130 |  | 130 | 11 | 75 | 10 | 75 | 10 | 75 |  | 185 |  | 150 | 365 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 346.75 | 4478.75 | 223.9375 | 4702.6875
2015-06-25 | BG1300319 | 38 | 4 | 11 | 150 |  | 130 |  | 130 | 11 | 75 | 8 | 75 | 8 | 75 |  | 185 |  | 150 | 360 | 0.95 | 327 | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 2 |  |  | 78.5 | [6 empty] | 603.6 | 4435.6 | 221.78 | 4657.38
2015-06-26 | BG1300320 | 29 | 3 | 10.5 | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 | 10.5 | 75 |  | 185 |  | 150 | 557 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 529.15 | 3570.15 | 178.5075 | 3748.6575
2015-06-27 | BG1300321 | 21 | 2 | 12 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 9 | 75 |  | 185 |  | 150 | 255 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 242.25 | 2795.75 | 139.7875 | 2935.5375
2015-06-28 | BG1300322 | 22 | 3 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 | 4 | 150 | 345 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 0.5 |  |  | 78.5 | [6 empty] | 327.75 | 3067 | 153.35 | 3220.35
2015-06-29 | BG1300323 | 45 | 4 | 11 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 11 | 75 | 12 | 185 | 11 | 150 | 534 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 507.3 | 6930.8 | 346.54 | 7277.34
2015-06-30 | BG1300324 | 24 | 3 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 | 6 | 150 | 468 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 444.6 | 3523.1 | 176.155 | 3699.255
2015-07-01 | BG1300325 | 18 | 2 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 114 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 108.3 | 2286.8 | 114.34 | 2401.14
2015-07-02 | BG1300326 | 19.5 | 2 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 9.5 | 75 |  | 185 |  | 150 | 222 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 210.9 | 2501.9 | 125.095 | 2626.995
2015-07-03 | BG1300327 | 20.5 | 2 | 10.5 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 10 | 75 |  | 185 |  | 150 | 162 | 0.95 |  | 0.8 |  | 115 | 1 | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 153.9 | 2612.4 | 130.62 | 2743.02
2015-07-04 | BG13003-28 | 24 | 2 | 12 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 12 | 75 |  | 185 |  | 150 | 482 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 457.9 | 3236.4 | 161.82 | 3398.22
2015-07-05 | BG13003-29 | 8.5 | 2 | 4 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 4.5 | 75 |  | 185 |  | 150 | 315 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 299.25 | 1236.75 | 61.8375 | 1298.5875
2015-07-06 | BG13003-30 | 22.5 | 2 | 12.5 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 10 | 75 |  | 185 |  | 150 | 132 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 125.4 | 2828.9 | 141.445 | 2970.345
2015-07-07 | BG13003-31 | 24 | 2 | 12 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 12 | 75 |  | 185 |  | 150 | 200 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 190 | 2968.5 | 148.425 | 3116.925
2015-07-08 | BG13003-32 | 28 | 3 | 12 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 12 | 75 |  | 185 | 4 | 150 | 278 | 0.95 |  | 0.8 | 1 | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 264.1 | 3757.6 | 187.88 | 3945.48
2015-07-09 | BG13003-33 | 21.5 | 2 | 11 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 10.5 | 75 |  | 185 |  | 150 | 142 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 134.9 | 2650.9 | 132.545 | 2783.445
2015-07-10 | BG13003-34 | 19 | 2 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 9 | 75 |  | 185 |  | 150 | 158 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 | 1 | 90 | 1 |  |  | 78.5 | [6 empty] | 150.1 | 2493.6 | 124.68 | 2618.28
2015-07-11 | BG13003-35 | 19 | 2 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 9 | 75 |  | 185 |  | 150 | 129 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 | 1 | 90 | 1 |  |  | 78.5 | [6 empty] | 122.55 | 2466.05 | 123.3025 | 2589.3525
2015-07-12 | BG13003-36 | 23 | 3 | 10 | 150 |  | 130 |  | 130 | 5 | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 85 | 0.95 | 346 | 0.8 |  | 115 |  | 55 |  | 110 | 1 | 90 | 1 |  |  | 78.5 | [6 empty] | 357.55 | 3001.05 | 150.0525 | 3151.1025
2015-07-13 | BG13003-37 | 26 | 3 | 10 | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 195 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 | 1 | 90 | 1 |  |  | 78.5 | [6 empty] | 185.25 | 3053.75 | 152.6875 | 3206.4375
2015-07-14 | BG13003-38 | 27.5 | 3 | 10 | 150 |  | 130 |  | 130 | 8.5 | 75 |  | 75 | 9 | 75 |  | 185 |  | 150 | 151 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 | 1 | 90 | 1 |  |  | 78.5 | [6 empty] | 143.45 | 3124.45 | 156.2225 | 3280.6725
2015-07-15 | BG13003-39 | 34 | 3 | 11.5 | 150 |  | 130 |  | 130 | 11 | 75 |  | 75 | 12.5 | 75 |  | 185 |  | 150 | 200 | 0.95 | 325 | 0.8 |  | 115 |  | 55 |  | 110 | 1 | 90 | 1 |  |  | 78.5 | [6 empty] | 450 | 4106 | 205.3 | 4311.3
2015-07-16 | BG13003-40 | 18 | 2 | 10 | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 129 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 122.55 | 2222.55 | 111.1275 | 2333.6775
2015-07-17 | BG13003-41 | 4 | 1 |  | 150 |  | 130 |  | 130 | 4 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 325 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 308.75 | 608.75 | 30.4375 | 639.1875
2015-07-18 | BG13003-42 | 1 | 1 |  | 150 |  | 130 |  | 130 | 1 | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 0 | 75 | 3.75 | 78.75
2015-07-19 | BG13003-43 | 8 | 2 | 4 | 150 |  | 130 |  | 130 | 4 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 320 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 304 | 1204 | 60.2 | 1264.2
2015-07-20 | BG13003-44 | 18.5 | 2 | 10 | 150 |  | 130 |  | 130 | 8.5 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 145 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 137.75 | 2353.75 | 117.6875 | 2471.4375
2015-07-21 | BG13003-45 | 18 | 2 | 10 | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 141 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 133.95 | 2312.45 | 115.6225 | 2428.0725
2015-07-22 | BG13003-46 | 18.5 | 2 | 10 | 150 |  | 130 |  | 130 | 8.5 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 180 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 171 | 2387 | 119.35 | 2506.35
2015-07-23 | BG13003-47 | 13.5 | 2 | 4 | 150 |  | 130 |  | 130 | 9.5 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 219 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 208.05 | 1599.05 | 79.9525 | 1679.0025
2015-07-24 | BG13003-48 | 8 | 1 |  | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 132 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 125.4 | 803.9 | 40.195 | 844.095
2015-07-25 | BG13003-49 | 8 | 1 |  | 150 |  | 130 |  | 130 | 9.5 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 123 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 116.85 | 907.85 | 45.3925 | 953.2425
2015-07-26 | BG13003-50 | 8 | 1 |  | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 219 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 208.05 | 886.55 | 44.3275 | 930.8775
2015-07-27 | BG13003-51 | 9.5 | 1 |  | 150 |  | 130 |  | 130 | 9.5 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 226 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 214.7 | 1005.7 | 50.285 | 1055.985
2015-07-28 | BG13003-52 | 8.5 | 1 |  | 150 |  | 130 |  | 130 | 8.5 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 227 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 215.65 | 931.65 | 46.5825 | 978.2325
2015-07-29 | BG13003-53 | 17 | 3 | 4 | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 | 5 | 75 |  | 185 |  | 150 | 219 | 0.95 | 321 | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 464.85 | 2118.35 | 105.9175 | 2224.2675
2015-07-30 | BG13003-54 | 27 | 3 | 10 | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 | 9 | 75 |  | 185 |  | 150 | 322 | 0.95 | 327 | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 567.5 | 3421 | 171.05 | 3592.05
2015-07-31 | BG13003-55 | 18.5 | 2 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8.5 | 75 |  | 185 |  | 150 | 245 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 232.75 | 2448.75 | 122.4375 | 2571.1875
2015-08-01 | BG13003-56 | 18 | 2 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 201 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 190.95 | 2369.45 | 118.4725 | 2487.9225
2015-08-02 | BG13003-57 | 8 | 1 |  | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 172 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 163.4 | 841.9 | 42.095 | 883.995
2015-08-03 | BG13003-58 | 8 | 1 |  | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 197 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 187.15 | 865.65 | 43.2825 | 908.9325
2015-08-04 | BG13003-59 | 8 | 1 |  | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 208 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 197.6 | 876.1 | 43.805 | 919.905
2015-08-05 | BG13003-60 | 12 | 2 | 4 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 203 | 0.95 |  | 0.8 |  | 116 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 192.85 | 1471.35 | 73.5675 | 1544.9175
2015-08-06 | BG13003-61 | 18 | 2 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 224 | 0.95 |  | 0.8 |  | 117 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 212.8 | 2391.3 | 119.565 | 2510.865
2015-08-07 | BG13003-62 | 18 | 2 | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 111 | 0.95 |  | 0.8 |  | 118 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 105.45 | 2283.95 | 114.1975 | 2398.1475
2015-08-08 | BG13003-63 | 18 |  | 10 | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 202 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 191.9 | 2370.4 | 118.52 | 2488.92
2015-08-09 | BG13003-64 | 23 |  | 10 | 150 |  | 130 |  | 130 | 5 | 75 |  | 75 | 8 | 75 |  | 185 |  | 150 | 510 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 484.5 | 3038 | 151.9 | 3189.9
2015-08-10 | BG13003-65 | 28.5 |  | 10 | 150 |  | 130 |  | 130 | 9.5 | 75 |  | 75 | 9 | 75 |  | 185 |  | 150 | 382 | 0.95 |  | 0.8 |  | 115 |  | 55 | 1 | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 362.9 | 3438.9 | 171.945 | 3610.845
2015-08-11 | BG13003-66 | 22 |  |  | 150 |  | 130 |  | 130 | 9 | 75 |  | 75 | 13 | 75 |  | 185 |  | 150 | 652 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 619.4 | 2347.9 | 117.395 | 2465.295
2015-08-12 | BG13003-67 | 8.5 |  |  | 150 |  | 130 |  | 130 | 8.5 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 245 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 232.75 | 948.75 | 47.4375 | 996.1875
2015-08-13 | BG13003-68 | 8 |  |  | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 227 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 215.65 | 894.15 | 44.7075 | 938.8575
2015-08-14 | BG13003-70 | 8 |  |  | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 125 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 118.75 | 797.25 | 39.8625 | 837.1125
2015-08-15 | BG13003-71 | 8 |  |  | 150 |  | 130 |  | 130 | 8 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 255 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 242.25 | 920.75 | 46.0375 | 966.7875
2015-08-16 | BG13003-72 | 6.5 |  |  | 150 |  | 130 |  | 130 | 2 | 75 |  | 75 | 4.5 | 75 |  | 185 |  | 150 | 452 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 | 1 |  |  | 78.5 | [6 empty] | 429.4 | 995.4 | 49.77 | 1045.17
2015-08-17 | BG13003-73 |  |  |  | 150 |  |  |  |  | 13 | 75 |  | 75 | 13 | 75 |  | 185 |  | 150 | 125 | 0.95 |  | 0.8 |  | 115 |  | 55 | 1 | 110 |  | 90 | 1 | 1 | 140 | 78.8 | [6 empty] | 118.75 | 2397.55 | 119.8775 | 2517.4275
2015-08-18 | BG13003.74 |  |  |  | 150 |  |  |  |  | 15 | 75 |  | 75 | 15 | 75 |  | 185 |  | 150 | 124 | 0.95 |  | 0.8 |  | 115 |  | 55 | 1 | 110 |  | 90 | 1 | 1 | 140 | 78.5 | 1 | 40 | 1 | 45 | 1 | 140 | 117.8 | 2921.3 | 146.065 | 3067.365
2015-08-19 | BG13003-75 |  |  |  | 150 |  |  |  |  | 13 | 75 |  | 75 | 13 | 75 |  | 185 |  | 150 | 99 | 0.95 |  | 0.8 |  | 115 |  | 55 | 1 | 110 |  | 90 | 1 | 1 | 140 | 78.5 | [6 empty] | 94.05 | 2372.55 | 118.6275 | 2491.1775
2015-08-20 | BG13003-76 | 26 | 2 |  | 150 |  | 130 |  | 130 | 13 | 75 |  | 75 | 13 | 75 |  | 185 |  | 150 | 98 | 0.95 |  | 0.8 |  | 115 |  | 55 | 1 | 110 |  | 90 | 1 | 1 | 140 | 78.5 | [6 empty] | 93.1 | 2371.6 | 118.58 | 2490.18
2015-08-21 | BG13003-77 | 25.5 | 2 |  | 150 |  | 130 |  | 130 | 13.5 | 75 |  | 75 | 12 | 75 |  | 185 |  | 150 | 100 | 0.95 |  | 0.8 |  | 115 |  | 55 | 1 | 110 |  | 90 | 1 | 1 | 140 | 78.5 | [6 empty] | 95 | 2336 | 116.8 | 2452.8
2015-08-22 | BG13003-78 | 20 | 2 |  | 150 |  | 130 |  | 130 | 13 | 75 |  | 75 | 7 | 75 |  | 185 |  | 150 | 422 | 0.95 |  | 0.8 |  | 115 |  | 55 | 1 | 110 |  | 90 | 1 | 1 | 140 | 78.5 | [6 empty] | 400.9 | 2229.4 | 111.47 | 2340.87
2015-08-26 | BG13003.79 |  |  |  | 150 |  | 130 |  | 130 | 10 | 75 |  | 75 |  | 75 |  | 185 |  | 150 | 722 | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 685.9 | 1435.9 | 71.795 | 1507.695
2015-08-27 |  |  |  |  | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
2015-08-28 | BG13003-80 |  |  |  | 150 |  | 130 |  | 130 |  | 75 |  | 75 | 5 | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 375 | 18.75 | 393.75
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  | 140 | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 150 |  | 130 |  | 130 |  | 75 |  | 75 |  | 75 |  | 185 |  | 150 |  | 0.95 |  | 0.8 |  | 115 |  | 55 |  | 110 |  | 90 |  |  |  | 78.5 | [6 empty] | 0 | 0 | 0 | 0
Note on C61: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 172 kms
Note on O61: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 172 kms
Note on U61: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 172 kms
Note on AG61: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 172 kms
Note on C62: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 197 kms
Note on O62: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 197 kms
Note on U62: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 197 kms
Note on AG62: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 197 kms
Note on C63: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 208 kms
Note on O63: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 208 kms
Note on U63: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 208 kms
Note on AG63: Lorraine Dunbar: Anna Weir - 8hrs 1 Field Kit 208 kms

## Davis Safety Added to Barry Fav
Davis Safety
Date | Site | LEM # | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Manpower | Labour | Day Rate | Truck | Rate | Labourer class | Rate | Labourer class | Rate | Labourer class | Rate | Labourer class | Rate | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-14 | RFS |  |  |  | 1 | 1.5 | 900 | 1.5 | 150 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1050 | 0 | AC mitigation June 18 |  | 1575 | 78.75 | 1653.75 | 145167 |  | 2625
2015-07-19 | RFS |  |  |  | 1 | 1 | 900 | 1 | 150 | [9 empty] | 0 | 1050 | 0 | AC mitigation July 19 |  | 1050 | 52.5 | 1102.5 | 145750
[20 empty] | 0 | 0 |  |  | 0 | 0 | 0
[20 empty] | 0 | 0 |  |  | 0 | 0 | 0
[20 empty] | 0 | 0 |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
[20 empty] | 0 |  |  |  | 0 | 0 | 0
0
0
0
0
0
0
0

## Davis Safety - Barry Favel
Davis Safety | [9 empty] | Barry Favel
Date | Site | LEM # | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Manpower | Labour | Day Rate | Truck | Rate | Labourer class | Rate | Truck | Rate | LOA | Rate | KM's above 150 | Rate | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-07-28 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 | [6 empty] | 1315 | 65.75 | 1380.75 | 145931 |  | 100519
2015-07-29 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 | [6 empty] | 1315 | 65.75 | 1380.75 | 145931
2015-07-30 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 | [6 empty] | 1315 | 65.75 | 1380.75 | 145931
2015-07-31 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 | 0 |  |  | 1315 | 65.75 | 1380.75 | 145931
2015-08-01 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 | 0 |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-02 | [10 empty] | 950 |  | 150 | 1 | 215 |  | 1 |  |  | 1100 | 0 |  |  | 215 | 10.75 | 225.75 | 145932
2015-08-03 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 | 0 |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-04 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-05 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-06 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-07 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-08 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-09 | [10 empty] | 950 |  | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 215 | 10.75 | 225.75 | 145932
2015-08-10 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-11 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-12 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-13 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-14 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 145932
2015-08-24 |  | EI916 | [7 empty] | 1 | 950 |  | 150 | 1 | 215 | 394 | 1 |  |  | 1100 |  |  |  | 1559 | 77.95 | 1636.95 | 146059
2015-08-25 |  | EI916 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146059
2015-08-26 |  | EI916 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146059
2015-08-27 |  | EI916 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146059
2015-08-28 |  | EI916 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146059
2015-08-29 |  | EI916 | [7 empty] | 1 | 950 |  | 150 | 1 | 215 | 420 | 1 |  |  | 1100 |  |  |  | 1585 | 79.25 | 1664.25 | 146059 |  | Dave Knight - | 8404
2015-08-16 |  | 11047 | [8 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0 | 146060 | Sunday
2015-08-17 |  | 11047 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146060
2015-08-18 |  | 11047 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146060
2015-08-19 |  | 11047 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146060
2015-08-20 |  | 11047 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146060
2015-08-21 |  | 11047 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146060
2015-08-22 |  | 11047 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146060
2015-08-23 |  | 11047 | [7 empty] | 0 | 950 | 0 | 150 | 0 | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0 | 146060 | Sunday
2015-08-30 |  | 11047 | [8 empty] | 950 |  | 150 | 1 | 215 | 411 | 1 |  |  | 1100 |  |  |  | 626 | 31.3 | 657.3 | 146060 | Sunday
2015-08-31 |  | 11047 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146060 |  | Barry Favel - | 9831 | Total Invoice Should Be - $18235.00
2015-09-01 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146226
2015-09-02 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146226
2015-09-03 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146226
2015-09-11 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 | 34 | 1 |  |  | 1100 |  |  |  | 1349 | 67.45 | 1416.45 | 146226
2015-09-12 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146226
2015-09-13 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146226
2015-09-14 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146226
2015-09-15 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146226 |  | Barry Favel | 10554
2015-09-16 | [9 empty] | 0 | 950 | 0 | 150 | 0 | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 65.75 | 1380.75 | 146463
2015-09-17 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-09-18 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-09-19 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-09-20 | [9 empty] | 0 | 950 | 0 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 215 | 10.75 | 225.75 | 146463
2015-09-21 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-09-22 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-09-23 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-09-24 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-09-25 | [9 empty] | 0 | 950 | 0 | 150 | 0 | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0 | 146463 |  | Day Off
2015-09-26 | [9 empty] | 0 | 950 | 0 | 150 | 0 | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0 | 146463 |  | Day Off
2015-09-27 | [9 empty] | 0 | 950 | 0 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 215 | 10.75 | 225.75 | 146463
2015-09-28 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-09-29 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-09-30 | [9 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146463
2015-10-01 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-02 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-03 |  | 11050 | [8 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0 | 146464 |  | Day Off
2015-10-04 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-05 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-06 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-07 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-08 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-09 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-10 |  | 11050 | [7 empty] | 0 | 950 | 0 | 150 | 1 | 215 |  | 1 |  |  | 1100 |  |  |  | 215 | 10.75 | 225.75 | 146464
2015-10-11 |  | 11050 | [7 empty] | 0 | 950 | 0 | 150 | 1 | 215 |  | 1 |  |  | 950 |  |  |  | 215 | 10.75 | 225.75 | 146464
2015-10-12 |  | 11050 | [7 empty] | 0 | 950 | 0 | 150 | 1 | 215 |  | 1 |  |  | 950 |  |  |  | 215 | 10.75 | 225.75 | 146464
2015-10-13 |  | 11050 | [7 empty] | 0 | 950 | 0 | 150 | 1 | 215 |  | 1 |  |  | 950 |  |  |  | 215 | 10.75 | 225.75 | 146464
2015-10-14 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-15 |  | 11050 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146464
2015-10-16 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-17 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-18 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-19 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-20 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-21 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-22 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-23 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-24 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-25 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-26 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-27 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-28 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-29 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-30 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-10-31 |  | e-7551 | [7 empty] | 1 | 950 | 1 | 150 | 1 | 215 |  | 1 |  |  | 951 |  |  |  | 1315 | 65.75 | 1380.75 | 146603
2015-11-01 |  | e-7552 | [7 empty] | 1 | 950 |  | 150 | 1 | 215 | 465 | 1 |  |  | 951 |  |  |  | 1630 | 81.5 | 1711.5 | 146729
2015-08-15 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0 | Day Off
2015-09-04 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0
2015-09-05 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0
2015-09-06 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0
2015-09-07 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0
2015-09-08 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0
2015-09-09 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0
2015-09-10 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 |  |  | 1100 |  |  |  | 0 | 0 | 0
2015-11-02 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-03 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-04 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-05 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-06 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-07 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-08 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-09 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-10 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-11 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-12 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-13 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-14 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-15 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-16 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-17 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-18 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-19 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-20 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-21 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-22 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-23 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-24 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-25 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-26 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-27 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-28 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-29 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0
2015-11-30 | [10 empty] | 950 |  | 150 |  | 215 |  | 1 | [6 empty] | 0 | 0 | 0

## Freeport - Curtis Hansen
Freeport
Date | Site | LEM # | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Curtis Hansen | Rate | inspector | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-05-30 | RFS | 2015-047 | 8 | 0 | 8 | 1550 |  | 1100 |  | 200 | 800 | 1 |  | 150 |  | 0 |  | 150 |  | 175 |  | 0 |  | 0 | 1701 | 12400 |  | 800 | 13200 | 660 | 13860 | 2015-047 |  | 309225
2015-06-01 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 | 1351 | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-02 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 | 1351 | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-03 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 | 1351 | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-04 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 | 1351 | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-05 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 | 1351 | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-06 | RFS |  | 1 |  |  | 1200 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  |  |  | 0 | 1351 | 1200 |  | 0 | 175 | 8.75 | 183.75 | 2015-048 | 0
2015-06-07 | RFS |  | 1 |  |  | 1200 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  |  |  | 0 | 1351 | 1200 |  | 0 | 175 | 8.75 | 183.75 | 2015-048
2015-06-08 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 | 150 | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 | 1351 | 1200 |  | 150 | 1875 | 93.75 | 1968.75 | 2015-048
2015-06-09 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 | 1351 | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-10 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-11 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-12 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-13 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-14 | RFS |  | 1 |  |  | 1200 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | 1200 |  | 0 | 325 | 16.25 | 341.25 | 2015-048
2015-06-15 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | 1200 |  | 0 | 1725 | 86.25 | 1811.25 | 2015-048
2015-06-16 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-17 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-18 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-19 | RFS |  | 1 |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-20 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-21 | RFS |  |  |  |  | 1200 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  |  |  | 0 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-050 | 0
2015-06-22 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-23 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-24 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-25 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-26 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-27 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-28 | RFS |  |  |  |  | 1200 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  |  |  | 0 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-050
2015-06-29 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-06-30 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-050
2015-07-01 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-02 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-03 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-04 | RFS |  |  |  | 1 | 1200 |  | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-05 | RFS |  |  |  |  | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 2015-18 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-06 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-07 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-08 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-09 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-10 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051 | 22775
2015-07-11 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-12 |  |  |  | 1 |  | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 2015-18 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-13 |  |  |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-14 |  |  |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-15 |  |  |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 2015-18 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-051
2015-07-16 |  |  |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-17 |  |  |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-18 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-19 |  | 425 |  | 1 |  | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-20 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-21 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-22 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052 | 24500
2015-07-23 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-24 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-25 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-26 |  | 425 |  | 1 |  | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-27 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-28 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-29 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-30 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-07-31 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-052
2015-08-01 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-02 |  | 425 |  | 1 |  | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-04 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-05 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-06 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-07 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053 | 0
2015-08-08 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-09 |  | 425 |  | 1 |  | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-11 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-12 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-13 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-14 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-15 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-053
2015-08-16 |  | 425 |  | 1 |  | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  | 425 |  | 1 | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-22 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-23 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054 | 0
2015-08-24 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-08-30 | [5 empty] | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-04 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-05 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-06 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-07 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055 | 0
2015-09-08 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-09 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-10 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-13 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-055
2015-09-16 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-19 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-20 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-059
2015-09-21 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-22 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-23 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-24 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059 | 0
2015-09-25 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-26 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-27 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-059
2015-09-28 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-29 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-09-30 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-059
2015-10-01 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-02 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-03 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-04 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-05 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-06 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-07 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062 | 0
2015-10-08 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-09 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-10 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-11 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-12 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-13 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-14 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-15 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-062
2015-10-16 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-17 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-18 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-065
2015-10-19 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-20 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-21 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065 | 0
2015-10-22 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-23 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-24 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-25 | [5 empty] | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-065
2015-10-26 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-27 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-28 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-29 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-30 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-10-31 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-065
2015-11-01 |  |  |  |  | 0 | 1200 |  |  | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-071
2015-11-02 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-03 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-04 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-05 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-06 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071 | 0
2015-11-07 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-08 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-09 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-10 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-11 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-12 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-13 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-14 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-071
2015-11-15 | [5 empty] | 1200 |  |  |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-071
2015-11-16 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-17 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-18 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-19 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-20 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-21 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-22 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075 | 0
2015-11-23 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-24 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-25 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-26 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-075
2015-11-27 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 | [5 empty] | 0 | 1550 | 77.5 | 1627.5 | 2015-075
2015-11-28 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-075
2015-11-29 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-075
2015-11-30 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-075
2015-12-01 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-081
2015-12-02 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-081
2015-12-03 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-081
2015-12-04 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-081
2015-12-05 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-081
2015-12-06 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-081 | 0
2015-12-07 |  |  |  |  | Vacation | 1200 |  |  |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 |  |  |  | 2015-081
2015-12-08 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-081
2015-12-09 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-081
2015-12-10 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-081
2015-12-11 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-081
2015-12-12 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-081
2015-12-13 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-081
2015-12-14 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-081
2015-12-15 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-081
2015-12-16 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-084
2015-12-17 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-084
2015-12-18 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-084 | 11900
2015-12-19 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-084
2015-12-20 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-084
2015-12-21 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1725 | 86.25 | 1811.25 | 2015-084
2015-12-22 |  |  |  |  | 1 | 1200 |  |  | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 | [5 empty] | 0 | 1550 | 77.5 | 1627.5 | 2015-084

## Freeport - Bart Holmes
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Bart Holmes | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-14 | 1 |  |  | 1200 | 1 | 1100 | 1 | 200 | 150 | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | 1200 |  | 150 | 1775 | 88.75 | 1863.75 | 2015-050 |  | 226450
2015-06-15 | 1 |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-16 | 1 |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-17 | 1 |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 150 | 1 | 175 |  | 150 |  | 0 |  | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-18 | 1 |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 |  | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-19 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-20 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-21 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050 | 26325
2015-06-22 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-23 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-24 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-25 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-26 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-27 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-28 |  |  |  | 1200 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  |  |  | 0 | 1201 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-050
2015-06-29 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-30 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-07-01 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-02 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-03 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-04 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-05 | [16 empty] | 1 | 175 |  |  |  | 0 | 0 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-06 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-07 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-08 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-09 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051 | 20025
2015-07-10 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-11 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-12 |  |  | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-13 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-14 |  |  | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-15 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-16 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-17 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-18 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-19 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-20 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-21 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-22 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-23 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052 | 24550
2015-07-24 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-25 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-26 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-27 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-28 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-29 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-30 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-31 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-08-01 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-02 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-04 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-07 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 20025
2015-08-08 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-09 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-11 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054 | 20200
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-04 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-05 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-06 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-07 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055 | 15675
2015-09-08 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-09 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-16 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-20 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-059
2015-09-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059 | 22925
2015-09-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-29 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-30 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-10-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-06 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062 | 15675
2015-10-07 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-08 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-09 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-10 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-11 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-12 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-13 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-16 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 0 | 175 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-17 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-18 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-19 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-20 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-21 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-22 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-24 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-25 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-26 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-27 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-28 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-29 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-10-31 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [7 empty] | 0 | 0 | 0 | 0 |  |  | MOVE TO CDH2
2015-11-01 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-071
2015-11-02 |  |  |  |  | 0 | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-071
2015-11-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-04 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-05 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071 | 20025
2015-11-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-15 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-071
2015-11-16 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-17 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075 | 22925
2015-11-23 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-29 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-075
2015-11-30 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-075
2015-12-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-04 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-05 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081 | 18100
2015-12-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-11 |  |  |  |  | 1 | 1100 | 1 | 200 | 400 | 1 |  | 150 | [5 empty] | 175 |  | 150 | [5 empty] | 400 | 1850 | 92.5 | 1942.5 | 2015-081

## Freeport - Robert Plante
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) |  | Chief inspector | Robert Plante | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 150 | 1775 | 88.75 | 1863.75 | 2015-050 |  | 165200
2015-06-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050 | 11700
2015-06-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-28 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  |  |  | 0 | #REF! | 0 |  | 0 | 175 | 8.75 | 183.75 | 2015-050
2015-06-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-30 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-07-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-04 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-05 | [16 empty] | 1 | 175 |  |  |  | 0 | #REF! | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-06 |  |  | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-07 |  |  | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-08 |  |  | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-09 |  |  | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-10 |  |  | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-11 |  |  | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051 | 18575
2015-07-12 |  |  | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-13 |  |  | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-14 |  |  | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-15 |  |  | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-16 |  |  | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-17 |  |  | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 0 |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-18 |  | 425 | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 425 |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-19 |  | 425 | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 425 |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-20 |  | 425 | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 425 |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-21 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-22 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-23 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052 | 18750
2015-07-24 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-25 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-26 |  | 425 | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 425 |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-27 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-28 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-29 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-30 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-31 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-08-01 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-02 |  | 425 | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 425 |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-04 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-07 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 21475
2015-08-08 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-09 |  | 425 | 1 | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 425 |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-11 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-17 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-18 |  | 425 | 1 | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 425 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 0 |  | 0 | 175 | 8.75 | 183.75 | 2015-054 | 23100
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | #REF! | 0 |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-04 | [16 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-05 | [16 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-06 | [16 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-07 | [16 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055 | 18575
2015-09-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-16 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | #REF! | 0 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-20 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 |  | 0 | #REF! | 0 |  | 0 | 175 | 8.75 | 183.75 | 2015-059
2015-09-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059 | 22925
2015-09-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-29 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-30 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-10-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062 | 17125
2015-10-06 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-07 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-08 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-09 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-10 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-11 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-12 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-062
2015-10-13 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-16 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-17 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-18 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-19 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-20 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-21 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-22 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-24 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-25 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-26 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-27 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-28 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-29 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-10-31 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | [8 empty] | 0 | 0 | 0 |  | Move to CDH_II
2015-11-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-04 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-071 | 12975
2015-11-05 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-08 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 |  | 150 | [5 empty] | 175 |  | 150 | [6 empty] | 1600 | 80 | 1680 | 2015-071

## Freeport - Brian Friedel
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Brian Friedel | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Subtotal before mark up | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-18 |  |  |  |  | 1 | 1100 | 1 | 200 | 60 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 |  |  |  | 60 | 1510 | 75.5 | 1585.5 | 2015-050 |  | 160660
2015-06-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050 | 11435
2015-06-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-28 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  |  |  | 0 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-050
2015-06-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-06-30 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 |  | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-050
2015-07-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-04 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-05 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 | 1 | 175 | 175 |  |  | 0 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-07-06 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 53400
2015-07-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-12 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 |  |  | 0 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-07-13 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 |  |  | 0 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-07-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-07-16 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-17 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 |  |  | 0 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-18 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 |  |  | 0 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-19 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 |  |  | 0 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052 | 15325
2015-07-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-23 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-26 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 |  |  | 0 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-29 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-31 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 2015-052
2015-08-01 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 2015-053
2015-08-02 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 2015-053
2015-08-03 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 2015-053
2015-08-04 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 0 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 1 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 2 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 3 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 4 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-09 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 |  |  | 4 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 |  |  | 6 |  |  |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 |  | 6 |  |  |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054 | 23100
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-23 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 | [7 empty] | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-04 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-05 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055 | 21475
2015-09-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-07 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 | [7 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-08 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 175 | [7 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-16 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059 | 24375
2015-09-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-29 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-30 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-10-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-06 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-07 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-08 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 0 | 175 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 2015-062 | 15500
2015-10-09 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-062
2015-10-10 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-062
2015-10-11 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-062
2015-10-12 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-062
2015-10-13 | [5 empty] | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-062
2015-10-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-16 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-065
2015-10-17 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-065
2015-10-18 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-065 | 11375
2015-10-19 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-065
2015-10-20 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-065
2015-10-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-065
2015-10-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 1475 | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-065
Note on A13: sacook000: Brian missed this period

## Freeport - Brandi Smith
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Brandy Smith | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
96467
2015-06-18 | 1 |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-050
2015-06-30 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-050 | 2900
2015-07-01 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-02 |  |  |  | 1200 | 1 | 1100 | 1 | 200 | 61 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 61 | 1511 | 75.55 | 1586.55 | 2015-051
2015-07-07 |  |  |  | 1200 | 1 | 1100 | 1 | 200 | 26 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 26 | 1476 | 73.8 | 1549.8 | 2015-051
2015-07-08 |  |  |  | 1200 | 1 | 1100 | 1 | 200 | 44 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 44 | 1494 | 74.7 | 1568.7 | 2015-051 | 8869
2015-07-09 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-10 |  |  |  | 1200 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 1201 | 2015-18 |  | 0 | 0 | 0 | 0 | 2015-051
2015-07-11 |  |  |  | 1200 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 1201 | 2015-18 |  | 0 | 0 | 0 | 0 | 2015-051
2015-07-12 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | 2015-18 |  | 0 | 0 | 0 | 0 | 2015-051
2015-07-13 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | 2015-18 |  | 0 | 0 | 0 | 0 | 2015-051
2015-07-14 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | 2015-18 |  | 0 | 0 | 0 | 0 | 2015-051
2015-07-15 |  |  |  | 1 | 1 | 1100 | 1 | 200 | 38 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | 2015-18 |  | 38 | 1488 | 74.4 | 1562.4 | 2015-051
2015-07-16 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-17 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | #REF! |  | 0 | 0 | 0 | 0
2015-07-18 |  | 425 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | #REF! |  | 0 | 0 | 0 | 0
2015-07-19 |  | 426 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | #REF! |  | 0 | 0 | 0 | 0
2015-07-20 |  | 427 |  | 1 | 1 | 1100 | 1 | 200 | 35 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 35 | 1485 | 74.25 | 1559.25 | 2015-052
2015-07-21 |  | 428 |  | 1 | 1 | 1100 | 1 | 200 | 35 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 35 | 1485 | 74.25 | 1559.25 | 2015-052
2015-07-22 |  | 429 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-23 |  | 430 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-24 |  | 431 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-25 |  | 432 |  | 1 | 1 | 1100 | 1 | 200 | 20 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 20 | 1470 | 73.5 | 1543.5 | 2015-052 | 17553
2015-07-26 |  | 433 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-27 |  | 434 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-28 |  | 435 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-29 |  | 436 |  | 1 | 1 | 1100 | 1 | 200 | 20 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 20 | 1470 | 73.5 | 1543.5 | 2015-052
2015-07-30 |  | 437 |  | 1 | 1 | 1100 | 1 | 200 | 18 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 18 | 1468 | 73.4 | 1541.4 | 2015-052
2015-07-31 |  | 438 |  | 1 | 1 | 1100 | 1 | 200 | 25 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 25 | 1475 | 73.75 | 1548.75 | 2015-052
2015-08-01 |  | 439 |  | 1 | 1 | 1100 | 1 | 200 | 18 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 18 | 1468 | 73.4 | 1541.4 | 2015-053
2015-08-02 |  | 440 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-053
2015-08-03 |  | 441 |  | 1 | 1 | 1100 | 1 | 200 | 11 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 11 | 1461 | 73.05 | 1534.05 | 2015-053
2015-08-04 |  | 442 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-05 |  | 443 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-06 |  | 444 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-07 |  | 445 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-08 |  | 446 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053 | 18889
2015-08-09 |  | 447 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-053
2015-08-10 |  | 448 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-11 |  | 449 |  | 1 | 1 | 1100 | 1 | 200 | 10 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 10 | 1460 | 73 | 1533 | 2015-053
2015-08-12 |  | 450 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-13 |  | 451 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-14 |  | 452 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-15 |  | 453 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-16 |  | 454 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-054
2015-08-17 |  | 455 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 2 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 | 50 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 50 | 1500 | 75 | 1575 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 40 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 40 | 1490 | 74.5 | 1564.5 | 2015-054 | 19146
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 10 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 10 | 1460 | 73 | 1533 | 2015-054
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-054
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 26 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 26 | 1476 | 73.8 | 1549.8 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 50 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 50 | 1500 | 75 | 1575 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 | 70 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 70 | 1520 | 76 | 1596 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 | 50 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 50 | 1500 | 75 | 1575 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 20 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 20 | 1470 | 73.5 | 1543.5 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 20 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 20 | 1470 | 73.5 | 1543.5 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 20 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 20 | 1470 | 73.5 | 1543.5 | 2015-055
2015-09-04 | [26 empty] | 0 | 0 | 0 | 2015-055
2015-09-05 | [26 empty] | 0 | 0 | 0 | 2015-055
2015-09-06 | [26 empty] | 0 | 0 | 0 | 2015-055
2015-09-07 | [26 empty] | 0 | 0 | 0 | 2015-055
2015-09-08 | [26 empty] | 0 | 0 | 0 | 2015-055
2015-09-09 | [26 empty] | 0 | 0 | 0 | 2015-055
2015-09-10 | [26 empty] | 0 | 0 | 0 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 | 10 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1 | #REF! |  | 10 | 1460 | 73 | 1533 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 | [6 empty] | 1450 | 72.5 | 1522.5 | 2015-055 | 11710
2015-09-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 | [6 empty] | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 40 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 | [6 empty] | 1490 | 74.5 | 1564.5 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 | [6 empty] | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-16 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 |  | 150 | [7 empty] | 0 | [6 empty] | 0 | 0 | 0 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 | [6 empty] | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 | [6 empty] | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-19 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 | [6 empty] | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-20 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 0 | [6 empty] | 0 | 0 | 0 | 2015-059
2015-09-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  | 0 |  | 0 |  | 175 |  | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059 | 17400
2015-09-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-29 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059 |  | Last Day
Note on F4: sacook000: No Sub for Brandi

## Freeport - Dan Higgins
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Dan Higggins | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-08 |  |  |  | 1200 | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-048 |  | 164332
2015-06-09 |  |  |  | 1200 | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-048 | 5846
2015-06-10 |  |  |  | 1200 | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-048
2015-06-11 |  |  |  | 1200 | 1 | 1100 | 1 | 200 | 46 | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | #REF! |  | 46 | 1496 | 74.8 | 1570.8 | 2015-048
2015-07-03 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-04 |  |  |  | 1200 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  | 0 |  | 0 |  | 175 |  | 150 |  | 0 | 1201 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-06 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-07 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-08 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-09 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051 | 14300
2015-07-10 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-11 |  |  | 1 |  | 1 | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1250 | 62.5 | 1312.5 | 2015-051
2015-07-13 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-14 |  |  | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | 2015-18 |  | 0 | 0 | 0 | 0 | 2015-051
2015-07-15 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1450 | 72.5 | 1522.5 | 2015-051
2015-07-16 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-17 |  |  | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-18 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-19 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-20 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-21 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-22 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052 | 20410
2015-07-23 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-24 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-25 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-26 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-27 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-28 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 | 47 | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 47 | 1497 | 74.85 | 1571.85 | 2015-052
2015-07-29 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 | 63 | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 63 | 1513 | 75.65 | 1588.65 | 2015-052
2015-07-30 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-07-31 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-052
2015-08-01 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-02 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-053
2015-08-03 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-04 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-05 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 | 63 | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 63 | 1513 | 75.65 | 1588.65 | 2015-053
2015-08-06 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-07 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-08 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053 | 18913
2015-08-09 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-053
2015-08-10 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-11 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-12 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-13 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-14 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-15 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-053
2015-08-16 |  | 425 | 1 |  |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-054
2015-08-17 |  | 425 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-054 | 18850
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-04 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-055
2015-09-05 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-055
2015-09-06 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-055 | 16046
2015-09-07 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-055
2015-09-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-10 |  |  |  |  | 1 | 1100 | 1 | 200 | 57 | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 57 | 1507 | 75.35 | 1582.35 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 | 39 | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 39 | 1489 | 74.45 | 1563.45 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055
2015-09-16 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1100 | 1 | 200 | 29 | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 29 | 1479 | 73.95 | 1552.95 | 2015-059
2015-09-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-20 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 0 |  | 0 | 1 | #REF! |  | 0 | 0 | 0 | 0 | 2015-059
2015-09-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 0 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 96 | 1 |  | 150 | [5 empty] | 175 |  | 150 | [5 empty] | 96 | 1546 | 77.3 | 1623.3 | 2015-059 | 19123
2015-09-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 46 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 46 | 1496 | 74.8 | 1570.8 | 2015-059
2015-09-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 27 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 27 | 1477 | 73.85 | 1550.85 | 2015-059
2015-09-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 30 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 30 | 1480 | 74 | 1554 | 2015-059
2015-09-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-09-27 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 |  | 150 | [7 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 2015-059
2015-09-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 19 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 19 | 1469 | 73.45 | 1542.45 | 2015-059
2015-09-29 |  |  |  |  | 1 | 1100 | 1 | 200 | 26 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 26 | 1476 | 73.8 | 1549.8 | 2015-059
2015-09-30 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-059
2015-10-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-062
2015-10-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-062
2015-10-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-062
2015-10-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 47 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 47 | 1497 | 74.85 | 1571.85 | 2015-062
2015-10-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 47 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 47 | 1497 | 74.85 | 1571.85 | 2015-062 | 16044
2015-10-06 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-062
2015-10-07 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-062
2015-10-08 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-062
2015-10-09 | [5 empty] | 1100 | 0 | 200 | 0 | 1 |  | 150 | [7 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 2015-062
2015-10-10 | [5 empty] | 1100 | 0 | 200 | 0 | 1 |  | 150 | [7 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 2015-062
2015-10-11 | [5 empty] | 1100 | 0 | 200 | 0 | 1 |  | 150 | [7 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 2015-062
2015-10-12 | [5 empty] | 1100 | 0 | 200 | 0 | 1 |  | 150 | [7 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 2015-062
2015-10-13 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-062
2015-10-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-062
2015-10-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-062
2015-10-16 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-17 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-18 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-19 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-20 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-21 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-22 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-23 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-24 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-25 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-26 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-27 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-28 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-29 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-30 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-10-31 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 |  | Move to CDH-II
2015-11-01 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 | 2015-071
2015-11-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071 | 18850
2015-11-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-06 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-07 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-08 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-09 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-10 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-11 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-12 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-13 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071
2015-11-15 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 | 2015-071
2015-11-16 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075
2015-11-17 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075
2015-11-18 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075
2015-11-19 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075
2015-11-20 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075
2015-11-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075 | 15950
2015-11-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075
2015-11-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075
2015-11-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075
2015-11-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075
2015-11-26 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 | 2015-075
2015-11-27 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 | 2015-075
2015-11-28 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 | 2015-075
2015-11-29 | [5 empty] | 1100 |  | 200 | 0 | 1 |  | 150 | [13 empty] | 0 | 0 | 0 | 0 | 2015-075
2015-11-30 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 |  | 150 | [7 empty] | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-075

## Freeport Sheldon Bolduc
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Sheldon Bolduc | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
[29 empty] | 0 |  |  | 74950
2015-07-05 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051 | 16425
2015-07-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051 |  | 260km
2015-07-12 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-13 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051 |  | 580km
2015-07-14 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-15 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-16 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-17 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-18 |  | 425 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-19 |  | 426 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-20 |  | 427 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-21 |  | 428 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-22 |  | 429 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-23 |  | 430 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-24 |  | 431 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052 | 20200
2015-07-25 |  | 432 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-26 |  | 433 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-27 |  | 434 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-28 |  | 435 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-29 |  | 436 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-30 |  | 437 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-31 |  | 438 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  |  | 1625 | 81.25 | 1706.25 | 2015-052
2015-08-01 |  | 439 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-02 |  | 440 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 441 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-04 |  | 442 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  | 443 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  | 444 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 18575
2015-08-07 |  | 445 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-08 |  | 446 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-09 |  | 447 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 448 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-11 |  | 449 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  | 450 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  | 451 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  | 452 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  | 453 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 |  | 454 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  | 455 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054 | 19750
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 75 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1525 | 76.25 | 1601.25 | 2015-054 | Last day

## Freeport Paul Retzlaff
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Paul Retzlaff | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
219225
2015-18
2015-07-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 150 | 1775 | 88.75 | 1863.75 | 2015-051
2015-07-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-12 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051 | 13675
2015-07-13 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-14 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-15 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-16 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-17 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-18 |  | 425 |  | 1 |  | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-19 |  | 426 |  | 1 |  | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-20 |  | 427 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-21 |  | 428 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-22 |  | 429 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-23 |  | 430 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052 | 21650
2015-07-24 |  | 431 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-25 |  | 432 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-26 |  | 433 |  | 1 |  | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-27 |  | 434 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-28 |  | 435 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-29 |  | 436 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-30 |  | 437 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-31 |  | 438 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-08-01 |  | 439 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-02 |  | 440 |  | 1 |  | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 441 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-04 |  | 442 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  | 443 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  | 444 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-07 |  | 445 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 0
2015-08-08 |  | 446 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-09 |  | 447 |  | 1 |  | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 448 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-11 |  | 449 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  | 450 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  | 451 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  | 452 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  | 453 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 |  | 454 |  | 1 |  | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  | 455 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054 | 0
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-04 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-05 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-055 | 0
2015-09-06 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-07 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-08 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-09 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-055
2015-09-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 22 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1647 | 82.35 | 1729.35 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-16 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-19 |  |  |  |  | 1 | 1100 | 1 | 200 | 13 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1638 | 81.9 | 1719.9 | 2015-059
2015-09-20 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-059
2015-09-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059 | 0
2015-09-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 69 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1694 | 84.7 | 1778.7 | 2015-059
2015-09-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 41 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1666 | 83.3 | 1749.3 | 2015-059
2015-09-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 47 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1672 | 83.6 | 1755.6 | 2015-059
2015-09-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 13 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1638 | 81.9 | 1719.9 | 2015-059
2015-09-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-29 |  |  |  |  | 1 | 1100 | 1 | 200 | 77 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1702 | 85.1 | 1787.1 | 2015-059
2015-09-30 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-059
2015-10-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-06 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062 | 0
2015-10-07 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-08 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-09 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 0 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 8.75 | 183.75 | 2015-062
2015-10-10 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 0 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 8.75 | 183.75 | 2015-062
2015-10-11 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 0 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 8.75 | 183.75 | 2015-062
2015-10-12 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 0 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 8.75 | 183.75 | 2015-062
2015-10-13 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-16 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-17 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-18 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-19 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-20 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-21 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-22 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-23 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-24 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-25 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-26 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-27 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-28 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-29 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-30 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-10-31 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 | [5 empty] | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 0 |  | Move to CDH_II
2015-11-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 71 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1696 | 84.8 | 1780.8 | 2015-071
2015-11-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-06 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071 | 0
2015-11-07 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-08 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-09 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-10 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-11 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-12 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-13 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-16 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-17 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-18 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-19 |  |  |  |  | 1 | 1100 | 1 | 200 | 79 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1704 | 85.2 | 1789.2 | 2015-075
2015-11-20 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 34 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1659 | 82.95 | 1741.95 | 2015-075 | 0
2015-11-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-11-29 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 |  | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 8.75 | 183.75 | 2015-075
2015-11-30 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-075
2015-12-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-06 |  |  |  |  | 1 | 1100 | 1 | 200 | 15 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1640 | 82 | 1722 | 2015-081
2015-12-07 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081 | 24425
2015-12-08 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-09 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-10 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-11 |  |  |  |  | 1 | 1100 | 1 | 200 | 35 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1660 | 83 | 1743 | 2015-081
2015-12-12 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-13 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-081
2015-12-16 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-084
2015-12-17 |  |  |  |  | 1 | 1100 | 1 | 200 | 59 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1684 | 84.2 | 1768.2 | 2015-084
2015-12-18 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-084
2015-12-19 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-084 | 11409
2015-12-20 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-084
2015-12-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1625 | 81.25 | 1706.25 | 2015-084
2015-12-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 | 0 | 150 | [5 empty] | 175 | 175 | 150 | 175 | 175 | 175 | 175 | 175 | 175 | 1600 | 80 | 1680 | 2015-084

## Freeport - Jay Barks
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Jay Barks | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
62925
2015-07-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1775 | 88.75 | 1863.75 | 2015-052 | 13325
2015-07-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-25 |  | 432 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-26 |  | 433 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-27 |  | 434 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-28 |  | 435 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-29 |  | 436 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-30 |  | 437 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-31 |  | 438 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-08-01 |  | 439 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-02 |  | 440 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 441 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-04 |  | 442 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  | 443 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  | 444 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 21475
2015-08-07 |  | 445 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-08 |  | 446 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-09 |  | 447 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 448 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-11 |  | 449 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  | 450 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  | 451 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  | 452 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  | 453 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 |  | 454 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  | 455 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054 | 21650
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055 | 6475
2015-09-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 |  | 150 |  |  |  |  | 0 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 150 | 1600 | 80 | 1680 | 2015-055
2015-09-05 | [26 empty] | 0 | 0 | 0
Note on F49: sacookadmin: Demob

## Freeport - Blair Schweitzer
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Blair Schweitzer | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
111225
2015-07-13 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 150 | 1775 | 88.75 | 1863.75 | 2015-051
2015-07-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-051 | 5025
2015-07-16 | [8 empty] | 0 |  | 0 | [5 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-052
2015-07-17 | [8 empty] | 0 |  | 0 | [5 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-052
2015-07-18 | [8 empty] | 0 |  | 0 | [5 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-052
2015-07-19 | [8 empty] | 0 |  | 0 | [5 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-052
2015-07-20 | [8 empty] | 0 |  | 0 | [5 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-052
2015-07-21 | [8 empty] | 0 |  | 0 | [5 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-052
2015-07-22 | [8 empty] | 0 |  | 0 | [5 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-052
2015-07-23 | [8 empty] | 0 |  | 0 | [5 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-052 | 12950
2015-07-24 | [8 empty] | 0 |  | 0 | [5 empty] | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-052
2015-07-25 |  | 432 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-26 |  | 433 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-27 |  | 434 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-28 |  | 435 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-29 |  | 436 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-30 |  | 437 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-31 |  | 438 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-08-01 |  | 439 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-02 |  | 440 |  | 1 |  | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 441 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-04 |  | 442 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  | 443 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  | 444 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-07 |  | 445 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 21475
2015-08-08 |  | 446 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-09 |  | 447 |  | 1 |  | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 448 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-11 |  | 449 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  | 450 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  | 451 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  | 452 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  | 453 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 |  | 454 |  | 1 |  | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  | 455 |  | 1 | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054 | 21650
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-23 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-04 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055 |  |  | Day Off
2015-09-05 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-06 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055 | 15675
2015-09-07 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-08 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055 |  |  | Rain Day
2015-09-09 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055 |  |  | Rain Day
2015-09-10 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-13 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-16 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059 | 6650
2015-09-19 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059 |  |  | Last Day- Travel Home
2015-09-20 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 | 0 | 150 |  |  |  |  | 0 | 175 |  | 150 | [5 empty] | 150 | 1600 | 80 | 1680 | 2015-059
2015-10-27 | [5 empty] | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-065
2015-10-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-065
2015-10-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-065 | 6675
2015-10-30 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-065
2015-10-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-065
2015-11-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-04 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-05 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071 | 21125
2015-11-07 | [5 empty] | 1100 |  | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 | [7 empty] | 0 | 175 | 8.75 | 183.75 | 2015-071
2015-11-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-071
2015-11-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 | 0 | 150 | [5 empty] | 175 |  | 150 | [5 empty] | 0 | 1450 | 72.5 | 1522.5 | 2015-071

## Freeport - Monty Shannon
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Monty Shannon | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
138150
2015-06-30 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 150 | 1775 | 88.75 | 1863.75 | 2015-050 | 1775
2015-07-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-04 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-05 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 0 | 1 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051 | 18575
2015-07-12 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-13 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-14 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 175 | 8.75 | 183.75 | 2015-051
2015-07-15 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-16 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-17 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-18 |  | 425 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-19 |  | 426 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-20 |  | 427 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-21 |  | 428 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-22 |  | 429 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-23 |  | 430 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052 | 20200
2015-07-24 |  | 431 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-25 |  | 432 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-26 |  | 433 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-052
2015-07-27 |  | 434 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-28 |  | 435 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-29 |  | 436 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-30 |  | 437 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-31 |  | 438 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-08-01 |  | 439 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-02 |  | 440 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 441 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-04 |  | 442 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  | 443 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  | 444 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-07 |  | 445 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-08 |  | 446 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 21475
2015-08-09 |  | 447 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 448 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-11 |  | 449 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  | 450 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  | 451 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  | 452 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  | 453 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 |  | 454 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  | 455 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054 | 21650
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-04 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-05 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-06 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055 | 20025
2015-09-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-16 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 0 | [6 empty] | 175 | 8.75 | 183.75 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-20 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-059 | 21475
2015-09-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-29 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-30 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-10-01 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-02 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-04 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062 | 12975
2015-10-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-06 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-07 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-08 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 | 0 | 150 |  |  |  |  | 0 | 175 |  | 150 | [5 empty] | 150 | 1600 | 80 | 1680 | 2015-062
2015-10-09
2015-10-10
2015-10-11
2015-10-12
2015-10-13
2015-10-14
2015-10-15
2015-10-16
2015-10-17
2015-10-18
2015-10-19
2015-10-20
2015-10-21
2015-10-22
2015-10-23
2015-10-24
2015-10-25
2015-10-26
2015-10-27
2015-10-28
2015-10-29
2015-10-30
2015-10-31
2015-11-01
2015-11-02
2015-11-03
2015-11-04
2015-11-05
2015-11-06
2015-11-07
2015-11-08
2015-11-09
2015-11-10
2015-11-11
2015-11-12
2015-11-13
2015-11-14
2015-11-15
2015-11-16
2015-11-17
2015-11-18
2015-11-19
2015-11-20
2015-11-21
2015-11-22
2015-11-23
2015-11-24
2015-11-25
2015-11-26
2015-11-27
2015-11-28
2015-11-29
2015-11-30
2015-12-01
2015-12-02
2015-12-03
2015-12-04
2015-12-05
2015-12-06
2015-12-07
2015-12-08
2015-12-09
2015-12-10
2015-12-11
2015-12-12
2015-12-13
2015-12-14
2015-12-15
2015-12-16
2015-12-17
2015-12-18
2015-12-19
2015-12-20
2015-12-21
2015-12-22
2015-12-23
2015-12-24
2015-12-25
2015-12-26
2015-12-27
2015-12-28
2015-12-29
2015-12-30
2015-12-31

## Freeport - Blaine Yohemas
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Blain Yohemas | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
108275
2015-07-05 |  |  |  |  | 1 | 1100 | 1 | 200 | 150 | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 0 | 1 | 2015-18 |  | 150 | 1775 | 88.75 | 1863.75 | 2015-051
2015-07-06 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-07 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-08 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051 | 13150
2015-07-09 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-12 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 0 | 0 | 0 | 2015-051
2015-07-13 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 0 | 0 | 0 | 2015-051
2015-07-14 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | 2015-18 |  | 0 | 0 | 0 | 0 | 2015-051
2015-07-15 |  |  |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | 2015-18 |  | 0 | 1625 | 81.25 | 1706.25 | 2015-051
2015-07-16 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-17 |  |  |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-18 |  | 425 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-19 |  | 426 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-20 |  | 427 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-21 |  | 428 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-22 |  | 429 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052 | 5100
2015-07-23 |  | 430 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-24 |  | 431 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-25 |  | 432 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-26 |  | 433 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-27 |  | 434 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 | [5 empty] | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 0 | 0 | 0 | 2015-052
2015-07-28 |  | 435 |  | 1 |  | 1100 |  | 200 | 50 | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 50 | 225 | 11.25 | 236.25 | 2015-052
2015-07-29 |  | 436 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-30 |  | 437 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-31 |  | 438 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-08-01 |  | 439 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-02 |  | 440 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 441 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-04 |  | 442 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  | 443 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  | 444 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-07 |  | 445 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 21475
2015-08-08 |  | 446 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-09 |  | 447 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 448 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-11 |  | 449 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  | 450 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  | 451 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  | 452 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  | 453 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 |  | 454 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  | 455 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-18 |  | 456 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054 | 21650
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-04 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-05 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-06 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-07 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055 | 14225
2015-09-08 |  |  |  |  | 0 | 1100 | 0 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-09 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-10 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-13 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-16 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-17 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-20 |  |  |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 0 | [5 empty] | 0 | 175 | 8.75 | 183.75 | 2015-059
2015-09-21 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059 | 19675
2015-09-22 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-23 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-24 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-25 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-26 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-27 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-09-28 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-059
2015-10-08 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-09 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-10 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062 | 13000
2015-10-11 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-12 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-13 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
2015-10-14 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062 |  |  | CDH2
2015-10-15 |  |  |  |  | 1 | 1100 | 1 | 200 | 0 | 1 | 0 | 150 |  |  |  |  | 1 | 175 |  | 150 | [5 empty] | 0 | 1625 | 81.25 | 1706.25 | 2015-062
Move to CDH_II

## Freeport - Dave Charleson
Freeport
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Chief inspector | Rate | Dave Charleson | Rate | Truck | Rate | Km Charged | KM Rate | Quad | Rate | labour class | Rate | Quad | Rate | Sub | Rate | Labourer class | Freeport mark up | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-07-27 |  | 434 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-28 |  | 435 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052 |  | 65125
2015-07-29 |  | 436 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052 | 8125
2015-07-30 |  | 437 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-07-31 |  | 438 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-052
2015-08-01 |  | 439 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-02 |  | 440 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-03 |  | 441 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-04 |  | 442 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-05 |  | 443 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-06 |  | 444 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-07 |  | 445 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053 | 21475
2015-08-08 |  | 446 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-09 |  | 447 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-053
2015-08-10 |  | 448 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-11 |  | 449 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-12 |  | 450 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-13 |  | 451 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-14 |  | 452 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-15 |  | 453 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-053
2015-08-16 |  | 454 |  | 1 |  | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 2 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-17 |  | 455 |  | 1 | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 2 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-18 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-19 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-20 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-21 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 | [6 empty] | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-22 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-23 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 | [8 empty] | 175 | 8.75 | 183.75 | 2015-054 | 21650
2015-08-24 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-25 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-26 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-27 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-28 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-29 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-08-30 | [5 empty] | 1100 |  | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  |  |  | 1 | 1 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-054
2015-08-31 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-054
2015-09-01 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-02 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-03 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-04 | [16 empty] | 1 | 175 |  |  |  | 1 | 0 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-05 | [16 empty] | 1 | 175 |  |  |  | 1 | 0 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-06 | [16 empty] | 1 | 175 |  |  |  | 1 | 0 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-07 | [16 empty] | 1 | 175 |  |  |  | 1 | 0 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-08 | [16 empty] | 1 | 175 |  |  |  | 1 | 0 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055 | 13875
2015-09-09 | [16 empty] | 1 | 175 |  |  |  | 1 | 0 | #REF! |  | 0 | 175 | 8.75 | 183.75 | 2015-055
2015-09-10 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-11 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-12 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-13 | [17 empty] | 175 | [8 empty] | 0 | 0 | 0 | 2015-055
2015-09-14 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 |  |  |  |  | 1 | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1625 | 81.25 | 1706.25 | 2015-055
2015-09-15 |  |  |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 150 | [5 empty] | 175 |  | 150 |  | 1 | 1 | #REF! |  | 0 | 1450 | 72.5 | 1522.5 | 2015-055

## sacook RPA
sacook RPA
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Manpower | Office Admin | Rate | SUB | Rate SUB | km's over 200 | Rate | vehicle | Rate | Labourer class | Rate | Labourer class | Rate | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Office Supplies + 10% | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
May 1-31 | 3 | 0 | Shelley | 3 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 2400 | 2575 |  |  |  | 2575 | 128.75 | 2703.75 | 31052015RFS | Curtis Hansen | 216371.74
2015-06-01 | 1 | 0 | Shelley | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 975 | 48.75 | 1023.75 | 15062015RFS | Curtis Hansen
2015-06-02 | 1 | 0 | Shelley | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 975 | 48.75 | 1023.75 | 15062015RFS | Curtis Hansen
2015-06-03 | 1 | 0 | Shelley | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 975 | 48.75 | 1023.75 | 15062015RFS | Curtis Hansen
2015-06-04 | 1 | 0 | Shelley | 1 | 800 | 0 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 800 | 40 | 840 | 15062015RFS | Curtis Hansen
2015-06-07 |  |  | Shelley | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 15062015RFS | Curtis Hansen
2015-06-08 | 1 | 0 | Shelley | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 975 | 48.75 | 1023.75 | 15062015RFS | Curtis Hansen
2015-06-09 | 1 | 0 | Shelley | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 975 | 48.75 | 1023.75 | 15062015RFS | Curtis Hansen
2015-06-10 | 1 | 0 | Shelley | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 975 | 48.75 | 1023.75 | 15062015RFS | Curtis Hansen
2015-06-11 | 1 | 0 | Shelley | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 975 | 48.75 | 1023.75 | 15062015RFS | Curtis Hansen
2015-06-12 | 1 | 0 | Shelley | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 975 | 48.75 | 1023.75 | 15062015RFS | Curtis Hansen
2015-06-13 | 1 | 0 | Shelley | 0 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 175 | 8.75 | 183.75 | 15062015RFS | Curtis Hansen
2015-06-14 | 1 | 0 | Shelley and Martine | 1 | 800 | 2 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 800 | 975 |  |  |  | 1150 | 57.5 | 1207.5 | 15062015RFS | Curtis Hansen
2015-06-15 | 2 | 0 | Shelley and Martine | 2 | 800 | 2 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1600 | 1775 |  |  | 199.9 | 2149.9 | 107.495 | 2257.395 | 15062015RFS | Curtis Hansen
2015-06-16 | 1 | 0 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | 975 |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-17 | 1 | 0 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-18 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-19 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-20 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-21 |  |  | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 175 | 8.75 | 183.75 | 30062015RFS | Curtis Hansen
2015-06-22 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-23 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-24 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-25 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-26 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-27 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-28 |  |  | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 175 | 8.75 | 183.75 | 30062015RFS | Curtis Hansen
2015-06-29 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-06-30 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 30062015RFS | Curtis Hansen
2015-07-01 |  |  | Shelley/Martine | 2 | 800 | 2 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-02 |  |  | Shelley/Martine | 2 | 800 | 2 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-03 |  |  | Shelley/Martine | 2 | 800 | 2 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-04 |  |  | Shelley/Martine | 1 | 800 | 2 | 175 |  | 1 |  | 200 |  | 0 |  | 0 |  | 0 | 1176 | #VALUE! |  |  |  | 1150 | 57.5 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-05 |  |  | Shelley/Martine | 0 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 350 | 17.5 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-06 |  |  | Shelley/Martine | 1 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1150 | 57.5 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-07 |  |  | Shelley/Martine | 2 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1775 | 88.75 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-08 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-09 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-10 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-11 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-12 |  |  | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 175 | 8.75 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-13 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-14 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-15 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 2015-18 | 15072015RFS | Curtis Hansen
2015-07-16 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-17 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-18 |  | 425 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-19 |  | 426 | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 175 | 8.75 | 183.75 | 31072015RFS | Curtis Hansen
2015-07-20 |  | 427 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-21 |  | 428 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-22 |  | 429 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-23 |  | 430 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-24 |  | 431 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-25 |  | 432 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-26 |  | 433 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-27 |  | 434 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-28 |  | 435 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-29 |  | 436 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-30 |  | 437 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-07-31 |  | 438 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 31072015RFS | Curtis Hansen
2015-08-01 |  | 439 | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 975 | 48.75 | 1023.75 | 15082015RFS | Curtis Hansen
2015-08-02 |  | 440 | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 175 | 8.75 | 183.75 | 15082015RFS | Curtis Hansen
2015-08-03 |  | 441 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-04 |  | 442 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-05 |  | 443 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-06 |  | 444 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-07 |  | 445 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-08 |  | 446 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-09 |  | 447 |  |  | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | 0 |  |  |  | 350 | 17.5 | 367.5 | 15082015RFS | Curtis Hansen
2015-08-10 |  | 448 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-11 |  | 449 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-12 |  | 450 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-13 |  | 451 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-14 |  | 452 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1950 | 97.5 | 2047.5 | 15082015RFS | Curtis Hansen
2015-08-15 |  | 453 | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  | 398.84 | 2348.84 | 117.442 | 2466.282 | 15082015RFS | Curtis Hansen
2015-08-16 |  | 454 | Martine | 1 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 1150 | 57.5 | 1207.5 | 31082015RFS | Curtis Hansen
2015-08-17 |  | 455 | Martine/Lorraine/Shelley | 3 | 800 | 2 | 175 |  | 1 |  | 200 | [6 empty] | 1176 | #VALUE! |  |  |  | 2750 | 137.5 | 2887.5 | 31082015RFS | Curtis Hansen
2015-08-18 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-19 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-20 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-21 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-22 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-23 |  |  | Shelley and Martine |  | 800 | 3 | 175 |  | 1 |  | 200 | [11 empty] | 525 | 26.25 | 551.25 | 31082015RFS | Curtis Hansen
2015-08-24 |  |  | Shelley/Martine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-25 |  |  | Shelley/Martine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-26 |  |  | Shelley/Martine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-27 |  |  | Shelley/Martine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-28 |  |  | Shelley/Martine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-08-29 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 31082015RFS | Curtis Hansen
2015-08-30 |  |  | Martine/Lorraine |  | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 350 | 17.5 | 367.5 | 31082015RFS | Curtis Hansen
2015-08-31 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 31082015RFS | Curtis Hansen
2015-09-01 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-02 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-03 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-04 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-05 |  |  |  |  | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 175 | 8.75 | 183.75 | 15092015RFS | Curtis Hansen
2015-09-06 |  |  |  |  | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 175 | 8.75 | 183.75 | 15092015RFS | Curtis Hansen
2015-09-07 |  |  |  |  | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 350 | 17.5 | 367.5 | 15092015RFS | Curtis Hansen
2015-09-08 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-09 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-10 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-11 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-12 |  |  | Shelley/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-13 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-14 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-15 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15092015RFS | Curtis Hansen
2015-09-16 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-17 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-18 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-19 |  |  | Martine/Lorraine | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-20 |  |  | Martine/Tammy |  | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 350 | 17.5 | 367.5 | 30092015RFS | Curtis Hansen
2015-09-21 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-22 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-23 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-24 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-25 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-26 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-27 |  |  | Martine/Tammy |  | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 350 | 17.5 | 367.5 | 30092015RFS | Curtis Hansen
2015-09-28 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-29 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-09-30 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 30092015RFS | Curtis Hansen
2015-10-01 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-02 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-03 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-04 |  |  | Martine/Tammy | 0 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 350 | 17.5 | 367.5 | 15102015RFS | Curtis Hansen
2015-10-05 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-06 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-07 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-08 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-09 |  |  | Martine | 1 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1150 | 57.5 | 1207.5 | 15102015RFS | Curtis Hansen
2015-10-10 |  |  | Martine/Tammy | 0 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 350 | 17.5 | 367.5 | 15102015RFS | Curtis Hansen
2015-10-11 |  |  | Martine/Tammy | 0 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 350 | 17.5 | 367.5 | 15102015RFS | Curtis Hansen
2015-10-12 |  |  | Martine/Tammy | 0 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 350 | 17.5 | 367.5 | 15102015RFS | Curtis Hansen
2015-10-13 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-14 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-15 |  |  | Martine/Tammy | 2 | 800 | 2 | 175 |  | 1 |  | 200 | [11 empty] | 1950 | 97.5 | 2047.5 | 15102015RFS | Curtis Hansen
2015-10-16 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-17 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-18 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-19 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-20 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-21 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-22 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-23 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-24 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-25 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-26 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-27 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-28 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-29 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-30 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-10-31 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-01 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-02 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-03 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-04 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-05 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-06 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-07 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-08 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-09 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-10 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-11 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-12 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-13 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-14 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-15 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | CDH-II
2015-11-16 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-17 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-18 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-19 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-20 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-21 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-22 |  |  | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 175 | 8.75 | 183.75 | 30112015RFS
2015-11-23 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-24 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-25 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-26 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-27 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-28 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-11-29 |  |  | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 175 | 8.75 | 183.75 | 30112015RFS
2015-11-30 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 30112015RFS
2015-12-01 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 15122015RFS
2015-12-02 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 15122015RFS
2015-12-03 |  |  | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 175 | 8.75 | 183.75 | 15122015RFS
2015-12-04 |  |  | Martine | 1 | 800 | 1 | 175 | 156 | 1 | 1 | 200 | [11 empty] | 1331 | 66.55 | 1397.55 | 15122015RFS
2015-12-05 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 15122015RFS
2015-12-06 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 15122015RFS
2015-12-07 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 15122015RFS
2015-12-08 |  |  | Martine | 1 | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 975 | 48.75 | 1023.75 | 15122015RFS
2015-12-09 |  |  | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 175 | 8.75 | 183.75 | 15122015RFS
2015-12-10 |  |  | Martine |  | 800 | 1 | 175 |  | 1 |  | 200 | [11 empty] | 175 | 8.75 | 183.75 | 15122015RFS
2015-12-11 |  |  | Martine | 1 | 800 | 1 | 175 | 156 | 1 | 1 | 200 | [11 empty] | 1331 | 66.55 | 1397.55 | 15122015RFS
2015-12-12 |  |  | Martine | 1 | 800 |  | 175 | 686 | 1 | 1 | 200 | [11 empty] | 1686 | 84.3 | 1770.3 | 15122015RFS
2015-12-13 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | 15122015RFS
2015-12-14 |  |  | Martine | 1 | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 800 | 40 | 840 | 15122015RFS
2015-12-15 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | 15122015RFS
2015-12-16 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-17 |  |  | Martine | 1 | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 800 | 40 | 840 | 311220115RFS
2015-12-18 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-19 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-20 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-21 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-22 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-23 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-24 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-25 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-26 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-27 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-28 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-29 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-30 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2015-12-31 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0
2016-01-01 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-02 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-03 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-04 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-05 |  |  | Martine | 1 | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 800 | 40 | 840 | 15012016RFS
2016-01-06 |  |  | Martine | 1 | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 800 | 40 | 840 | 15012016RFS
2016-01-07 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-08 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-09 |  |  | Martine |  | 800 |  | 175 |  | 1 |  | 200 | [11 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-10 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-11 |  |  | Martine | 1 | 800 |  | 175 |  | 1 | [13 empty] | 800 | 40 | 840 | 15012016RFS
2016-01-12 |  |  | Martine | 1 | 800 |  | 175 |  | 1 | [13 empty] | 800 | 40 | 840 | 15012016RFS
2016-01-13 |  |  | Martine | 1 | 800 |  | 175 |  | 1 | [13 empty] | 800 | 40 | 840 | 15012016RFS
2016-01-14 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-15 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 15012016RFS
2016-01-16 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 31122016RFS
2016-01-17 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 31122016RFS
2016-01-18 |  |  | Martine | 1 | 800 |  | 175 |  | 1 | [13 empty] | 800 | 40 | 840 | 31122016RFS
2016-01-19 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 31122016RFS
2016-01-20 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 31122016RFS
2016-01-21 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 31122016RFS
2016-01-22 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 31122016RFS
2016-01-23 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 31122016RFS
2016-01-24 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 31122016RFS
2016-01-25 |  |  | Martine | 1 | 800 |  | 175 |  | 1 | [13 empty] | 800 | 40 | 840 | 31122016RFS
2016-01-26 |  |  | Martine |  | 800 |  | 175 |  | 1 | [13 empty] | 0 | 0 | 0 | 31122016RFS
0
0
0
0
0
0
0
Note on E108: sacookadmin: Shelley Demob
Note on G108: sacookadmin: Lorraine And Martine Sub

## RDM
RDM
Date | Straight Hours Charged (ea.) | Robert Meidinger | Rate | Truck | Rate | Sub | Rate | KM's over 200 | Rate | Quad | Rate | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-21 |  | 1 | 1100 | 1 | 200 | 1 | 175 | 150 | 1 |  | 150 | 1625 | 81.25 | 1706.25 | RDM0032 |  | 87775
2015-06-22 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0032
2015-06-23 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0032
2015-06-24 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0032
2015-06-25 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0032
2015-06-26 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0032
2015-06-27 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0032
2015-06-28 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0032
2015-06-29 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0032
2015-06-30 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0032
2015-07-01 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-02 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-03 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-04 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-05 | [5 empty] | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0033
2015-07-06 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-07 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-08 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-09 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-10 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-11 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-12 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0033
2015-07-13 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0033
2015-07-14 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-15 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0033
2015-07-16 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-17 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0034
2015-07-18 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0034
2015-07-19 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0034
2015-07-20 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-21 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-22 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-23 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034 | 18400
2015-07-24 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-25 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-26 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0034
2015-07-27 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-28 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-29 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-30 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-07-31 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0034
2015-08-01 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-02 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0035
2015-08-03 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-04 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-05 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-06 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-07 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-08 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-09 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0035
2015-08-10 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-11 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-12 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-13 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-14 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035
2015-08-15 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0035 |  | INVOICE#RDM0035 | 19525
2015-08-16 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0037
2015-08-17 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0037
2015-08-18 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0037
2015-08-19 |  |  | 1100 |  | 200 |  | 175 |  | 1 |  | 150 | 0 | 0 | 0 | RDM0037
2015-08-24 |  | 0 | 1100 |  | 200 |  | 175 |  | 1 |  | 150 | 0 | 0 | 0 | RDM0037
2015-08-25 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0037
2015-08-26 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0037
2015-08-27 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0037
2015-08-28 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0037
2015-08-29 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0037
2015-08-30 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | 175 | 8.75 | 183.75 | RDM0037
2015-08-31 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0037
2015-09-01 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0038
2015-09-02 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0038
2015-09-03 |  | 1 | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | 1475 | 73.75 | 1548.75 | RDM0038
2015-09-04 |  | 1 | 1100 | 1 | 200 |  | 175 | 150 | 1 |  | 150 | 1450 | 72.5 | 1522.5 | RDM0038 |  | Invoice RDM0038 6168.75
Note on C76: sacookadmin: DEMOB

## Scott Ferner
Ferner Safety Services
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Scott Ferner | Rate | Truck | Rate | Km over 200 | Rate | Sub | Rate | Labourer class | Rate | Labourer class | Rate | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
May 1-31 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 |  | 0 |  | 0 |  | 0 |  |  |  |  | 11250 | 562.5 | 11812.5 | 48 |  | 195250
2015-06-01 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1300 | 65 | 1365 | 49
2015-06-02 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1300 | 65 | 1365 | 49
2015-06-03 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1300 | 65 | 1365 | 49
2015-06-04 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1300 | 65 | 1365 | 49
2015-06-05 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 |  | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1300 | 65 | 1365 | 49
2015-06-06 |  |  | 1 | 1100 | 1 | 200 |  | 1 |  | 175 | [9 empty] | 0 | 1300 | 65 | 1365 | 49
2015-06-07 |  |  |  | 1100 |  | 200 |  | 1 | 1 | 175 | [9 empty] | 0 | 175 | 8.75 | 183.75 | 49
2015-06-08 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-09 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-10 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-11 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-12 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-13 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-14 | 0 |  |  | 1100 |  | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 175 | 8.75 | 183.75 | 49
2015-06-15 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-16 | 1 |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-17 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-18 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-19 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-20 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-21 |  |  |  | 1100 |  | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 175 | 8.75 | 183.75 | 49
2015-06-22 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-23 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-24 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-25 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-26 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | #REF! |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-27 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | 1476 |  |  | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-28 |  |  |  | 1100 |  | 200 |  | 1 | 1 | 175 |  | 0 |  | 0 |  | 0 | 1476 |  |  | 0 | 175 | 8.75 | 183.75 | 49
2015-06-29 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [9 empty] | 0 | 1475 | 73.75 | 1548.75 | 49
2015-06-30 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [9 empty] | 0 | 1475 | 73.75 | 1548.75 | 49
2015-07-01 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [9 empty] | 0 | 1475 | 73.75 | 1548.75 | 50
2015-07-02 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [9 empty] | 0 | 1475 | 73.75 | 1548.75 | 50
2015-07-03 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [9 empty] | 0 | 1475 | 73.75 | 1548.75 | 50
2015-07-04 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [9 empty] | 0 | 1475 | 73.75 | 1548.75 | 50
2015-07-05 | [8 empty] | 1 | 175 | [9 empty] | 0 | 175 | 8.75 | 183.75 | 50
2015-07-06 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-07 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-08 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-09 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-10 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-11 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-12 |  |  |  | 1100 |  | 200 |  | 1 | 1 | 175 | [10 empty] | 175 | 8.75 | 183.75 | 50
2015-07-13 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-14 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-15 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-16 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50 | 37225
2015-07-20 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-21 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-22 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-23 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-24 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-25 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-27 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-28 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-29 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-30 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-07-31 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 50
2015-08-01 |  | 427 |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 51
2015-08-02 |  | 427 |  | 1100 |  | 200 |  | 1 | 0 | 175 | [10 empty] | 0 | 0 | 0 | 51
2015-08-03 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-04 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-05 |  | 427 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-06 |  | 427 |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 51
2015-08-07 |  | 428 |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 51
2015-08-08 |  | 429 |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 51
2015-08-09 |  | 430 |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 51
2015-08-10 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-11 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-12 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-13 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-14 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-15 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-16 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-17 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-18 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-19 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-20 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-21 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-22 |  | 431 | 0 | 1100 | 0 | 200 |  | 1 | 0 | 175 | [10 empty] | 0 | 0 | 0 | 51
2015-08-23 |  | 431 | 0 | 1100 | 0 | 200 |  | 1 | 0 | 175 | [10 empty] | 0 | 0 | 0 | 51
2015-08-24 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-25 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-26 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-27 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-28 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-29 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51
2015-08-30 |  | 431 |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 51
2015-08-31 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 51 | 34072.5
2015-09-01 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-02 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-03 |  | 431 | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-08 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-09 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-10 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-11 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-12 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-13 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-14 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-15 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-16 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-17 |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 175 | [10 empty] | 0 | 0 | 0 | 52
2015-09-18 |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 175 | [10 empty] | 0 | 0 | 0 | 52
2015-09-19 |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 175 | [10 empty] | 0 | 0 | 0 | 52
2015-09-20 |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 175 | [10 empty] | 0 | 0 | 0 | 52
2015-09-21 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-22 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-23 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-24 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-25 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-26 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-27 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-28 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-29 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52
2015-09-30 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 52 | 34072.5
2015-10-01 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 53
2015-10-02 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 53
2015-10-03 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 53
2015-10-04 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 53
2015-10-05 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 53 |  |  | CDH-2
2015-10-06 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 53
2015-10-07 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 53
2015-10-08 |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 175 | [10 empty] | 0 | 0 | 0 |  |  |  | CDH2
2015-10-09 |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 53
2015-10-10 |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 53
2015-10-11 |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 53
2015-10-12 |  |  | 0 | 1100 | 0 | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 53
2015-10-13 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 53
2015-10-14 |  |  | 0 | 1100 | 0 | 200 |  | 1 | 0 | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II |  | \
2015-10-15 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-16 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-17 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-18 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-19 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-20 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-21 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-22 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-23 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-24 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-25 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-26 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-27 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-28 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-29 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-30 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-10-31 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-01 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-02 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-03 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-04 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-05 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-06 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-07 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-08 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-09 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 |  | CDH-II
2015-11-10 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-11 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-12 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-13 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-14 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-15 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 55
2015-11-16 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-17 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-18 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-19 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-20 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-21 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-22 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-23 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-24 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-25 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-26 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-27 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 55
2015-11-28 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0
2015-11-29 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0
2015-11-30 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0
2015-12-01 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0
2015-12-02 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0
2015-12-03 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0
2015-12-04 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0
2015-12-05 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0
2015-12-06 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0
2015-12-07 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 57
2015-12-08 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 57
2015-12-09 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 57
2015-12-10 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 57
2015-12-11 |  |  | 1 | 1100 | 1 | 200 |  | 1 | 1 | 175 | [10 empty] | 1475 | 73.75 | 1548.75 | 57
2015-12-12 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-13 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-14 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-15 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-16 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-17 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-18 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-19 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-20 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-21 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-22 |  |  | 0.5 | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 550 | 27.5 | 577.5 | 57
2015-12-23 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-24 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-25 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-26 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-27 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-28 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-29 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-30 |  |  |  | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 0 | 0 | 0 | 57
2015-12-31 |  |  | 0.5 | 1100 |  | 200 |  | 1 |  | 175 | [10 empty] | 550 | 27.5 | 577.5 | 57

## Ground Hound - Gary McIntyre
Ground hound
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Gary McIntyre | Labourer class | Rate | Truck | Rate | Sub | Rate | KM's over 200 | Rate | Quad | Rate | Labourer class | Rate | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (beforeGST)
2015-05-25 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 | 150 | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1625 | 81.25 | 1706.25 | 13 |  | 119300
2015-05-26 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 13
2015-05-27 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 13
2015-05-28 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 13
2015-05-29 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 13
2015-06-01 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-02 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-03 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-04 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-05 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-17 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-18 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-21 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-22 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-23 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-24 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-25 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-06-26 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 1548.75 | 14
2015-07-01 |  |  |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 175 | 8.75 | 2015-18 | 15
2015-07-02 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 2015-18 | 15
2015-07-03 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 2015-18 | 15
2015-07-04 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 1475 | 73.75 | 2015-18 | 15
2015-07-05 |  |  |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 |  | 0 |  | 0 | 1476 | 0 |  |  | 175 | 8.75 | 2015-18 | 15
2015-07-06 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 2015-18 | 15
2015-07-07 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 2015-18 | 15
2015-07-08 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 2015-18 | 15
2015-07-09 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 2015-18 | 15
2015-07-10 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 2015-18 | 15
2015-07-11 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 2015-18 | 15
2015-07-12 |  |  |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 2015-18 | 15
2015-07-13 |  |  |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 2015-18 | 15
2015-07-14 |  |  |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 2015-18 | 15
2015-07-15 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 2015-18 | 15 | 34025
2015-07-16 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-17 |  |  |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 15
2015-07-18 |  | 425 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 15
2015-07-19 |  | 426 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 15
2015-07-20 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-21 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-22 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-23 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-24 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-25 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-26 |  | 427 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 15
2015-07-27 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-28 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-29 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-30 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-07-31 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 15
2015-08-01 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-02 |  | 427 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 16
2015-08-03 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-04 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-05 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-06 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-07 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-08 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-09 |  | 427 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 16
2015-08-10 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-11 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-12 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-13 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-14 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-15 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-16 |  | 427 |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 16
2015-08-17 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-18 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-19 |  | 427 | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-20 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-21 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-22 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-23 |  |  | 0 |  | 1100 | 0 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 16
2015-08-24 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-25 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-26 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-27 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-28 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-29 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16
2015-08-30 |  |  |  |  | 1100 |  | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 16
2015-08-31 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 16 |  | Invoice#16
2015-09-01 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-09-02 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-09-03 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-09-20 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-09-21 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-09-22 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-09-23 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17 |  | Moving between RFS and CDH2
2015-09-24 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-09-25 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-09-27 |  |  | 0 |  | 1100 | 0 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 175 | 8.75 | 183.75 | 17
2015-09-29 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-09-30 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 17
2015-10-01 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 19
2015-10-02 |  |  | 1 |  | 1100 | 1 | 200 | 1 | 175 |  | 1 |  | 150 | [8 empty] | 1475 | 73.75 | 1548.75 | 19
2015-10-03 | [26 empty] | Moved to CDHII
2015-10-04
2015-10-05
2015-10-06
2015-10-07
2015-10-08
2015-10-09
2015-10-10
2015-10-11
2015-10-12
2015-10-13
2015-10-14
2015-10-15
2015-10-16

## Don Durda - Welding
Don Durda Welding LTD.
Date | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | DON DURDA | DAY RATE | Truck | Subsistence | Kms | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
RATES |  |  |  | 1100 | 200 | 1 | 1 | [8 empty] | 36050
2015-08-09 |  |  | 1 | 1 | 1 | 175 | 150 |  |  |  | 1625 | 81.25 | 1706.25 | 31
2015-08-10 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 31
2015-08-11 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 31
2015-08-12 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 31
2015-08-13 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 31
2015-08-14 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 31
2015-08-15 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 31
2015-08-16 |  |  | 0 | 0 | 0 | 175 |  |  |  |  | 175 | 8.75 | 183.75 | 32
2015-08-17 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-18 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-19 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-20 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-21 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-22 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-23 |  |  | 0 | 0 | 0 | 175 |  |  |  |  | 175 | 8.75 | 183.75 | 32
2015-08-24 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-25 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-26 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-27 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-28 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-29 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-08-30 | [5 empty] | 175 |  |  |  |  | 175 | 8.75 | 183.75 | 32
2015-08-31 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 32
2015-09-01 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 33
2015-09-02 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 33
2015-09-03 |  |  | 1 | 1 | 1 | 175 |  |  |  |  | 1475 | 73.75 | 1548.75 | 33
2015-09-04 |  |  | 1 | 1 | 1 |  | 150 |  |  |  | 1450 | 72.5 | 1522.5 | 33

## NorthStar
NorthStar
Date | LEM # | Manpower | hrs | Tri-drive hydrovac Day Rate $215 | Vac truck | rate | Tri-axle water truck | rate | Water truck hrs at No charge | Crew cab | Rate | Labour | Rate | Water | Rate | Misc equipment | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-08-06 | 28494 | 1 |  | 215 |  | 205 |  | 155 | 12 |  | 110 |  | 60 |  | 15 |  | 0 | 0 | 0 | 0 |  | 850360.14
2015-08-13 | 29350 | 1 |  | 215 |  | 205 |  | 155 | 12 |  | 110 |  | 60 |  | 15 |  | 0 | 0 | 0 | 0
2015-08-18 | 29325 | 1 |  | 215 |  | 205 |  | 155 | 12 |  | 110 |  | 60 |  | 15 |  | 0 | 0 | 0 | 0
2015-06-29 | 29653 | 2 | 12 | 215 |  | 205 |  | 155 |  | 1 | 110 | 13 | 60 |  | 15 |  | 3470 | 173.5 | 3643.5 | 12147
2015-06-29 | 29654 | 2 | 12 | 215 |  | 205 |  | 155 |  | 1 | 110 | 13 | 60 |  | 15 |  | 3470 | 173.5 | 3643.5 | 12147
2015-07-02 | 29655 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12147
2015-07-02 | 29656 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12147
2015-07-03 | 29657 | 2 | 12 | 215 |  | 205 |  | 155 |  | 1 | 110 | 13 | 60 |  | 15 |  | 3470 | 173.5 | 3643.5 | 12194
2015-07-03 | 29658 | 2 | 12 | 215 |  | 205 |  | 155 |  | 1 | 110 | 13 | 60 |  | 15 |  | 3470 | 173.5 | 3643.5 | 12194
2015-07-04 | 29659 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12194
2015-07-04 | 29660 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12194
2015-07-06 | 29661 | 2 | 12.5 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12.5 | 60 |  | 15 |  | 3547.5 | 177.375 | 3724.875 | 12194
2015-07-06 | 29662 | 2 | 12.5 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12.5 | 60 |  | 15 |  | 3547.5 | 177.375 | 3724.875 | 12194
2015-07-07 | 29663 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12194
2015-07-07 | 29664 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12194
2015-07-08 | 29665 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12194
2015-07-08 | 29666 | 1 | 0 | 215 |  | 205 | 8 | 155 |  |  | 110 | 0 | 60 |  | 15 |  | 1240 | 62 | 1302 | 12194
2015-07-08 | 29667 | 2 | 10 | 215 |  | 205 |  | 155 |  | 1 | 110 | 11 | 60 |  | 15 |  | 2920 | 146 | 3066 | 12194
2015-07-09 | 29668 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12194
2015-07-09 | 29669 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12194
2015-07-09 | 29670 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12194
2015-07-10 | 29671 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12266
2015-07-10 | 29672 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12266
2015-07-11 | 29673 | 1 |  | 215 |  | 205 | 11 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1705 | 85.25 | 1790.25 | 12266
2015-07-11 | 29674 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12266
2015-07-14 | 29776 | 2 |  | 215 | 8 | 205 |  | 155 |  | 1 | 110 | 9 | 60 |  | 15 |  | 2290 | 114.5 | 2404.5 | 12299
2015-07-14 | 29777 | 1 |  | 215 |  | 205 | 5 | 155 |  |  | 110 |  | 60 |  | 15 |  | 775 | 38.75 | 813.75 | 12299
2015-07-15 | 29778 | 2 |  | 215 | 11 | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12299
2015-07-15 | 29779 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12299
2015-07-19 | 29781 | 2 |  | 215 | 11 | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12299
2015-07-20 | 29782 | 2 | 6 | 215 | 5 | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3145 | 157.25 | 3302.25 | 12299
2015-07-20 | 29783 | 2 | 11 | 215 |  | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3195 | 159.75 | 3354.75 | 12299
2015-07-19 | 29780 | 2 |  | 215 | 11 | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12339
2015-07-21 | 29784 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12343
2015-07-21 | 29785 | 2 |  | 215 | 12 | 205 |  | 155 |  | 1 | 110 | 13 | 60 |  | 15 |  | 3350 | 167.5 | 3517.5 | 12360
2015-07-21 | 29786 | 2 | 6 | 215 | 6 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3300 | 165 | 3465 | 12360
2015-07-22 | 29787 | 2 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12360
2015-07-22 | 29788 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12360
2015-07-22 | 29789 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12360
2015-07-22 | 29790 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12360
2015-07-23 | 29791 | 1 |  | 215 |  | 205 | 10 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1660 | 83 | 1743 | 12360
2015-07-23 | 29792 | 2 | 4 | 215 | 7.5 | 205 |  | 155 |  |  | 110 | 12.5 | 60 |  | 15 |  | 3147.5 | 157.375 | 3304.875 | 12360
2015-07-23 | 29793 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12360
2015-07-23 | 29794 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12360
2015-07-24 | 29795 | 2 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12376
2015-07-24 | 29796 | 2 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12376
2015-07-24 | 29797 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12376
2015-07-24 | 29798 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12376
2015-07-24 | 29799 | 2 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12376
2015-07-25 | 21908 | 2 |  | 215 | 11 | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12376
2015-07-25 | 21909 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12376
2015-07-25 | 21910 | 2 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12376
2015-07-25 | 21911 | 2 | 6 | 215 | 5 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3035 | 151.75 | 3186.75 | 12376
2015-07-25 | 29800 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12376
2015-07-27 | 21912 | 2 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12416
2015-07-27 | 21913 | 2 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12416
2015-07-27 | 21914 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12416
2015-07-27 | 21915 | 2 |  | 215 | 11.5 | 205 |  | 155 |  |  | 110 | 12.5 | 60 |  | 15 |  | 3107.5 | 155.375 | 3262.875 | 12416
2015-07-27 | 21916 | 2 | 8 | 215 | 3 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3055 | 152.75 | 3207.75 | 12416
2015-07-28 | 21917 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12416
2015-07-28 | 21918 | 2 | 9 | 215 | 3 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3330 | 166.5 | 3496.5 | 12416
2015-07-28 | 21919 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12416
2015-07-28 | 21920 | 2 | 10.5 | 215 | 2.5 | 205 |  | 155 |  |  | 110 | 13.5 | 60 |  | 15 |  | 3580 | 179 | 3759 | 12416
2015-07-28 | 21922 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12416
2015-07-29 | 21924 | 2 |  | 215 | 12 | 205 |  | 155 |  | 1 | 110 | 13 | 60 |  | 15 |  | 3350 | 167.5 | 3517.5 | 12416
2015-07-29 | 21925 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12416
2015-07-29 | 29801 | 2 | 10 | 215 |  | 205 |  | 155 |  |  | 110 | 11 | 60 |  | 15 |  | 2810 | 140.5 | 2950.5 | 12416
2015-07-29 | 29802 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12416
2015-07-30 | 29803 | 2 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12416
2015-07-30 | 29804 | 2 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12416
2015-07-30 | 29805 | 2 | 8 | 215 | 3 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3055 | 152.75 | 3207.75 | 12416
2015-07-30 | 29806 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12416
2015-07-30 | 29807 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12416
2015-07-31 | 28484 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12416
2015-07-31 | 28485 | 1 |  | 215 |  | 205 | 9 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1395 | 69.75 | 1464.75 | 12416
2015-07-31 | 28487 | 2 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12416
2015-07-31 | 28489 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12416
2015-07-31 | 28490 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12416
2015-08-01 | 29808 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12416
2015-08-01 | 29809 | 2 | 10 | 215 | 1 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3075 | 153.75 | 3228.75 | 12416
2015-08-01 | 29810 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12416
2015-08-01 | 29811 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12416
2015-08-01 | 29812 | 1 |  | 215 |  | 205 | 11 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1705 | 85.25 | 1790.25 | 12416
2015-08-03 | 29813 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12502
2015-08-03 | 29814 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12502
2015-08-03 | 29815 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12502
2015-08-03 | 29816 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12502
2015-08-03 | 29817 | 2 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12502
2015-08-04 | 29818 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12502
2015-08-04 | 29819 | 1 |  | 215 |  | 205 | 6 | 155 |  |  | 110 |  | 60 |  | 15 |  | 930 | 46.5 | 976.5 | 12502
2015-08-04 | 29820 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12502
2015-08-04 | 29821 | 2 |  | 215 | 11.5 | 205 |  | 155 |  |  | 110 | 12.5 | 60 |  | 15 |  | 3107.5 | 155.375 | 3262.875 | 12502
2015-08-04 | 29822 | 2 | 4 | 215 |  | 205 |  | 155 |  |  | 110 | 4 | 60 |  | 15 |  | 1100 | 55 | 1155 | 12502
2015-08-05 | 28491 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12502
2015-08-05 | 28492 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12502
2015-08-05 | 29823 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12502
2015-08-05 | 29824 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12502
2015-08-05 | 29825 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12502
2015-08-06 | 28493 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12502
2015-08-06 | 28495 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12502
2015-08-06 | 28496 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12502
2015-08-06 | 28497 | 2 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12502
2015-08-06 | 28498 | 2 |  | 215 | 6 | 205 |  | 155 |  |  | 110 | 6 | 60 |  | 15 |  | 1590 | 79.5 | 1669.5 | 12502
2015-08-07 | 28499 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12503
2015-08-07 | 28500 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12503
2015-08-07 | 29326 | 2 | 7 | 215 | 4 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3045 | 152.25 | 3197.25 | 12503
2015-08-07 | 29327 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12503
2015-08-07 | 29328 | 2 |  | 215 | 11.5 | 205 |  | 155 |  |  | 110 | 12.5 | 60 |  | 15 |  | 3107.5 | 155.375 | 3262.875 | 12503
2015-08-08 | 29330 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12503
2015-08-08 | 29331 |  |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12503
2015-08-08 | 29332 |  | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12503
2015-08-08 | 29333 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12503
2015-08-08 | 29334 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12503
2015-08-10 | 29335 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12545
2015-08-10 | 29336 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12545
2015-08-10 | 29337 |  | 10.5 | 215 |  | 205 |  | 155 |  |  | 110 | 11.5 | 60 |  | 15 |  | 2947.5 | 147.375 | 3094.875 | 12545
2015-08-10 | 29338 |  |  | 215 | 9 | 205 |  | 155 |  |  | 110 | 10 | 60 |  | 15 |  | 2445 | 122.25 | 2567.25 | 12545
2015-08-10 | 29339 |  |  | 215 | 9 | 205 |  | 155 |  |  | 110 | 10 | 60 |  | 15 |  | 2445 | 122.25 | 2567.25 | 12545
2015-08-11 | 29340 | 1 |  | 215 |  | 205 | 12.5 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 2047.5 | 102.375 | 2149.875 | 12545
2015-08-11 | 29341 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12545
2015-08-11 | 29342 | 2 |  | 215 | 10 | 205 |  | 155 |  |  | 110 | 11 | 60 |  | 15 |  | 2710 | 135.5 | 2845.5 | 12545
2015-08-11 | 29343 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12545
2015-08-11 | 29344 | 2 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12545
2015-08-12 | 29345 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12545
2015-08-12 | 29346 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12545
2015-08-12 | 29347 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12545
2015-08-12 | 29348 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12545
2015-08-12 | 29349 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12545
2015-08-13 | 29301 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12574
2015-08-13 | 29302 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12574
2015-08-13 | 29303 | 2 |  | 215 | 11.5 | 205 |  | 155 |  |  | 110 | 12.5 | 60 |  | 15 |  | 3107.5 | 155.375 | 3262.875 | 12574
2015-08-13 | 29304 | 2 |  | 215 | 10 | 205 |  | 155 |  |  | 110 | 11 | 60 |  | 15 |  | 2710 | 135.5 | 2845.5 | 12574
2015-08-13 | 29305 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12574
2015-08-13 | 29306 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12574
2015-08-14 | 29307 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12574
2015-08-14 | 29308 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12574
2015-08-14 | 29309 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12574
2015-08-14 | 29310 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12574
2015-08-14 | 29311 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12574
2015-08-14 | 29312 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12574
2015-08-15 | 29313 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12639
2015-08-15 | 29314 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12639
2015-08-15 | 29315 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12639
2015-08-15 | 29316 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-15 | 29317 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-15 | 29318 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-17 | 29319 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12639
2015-08-17 | 29320 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12639
2015-08-17 | 29321 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-17 | 29322 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-17 | 29323 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-17 | 29324 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12639
2015-08-18 | 26726 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12639
2015-08-18 | 26727 | 2 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12639
2015-08-18 | 26728 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-18 | 26729 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-18 | 26730 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-18 | 26731 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-19 | 26732 |  |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12639
2015-08-19 | 26733 |  |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12639
2015-08-19 | 26735 |  |  | 215 | 13.5 | 205 |  | 155 |  |  | 110 | 14.5 | 60 |  | 15 |  | 3637.5 | 181.875 | 3819.375 | 12639
2015-08-19 | 26736 |  |  | 215 | 13.5 | 205 |  | 155 |  |  | 110 | 14.5 | 60 |  | 15 |  | 3637.5 | 181.875 | 3819.375 | 12639
2015-08-19 | 26737 |  |  | 215 | 13.5 | 205 |  | 155 |  |  | 110 | 14.5 | 60 |  | 15 |  | 3637.5 | 181.875 | 3819.375 | 12639
2015-08-19 | 26738 |  |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12639
2015-08-20 | 26739 |  |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12639
2015-08-20 | 26740 |  |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12639
2015-08-20 | 26741 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-20 | 26742 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-20 | 26743 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-21 | 26744 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12639
2015-08-21 | 26745 | 1 |  | 215 |  | 205 | 13 | 155 |  |  | 110 |  | 60 |  | 15 |  | 2015 | 100.75 | 2115.75 | 12639
2015-08-21 | 26746 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12639
2015-08-21 | 26747 | 2 |  | 215 | 10.5 | 205 |  | 155 |  |  | 110 | 11.5 | 60 |  | 15 |  | 2842.5 | 142.125 | 2984.625 | 12639
2015-08-21 | 26748 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12639
2015-08-22 | 26749 | 1 |  | 215 |  | 205 | 10 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1660 | 83 | 1743 | 12639
2015-08-22 | 26750 | 1 |  | 215 |  | 205 | 10 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1550 | 77.5 | 1627.5 | 12639
2015-08-22 | 29951 | 2 |  | 215 | 5 | 205 |  | 155 |  |  | 110 | 6 | 60 |  | 15 |  | 1385 | 69.25 | 1454.25 | 12639
2015-08-22 | 29952 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12639
2015-08-22 | 29953 | 2 |  | 215 | 9 | 205 |  | 155 |  |  | 110 | 10 | 60 |  | 15 |  | 2445 | 122.25 | 2567.25 | 12639
2015-08-24 | 29954 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12639
2015-08-24 | 29955 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12639
2015-08-24 | 29956 | 2 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12639
2015-08-24 | 29957 | 2 |  | 215 | 12.5 | 205 |  | 155 |  |  | 110 | 13.5 | 60 |  | 15 |  | 3372.5 | 168.625 | 3541.125 | 12639
2015-08-24 | 29958 | 2 | 2 | 215 | 5 | 205 |  | 155 |  |  | 110 | 7 | 60 |  | 15 |  | 1875 | 93.75 | 1968.75 | 12639
2015-08-25 | 29959 |  |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12699
2015-08-25 | 29960 |  |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12699
2015-08-25 | 29961 |  |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12699
2015-08-25 | 29962 |  | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12699
2015-08-25 | 29963 |  | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12699
2015-08-25 | 29964 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12699
2015-08-25 | 29973 |  |  | 215 | 4.5 | 205 |  | 155 |  |  | 110 | 4.5 | 60 |  | 15 |  | 1192.5 | 59.625 | 1252.125 | 12699
2015-08-26 | 29965 |  |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12699
2015-08-26 | 29966 |  |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12699
2015-08-26 | 29967 |  | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12699
2015-08-26 | 29968 |  |  | 215 | 12.5 | 205 |  | 155 |  |  | 110 | 13.5 | 60 |  | 15 |  | 3372.5 | 168.625 | 3541.125 | 12699
2015-08-27 | 29969 |  |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12699
2015-08-27 | 29970 |  |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12699
2015-08-27 | 29971 |  | 6 | 215 | 5 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3035 | 151.75 | 3186.75 | 12699
2015-08-27 | 29972 |  |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12699
2015-08-28 | 29876 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12699
2015-08-28 | 29877 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12699
2015-08-28 | 29878 | 1 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12699
2015-08-28 | 29879 | 2 |  | 215 | 10 | 205 |  | 155 |  |  | 110 | 11 | 60 |  | 15 |  | 2710 | 135.5 | 2845.5 | 12699
2015-08-28 | 29882 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12699
2015-08-28 | 29974 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12699
2015-08-28 | 29881 | 1 |  | 215 | 9 | 205 |  | 155 |  |  | 110 | 10 | 60 |  | 15 |  | 2445 | 122.25 | 2567.25 | 12739
2015-08-28 | 29975 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12739
2015-08-29 | 29883 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12739
2015-08-29 | 29884 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12739
2015-08-29 | 29885 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12739
2015-08-29 | 29886 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12739
2015-08-29 | 29887 | 1 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12739
2015-08-29 | 29888 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12739
2015-08-29 | 29889 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12739
2015-08-30 | 29890 | 2 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12739
2015-08-30 | 29891 | 2 |  | 215 | 8 | 205 |  | 155 |  |  | 110 | 9 | 60 |  | 15 |  | 2180 | 109 | 2289 | 12739
2015-08-31 | 29892 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12739
2015-08-31 | 29893 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12739
2015-08-31 | 29894 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12739
2015-08-31 | 29895 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12739
2015-08-31 | 29896 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12739
2015-08-31 | 29897 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12739
2015-08-31 | 29898 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12739
2015-08-30 | 30107 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12773
2015-09-01 | 30101 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12773
2015-09-01 | 30102 | 2 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12773
2015-09-01 | 30103 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12773
2015-09-01 | 30104 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12773
2015-09-01 | 30105 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12773
2015-09-01 | 30106 | 2 |  | 215 | 10 | 205 |  | 155 |  |  | 110 | 11 | 60 |  | 15 |  | 2710 | 135.5 | 2845.5 | 12773
2015-09-02 | 27526 |  |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12773
2015-09-02 | 27527 |  |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12773
2015-09-02 | 27530 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12773
2015-09-02 | 27531 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12773
2015-09-02 | 27532 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12773
2015-09-02 | 27533 |  |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12773
2015-09-02 | 27529 |  |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12816
2015-09-03 | 27534 | 1 |  | 215 |  | 205 | 12 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1970 | 98.5 | 2068.5 | 12816
2015-09-03 | 27535 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12816
2015-09-03 | 27536 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12816
2015-09-03 | 27537 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12816
2015-09-03 | 27538 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12816
2015-09-03 | 27539 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12816
2015-09-03 | 27540 | 2 |  | 215 | 11 | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 2975 | 148.75 | 3123.75 | 12816
2015-09-04 | 27541 | 1 |  | 215 |  | 205 | 13.5 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 2202.5 | 110.125 | 2312.625 | 12816
2015-09-04 | 27542 | 2 |  | 215 | 11.5 | 205 |  | 155 |  |  | 110 | 12.5 | 60 |  | 15 |  | 3107.5 | 155.375 | 3262.875 | 12816
2015-09-04 | 27543 | 2 |  | 215 | 12.5 | 205 |  | 155 |  |  | 110 | 13.5 | 60 |  | 15 |  | 3372.5 | 168.625 | 3541.125 | 12816
2015-09-05 | 27544 | 1 |  | 215 |  | 205 | 14 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 2280 | 114 | 2394 | 12816
2015-09-05 | 27545 | 2 |  | 215 | 15 | 205 |  | 155 |  |  | 110 | 16 | 60 |  | 15 |  | 4035 | 201.75 | 4236.75 | 12816
2015-09-05 | 27546 | 2 |  | 215 | 15 | 205 |  | 155 |  |  | 110 | 16 | 60 |  | 15 |  | 4035 | 201.75 | 4236.75 | 12816
2015-09-05 | 27547 | 2 |  | 215 | 15 | 205 |  | 155 |  |  | 110 | 16 | 60 |  | 15 |  | 4035 | 201.75 | 4236.75 | 12816
2015-09-08 | 27548 | 1 |  | 215 |  | 205 | 9 | 155 |  | 1 | 110 |  | 60 | 45 | 15 |  | 2180 | 109 | 2289 | 12816
2015-09-08 | 27549 | 2 |  | 215 | 9 | 205 |  | 155 |  |  | 110 | 9 | 60 |  | 15 |  | 2385 | 119.25 | 2504.25 | 12816
2015-09-09 | 30326 | 1 |  | 215 |  | 205 | 13 | 155 |  | 1 | 110 |  | 60 | 60 | 15 |  | 3025 | 151.25 | 3176.25 | 12816
2015-09-09 | 30327 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12816
2015-09-10 | 30328 | 2 |  | 215 | 4 | 205 |  | 155 |  |  | 110 | 4 | 60 |  | 15 |  | 1060 | 53 | 1113 | 12826
2015-09-10 | 30329 | 1 |  | 215 |  | 205 | 13 | 155 |  |  | 110 |  | 60 | 96 | 15 |  | 3455 | 172.75 | 3627.75 | 12826
2015-09-10 | 30330 | 2 |  | 215 | 12 | 205 |  | 155 |  | 1 | 110 | 13 | 60 |  | 15 |  | 3350 | 167.5 | 3517.5 | 12826
2015-09-11 | 30331 | 2 |  | 215 | 12 | 205 |  | 155 |  | 1 | 110 | 13 | 60 |  | 15 |  | 3350 | 167.5 | 3517.5 | 12826
2015-09-11 | 30332 | 1 |  | 215 |  | 205 | 13 | 155 |  |  | 110 |  | 60 |  | 15 |  | 2015 | 100.75 | 2115.75 | 12826
2015-09-13 | 30345 | 2 |  | 215 | 4.5 | 205 |  | 155 |  |  | 110 | 4.5 | 60 |  | 15 |  | 1192.5 | 59.625 | 1252.125 | 12868
2015-09-17 | 30344 | 1 |  | 215 |  | 205 | 13 | 155 |  |  | 110 |  | 60 |  | 15 |  | 2015 | 100.75 | 2115.75 | 12868
2015-09-17 | 30346 | 2 |  | 215 | 12 | 205 |  | 155 |  | 1 | 110 | 13 | 60 |  | 15 |  | 3350 | 167.5 | 3517.5 | 12868
2015-09-17 | 30347 | 2 | 9 | 215 |  | 205 |  | 155 |  |  | 110 | 10 | 60 |  | 15 |  | 2535 | 126.75 | 2661.75 | 12868
2015-09-18 | 30348 | 1 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12868
2015-09-18 | 30349 | 1 |  | 215 |  | 205 | 13 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 2125 | 106.25 | 2231.25 | 12868
2015-09-18 | 30350 | 1 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12868
2015-09-18 | 29977 | 1 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12868
2015-09-19 | 29979 | 1 |  | 215 |  | 205 | 13 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 2125 | 106.25 | 2231.25 | 12868
2015-09-19 | 29980 | 1 | 11 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12868
2015-09-20 | 29981 | 1 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12868
2015-09-20 | 29982 | 1 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12868
2015-09-20 | 29983 | 1 |  | 215 |  | 205 | 13 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 2125 | 106.25 | 2231.25 | 12868
2015-09-20 | 29985 | 1 |  | 215 | 7.5 | 205 |  | 155 |  |  | 110 | 8.5 | 60 |  | 15 |  | 2047.5 | 102.375 | 2149.875 | 12868
2015-09-19 | 29978 | 1 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12950
2015-09-20 | 29984 | 1 |  | 215 | 7.5 | 205 |  | 155 |  |  | 110 | 8.5 | 60 |  | 15 |  | 2047.5 | 102.375 | 2149.875 | 12950
2015-09-21 | 29989 | 1 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12950
2015-09-21 | 29991 | 1 |  | 215 | 14 | 205 |  | 155 |  |  | 110 | 15 | 60 |  | 15 |  | 3770 | 188.5 | 3958.5 | 12950
2015-09-21 | 29990 | 1 |  | 215 | 14 | 205 |  | 155 |  |  | 110 | 15 | 60 |  | 15 |  | 3770 | 188.5 | 3958.5 | 12950
2015-09-21 | 29988 | 1 |  | 215 |  | 205 | 13 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 2125 | 106.25 | 2231.25 | 12950
2015-09-21 | 29987 | 1 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12950
2015-09-21 | 29986 | 1 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12950
2015-09-22 | 29992 | 1 |  | 215 |  | 205 | 11 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 1815 | 90.75 | 1905.75 | 12950
2015-09-22 | 29993 | 1 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12950
2015-09-22 | 29994 | 1 |  | 215 | 14 | 205 |  | 155 |  |  | 110 | 15 | 60 |  | 15 |  | 3770 | 188.5 | 3958.5 | 12950
2015-09-22 | 29995 | 1 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12950
2015-09-22 | 29996 | 1 |  | 215 | 12.5 | 205 |  | 155 |  |  | 110 | 13.5 | 60 |  | 15 |  | 3372.5 | 168.625 | 3541.125 | 12950
2015-09-22 | 29997 | 1 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12950
2015-09-22 | 29998 | 1 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12950
2015-09-23 | 29852 | 1 |  | 215 |  | 205 | 13 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 2125 | 106.25 | 2231.25 | 12950
2015-09-23 | 29853 | 1 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12950
2015-09-23 | 29854 | 1 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12950
2015-09-23 | 29855 | 1 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12950
2015-09-23 | 29856 | 1 |  | 215 | 13 | 205 |  | 155 |  |  | 110 | 14 | 60 |  | 15 |  | 3505 | 175.25 | 3680.25 | 12950
2015-09-23 | 29857 | 1 |  | 215 | 14.5 | 205 |  | 155 |  |  | 110 | 15.5 | 60 |  | 15 |  | 3902.5 | 195.125 | 4097.625 | 12950
2015-09-23 | 29858 | 1 |  | 215 | 4 | 205 |  | 155 |  |  | 110 | 4 | 60 |  | 15 |  | 1060 | 53 | 1113 | 12950
2015-09-24 | 29860 | 1 | 1 | 215 | 4 | 205 |  | 155 |  |  | 110 | 5 | 60 |  | 15 |  | 1335 | 66.75 | 1401.75 | 12950
2015-09-25 | 29865 | 1 | 13 | 215 |  | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3575 | 178.75 | 3753.75 | 12950
2015-09-26 | 29866 | 1 | 7.5 | 215 |  | 205 |  | 155 |  |  | 110 | 7.5 | 60 |  | 15 |  | 2062.5 | 103.125 | 2165.625 | 12950
2015-09-12 | 30333 | 1 |  | 215 |  | 205 | 13 | 155 |  | 1 | 110 |  | 60 | 48 | 15 |  | 2845 | 142.25 | 2987.25 | 12830 | invoice not received in the field
2015-09-12 | 30334 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12830 | invoice not received in the field
2015-09-12 | 30335 | 2 |  | 215 | 7.5 | 205 |  | 155 |  |  | 110 | 8.5 | 60 |  | 15 |  | 2047.5 | 102.375 | 2149.875 | 12830 | invoice not received in the field
2015-09-12 | 30336 | 2 | 6.5 | 215 |  | 205 |  | 155 |  |  | 110 | 7.5 | 60 |  | 15 |  | 1847.5 | 92.375 | 1939.875 | 12830 | invoice not received in the field
2015-09-12 | 30337 | 2 | 12 | 215 |  | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3360 | 168 | 3528 | 12830 | invoice not received in the field
2015-09-13 | 30338 | 2 |  | 215 | 12 | 205 |  | 155 |  |  | 110 | 13 | 60 |  | 15 |  | 3240 | 162 | 3402 | 12830 | invoice not received in the field
2015-09-13 | 30339 | 1 |  | 215 |  | 205 | 13 | 155 |  | 1 | 110 |  | 60 |  | 15 |  | 2125 | 106.25 | 2231.25 | 12830 | invoice not received in the field
2015-09-14 | 30340 | 1 |  | 215 |  | 205 | 12 | 155 |  |  | 110 |  | 60 |  | 15 |  | 1860 | 93 | 1953 | 12830 | invoice not received in the field
2015-09-14 | 30341 | 2 |  | 215 | 11 | 205 |  | 155 |  | 1 | 110 | 12 | 60 |  | 15 |  | 3085 | 154.25 | 3239.25 | 12830 | invoice not received in the field
2015-09-15 | 30342 | 2 | 6 | 215 |  | 205 |  | 155 |  |  | 110 | 6 | 60 |  | 15 |  | 1650 | 82.5 | 1732.5 | 12830 | invoice not received in the field
2015-09-16 | 30343 | 2 | 7 | 215 |  | 205 |  | 155 |  |  | 110 | 7 | 60 |  | 15 |  | 1925 | 96.25 | 2021.25 | 12830 | invoice not received in the field
2015-09-26 | 29867 | 1 | 7.5 | 215 |  | 205 |  | 155 |  |  | 110 | 7.5 | 60 |  | 15 |  | 2062.5 | 103.125 | 2165.625 | 13024 | invoice not received in the field
2015-09-28 | 29871 | 1 | 9.5 | 215 |  | 205 |  | 155 |  |  | 110 | 9.5 | 60 |  | 15 |  | 2612.5 | 130.625 | 2743.125 | 13024 | invoice not received in the field
2015-11-03 | 26721 | 2 | 12 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 | 16 | 15 |  | 3540 | 177 | 3717 | 13077 | invoice not received in the field
2015-11-03 | 30139 | 1 |  | 215 |  | 205 | 3 | 155 |  |  | 110 |  | 60 | 8 | 15 |  | 585 | 29.25 | 614.25 | 13077 | invoice not received in the field
2015-11-04 | 30176 |  |  | 215 |  | 205 |  | 155 |  |  | 110 |  | 60 |  | 15 | 1196.14 | 1196.14 | 59.807 | 1255.947 | 13395 | invoice not received in the field
2015-11-04 | 26722 | 2 | 12 | 215 |  | 205 |  | 155 |  |  | 110 | 12 | 60 | 8 | 15 |  | 3420 | 171 | 3591 | 13077 | invoice not received in the field
2015-11-05 | 26723 | 2 | 8 | 215 |  | 205 |  | 155 |  |  | 110 | 8 | 60 | 8 | 15 |  | 2320 | 116 | 2436 | 13395 | invoice not received in the field
2015-11-18 | 30061 | 2 | 8 | 215 |  | 205 |  | 155 |  |  | 110 | 8 | 60 | 8 | 15 |  | 2320 | 116 | 2436 | 13527 | invoice not received in the field
2015-12-02 | 31841 |  |  | 215 |  | 205 |  | 155 |  |  | 110 |  | 60 |  | 15 | 4794 | 4794 | 239.7 | 5033.7 | 13739
2015-12-04 | 31886 |  |  | 215 |  | 205 |  | 155 |  |  | 110 |  | 60 |  | 15 | Duplicate for 31841 | VOID | #VALUE! | #VALUE!
2016-01-19 | 30252 | 4 | 4 | 215 | 0.5 | 25 |  | 155 |  |  | 110 | 4 | 60 | 1 | 15 | 250 | 1377.5 | 68.875 | 1446.375
|  |  |  | 215 |  | 205 |  | 155 |  |  | 110 |  | 60 |  | 15 |  | 0 | 0 | 0
|  |  |  | 215 |  | 205 |  | 155 |  |  | 110 |  | 60 |  | 15 |  | 0 | 0 | 0
|  |  |  | 215 |  | 205 |  | 155 |  |  | 110 |  | 60 |  | 15 |  | 0 | 0 | 0
|  |  |  | 215 |  | 205 |  | 155 |  |  | 110 |  | 60 |  | 15 |  | 0 | 0 | 0
|  |  |  | 215 |  | 205 |  | 155 |  |  | 110 |  | 60 |  | 15 |  | 0 | 0 | 0
0
0
0
0
0
0
Note on J5: sacookadmin: Shannon Budgell - No Charge due to 4 hydro vac on site.
Note on J7: sacookadmin: No Charge due to 4 Hydrovacs.
Note on H103: sacookadmin: Steven Jackson - 12 hrs
Note on F104: sacookadmin: Bryne Jones - Operator - 12 hrs Mike Rawson - Helper - 12 hrs
Note on M104: sacookadmin: Mike Rawson - Helper - 12 hrs
Note on F105: Lorraine Dunbar: Brent Pelleboes - Operator - 12 hrs Tina Pelleboes - Helper - 12 hrs
Note on M105: Lorraine Dunbar: Tina Pelleboes - Helper - 12 hrs
Note on F106: Lorraine Dunbar: Toby Brooks - Operator - 12 hrs Jimmy Myers - Helper - 12 hrs
Note on M106: Lorraine Dunbar: Jimmy Myers - Helper - 12 hrs
Note on F107: Lorraine Dunbar: Shane Parker - Operator - 6 hrs Kyle Kruger - Helper - 6 hrs
Note on M107: Lorraine Dunbar: Kyle Kruger - Helper - 6 hrs
Note on H108: sacookadmin: Steven Jackson - 12 hrs
Note on H109: sacookadmin: Shannon Budgell - 12 hrs
Note on D110: Lorraine Dunbar: Toby Brooks - Operator - 12 hrs Jimmy Myers - Helper - 12 hrs
Note on F110: Lorraine Dunbar: Toby Brooks - Operator - 12 hrs Jimmy Myers - Helper - 12 hrs
Note on M110: Lorraine Dunbar: Toby Brooks - Operator - 12 hrs Jimmy Myers - Helper - 12 hrs
Note on F111: Lorraine Dunbar: Brent Pelleboes - Operator - 12 hrs Tina Pelleboes - Helper - 12 hrs
Note on M111: Lorraine Dunbar: Tina Pelleboes - Helper - 12 hrs
Note on F112: sacookadmin: Bryne Jones - Operator - 11.5 hrs Mike Rawson - Helper - 12.5 hrs
Note on M112: LDunbar: Mike Rawson - Helper - 12.5 hrs
Note on H113: sacookadmin: Steven Jackson - 12 hrs
Note on K113: sacookadmin: Steven Jackson - 1 Crew Van
Note on H114: sacookadmin: Shannon Budgell - 12 hrs
Note on D115: Lorraine Dunbar: Toby Brooks - Operator - 12 hrs Jimmy Myers - Helper - 12 hrs
Note on M115: Lorraine Dunbar: Jimmy Myers - Helper - 12 hrs
Note on F116: sacookadmin: Bryne Jones - Operator - 11 hrs Mike Rawson - Helper - 12 hrs
Note on M116: sacookadmin: Mike Rawson - Helper - 12 hrs
Note on F117: Lorraine Dunbar: Brent Pelleboes - Operator - 11 hrs Tina Pelleboes - Helper - 12 hrs
Note on M117: Lorraine Dunbar: Tina Pelleboes - Helper - 12 hrs
Note on F325: sacook000: Steamer

## OPUS
OPUS
Date | LEM # | Pipeline Tech | CAD Tech | Field Supervisor | 2 Man Survey Crew | one man survey crew | Additional Person | GIS Tech | Safety Officer | Subsistance | Project Manager | ATV | GPS | additional GPS | Vehicle | km | Total Hours Charged | Equipment Detail | Km's Charged | Invoicing coordinator | Professional surveyor | Misc. materials | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
|  | Per Hr | Per Hr | Per Hr | Per Hr | Per Hr | Per Hr | Per Hr | Per Hr | Per Day | Per Hr | Per Day | Per Day | Per Day | Per Hr | Per Km |  |  |  | Per Hr | Per hr
|  | 94.5 | 90 | 103.5 | 144 | 90 | 54 | 94.5 | 90 | 250 | 112.5 | 150 | 500 | 250 | 23 | 1.1 | 0 | 0 | 0 | 67.5 | 135 | 1
2015-06-11 | May 20 to May 30 |  | 0.5 |  |  |  |  | 30 |  |  | 25 | [5 empty] | 55.5 |  | 0 |  |  |  | 5692.5 | 284.625 | 5977.125 | 33041 |  | 1224133.505
2015-06-11 | June 1 to June 7 | 8 | 6 | 22 | 14 |  |  | 20.5 | 4 |  | 8.5 |  | 1 |  | 28 | 225 | 83 |  | 225 |  |  |  | 10234 | 511.7 | 10745.7 | 33041
2015-08-10 | May 20 to June 30 |  | 8.5 |  |  |  |  | 18 |  |  | 8 |  |  |  |  | 700 | [6 empty] | 4136 | 206.8 | 4342.8 | 33041
2015-05-24 | 10621 | [21 empty] | 494.75 | 24.7375 | 519.4875 | 33041 | soup and sandwich
2015-06-09 | 26367 | [21 empty] | 10399 | 519.95 | 10918.95 | 33041 | stake and lath
2015-06-09 | 28609518 | [21 empty] | 10 | 0.5 | 10.5 | 33041
2015-06-09 | 28611176 | [21 empty] | 10 | 0.5 | 10.5 | 33041
2015-06-08 | 1 |  |  | 12 | 21 |  |  |  | 4 |  |  | 0 | 2 |  | 33 | 84 | 37 |  | 84 |  |  |  | 6477.4 | 323.87 | 6801.27 | 33041 | Additioanl $630 added to LEM
2015-06-09 | 2-Revised |  | 8 | 11 | 23 | [6 empty] | 4 | 2 |  | 34 | [7 empty] | 7552.5 | 377.625 | 7930.125 | 33041
2015-06-10 | 3-Revised |  | 1 | 12 | 21 | [5 empty] | 3 | 4 | 2 |  | 33 | 0 | 37 |  | 0 |  |  |  | 7052.5 | 352.625 | 7405.125 | 33041 | Additional $90 added to LEM
2015-06-11 | 4 | 6 |  | 13 | 22.5 |  | 11.5 |  |  |  | 2 | 4 | 2 |  | 22.5 | 275 | 55 |  | 275 |  |  |  | 8418.5 | 420.925 | 8839.425 | 33041
2015-06-12 | 5 | 4 |  | 11 | 24 | [5 empty] | 2 | 4 | 2 |  | 35 |  | 41 |  | 0 |  |  |  | 7602.5 | 380.125 | 7982.625 | 33041
2015-06-13 | 6 |  |  | 12 | 20 | [5 empty] | 1 | 4 | 2 |  | 32 |  | 33 |  | 0 |  |  |  | 6570.5 | 328.525 | 6899.025 | 33041
2015-06-15 | 7 | 2 |  | 12 | 32 | [5 empty] | 2 | 4 | 2 |  | 44 |  | 48 |  | 0 |  |  |  | 8876 | 443.8 | 9319.8 | 33041
2015-06-16 | 8 | 2 |  | 11 | 33.5 | [5 empty] | 2 | 4 | 3 |  | 44.5 |  | 48.5 |  | 0 |  |  |  | 9500 | 475 | 9975 | 33041
2015-06-17 | 9 | 2 |  | 12 | 33.5 | [5 empty] | 1 | 4 | 3 |  | 45.5 |  | 48.5 |  | 0 |  |  |  | 9514 | 475.7 | 9989.7 | 33041 | Additional $135 added to LEM
2015-06-18 | 10 |  | 1 | 12 | 32.5 | 5 | [5 empty] | 6 | 3 |  | 44.5 | 110 | 50.5 |  | 110 |  |  |  | 10006.5 | 500.325 | 10506.825 | 33041
2015-06-19 | 11 |  |  | 11 | 22.5 | 12 | 5.5 |  |  |  |  | 4 | 2 |  | 45.5 |  | 51 |  | 0 |  |  |  | 8402 | 420.1 | 8822.1 | 33041 | Additional $425.25 added to LEM
2015-06-19 | 12 | 6 | [14 empty] | 6 |  | 0 |  |  |  | 567 | 28.35 | 595.35 | 33041
2015-06-20 | 13 |  |  | 12 | 26.5 | [6 empty] | 6 | 2 | 1 | 38.5 |  | 38.5 |  | 0 |  |  |  | 8093.5 | 404.675 | 8498.175 | 33041
2015-06-22 | 14 | 6 |  | 11 | 32 | [5 empty] | 8 | 6 | 2 | 2 | 43 | 440 | 57 |  | 440 |  |  |  | 11086.5 | 554.325 | 11640.825 | 33041
2015-06-23 | 15 | 8 | 5 | 11 | 30 |  |  | 0.5 |  |  | 2 | 6 | 2 | 1 | 41 |  | 56.5 |  | 230 |  |  |  | 10029.75 | 501.4875 | 10531.2375 | 33041 | Additional $519 added to LEM
2015-06-24 | 16 | 10 |  | 13 | 30.5 |  |  | 1 |  |  |  | 4 | 3 |  | 33.5 | 230 | 54.5 |  | 230 |  |  |  | 9900.5 | 495.025 | 10395.525 | 33041 | Additional $330 added to LEM
2015-06-25 | 17 | 9 |  | 12 | 34 | [5 empty] | 1 | 4 | 3 |  | 35 | 230 | 56 |  | 230 |  |  |  | 10259 | 512.95 | 10771.95 | 33041
2015-06-26 | 18 | 9 |  |  | 36 | [6 empty] | 6 | 3 |  | 36 |  | 45 |  | 0 |  |  |  | 9262.5 | 463.125 | 9725.625 | 33041 | Additional $567 added to LEM
2015-06-27 | 19 |  |  |  | 24.5 | [6 empty] | 6 | 2 | 1 | 24.5 |  | 24.5 |  | 0 |  |  |  | 6241.5 | 312.075 | 6553.575 | 33041
2015-06-29 | 20 | 11 | 0.5 | 12 | 33.5 | [5 empty] | 3 | 6 | 2 | 1 | 45.5 |  | 60 |  | 0 |  |  |  | 10684.5 | 534.225 | 11218.725 | 33041
2015-06-30 | 21 | 11 |  | 10 | 15 | [5 empty] | 1 |  |  | 3 | 15 | 283 | 37 |  | 283 |  |  |  | 5753.3 | 287.665 | 6040.965 | 33041
2015-07-01 | 22 | 6 |  | 6 |  | 12 | [9 empty] | 515 | 24 |  | 515 |  |  |  | 2834.5 | 141.725 | 2976.225 | 33272
2015-07-02 | 23 Revised | 3 |  | 13 | 33.5 |  |  | 6 |  |  | 6 | 6 | 2 | 1 | 35.5 | 280 | 61.5 |  | 280 |  |  |  | 10969.5 | 548.475 | 11517.975 | 33272
2015-07-03 | 24 Revised | 4 | 1.5 | 12 | 36 | [5 empty] | 2 | 4 | 2 | 1 | 24 | 450 | 55.5 |  | 450 |  |  |  | 10061 | 503.05 | 10564.05 | 33272
2015-07-04 | 25 | 2 |  | 12 | 30 | [6 empty] | 2 | 3 |  | 30 | 220 | 44 |  | 220 |  |  |  | 8483 | 424.15 | 8907.15 | 33272
2015-07-06 | 26 |  |  | 12 | 35.5 | [6 empty] | 4 | 2 | 1 | 47.5 |  | 47.5 |  | 0 |  |  |  | 9296.5 | 464.825 | 9761.325 | 33272
2015-07-07 | 27 Revised |  | 2 | 10 | 33.5 | [5 empty] | 2 | 4 | 2 | 1 | 43.5 |  | 47.5 |  | 0 |  |  |  | 9114.5 | 455.725 | 9570.225 | 33272
2015-07-08 | 28 |  | 2.5 | 11 | 34 | [6 empty] | 4 | 2 | 1 | 45 |  | 47.5 |  | 0 |  |  |  | 9144.5 | 457.225 | 9601.725 | 33272
2015-07-09 | 29 Revised |  | 5 | 13 | 35.5 |  |  | 5 |  |  | 2.5 | 4 | 3 |  | 48.5 |  | 61 |  | 0 | 0.5 |  |  | 10910.5 | 545.525 | 11456.025 | 33272
2015-07-10 | 30 Revised |  | 4 | 10 | 35 | [5 empty] | 2 | 5 | 3 |  | 45 |  | 51 |  | 0 | 2.5 |  |  | 10113.75 | 505.6875 | 10619.4375 | 33272
2015-07-11 | 31 |  |  | 11 | 32.5 | [6 empty] | 4 | 2 | 1 | 43.5 |  | 43.5 |  | 0 |  |  |  | 8669 | 433.45 | 9102.45 | 33272
2015-07-13 | 32 | 8 | 2 | [7 empty] | 3 | [5 empty] | 13 |  | 0 |  |  |  | 1273.5 | 63.675 | 1337.175 | 33272
2015-07-14 | 33 | 8 |  |  |  | 12 |  |  |  |  | 1 | [5 empty] | 21 |  | 0 |  |  |  | 1948.5 | 97.425 | 2045.925 | 33272
2015-07-15 | 34 |  | 0.5 | 8 | 35.5 | 12 |  |  |  |  | 1 | 2 | 3 |  | 55.5 |  | 57 |  | 0 |  |  |  | 10254 | 512.7 | 10766.7 | 33272
2015-07-16 | 35 |  |  | 10 | 17 | [5 empty] | 1.5 |  | 1 |  | 27 |  | 28.5 |  | 0 |  |  |  | 4772.75 | 238.6375 | 5011.3875 | 33272
2015-07-17 | 36 |  | 4.5 | [7 empty] | 1 | [5 empty] | 5.5 |  | 0 |  |  |  | 517.5 | 25.875 | 543.375 | 33272
2015-07-20 | 37 Revised | 4 | 5 |  | 23 | 12 |  |  |  |  | 1 | 4 | 2 |  | 23 | 260 | 45 |  | 260 |  |  |  | 7747.5 | 387.375 | 8134.875 | 33272
2015-07-21 | 38 Revised | 6 | 4.5 | 12 | 32 | [5 empty] | 2 | 2 | 1 |  | 34.5 | 200 | 56.5 |  | 200 |  |  |  | 8860.5 | 443.025 | 9303.525 | 33272
2015-07-22 | 39 Revised | 4 | 7 | 12 | 34 | [5 empty] | 2 | 2 | 2 |  | 46 |  | 59 |  | 0 |  |  |  | 9729 | 486.45 | 10215.45 | 33272
2015-07-23 | 40 | 6 | 5.5 | 12 | 33 | [5 empty] | 1 | 4 | 2 |  | 33 | 265 | 57.5 |  | 265 | 4 |  |  | 10089 | 504.45 | 10593.45 | 33272
2015-07-24 | 41 Revised | 3 | 4 | 10 | 36 | [5 empty] | 2 | 4 | 2 |  | 36 | 250 | 55 |  | 250 |  |  |  | 9790.5 | 489.525 | 10280.025 | 33272
2015-07-25 | 42 | 2 |  | 12 | 33.5 | [6 empty] | 4 | 2 |  | 33.5 | 265 | 47.5 |  | 265 |  |  |  | 8917 | 445.85 | 9362.85 | 33272
2015-07-26 | 43 Revised |  |  |  |  | 8 |  |  |  |  | 1.5 | [5 empty] | 9.5 |  | 0 |  |  |  | 888.75 | 44.4375 | 933.1875 | 33272
2015-07-27 | 44 Revised | 7 | 11 | 12 | 47 | 12 | [5 empty] | 7 | 3 |  | 59 | 258 | 89 |  | 258 | 2 |  |  | 15067.3 | 753.365 | 15820.665 | 33272
2015-07-28 | 45 Revised | 11 | 7.75 | 12 | 46.5 | 11 |  |  |  |  | 1 | 6 | 2 | 1 | 69.5 |  | 89.25 |  | 0 |  |  |  | 14526 | 726.3 | 15252.3 | 33272
2015-07-29 | 46 | 10 | 9.25 | 12 | 57 | [5 empty] | 1 | 6 | 2 | 1 | 57 | 293 | 89.25 |  | 293 |  |  |  | 15123.3 | 756.165 | 15879.465 | 33272
2015-07-30 | 47 | 10 | 3 | 11 | 46.5 | [5 empty] | 3 | 4 | 1 | 1 | 45.5 | 268 | 73.5 |  | 268 |  |  |  | 12078.3 | 603.915 | 12682.215 | 33272
2015-07-31 | 48 Revised | 4 |  | 10 | 31.5 | [5 empty] | 2 | 4 | 2 |  | 19.5 | 508 | 47.5 |  | 508 |  |  |  | 8781.3 | 439.065 | 9220.365 | 33272
2015-07-31 | ipads | [16 empty] | 2400 |  |  |  |  | 2400 | 120 | 2520 | 33272
2015-07-31 | Expenses | [16 empty] | 124 |  |  |  |  | 124 | 6.2 | 130.2 | 33272
2015-08-01 | 49 |  |  |  | 33 | [6 empty] | 4 | 2 |  | 12 | 513 | 33 |  | 513 |  |  |  | 7192.3 | 359.615 | 7551.915 | 33529
2015-08-02 | 50 |  |  |  |  | 21.5 | [10 empty] | 21.5 |  | 0 |  |  |  | 1935 | 96.75 | 2031.75 | 33529
2015-08-03 | 51 | 4 |  | 8 | 36 | [6 empty] | 2 | 2 |  | 24 | 508 | 48 |  | 508 |  |  |  | 8800.8 | 440.04 | 9240.84 | 33529
2015-08-04 | 52 | 12 | 2 | 12 | 36.5 | [5 empty] | 1 |  | 2 |  | 11.5 | 859 | 63.5 |  | 859 |  |  |  | 10133.9 | 506.695 | 10640.595 | 33529
2015-08-05 | 53 |  | 1 | 12 | 48.5 |  |  | 12 |  |  | 2.5 | 2 | 2 | 1 | 48 | 331 | 76 |  | 331 |  |  |  | 12749.35 | 637.4675 | 13386.8175 | 33529
2015-08-06 | 54 | 8 | 3 | 11 | 47.5 | [5 empty] | 1 | 2 | 3 |  | 58.5 |  | 70.5 |  | 0 |  |  |  | 12262.5 | 613.125 | 12875.625 | 33529
2015-08-07 | 55 |  | 3 | 12 | 44.5 |  |  | 6 |  |  |  | 2 | 2 | 1 | 44.5 | 286 | 65.5 |  | 286 |  |  |  | 11375.1 | 568.755 | 11943.855 | 33529
2015-08-08 | 56 | 5 |  | 11 | 45.5 | [7 empty] | 2 |  | 44.5 | 285 | 61.5 |  | 285 |  |  |  | 10500 | 525 | 11025 | 33529
2015-08-09 | 57 |  |  |  |  | 12 | [10 empty] | 12 |  | 0 |  |  |  | 1080 | 54 | 1134 | 33529
2015-08-10 | 58 | 18 | 1.5 | 12 | 45.5 |  |  |  |  | 1 | 6 | 2 | 2 |  | 24 | 1358 | 83 |  | 1358 | 0.25 |  |  | 13917.675 | 695.8837 | 14613.5588 | 33529
2015-08-11 | 59 | 12 | 4 | 14 | 37 |  |  |  |  | 1 |  |  | 2 |  | 39 | 595 | 67 |  | 595 | 4 |  |  | 11342.5 | 567.125 | 11909.625 | 33529
2015-08-12 | 60 | 12 |  | 12 | 51 |  |  | 8 |  |  | 5.5 | 2 | 2 |  | 37 | 1676 | 88.5 |  | 1676 | 2 |  |  | 15224.35 | 761.2175 | 15985.5675 | 33529
2015-08-13 | 61 | 8 | 6 | 12 | 36.5 | 12 |  | 4 |  |  | 12 | 2 | 2 |  | 35.5 | 1079 | 90.5 |  | 1079 |  |  |  | 13905.4 | 695.27 | 14600.67 | 33529
2015-08-14 | 62 | 9 |  | 11 | 33 | 16.5 | [5 empty] | 2 | 3 |  | 44 | 474 | 69.5 |  | 474 |  |  |  | 11559.4 | 577.97 | 12137.37 | 33529
2015-08-15 | 63 |  |  | 10 | 35 | 11 | [5 empty] | 1 | 3 |  | 46 | 230 | 56 |  | 230 |  |  |  | 10026 | 501.3 | 10527.3 | 33529
2015-08-16 | [16 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 33529
2015-08-17 | 64 | 22 |  | 12 | 48.5 | [7 empty] | 3 |  | 48 | 268 | 82.5 |  | 268 | 2 |  |  | 13338.8 | 666.94 | 14005.74 | 33529
2015-08-18 | 65 | 5 | 1 | 12 | 50 | [7 empty] | 3 |  | 49 | 277 | 68 |  | 277 |  |  |  | 11936.2 | 596.81 | 12533.01 | 33529
2015-08-19 | 66 | 10 | 5.5 | 12 | 38.5 | 24.5 |  |  | 1 |  |  |  | 3 | 1 | 64 | 262 | 91.5 |  | 262 | 0.25 |  |  | 14048.075 | 702.4038 | 14750.4788 | 33529
2015-08-20 | 67 |  |  | 13 | 46 | [6 empty] | 2 | 3 |  | 47 | 261 | 59 |  | 261 |  |  |  | 11137.6 | 556.88 | 11694.48 | 33529
2015-08-21 | 68 |  | 1 | 11 | 47.5 | [6 empty] | 2 | 3 |  | 58.5 | 0 | 59.5 |  | 0 |  |  |  | 11214 | 560.7 | 11774.7 | 33529
2015-08-22 | 69 |  |  |  | 23 | 21.5 | [6 empty] | 3 |  | 22.5 | 531 | 44.5 |  | 531 |  |  |  | 7848.6 | 392.43 | 8241.03 | 33529
2015-08-23 | 70 |  |  |  |  | 15 | [10 empty] | 15 |  | 0 |  |  |  | 1350 | 67.5 | 1417.5 | 33529
2015-08-24 | 71 | 10 | 0.5 | 12 | 46.5 | 10.5 | [5 empty] | 2 | 3 |  | 45.5 | 509 | 79.5 |  | 509 |  |  |  | 13279.4 | 663.97 | 13943.37 | 33529
2015-08-25 | 72 | 11 |  | 11.5 | 48.5 | 10 | [5 empty] | 2 | 1 | 3 | 59 | 263 | 81 |  | 263 |  |  |  | 13310.05 | 665.5025 | 13975.5525 | 33529
2015-08-26 | 73 | 11 |  | 13 | 47 | 8 | [6 empty] | 2 | 1 | 56 | 284 | 79 |  | 284 |  |  |  | 12723.4 | 636.17 | 13359.57 | 33529
2015-08-27 | 74 |  | 1.5 | 12 | 46 | [6 empty] | 2 | 2 | 1 | 58 |  | 59.5 |  | 0 |  |  |  | 10885 | 544.25 | 11429.25 | 33529
2015-08-28 | 75 |  | 2 | 12 | 49.5 |  |  | 8 |  |  |  | 1 | 3 |  | 61.5 |  | 71.5 |  | 0 |  |  |  | 12370.5 | 618.525 | 12989.025 | 33529
2015-08-29 | 76 |  |  | 5 | 46 |  |  | 12 |  |  |  | 2 | 2 | 1 | 46 | 175 | 63 |  | 175 |  |  |  | 11076 | 553.8 | 11629.8 | 33529
2015-08-30 | 77 |  |  |  |  | 10 | [10 empty] | 10 |  | 0 |  |  |  | 900 | 45 | 945 | 33529
2015-08-31 | 78 |  | 1 | 11 | 47 |  |  | 12 |  |  | 2 |  | 2 |  | 58 |  | 73 |  | 0 | 2.25 |  |  | 11841.375 | 592.0688 | 12433.4438 | 33529
2015-08-31 | iPads | [16 empty] | 2079.68 |  |  |  |  | 2079.68 | 103.984 | 2183.664 | 33529
2015-09-01 | 79 | 12 | 2.5 | 10 | 45 | [5 empty] | 4 |  | 3 |  | 45 | 265 | 73.5 |  | 265 |  |  |  | 12150.5 | 607.525 | 12758.025 | 33794
2015-09-02 | 80 | 8 | 1 | 12 | 33 | 10 |  |  |  |  | 5 |  | 3 |  | 35 | 475 | 69 |  | 475 |  |  |  | 11130 | 556.5 | 11686.5 | 33794
2015-09-03 | 81 | 10 |  | 12 | 35.5 | [5 empty] | 5 |  | 2 | 1 | 47.5 |  | 62.5 |  | 0 |  |  |  | 10204 | 510.2 | 10714.2 | 33794
2015-09-04 | 82 | 9 | [8 empty] | 5 | [5 empty] | 14 |  | 0 |  |  |  | 1413 | 70.65 | 1483.65 | 33794
2015-09-05 | 83 | 10 | [8 empty] | 8 | [5 empty] | 18 |  | 0 |  |  |  | 1845 | 92.25 | 1937.25 | 33794
2015-09-06 | 84 | 3 | [14 empty] | 3 |  | 0 |  |  |  | 283.5 | 14.175 | 297.675 | 33794
2015-09-07 | 85 | 6 | [14 empty] | 6 |  | 0 |  |  |  | 567 | 28.35 | 595.35 | 33794
2015-09-08 | 86 | 8 | [8 empty] | 2 | [5 empty] | 10 |  | 0 |  |  |  | 981 | 49.05 | 1030.05 | 33794
2015-09-09 | 87 | 2 | [14 empty] | 2 |  | 0 |  |  |  | 189 | 9.45 | 198.45 | 33794
2015-09-10 | 88 | 6 |  | 12 | 20.5 | [7 empty] | 2 |  | 32.5 |  | 38.5 |  | 0 |  |  |  | 6508.5 | 325.425 | 6833.925 | 33794
2015-09-11 | 89 | 11 |  | 10 | 44.5 | [7 empty] | 3 |  | 54.5 |  | 65.5 |  | 0 |  |  |  | 11236 | 561.8 | 11797.8 | 33794
2015-09-12 | 90 |  |  | 4 | 33 | [7 empty] | 3 |  | 33 | 160 | 37 |  | 160 |  |  |  | 7601 | 380.05 | 7981.05 | 33794
2015-09-13 | 91 |  |  | 6 | 31 | 10 | [6 empty] | 3 |  | 37 | 210 | 47 |  | 210 |  |  |  | 8567 | 428.35 | 8995.35 | 33794
2015-09-14 | 92 | 12 | 1 | 11 | 34 | 21.5 |  |  |  |  | 5 | 1 | 3 |  | 66.5 |  | 84.5 |  | 0 |  |  |  | 12935.5 | 646.775 | 13582.275 | 33794
2015-09-15 | 93 | 5 | 0.5 | 8 | 18 | [5 empty] | 3 |  | 1 | 2 | 8 | 435 | 34.5 |  | 435 |  |  |  | 5937.5 | 296.875 | 6234.375 | 33794
2015-09-16 | 94 | 12 | 0.5 | 8 | 11.5 | [5 empty] | 2 |  | 1 |  | 11.5 | 180 | 34 |  | 180 |  |  |  | 4850.5 | 242.525 | 5093.025 | 33794
2015-09-17 | 95 | 12 | 1 | 11 | 21.5 | 8 |  |  |  |  | 2 |  | 2 |  | 21.5 | 489 | 55.5 |  | 489 |  |  |  | 8435.9 | 421.795 | 8857.695 | 33794
2015-09-18 | 96 | 5 |  | 11 | 22.5 | [7 empty] | 2 |  | 22.5 | 250 | 38.5 |  | 250 |  |  |  | 6643.5 | 332.175 | 6975.675 | 33794
2015-09-19 | 97 | 8 |  | 12 | 36 | [7 empty] | 2 |  | 36 | 260 | 56 |  | 260 |  |  |  | 9296 | 464.8 | 9760.8 | 33794
2015-09-20 | [16 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 33794
2015-09-21 | 98 | 12 |  | 11 | 33.5 | 12 |  |  |  |  | 4 |  | 3 |  | 56.5 |  | 72.5 |  | 0 |  |  |  | 11426 | 571.3 | 11997.3 | 33794
2015-09-22 | 99 | 12 |  | 11 | 27.5 | 11 |  |  |  |  | 2 |  | 2 |  | 49.5 |  | 63.5 |  | 0 |  |  |  | 9586 | 479.3 | 10065.3 | 33794
2015-09-23 | 100 | 10 |  | 11 | 34 | [5 empty] | 2 |  | 2 |  | 34 | 240 | 57 |  | 240 |  |  |  | 9250.5 | 462.525 | 9713.025 | 33794
2015-09-24 | 101 | 9 |  | 6 | 34.5 | 11 |  |  |  |  | 1 | 2 | 2 | 1 | 45.5 | 180 | [6 empty] | 10336.5 | 516.825 | 10853.325 | 33794
2015-09-25 | 102 rev 1 | 11 |  | 10 | 37.5 | [5 empty] | 3 | 2 | 3 |  | 47.5 |  |  |  |  | 0.5 |  |  | 10738.25 | 536.9125 | 11275.1625 | 33794
2015-09-26 | 102 | 7 |  |  | 36.5 | [6 empty] | 2 | 2 | 1 | 36.5 | [7 empty] | 8307 | 415.35 | 8722.35 | 33794
2015-09-28 | 104 | 12 |  | 12 | 29.5 | [7 empty] | 3 |  | 35.5 | 220 |  |  | 220 | 0.25 |  |  | 9199.375 | 459.9688 | 9659.3438 | 33794
2015-09-29 | 105 | 14 |  | 12 | 21.5 | [7 empty] | 2 |  | 33.5 |  | 47.5 |  | 0 |  |  |  | 7431.5 | 371.575 | 7803.075 | 33794
2015-09-30 | 106 rev 1 | 10.5 |  | 12 | 22 | 11 |  |  |  |  | 2 |  | 2 |  | 45 |  | 57.5 |  | 0 |  |  |  | 8652.25 | 432.6125 | 9084.8625 | 33794
2015-09-30 | Ipads | [21 empty] | 1800 | 90 | 1890 | 33794
29352388 | registries | [21 empty] | 10 | 0.5 | 10.5 | 33794
2015-10-01 | 107 | 4 |  | 12 | 20 | 12 |  |  |  |  | 0.5 |  | 2 |  | 44 |  | 48.5 |  | 0 |  |  |  | 7648.25 | 382.4125 | 8030.6625 | 34210
2015-10-02 | 108 | 12 | 9 | 12 | 21 | 8 |  | 4 |  |  |  |  | 2 |  | 33 |  | 66 |  | 0 |  |  |  | 9067 | 453.35 | 9520.35 | 34210
2015-10-03 | 109 | 5 |  | 10.5 | 23.5 | 4 | [6 empty] | 2 |  | 34 |  | 43 |  | 0 |  |  |  | 7085.25 | 354.2625 | 7439.5125 | 34210
2015-10-04 | 110 | 7 |  | 6 | 11.5 | [7 empty] | 1 |  | 11.5 | 190 | 24.5 |  | 190 |  |  |  | 3912 | 195.6 | 4107.6 | 34210
2015-10-05 | 111 | 12 | 5 | 12 | 21 |  |  | 7 |  |  | 2 |  | 2 |  | 23 | 213 | 59 |  | 213 |  |  |  | 8499.8 | 424.99 | 8924.79 | 34210
2015-10-06 | 112 | 7 | 5 | 11.5 | 19.5 | [5 empty] | 2 |  | 2 |  | 31 |  | 45 |  | 0 |  |  |  | 7047.75 | 352.3875 | 7400.1375 | 34210
2015-10-07 | 113 | 12 | 5 | 11 | 23 | 12 |  |  |  |  | 2 |  | 2 |  | 35 | 260 | 65 |  | 260 |  |  |  | 9430.5 | 471.525 | 9902.025 | 34210
2015-10-08 | 114 | 10 | 1 | 10 |  | 12 |  | 8 |  |  | 3 |  |  |  | 22 |  | 44 |  | 0 | 5 |  |  | 5087 | 254.35 | 5341.35 | 34210
2015-10-09 | 115 | 7 | 9 | [7 empty] | 1 | [5 empty] | 17 |  | 0 |  |  |  | 1584 | 79.2 | 1663.2 | 34210
2015-10-10 | 116 | 2 | [14 empty] | 2 |  | 0 |  |  |  | 189 | 9.45 | 198.45 | 34210
2015-10-11 | 117 |  |  | 8 | 13 | [5 empty] | 5 |  |  |  | 4 | 449 | 26 |  | 449 |  |  |  | 3848.4 | 192.42 | 4040.82 | 34210
2015-10-12 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 34210
2015-10-13 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 34210
2015-10-14 | 118 | 2 | 1 | 12 | 11.5 | [5 empty] | 1 |  | 1 |  | 23.5 |  | 27.5 |  | 0 |  |  |  | 4330 | 216.5 | 4546.5 | 34210
2015-10-15 | 119 | 3 | 1.5 | 12 | 6 | [5 empty] | 2 |  |  | 1 |  | 389 | 24.5 |  | 389 | 2 |  |  | 3562.4 | 178.12 | 3740.52 | 34210
2015-10-16 | 120 | 6 |  |  | 6 | [5 empty] | 2 |  |  |  |  | 126 | 14 |  | 126 |  |  |  | 1794.6 | 89.73 | 1884.33 | 34210
2015-10-17 | 121 | 5.5 |  | 11 | 8 | 4 | [7 empty] | 1 | 23 |  | 28.5 |  | 0 |  |  |  | 3949.25 | 197.4625 | 4146.7125 | 34210
2015-10-18 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 34210
2015-10-19 | 122 | 8 | 4.5 | 11 | 10 | 14 |  | 0 |  |  | 1 |  | 1 |  | 35 |  | 48.5 |  | 0 |  |  |  | 6417 | 320.85 | 6737.85 | 34210
2015-10-20 | 123 | 8 |  | 11 | 11 | 11 |  |  | 2 |  | 2 |  | 1 |  | 33 |  | 45 |  | 0 |  |  |  | 6132.5 | 306.625 | 6439.125 | 34210
2015-10-21 | 124 | 6 |  | 10.5 | 1.5 | 23 |  |  |  |  | 3 |  |  |  | 21.5 | 352 | 44 |  | 352 |  |  |  | 5158.95 | 257.9475 | 5416.8975 | 34210
2015-10-22 | 125 | 4 |  | 6 | 10 | 22.5 | [6 empty] | 1 |  | 32.5 | 200 | 42.5 |  | 200 |  |  |  | 5931.5 | 296.575 | 6228.075 | 34210
2015-10-23 | 126 | 4 |  | 10 | 10 | 12 |  |  |  |  | 2 |  | 1 |  | 32 |  | 38 |  | 0 |  |  |  | 5394 | 269.7 | 5663.7 | 34210
2015-10-24 | 127 | 4 |  | 10.5 | 10 | 12 | [6 empty] | 1 |  | 32.5 |  | 36.5 |  | 0 |  |  |  | 5232.25 | 261.6125 | 5493.8625 | 34210
2015-10-25 | 128 |  |  | 5 |  | 9 | [6 empty] | 1 |  | 5 | 130 | 14 |  | 130 |  |  |  | 2085.5 | 104.275 | 2189.775 | 34210
2015-10-26 | 129 | 8 | 0.5 |  |  | 8 |  |  | 2.5 |  | 1 |  |  |  | 8 | 84 | 20 |  | 84 |  |  |  | 2134.9 | 106.745 | 2241.645 | 34210
2015-10-27 | 130 | 10 | 1 |  |  | 4 |  |  |  |  | 4 | [5 empty] | 19 |  | 0 |  |  |  | 1845 | 92.25 | 1937.25 | 34210
2015-10-28 | 131 | 8 | [8 empty] | 2 | [5 empty] | 10 |  | 0 | 7 |  |  | 1453.5 | 72.675 | 1526.175 | 34210
2015-10-29 | 132 | 8 | 2 |  |  | 4 |  |  |  |  | 3 |  |  |  | 4 |  | 17 |  | 0 | 2 |  |  | 1860.5 | 93.025 | 1953.525 | 34210
2015-10-30 | 133 | 8 |  |  | 10 | 6 |  |  |  |  | 0.5 |  | 1 |  | 16 |  | 24.5 |  | 0 |  |  |  | 3660.25 | 183.0125 | 3843.2625 | 34210
2015-10-31 | 134 |  |  | 2 | 10 | [7 empty] | 1 |  | 10 | 80 | 12 |  | 80 |  |  |  | 2465 | 123.25 | 2588.25 | 34210
October | Ipads | [21 empty] | 1800 |  |  | 34210
2015-11-01 | 135 |  |  |  | 4 | [10 empty] | 100 | 4 |  | 100 |  |  |  | 686 | 34.3 | 720.3 | 34605
2015-11-02 | 136 | 8 |  |  |  | 4 |  |  |  |  | 0.5 | [5 empty] | 12.5 |  | 0 |  |  |  | 1172.25 | 58.6125 | 1230.8625 | 34605
2015-11-03 | 137 | 4 |  |  | 11 | [7 empty] | 1 |  | 11 |  | 15 |  | 0 | 1 |  |  | 2782.5 | 139.125 | 2921.625 | 34605
2015-11-04 | 138 | 11 |  |  | 7 | [7 empty] | 1 |  | 2 | 120 | 18 |  | 120 | 1 |  |  | 2793 | 139.65 | 2932.65 | 34605
2015-11-05 | 139 | 12 | 2.5 | [7 empty] | 3 | [5 empty] | 17.5 |  | 0 |  |  |  | 1696.5 | 84.825 | 1781.325 | 34605
2015-11-06 | 140 | 4 |  |  | 10.5 | [7 empty] | 1 |  |  | 245 | 14.5 |  | 245 |  |  |  | 2659.5 | 132.975 | 2792.475 | 34605
2015-11-07 | 141 |  | 2 | [13 empty] | 2 |  | 0 |  |  |  | 180 | 9 | 189 | 34605
2015-11-08 | 142 | 7 | 1.5 |  |  |  |  | 7 |  |  | 0.5 | [5 empty] | 16 |  | 0 |  |  |  | 1514.25 | 75.7125 | 1589.9625 | 34605
2015-11-09 | 143 | 10 |  |  | 13 | [7 empty] | 1 |  | 1 | 273 | 23 |  | 273 |  |  |  | 3640.3 | 182.015 | 3822.315 | 34605
2015-11-10 | 144 | 11 |  |  | 8 | [5 empty] | 0.5 |  | 1 |  |  | 220 | 19.5 |  | 220 |  |  |  | 2989.75 | 149.4875 | 3139.2375 | 34605
2015-11-11 | 145 | 10 | 5.5 |  | 6 | [7 empty] | 1 |  |  | 210 | 21.5 |  | 210 |  |  |  | 3035 | 151.75 | 3186.75 | 34605
2015-11-12 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 34605
2015-11-13 | 146 | 7.5 | 10 | 10 | [6 empty] | 1 |  |  |  | 10 |  | 28.5 |  | 0 |  |  |  | 2986.25 | 149.3125 | 3135.5625 | 34605
2015-11-14 | 147 | 2 |  | 3 | [11 empty] | 160 | 5 |  | 160 |  |  |  | 675.5 | 33.775 | 709.275 | 34605
2015-11-15 | 148 |  | 10 | [13 empty] | 10 |  | 0 |  |  |  | 900 | 45 | 945 | 34605
2015-11-16 | 149 | 12 | 4.5 |  |  | 10 |  |  |  |  | 1 |  | 1 |  | 10 |  | 27.5 |  | 0 |  |  |  | 3281.5 | 164.075 | 3445.575 | 34605
2015-11-17 | 150 | 9 | 4.5 |  | 7 | [8 empty] | 1 | 7 |  | 20.5 |  | 0 |  |  |  | 2674.5 | 133.725 | 2808.225 | 34605
2015-11-18 | 151 | 12 |  |  | 11 | [7 empty] | 1 |  | 11 |  | 23 |  | 0 |  |  |  | 3471 | 173.55 | 3644.55 | 34605
2015-11-19 | 152 | 12.5 |  |  | 12 | [7 empty] | 1 |  | 12 |  | 24.5 |  | 0 |  |  |  | 3685.25 | 184.2625 | 3869.5125 | 34605
2015-11-20 | 153 | 12 |  |  | 10 | [7 empty] | 1 |  | 10 |  | 22 |  | 0 |  |  |  | 3304 | 165.2 | 3469.2 | 34605
2015-11-21 | 154 | 8 |  |  | 4 | [10 empty] | 100 | 12 |  | 100 |  |  |  | 1442 | 72.1 | 1514.1 | 34605
2015-11-22 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 34605
2015-11-23 | 155 | 11.5 |  | 10 | 9 | [5 empty] | 0.5 |  | 1 |  | 19 |  | 31 |  | 0 |  |  |  | 4411 | 220.55 | 4631.55 | 34605
2015-11-24 | 156 | 12 |  |  | 10 | [7 empty] | 1 |  |  | 235 | 22 |  | 235 |  |  |  | 3332.5 | 166.625 | 3499.125 | 34605
2015-11-25 | 157 | 12.5 | 2 |  | 10 | [5 empty] | 1 |  | 1 |  | 10 |  | 25.5 |  | 0 |  |  |  | 3643.75 | 182.1875 | 3825.9375 | 34605
2015-11-26 | 158 | 2 | 9 | 1.5 | 9 | [5 empty] | 2 |  | 1 |  | 1.5 | 198 | 23.5 |  | 198 | 2 |  |  | 3562.55 | 178.1275 | 3740.6775 | 34605
2015-11-27 | 159 |  | 8 | [7 empty] | 1 | [5 empty] | 9 |  | 0 |  |  |  | 832.5 | 41.625 | 874.125 | 34605
2015-11-28 | 160 |  | 8.5 | [13 empty] | 8.5 |  | 0 |  |  |  | 765 | 38.25 | 803.25 | 34605
2015-11-29 | 161 |  | 8 | [13 empty] | 8 |  | 0 |  |  |  | 720 | 36 | 756 | 34605
2015-11-30 | 162 | 5 | 15.5 |  | 12 | [5 empty] | 1 |  | 1 |  | 12 |  | 33.5 |  | 0 |  |  |  | 4484 | 224.2 | 4708.2 | 34605
switab | november | [21 empty] | 600 | 30 | 630 | 34605
2015-12-01 | 163 | 2 | 16.5 |  | 7 | [5 empty] | 1.5 |  | 1 |  | 7 |  | 27 |  | 0 | 7 |  |  | 3984.25 | 199.2125 | 4183.4625 | 34968
2015-12-02 | 164 | 2 | 11.5 |  | 6.5 | [5 empty] | 5 |  | 0.5 |  | 6.5 |  | 25 |  | 0 |  |  |  | 3122 | 156.1 | 3278.1 | 34968
2015-12-03 | 165 | 10 | 17.5 |  | 8 | [5 empty] | 1.5 |  | 1 |  |  | 220 | 37 |  | 220 |  |  |  | 4582.75 | 229.1375 | 4811.8875 | 34968
2015-12-04 | 166 | 3 | 12.5 |  | 4 | [9 empty] | 4 |  | 19.5 |  | 0 |  |  |  | 2076.5 | 103.825 | 2180.325 | 34968
2015-12-05 | 167 |  | 8 | [13 empty] | 8 |  | 0 |  |  |  | 720 | 36 | 756 | 34968
2015-12-06 | 168 | [9 empty] | 3.5 | [5 empty] | 3.5 |  | 0 |  |  |  | 393.75 | 19.6875 | 413.4375 | 34968
2015-12-07 | 169 |  | 8.5 |  | 8 | [5 empty] | 4 |  | 1 |  |  | 200 | 20.5 |  | 200 | 3 |  |  | 3289.5 | 164.475 | 3453.975 | 34968
2015-12-08 | 170 | 1.5 | 0.5 |  | 12 | [5 empty] | 1 |  | 1 |  | 12 |  | 15 |  | 0 |  |  |  | 2803.25 | 140.1625 | 2943.4125 | 34968
2015-12-09 | 171 | 2 | 6.5 | [7 empty] | 1 | [5 empty] | 9.5 |  | 0 |  |  |  | 886.5 | 44.325 | 930.825 | 34968
2015-12-10 | 172 |  | 6 | [7 empty] | 1 | [5 empty] | 7 |  | 0 |  |  |  | 652.5 | 32.625 | 685.125 | 34968
2015-12-11 | 173 | 7 |  |  |  | 4 | [6 empty] | 0.5 |  | 4 |  | 11 |  | 0 |  |  |  | 1363.5 | 68.175 | 1431.675 | 34968
2015-12-12 | 174 |  |  |  |  | 4 | [6 empty] | 0.5 |  | 4 |  | 4 |  | 0 |  |  |  | 702 | 35.1 | 737.1 | 34968
2015-12-13 | 175 |  |  | 5 | [12 empty] | 5 |  | 0 |  |  |  | 517.5 | 25.875 | 543.375 | 34968
2015-12-14 | 176 | 9 | [8 empty] | 1 | [5 empty] | 10 |  | 0 |  |  |  | 963 | 48.15 | 1011.15 | 34968
2015-12-15 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-16 | 177 |  | 10 | [13 empty] | 10 |  | 0 |  |  |  | 900 | 45 | 945 | 34968
2015-12-17 | 178 |  | 10.5 |  |  | 7 | [6 empty] | 1 |  | 3 |  | 17.5 |  | 0 |  |  |  | 2144 | 107.2 | 2251.2 | 34968
2015-12-18 | 179 | [15 empty] | 0 |  | 0 | 0.25 |  |  | 16.875 | 0.84375 | 17.7188 | 34968
2015-12-19 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-20 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-21 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-22 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-23 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-24 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-25 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-26 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-27 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-28 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-29 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-30 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
2015-12-31 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
Dec 18-15 | SWiTab | [21 empty] | 600 | 30 | 630 | 34968
2016-01-01 | none | [24 empty] | 35396
2016-01-02 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35396
2016-01-03 | 180 |  |  | 2 | [12 empty] | 2 |  | 0 |  |  |  | 207 | 10.35 | 217.35 | 35396
2016-01-04 | 181 |  | 9.5 |  | 10 | [6 empty] | 2 | 1 |  | 10 |  | 19.5 |  | 0 | 0.5 | 1.5 |  | 3561.25 | 178.0625 | 3739.3125 | 35396
2016-01-05 | 182 |  | 16.5 |  | 11 | [6 empty] | 2 | 1 |  | 11 |  | 27.5 |  | 0 |  | 1.5 | 105 | 4429.5 | 221.475 | 4650.975 | 35396
2016-01-06 | 183 |  | 12.5 |  | 10.5 | [5 empty] | 2 | 2 | 1 |  | 10.5 |  | 25 |  | 0 | 7 | 1.5 | 210 | 4788.5 | 239.425 | 5027.925 | 35396
2016-01-07 | 184 |  | 16.75 |  | 10.5 | [5 empty] | 2 | 2 | 1 |  | 10.5 |  | 29.25 |  | 0 |  | 1.5 | 75 | 4563.5 | 228.175 | 4791.675 | 35396
2016-01-08 | 185 |  | 9.25 | [13 empty] | 9.25 |  | 0 |  | 1 |  | 967.5 | 48.375 | 1015.875 | 35396
2016-01-09 | 186 |  | 6 | [13 empty] | 6 |  | 0 |  |  |  | 540 | 27 | 567 | 35396
2016-01-10 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35396
2016-01-11 | 187 |  | 21.25 | [13 empty] | 21.25 |  | 0 |  |  |  | 1912.5 | 95.625 | 2008.125 | 35396
2016-01-12 | 188 |  | 18.5 | [7 empty] | 1 | [5 empty] | 19.5 |  | 0 |  |  |  | 1777.5 | 88.875 | 1866.375 | 35396
2016-01-13 | 189 |  | 15.5 | [13 empty] | 15.5 |  | 0 |  | 1 |  | 1530 | 76.5 | 1606.5 | 35396
2016-01-14 | 190 |  | 24.5 | [7 empty] | 1 | [5 empty] | 25.5 |  | 0 |  | 1 |  | 2452.5 | 122.625 | 2575.125 | 35396
2016-01-15 | 191 |  | 11 | [13 empty] | 11 |  | 0 |  |  |  | 990 | 49.5 | 1039.5 | 35396
2016-01-16 | 192 |  | 8 | [13 empty] | 8 |  | 0 |  |  |  | 720 | 36 | 756 | 35396
2016-01-17 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35396
2016-01-18 | 193 | [9 empty] | 1 | [5 empty] | 1 |  | 0 |  |  |  | 112.5 | 5.625 | 118.125 | 35396
2016-01-19 | 194 |  | 5.5 | [13 empty] | 5.5 |  | 0 |  |  |  | 495 | 24.75 | 519.75 | 35396
2016-01-20 | 195 |  | 7 | [13 empty] | 7 |  | 0 |  |  |  | 630 | 31.5 | 661.5 | 35396
2016-01-21 | 196 |  | 1 | [7 empty] | 1 | [5 empty] | 2 |  | 0 |  |  |  | 202.5 | 10.125 | 212.625 | 35396
2016-01-22 | 197 | [9 empty] | 2 | [5 empty] | 2 |  | 0 |  |  |  | 225 | 11.25 | 236.25 | 35396
2016-01-23 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35396
2016-01-24 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35396
2016-01-25 | 198 |  | 0.5 | [7 empty] | 2 | [5 empty] | 2.5 |  | 0 |  |  |  | 270 | 13.5 | 283.5 | 35396
2016-01-26 | 199 |  | 2 | [7 empty] | 2 | [5 empty] | 4 |  | 0 |  |  |  | 405 | 20.25 | 425.25 | 35396
2016-01-27 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35396
2016-01-28 | 200 |  | 0.5 | [7 empty] | 1 | [5 empty] | 1.5 |  | 0 |  |  |  | 157.5 | 7.875 | 165.375 | 35396
2016-01-29 | 201 | [9 empty] | 1 | [5 empty] | 1 |  | 0 |  |  |  | 112.5 | 5.625 | 118.125 | 35396
2016-01-30 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35396
2016-01-31 | AB registeries | [15 empty] | 0 |  | 0 |  |  |  | 12.6 | 0.63 | 13.23 | 35396
2016-02-01 | 202 |  | 0.5 |  |  | 1 |  |  |  |  | 1 | [5 empty] | 2.5 |  | 0 |  |  |  | 247.5 | 12.375 | 259.875 | 35403
2016-02-02 | 203 |  | 1 |  | 8 | 0.5 | [6 empty] | 1 |  | 8 |  | 9.5 |  | 0 |  |  |  | 1971 | 98.55 | 2069.55 | 35403
2016-02-03 | 204 |  | 0.75 | [7 empty] | 1 | [5 empty] | 1.75 |  | 0 |  |  |  | 180 | 9 | 189 | 35403
2016-02-04 | 205 | [9 empty] | 1 | [5 empty] | 1 |  | 0 |  |  |  | 112.5 | 5.625 | 118.125 | 35403
2016-02-05 | 206 | [9 empty] | 1 | [5 empty] | 1 |  | 0 |  |  |  | 112.5 | 5.625 | 118.125 | 35403
2016-02-06 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-07 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-08 | 207 | [9 empty] | 0.5 | [5 empty] | 0.5 |  | 0 |  |  |  | 56.25 | 2.8125 | 59.0625 | 35403
2016-02-09 | 208 | [9 empty] | 5 | [5 empty] | 5 |  | 0 |  |  |  | 562.5 | 28.125 | 590.625 | 35403
2016-02-10 | 209 | [9 empty] | 3 | [5 empty] | 3 |  | 0 |  |  |  | 337.5 | 16.875 | 354.375 | 35403
2016-02-11 | 210 | [9 empty] | 1 | [5 empty] | 1 |  | 0 |  |  |  | 112.5 | 5.625 | 118.125 | 35403
2016-02-12 | 211 |  |  |  | 9.5 | [7 empty] | 1 |  | 9.5 |  | 9.5 |  | 0 |  |  |  | 2086.5 | 104.325 | 2190.825 | 35403
2016-02-13 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-14 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-15 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-16 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-17 | 212 | 5 | 0.75 | [13 empty] | 5.75 |  | 0 |  |  |  | 540 | 27 | 567 | 35403
2016-02-18 | 213 | 8 | [14 empty] | 8 |  | 0 |  | 2.5 |  | 1093.5 | 54.675 | 1148.175 | 35403
2016-02-19 | 214 | 8 |  |  | 8 | [7 empty] | 1 |  | 8 |  | 16 |  | 0 |  |  | 30 | 2622 | 131.1 | 2753.1 | 35403
2016-02-20 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-21 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-22 | 215 | 9.5 | [14 empty] | 9.5 |  | 0 |  |  |  | 897.75 | 44.8875 | 942.6375 | 35403
2016-02-23 | 216 | 9 | 3.25 | [13 empty] | 12.25 |  | 0 |  |  |  | 1143 | 57.15 | 1200.15 | 35403
2016-02-24 | 217 |  | 1.25 | [7 empty] | 1 | [5 empty] | 2.25 |  | 0 |  |  |  | 225 | 11.25 | 236.25 | 35403
2016-02-25 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-26 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-27 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-28 | none | [15 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 35403
2016-02-29 | 218 |  | 1.5 | [7 empty] | 2 | [5 empty] | 3.5 |  | 0 |  |  |  | 360 | 18 | 378 | 35403
2016-03-01 | [16 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
Note on B9: sacookadmin: LEM Date Aug 10th Charges for missed time during this time period.
Note on G65: sacookadmin: Jennifer Sprowl - 12 hrs @1 man Survey Crew Daniel Colby - 9.5 hrs @1 man Survey Crew
Note on C66: Lorraine Dunbar: Bryce Lybert - 4hrs LEM#51
Note on E66: sacookadmin: Matthew Nelson Supervisor - 8hrs
Note on F66: Lorraine Dunbar: Jennifer Sprowl & Layne Hunter 2 Man crew - 12 hrs Ben Carrol & Daniel Colby 2 Man survey crew - 12hrs John Groves & Scott Emerson 2 Man survey crew - 12hrs
Note on C67: Lorraine Dunbar: Bryce Lybert -12hrs LEM#52
Note on D67: sacookadmin: Scott McGaffin - 2 hrs
Note on E67: sacookadmin: Matthew Nelson - Survey Supervisor - 12 hrs - 280 kms
Note on F67: Lorraine Dunbar: Jennifer Sprowl & Layne Hunter 2 Man crew - 12 hrs - 299 km Ben Carrol & Daniel Colby 2 Man survey crew - 13 hrs - 280 km John Groves & Scott Emerson 2 Man survey crew - 11.5 hrs - 180 km
Note on D68: sacookadmin: Scott McGaffin - .5 hrs Scott McGaffin - .5 hrs
Note on E68: Lorraine Dunbar: Matthew Nelson - Survey Supervisor - 12 hrs - 210 kms
Note on F68: Lorraine Dunbar: Jennifer Sprowl & Layne Hunter 2 Man crew - 12.5 hrs - 331 km Ben Carrol & Daniel Colby 2 Man survey crew - 12 hrs - 240 km John Groves & Scott Emerson 2 Man survey crew - 12 hrs - 190 km Devin Nonay & Mark Kelly 2 Man survey crew - 12 hrs - 223 km
Note on I68: Lorraine Dunbar: Bryce Lybert - 12 hrs
Note on L68: sacookadmin: Dean Reiter - 2.5 hrs
Note on D70: sacookadmin: Scott McGaffin - 3 hrs
Note on E70: Lorraine Dunbar: Matthew Nelson - Survey Supervisor - 12 hrs - 240 kms
Note on F70: Lorraine Dunbar: Devin Nonay & Mark Kelly 2 Man Crew - 9.5 hrs Jennifer Sprowl & Layne Hunter 2 Man crew - 12 hrs Ben Carrol & Daniel Colby 2 Man survey crew - 12hrs John Groves & Scott Emerson 2 Man survey crew - 11hrs
Note on I70: Lorraine Dunbar: Bryce Lybert - 6 hrs
Note on P70: Lorraine Dunbar: Devin Nonay & Mark Kelly 2 Man Crew - 9.5 hrs Jennifer Sprowl & Layne Hunter 2 Man crew - 12 hrs Ben Carrol & Daniel Colby 2 Man survey crew - 12hrs John Groves & Scott Emerson 2 Man survey crew - 11hrs

## Jack Slack - Tyrone
Tyrone
Date | LEM # | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Manpower | Calgary office | Rate | Field assistant chief | Rate | KM | Rate | Truck | Rate | Labourer class | Rate | Sub | Rate | Quad | Rate | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
April 15-30 | 55J | 2 |  | Jack Slack | 2 | 1100 |  | 1300 |  | 1 |  | 200 |  | 0 |  | 175 |  | 150 |  | 0 | 1301 | 2200 |  |  | 2200 | 110 | 2310 | 55J |  | 72383
May 1-15 | 56J | 2 |  | Jack Slack | 2 | 1100 | 1 | 1300 | 389 | 1 | 1 | 200 |  | 1300 |  | 175 |  | 150 |  | 0 | 2601 | 2789 |  | 389 | 4089 | 204.45 | 4293.45 | 56J
2015-06-01 |  |  |  | Jack Slack |  | 1100 |  | 1300 |  | 1 |  | 200 |  | 1300 |  | 175 |  | 150 |  | 0 | 2601 | 0 |  | 0 | 0 | 0 | 0 | 58J
2015-06-02 |  |  |  | Jack Slack |  | 1100 |  | 1300 |  | 1 |  | 200 |  | 1300 |  | 175 |  | 150 |  | 0 | 2601 | 0 |  |  | 0 | 0 | 0 | 58J
2015-06-03 |  |  |  | Jack Slack |  | 1100 |  | 1300 |  | 1 |  | 200 |  | 1300 |  | 175 |  | 150 |  | 0 | 2601 | 0 |  |  | 0 | 0 | 0 | 58J
2015-06-04 |  |  |  | Jack Slack |  | 1100 |  | 1300 |  | 1 |  | 200 |  | 1300 |  | 175 |  | 150 |  | 0 | 2601 | 0 |  |  | 0 | 0 | 0 | 58J
2015-06-05 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 | 119 | 1 | 1 | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 494 |  |  | 1794 | 89.7 | 1883.7 | 58J
2015-06-06 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 375 |  |  | 1675 | 83.75 | 1758.75 | 58J
2015-06-07 |  |  |  | Jack Slack |  | 1100 |  | 1300 |  | 1 |  | 200 |  | 1300 |  | 175 |  | 150 |  | 0 | 2601 | 0 |  |  | 0 | 0 | 0 | 58J
2015-06-08 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 375 |  |  | 1675 | 83.75 | 1758.75 | 58J
2015-06-09 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 375 |  |  | 1675 | 83.75 | 1758.75 | 58J
2015-06-10 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 375 |  |  | 1675 | 83.75 | 1758.75 | 58J
2015-06-11 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 375 |  |  | 1675 | 83.75 | 1758.75 | 58J
2015-06-12 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 375 |  |  | 1675 | 83.75 | 1758.75 | 58J
2015-06-14 |  |  |  | Jack Slack |  | 1100 |  | 1300 |  | 1 |  | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 175 |  |  | 175 | 8.75 | 183.75 | 58J
2015-06-15 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-16 |  |  |  | Jack Slack |  | 1100 |  | 1300 |  | 1 |  | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 175 |  |  | 175 | 8.75 | 183.75
2015-06-17 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 1300 | 1 | 175 |  | 150 |  | 0 | 2601 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-18 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-19 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-20 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-21 |  |  |  | Jack Slack |  | 1100 |  | 1300 |  | 1 |  | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 175 |  |  | 175 | 8.75 | 183.75
2015-06-22 |  |  |  | Jack Slack | 1 | 1100 |  | 1300 |  | 1 |  | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 175 |  |  | 1275 | 63.75 | 1338.75
2015-06-23 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-24 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-25 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-27 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-28 |  |  |  | Jack Slack |  | 1100 |  | 1300 |  | 1 |  | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 175 |  |  | 175 | 8.75 | 183.75
2015-06-29 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  |  | 1675 | 83.75 | 1758.75
2015-06-30 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
[22 empty] | 0 |  | 2015-18
2015-07-01 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-02 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-03 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-04 |  |  |  | Jack Slack |  | 1100 | 1 | 1300 |  | 1 | 1 | 200 |  | 0 | 1 | 175 |  | 150 |  | 0 | 1301 | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-05 | [14 empty] | 1 | 175 |  | 150 |  | 0 | 0 | 175 |  | 2015-18 | 175 | 8.75 | 183.75
2015-07-06 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-07 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-08 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-09 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-10 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-11 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-12 | [7 empty] | 1300 |  | 1 |  | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 175 |  | 2015-18 | 175 | 8.75 | 183.75
2015-07-13 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-14 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-15 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  | 2015-18 | 1675 | 83.75 | 1758.75
2015-07-16 | [7 empty] | 1300 |  | 1 |  | 200 |  |  |  | 175 |  | 150 |  |  |  | 0 |  |  | 0 | 0 | 0
2015-07-17 | [7 empty] | 1300 |  | 1 |  | 200 |  |  |  | 175 |  | 150 |  |  |  | 0 |  |  | 0 | 0 | 0
2015-07-18 |  | 425 |  |  |  | 0 |  | 1300 |  | 1 |  | 200 |  |  |  | 175 |  | 150 |  |  |  | 0 |  |  | 0 | 0 | 0
2015-07-19 |  | 426 |  |  |  | 0 |  | 1300 |  | 1 |  | 200 |  |  |  | 175 |  | 150 |  |  |  | 0 |  |  | 0 | 0 | 0
2015-07-20 |  | 427 |  |  |  | 0 |  | 1300 |  | 1 |  | 200 |  |  |  | 175 |  | 150 |  |  |  | 0 |  |  | 0 | 0 | 0
2015-07-21 |  | 428 |  |  |  | 0 | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  |  | 1675 | 83.75 | 1758.75
2015-07-22 |  | 429 |  |  |  | 0 | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  |  | 1675 | 83.75 | 1758.75
2015-07-23 |  | 430 |  |  |  | 0 | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  |  | 1675 | 83.75 | 1758.75
2015-07-24 |  | 431 |  |  |  | 0 | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  |  | 1675 | 83.75 | 1758.75
2015-07-25 |  | 432 |  |  |  | 0 |  | 1300 |  | 1 |  | 200 |  |  |  | 175 |  | 150 |  |  |  | 0 |  |  | 0 | 0 | 0
2015-07-26 |  | 433 |  |  |  | 0 |  | 1300 |  | 1 |  | 200 |  |  |  | 175 |  | 150 |  |  |  | 0 |  |  | 0 | 0 | 0
2015-07-27 |  | 434 |  |  |  | 0 | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  |  | 1675 | 83.75 | 1758.75
2015-09-08 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  |  | 1675 | 83.75 | 1758.75
2015-09-09 | [6 empty] | 1 | 1300 |  | 1 | 1 | 200 |  |  | 1 | 175 |  | 150 |  |  |  | 375 |  |  | 1675 | 83.75 | 1758.75

## X-Calibur
X-Calibur
Date | LEM # | Straight Hours Charged (ea.) | Overtime Hours Charged (ea.) | Manpower | Locate crew hours | Rate | Quad | Rate | Side by side | Rate | Sub | Rate | Digital map | Rate | Labourer class | Rate | Labourer class | Rate | Labourer class | Rate | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-15 | 66960 |  |  | 2 | 4 | 182 |  | 138 |  | 276 | 2 | 161 |  | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | Locate crew |  | 1050 | 52.5 | 1102.5 | 27913 |  | 89327
2015-06-16 | 66962 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 |  | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | Locate crew and quad |  | 2782 | 139.1 | 2921.1 | 27913
2015-06-17 | 66966 |  |  | 2 | 4 | 182 | 2 | 138 |  | 276 | 2 | 161 |  | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | Locate crew |  | 1326 | 66.3 | 1392.3 | 27913
2015-06-17 | 66967 |  |  | 2 | 8 | 182 |  | 138 |  | 276 |  | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | Digital maps |  | 1540 | 77 | 1617 | 27913
2015-06-18 | 66968 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | locate crew and dig maps |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-19 | 66970 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 1 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | locate crew and dig map |  | 2824 | 141.2 | 2965.2 | 27913
2015-06-20 | 66971 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | locate crew and dig maps |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-21 | 66972 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 3 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | Locate crew and dig maps |  | 2908 | 145.4 | 3053.4 | 27913
2015-06-21 | 55726 |  |  | 2 | 4 | 182 |  | 138 |  | 276 | 2 | 161 |  | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | Travel - Steve Donovan |  | 1050 | 52.5 | 1102.5 | 27913
2015-06-22 | 66973 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Gandzalas & B.Holt |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-22 | 55727 |  |  | 2 | 12 | 182 |  | 138 | 1 | 276 | 2 | 161 | 1 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Donovan & B. Gibb |  | 2824 | 141.2 | 2965.2 | 27913
2015-06-23 | 66974 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Gandzalas & B.Holt |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-23 | 55728 |  |  | 2 | 12 | 182 |  | 138 | 1 | 276 | 2 | 161 | 3 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Donovan & B. Gibb |  | 2908 | 145.4 | 3053.4 | 27913
2015-06-24 | 50531 |  |  | 2 | 12 | 182 |  | 138 | 1 | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Donovan & B. Gibb |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-24 | 66975 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Gandzalas & B.Holt |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-25 | 50532 |  |  | 2 | 12 | 182 |  | 138 | 1 | 276 | 2 | 161 | 1 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Donovan & B. Gibb |  | 2824 | 141.2 | 2965.2 | 27913
2015-06-25 | 66701 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Gandzalas & B.Holt |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-26 | 66702 |  |  | 2 | 7 | 182 | 2 | 138 |  | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Gandzalas & B.Holt |  | 1956 | 97.8 | 2053.8 | 27913
2015-06-26 | 50533 |  |  | 2 | 12 | 182 |  | 138 | 1 | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Donovan & B. Gibb |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-27 | 55729 |  |  | 2 | 12 | 182 |  | 138 | 1 | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Donovan & B. Gibb |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-27 | 66704 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 3 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Gandzalas & B.Holt |  | 2908 | 145.4 | 3053.4 | 27913
2015-06-28 | 66705 |  |  | 2 |  | 182 |  | 138 |  | 276 | 2 | 161 |  | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Gandzalas & B.Holt |  | 322 | 16.1 | 338.1 | 27913
2015-06-28 | 55730 |  |  | 2 | 4 | 182 |  | 138 |  | 276 |  | 161 |  | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Donovan & B. Gibb |  | 728 | 36.4 | 764.4 | 27913
2015-06-29 | 66706 |  |  | 2 | 12 | 182 | 2 | 138 |  | 276 | 2 | 161 | 2 | 42 |  | 0 |  | 0 |  | 0 |  | 0 | 385 | 0 | S.Gandzalas & B.Holt |  | 2866 | 143.3 | 3009.3 | 27913
2015-06-30 | 66707 |  |  | 2 | 4 | 182 |  | 138 |  | 276 | 2 | 161 |  | 42 | [9 empty] | 0 | S.Gandzalas & B.Holt |  | 1050 | 52.5 | 1102.5 | 27913
2015-07-01 | 66709 |  |  | 2 | 4 | 182 |  | 138 |  | 276 | 2 | 161 |  | 42 | [10 empty] | S.Gandzalas & B.Holt |  | 1050 | 52.5 | 1102.5 | 28029
2015-07-02 | 66710 |  |  | 2 |  | 182 |  | 138 |  | 276 | 2 | 161 |  | 42 | [10 empty] | S.Gandzalas & B.Holt |  | 322 | 16.1 | 338.1 | 28029
2015-07-03 | 66711 |  |  | 2 | 12 | 182 |  | 138 |  | 276 | 2 | 161 | 1 | 42 | [10 empty] | S.Gandzalas & B.Holt |  | 2548 | 127.4 | 2675.4 | 28029
2015-07-04 | 66712 |  |  | 2 | 12 | 182 |  | 138 |  | 276 | 2 | 161 | 1 | 42 | [10 empty] | S.Gandzalas & B.Holt |  | 2548 | 127.4 | 2675.4 | 28029
2015-07-05 | 66713 |  |  | 2 | 12 | 182 |  | 138 |  | 276 | 2 | 161 | 1 | 42 | [10 empty] | S.Gandzalas & B.Holt |  | 2548 | 127.4 | 2675.4 | 28029
2015-07-06 | 66714 |  |  | 2 | 12 | 182 |  | 138 |  | 276 | 2 | 161 | 1 | 42 | [10 empty] | S.Gandzalas & B.Holt |  | 2548 | 127.4 | 2675.4 | 28029
2015-07-07 | 66715 |  |  | 2 | 12 | 182 |  | 138 |  | 276 | 2 | 161 | 2 | 42 | [10 empty] | S.Gandzalas & B.Holt |  | 2590 | 129.5 | 2719.5 | 28029
2015-07-08 | 66716 |  |  | 2 | 12 | 182 |  | 138 |  | 276 | 0 | 161 | 1 | 42 | [10 empty] | S.Gandzalas & B.Holt |  | 2226 | 111.3 | 2337.3 | 28029
2015-08-11 | 46503 |  |  | 2 | 5 | 182 |  | 138 |  | 276 |  | 161 | 1 | 42 | [10 empty] | Korry Loeden &G. Deford |  | 952 | 47.6 | 999.6 | 28169
2015-08-12 | 46504 |  |  | 2 | 9 | 182 |  | 138 |  | 276 |  | 161 | 1 | 42 | [10 empty] | Korry Loeden &G. Deford |  | 1680 | 84 | 1764 | 28185
2015-08-17 | 46505 |  |  | 2 | 6 | 182 |  | 138 |  | 276 |  | 161 | 1 | 42 | [10 empty] | Korry Loeden &G. Deford |  | 1134 | 56.7 | 1190.7 | 28249
2015-08-18 | 46506 |  |  | 2 | 7 | 182 |  | 138 |  | 276 |  | 161 | 1 | 42 | [10 empty] | Korry Loeden &G. Deford |  | 1316 | 65.8 | 1381.8 | 28249
2015-08-21 | 46508 |  |  | 2 | 10 | 182 | [6 empty] | 2 | 42 | [10 empty] | Korry Loeden &G. Deford |  | 1904 | 95.2 | 1999.2 | 28274
2015-08-25 | 51833 |  |  | 1 | [6 empty] | 1 | 161 | [14 empty] | 161 | 8.05 | 169.05 | 28385
2015-08-26 | 51834 |  |  | 1 | 12 | 125 |  |  |  |  | 1 | 161 | [12 empty] | S.Ganzalas |  | 1661 | 83.05 | 1744.05 | 28385
2015-08-27 | 51835 |  |  | 1 | 12 | 125 | [6 empty] | 3 | 45 | [10 empty] | S.Ganzalas |  | 1635 | 81.75 | 1716.75 | 28385
2015-10-02 | 56959 |  |  | 2 | 8 | 182 | [6 empty] | 1 | 42 | [12 empty] | 1498 | 74.9 | 1572.9 | 28764
2015-11-21 | 46807 |  |  | 2 | 11 | 182 | [6 empty] | 5 | 42 | [10 empty] | Brendan Hayes & Mark Honc |  | 2212 | 110.6 | 2322.6
2015-12-07 | 46816 |  |  | 2 | 6 | 182 | [6 empty] | 1 | 42 | [10 empty] | Brandon Hayes & Randal S. |  | 1134 | 56.7 | 1190.7
[27 empty] | 0 | 0 | 0
[27 empty] | 0 | 0 | 0
[27 empty] | 0 | 0 | 0
[27 empty] | 0 | 0 | 0
[27 empty] | 0 | 0 | 0

## Clean Harbours
Clean Harbours
Date | LEM # | Unit # 791524 | Rate | Unit # 791526 | rate | Unit # 7911287 | Rate | Unit # 7910676 | Rate | Unit # 790218 | Rate | Unit # 791200 | Rate | Unit # 79093 | rate/day | Unit #790127 | Rate | Unit # 792761A | rate | Trix axle hydro vac | Hourly rate | Labourer class | Rate | Labourer class | Rate | Total Labour Rate per hr | Total Hours Charged | Equipment Detail | Km's Charged | Overtime | Rate | Water | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
615159.5
2015-07-02 | 498451 | 1 | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-03 | 498453 | 1 | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-04 | 498454 | 1 | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-06 | 498455 | 1 | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-07 | 498456 | 1 | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-08 | 498457 | 0 | 2600 |  | 2600 | 0 | 2600 | 9 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1170 | 58.5 | 1228.5 | 1001037136
2015-07-08 | 498458 | 1 | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-09 | 498459 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001037136
2015-07-09 | 498460 | 1 | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-10 | 498461 | 1 | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-11 | 498462 | 1 | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-14 | 498463 |  | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 2600 | 130 | 2730 | 1001037136
2015-07-15 | 498464 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-19 | 498465 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-20 | 498466 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-20 | 498467 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001037136
2015-07-21 | 498468 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-21 | 498469 |  | 2600 | 1 | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-21 | 498471 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 | 1 | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 2600 | 130 | 2730 | 1001037136
2015-07-21 | 498472 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 | 2 | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 490 | 24.5 | 514.5 | 1001037136
2015-07-22 | 498473 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-22 | 498474 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 | 1 | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-22 | 498475 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001037136
2015-07-23 | 574339 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001037136
2015-07-23 | 574340 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-23 | 574341 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-24 | 574342 |  | 2600 | 1 | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-24 | 574343 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-24 | 574344 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-25 | 574345 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-25 | 574346 |  | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-25 | 574347 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001037136
2015-07-27 | 574851 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-27 | 574852 |  | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-27 | 574853 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-28 | 574856 |  | 2600 |  | 2600 | 1 | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-28 | 574855 |  | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-28 | 574854 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-29 | 574857 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-29 | 574858 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-29 | 574859 |  | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-30 | 574860 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-30 | 574861 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001037136
2015-07-30 | 574862 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-31 | 574863 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-31 | 574864 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001037136
2015-07-31 | 574865 |  | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001037136
2015-07-31 | 574866 |  | 2600 |  | 2600 |  | 2600 | 3 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 390 | 19.5 | 409.5 | 1001037136
2015-08-01 | 574867 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-01 | 574868 |  | 2600 |  | 2600 | 1 | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-01 | 574869 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-03 | 574872 |  | 2600 |  | 2600 |  | 2600 | 10 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1300 | 65 | 1365 | 1001161064
2015-08-03 | 574870 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-03 | 574871 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 4 | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 | 4 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 3120 | 156 | 3276 | 1001161064
2015-08-05 | 574873 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-05 | 574874 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-05 | 574875 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 2600 | 130 | 2730 | 1001161064
2015-08-05 | 574348 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 5460 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-05 | 574349 |  | 2600 |  | 2600 |  | 2600 | 14 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1820 | 91 | 1911 | 1001161064
2015-08-05 | 574350 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001161064
2015-08-06 | 615454 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-06 | 615455 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-06 | 615456 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 | 1 | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 2600 | 130 | 2730 | 1001161064
2015-08-07 | 615457 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-07 | 615458 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-07 | 615459 |  | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 2600 | 130 | 2730 | 1001161064
2015-08-08 | 615460 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-08 | 615461 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 | 1 | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 2600 | 130 | 2730 | 1001161064
2015-08-08 | 615463 |  | 2600 |  | 2600 |  | 2600 | 4 | 130 |  | 2600 | 8 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 8 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-10 | 615464 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-10 | 615465 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-10 | 615466 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 47 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001161064
2015-08-11 | 615470 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 48 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-11 | 615467 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-11 | 615468 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-11 | 615469 | 1 | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001161064
2015-08-12 | 615471 | 2 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-12 | 615472 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-12 | 615473 |  | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 2600 | 130 | 2730 | 1001161064
2015-08-13 | 615474 | 2 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-13 | 615475 | 1 | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001161064
2015-08-13 | 615576 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-14 | 615577 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-14 | 651578 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-14 | 651579 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-15 | 651580 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-15 | 651581 |  | 2600 |  | 2600 | 2 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-15 | 651582 |  | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 2600 | 130 | 2730 | 1001161064
2015-08-17 | 651583 |  | 2600 |  | 2600 | 2 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-17 | 651584 |  | 2600 |  | 2600 | 1 | 2600 | 10 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 3900 | 195 | 4095 | 1001161064
2015-08-17 | 651585 |  | 2600 |  | 2600 | 1 | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-17 | 651586 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001161064
2015-08-19 | 615589 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-19 | 615588 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4160 | 208 | 4368 | 1001161064
2015-08-19 | 615587 | 1 | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-20 | 615591 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-20 | 615590 | 1 | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-21 | 615593 |  | 2600 |  | 2600 |  | 2600 | 14.5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1885 | 94.25 | 1979.25 | 1001161064
2015-08-21 | 615592 | 1 | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-24 | 615595 |  | 2600 |  | 2600 |  | 2600 | 14 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1820 | 91 | 1911 | 1001161064
2015-08-24 | 615594 |  | 2600 |  | 2600 |  | 2600 |  | 130 | 2 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 5200 | 260 | 5460 | 1001161064
2015-08-25 | 615596 | 1 | 2600 |  | 2600 |  | 2600 | 13.5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4355 | 217.75 | 4572.75 | 1001161064
2015-08-26 | 497826 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-26 | 615597 | 1 | 2600 |  | 2600 |  | 2600 | 12.5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4225 | 211.25 | 4436.25 | 1001161064
2015-08-27 | 497827 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-27 | 615598 | 1 | 2600 |  | 2600 |  | 2600 | 13 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4290 | 214.5 | 4504.5 | 1001161064
2015-08-27 | 497828 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 7 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 7 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 910 | 45.5 | 955.5 | 1001161064
2015-08-28 | 615599 | 1 | 2600 |  | 2600 |  | 2600 | 13 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4290 | 214.5 | 4504.5 | 1001161064
2015-08-29 | 497829 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 5 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 5 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 650 | 32.5 | 682.5 | 1001161064
2015-08-29 | 615600 | 1 | 2600 |  | 2600 |  | 2600 | 12.5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4225 | 211.25 | 4436.25 | 1001161064
2015-08-30 | 614527 | 1 | 2600 |  | 2600 |  | 2600 | 12.5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4225 | 211.25 | 4436.25 | 1001161064
2015-08-31 | 497830 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001161064
2015-08-31 | 614526 |  | 2600 |  | 2600 | 1 | 2600 | 12.5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 | 2 | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 4715 | 235.75 | 4950.75 | 1001161064
2015-09-01 | 498831 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 3120 | 156 | 3276 | 1001154781
2015-09-01 | 614528 |  | 2600 |  | 2600 | 0.5 | 2600 | 7 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! | [5 empty] | 2210 | 110.5 | 2320.5 | 1001154781
2015-09-02 | 497832 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 12 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 12 | 60 |  | 46 | 7930 | #REF! | [5 empty] | 1560 | 78 | 1638 | 1001154781
2015-09-02 | 614529 |  |  |  |  | 1 | 2600 | 13 | 130 | [10 empty] | 2 | 245 | [11 empty] | 4780 | 239 | 5019 | 1001154781
2015-09-03 | 614530 |  | 2600 |  | 2600 | 1 | 2600 | 12.5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 |  |  |  |  | 2 | 245 |  | 4715 | 235.75 | 4950.75 | 1001154781
2015-09-03 | 497833 | [12 empty] | 11 | 130 | [17 empty] | 1430 | 71.5 | 1501.5 | 1001154781
2015-09-04 | 614531 |  | 2600 |  | 2600 | 1 | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 4160 | 208 | 4368 | 1001154781
2015-09-05 | 614532 |  | 2600 |  | 2600 |  | 2600 | 9 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 3770 | 188.5 | 3958.5 | 1001154781
2015-09-06 | 614533 |  | 2600 |  | 2600 |  | 2600 | 3 | 130 | 0.5 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 1690 | 84.5 | 1774.5 | 1001154781
2015-09-08 | 614534 |  | 2600 |  | 2600 |  | 2600 | 12.5 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4715 | 235.75 | 4950.75 | 1001154781
2015-09-08 | 497834 | [10 empty] | 3 | 70 | [8 empty] | 3 | 60 | [9 empty] | 390 | 19.5 | 409.5 | 1001154781
2015-09-09 | 614535 |  | 2600 |  | 2600 |  | 2600 | 13.5 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4845 | 242.25 | 5087.25 | 1001154781
2015-09-09 | 497835 | [10 empty] | 4 | 70 | [8 empty] | 4 | 60 | [9 empty] | 520 | 26 | 546 | 1001154781
2015-09-10 | 614536 |  | 2600 |  | 2600 |  | 2600 | 13 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4780 | 239 | 5019 | 1001154781
2015-09-11 | 614537 |  | 2600 |  | 2600 |  | 2600 | 14.5 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4975 | 248.75 | 5223.75 | 1001154781
2015-09-12 | 614538 |  | 2600 |  | 2600 | 1 | 2600 | 14 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4910 | 245.5 | 5155.5 | 1001154781
2015-09-13 | 614539 |  | 2600 |  | 2600 | 1 | 2600 | 12.5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4715 | 235.75 | 4950.75 | 1001154781
2015-09-14 | 497836 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 | 11 | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 11 | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 1430 | 71.5 | 1501.5 | 1001154781
2015-09-16 | 614540 |  | 2600 |  | 2600 |  | 2600 | 14 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4910 | 245.5 | 5155.5 | 1001154781
2015-09-17 | 614541 |  | 2600 |  | 2600 |  | 2600 | 14 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4910 | 245.5 | 5155.5 | 1001154781
2015-09-18 | 614542 |  | 2600 |  | 2600 |  | 2600 | 14 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4910 | 245.5 | 5155.5 | 1001154781
2015-09-19 | 614543 |  | 2600 |  | 2600 | 1 | 2600 | 13 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4780 | 239 | 5019 | 1001154781
2015-09-20 | 614544 |  | 2600 |  | 2600 | 0.5 | 2600 | 8 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2340 | 117 | 2457 | 1001154781
2015-09-21 | 614545 |  | 2600 |  | 2600 |  | 2600 | 12.5 | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4715 | 235.75 | 4950.75 | 1001154781
2015-09-22 | 614547 | 1 | 2600 |  | 2600 |  | 2600 | 12.5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4715 | 235.75 | 4950.75 | 1001154781
2015-09-22 | 615331 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 3090 | 154.5 | 3244.5 | 1001154781
2015-09-23 | 614548 | 1 | 2600 |  | 2600 |  | 2600 | 13 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4780 | 239 | 5019 | 1001154781
2015-09-23 | 614549 | 1 | 2600 |  | 2600 |  | 2600 | 14 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4910 | 245.5 | 5155.5 | 1001154781
2015-09-24 | 615330 |  | 2600 |  | 2600 |  | 2600 | 13 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 1690 | 84.5 | 1774.5 | 1001154781
2015-09-24 | 615327 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2.5 | 245 |  | 5812.5 | 290.625 | 6103.125 | 1001154781
2015-09-24 | 615328 | 1 | 2600 |  | 2600 |  | 2600 | 13 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 2 | 245 |  | 4780 | 239 | 5019 | 1001154781
2015-09-24 | 615329 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 5 | 245 |  | 6425 | 321.25 | 6746.25 | 1001154781
2015-09-25 | 615333 | 1 | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 8 | 245 |  | 7160 | 358 | 7518 | 1001154781
2015-09-25 | 615334 | 1 | 2600 |  | 2600 |  | 2600 | 14 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 4 | 245 |  | 5400 | 270 | 5670 | 1001154781
2015-09-25 | 615347 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 8 | 60 | 8 | 46 | 7930 | #REF! |  |  |  | 245 |  | 848 | 42.4 | 890.4 | 1001154781
2015-09-25 | 615346 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 | 4 | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 240 | 12 | 252 | 1001154781
2015-09-26 | 615339 | 0 | 2600 |  | 2600 |  | 2600 | 0 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 0 | 245 |  | 0 | 0 | 0 | 1001154781
2015-09-26 | 615338 | 1 | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 3 | 245 |  | 5935 | 296.75 | 6231.75 | 1001154781
2015-09-26 | 615342 | 1 | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 5200 | 260 | 5460 | 1001154781
2015-09-27 | 615341 | 0 | 2600 | 0 | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0 | 1001154781
2015-09-27 | 615340 | 1 | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 5200 | 260 | 5460 | 1001154781
2015-09-28 | 615349 | 0 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0 | 1001154781
2015-09-28 | 615345 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0 | 1001154781
2015-09-28 | 615344 | 1 | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 5200 | 260 | 5460 | 1001154781
2015-09-28 | 615343 | 1 | 2600 | 1 | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  | 3 | 245 |  | 5935 | 296.75 | 6231.75 | 1001154781
2015-09-29 | 615348 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 | 0.5 | 2600 |  | 91 |  | 2600 | 1 | 245 | 4 | 60 | 4 | 46 | 7930 | #REF! |  |  |  | 245 |  | 1969 | 98.45 | 2067.45 | 1001154781
2015-09-30 | 614702 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001154781
2015-10-01 | 614703 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 1560 | 78 | 1638 | 1001231770
2015-10-02 | 614705 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 1560 | 78 | 1638 | 1001231770
2015-10-02 | 614704 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001231770
2015-10-03 | 614706 |  | 2600 |  | 2600 |  | 2600 | 4 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 520 | 26 | 546 | 1001231770
2015-10-03 | 614707 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001231770
2015-10-05 | 614708 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 1560 | 78 | 1638 | 1001231770
2015-10-06 | 614709 |  | 2600 |  | 2600 |  | 2600 | 12 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 1560 | 78 | 1638 | 1001231770
2015-10-14 | 614711 | 1 | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001231770
2015-10-15 | 614713 |  | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001231770
2015-10-16 | 614714 |  | 2600 |  | 2600 |  | 2600 |  | 130 | 1 | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001231770
2015-10-16 | 614715 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 | 1 | 2600 | 2 | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 3090 | 154.5 | 3244.5 | 1001231770
2015-10-17 | 614718 |  | 2600 |  | 2600 |  | 2600 | 5 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 650 | 32.5 | 682.5 | 1001231770
2015-10-17 | 614716 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 | 1 | 2600 |  | 91 |  | 2600 | 2 | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 3090 | 154.5 | 3244.5 | 1001231770
2015-10-19 | 614720 |  | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001231770
| 614721 |  | 2600 |  | 2600 |  | 2600 | 10 | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 1300 | 65 | 1365 | 1001231770
2015-10-20 | 614722 |  | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001231770
2015-10-21 | 614553 |  | 2600 |  | 2600 |  | 2600 | NC | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | No Charge | No Charge | No Charge | 1001231770
2015-10-22 | 614556 |  | 2600 |  | 2600 |  | 2600 | NC | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | No Charge | No Charge | No Charge | 1001231770
2015-11-02 | 498608 |  | 2600 |  | 2600 |  | 2600 | NC | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | No Charge | No Charge | No Charge | 1001173212
2015-11-02 | 498607 |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 | 1 | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001173212
2015-11-02 | 498606 |  | 2600 |  | 2600 | 1 | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 2600 | 130 | 2730 | 1001173212
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
|  |  | 2600 |  | 2600 |  | 2600 |  | 130 |  | 2600 |  | 70 |  | 2600 |  | 91 |  | 2600 |  | 245 |  | 60 |  | 46 | 7930 | #REF! |  |  |  | 245 |  | 0 | 0 | 0
Note on C63: sacookadmin: Tom Hudson Jill Cullen
Note on K63: sacookadmin: Sean Smith Derek Allan
Note on Q64: Lorraine Dunbar: Clint Bougeralle - 6 hrs Vac Truck Unit #791200 Clint Bougeralle - 8 hrs Pressure Truck Unit #790127
Note on C66: sacookadmin: Tom Hudson Jill Cullen
Note on K66: sacookadmin: Sean Smith Derek Allan
Note on I67: Lorraine Dunbar: Clint Bougerolle - 12 hrs
Note on S68: Lorraine Dunbar: Chris Mclean Dave Mills
Note on C69: sacookadmin: Tom Hudson & Jill Cullen Unit #791524 1 Day @ 2600/day
Note on K69: Lorraine Dunbar: Sean Smith & Derek Allen Unit#790218 1 Day @ 2600/day
Note on G71: sacookadmin: Chris Mclean & Dave Mills Unit #79093 - 1 Day @ 2600.00/ day
Note on C72: sacookadmin: Tom Hudson & Jill Cullen Unit #791524 1 Day @ 2600/day
Note on K72: Lorraine Dunbar: Sean Smith & Derek Allen Unit#790218 1 Day @ 2600/day
Note on O73: Lorraine Dunbar: Chris Mclean Dave Mills
Note on I74: Lorraine Dunbar: Clint Bougerolle -Water Truck - 4 hrs
Note on M74: sacookadmin: Robert Buete - 8 hrs Vac Truck
Note on W74: Lorraine Dunbar: Clint Bougerolle - 8 hrs
Note on I76: sacookadmin: Unit 7910676 - 12 hrs
Note on C77: Ldunbar: Unit 7910646 - 1 day
Note on M78: LDunbar: Unit 010437 - 12 hrs
Note on C82: sacookadmin: Unit # 791524 Unit #7910646
Note on C85: LDunbar: Unit# 7910640 - 1 day Unit# 790218 - 1 day
Note on C86: sacookadmin: Unit# 7911287 - 1 Day
Note on G94: LDunbar: Unit 701518 - 1 day Unit 79095 - 1 day
Note on G95: sacookadmin: Unit 791420 - 1 day
Note on I95: sacookadmin: Unit 7910669 - 10 hrs Unit 7910676 - Free WT
Note on G96: LDunbar: Unit 79095 - 1 day
Note on I97: LDunbar: Unit 7910669 - 12 hrs Unit 7910676 - Free
Note on K97: sacookadmin: Unit 791518 - 1 day
Note on C111: sacookadmin: Unit 791518
Note on C113: sacookadmin: Unit 791518
Note on C115: sacookadmin: Unit 791518
Note on C116: sacookadmin: Unit 791518

## Terra HDD
Terra HDD
Date | LEM # | Adam McTavish | Lawrrence Barry | KM | Ben Lippett | KM | Trente Barclay | KM | LOA | travel sub | Communication | KM 1.25 | Salinity kit | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-30 | 15-027E-01 | 850 | [6 empty] | 250 |  | 75 | 260 |  | 1500 | 75 | 1575 | 1131 |  | 222566.21
2015-07-01 | 15-027E-02 | 850 | [6 empty] | 250 |  | 75 | 150 |  | 1362.5 | 68.125 | 1430.625 | 1131
2015-07-02 | 15-027E-03 | 850 | [6 empty] | 250 |  | 75 | 180 |  | 1400 | 70 | 1470 | 1131
2015-07-03 | 15-027E-04 | 850 | [6 empty] | 250 |  | 75 | 240 |  | 1475 | 73.75 | 1548.75 | 1131
2015-07-04 | 15-027E-05 | 850 | [6 empty] | 0 | 75 | 75 | 290 |  | 1362.5 | 68.125 | 1430.625 | 1131
2015-07-12 | 15-027E-06 | 850 | [6 empty] | 250 |  | 75 | 250 |  | 1487.5 | 74.375 | 1561.875 | 1131
2015-07-13 | 15-027E-07 | 850 | [6 empty] | 250 |  | 75 | 150 |  | 1362.5 | 68.125 | 1430.625 | 1131
2015-07-14 | 15-027E-08 | 850 | [6 empty] | 250 |  | 75 | 180 |  | 1400 | 70 | 1470 | 1131
2015-07-15 | 15-027E-09 | 850 | [6 empty] | 250 |  | 75 | 260 |  | 1500 | 75 | 1575 | 1131
2015-07-15 | 15-02707-15-15 | [12 empty] | 5620.46 | 281.023 | 5901.483 | 1130 | Third Party
2015-07-16 | 15-027E-10 | 850 | [6 empty] | 250 |  | 75 | 150 |  | 1362.5 | 68.125 | 1430.625 | 1151
2015-07-17 | 15-027E-11 | 850 | [6 empty] | 250 |  | 75 | 0 |  | 1175 | 58.75 | 1233.75 | 1151
2015-07-18 | 15-027E-12 | [7 empty] | 250 |  |  | 0 |  | 250 | 12.5 | 262.5 | 1151
2015-07-19 | 15-027E-13 | [7 empty] | 250 |  |  | 0 |  | 250 | 12.5 | 262.5 | 1151
2015-07-20 | 15-027E-14 | 850 | [6 empty] | 250 |  | 75 | 210 | 50 | 1487.5 | 74.375 | 1561.875 | 1151
2015-07-21 | 15-027E-15 | 850 | [6 empty] | 250 |  | 75 | 275 | 50 | 1568.75 | 78.4375 | 1647.1875 | 1151
2015-07-22 | 15-027E-16 | 850 | [6 empty] | 250 |  | 75 | 215 | 50 | 1493.75 | 74.6875 | 1568.4375 | 1151
2015-07-23 | 15-027E-17 | 850 | [6 empty] | 250 |  | 75 | 225 | 50 | 1506.25 | 75.3125 | 1581.5625 | 1151
2015-07-24 | 15-027E-18 | 850 | [6 empty] | 250 |  | 75 | 230 | 50 | 1512.5 | 75.625 | 1588.125 | 1151
2015-07-25 | 15-027E-19 | 850 | [6 empty] | 250 |  | 75 | 210 | 50 | 1487.5 | 74.375 | 1561.875 | 1151
2015-07-26 | [8 empty] | 250 |  |  | 0 |  | 250 | 12.5 | 262.5 | 1151
2015-07-27 | 15-027E-20 | 850 | [6 empty] | 250 |  | 75 | 240 | 50 | 1525 | 76.25 | 1601.25 | 1151
2015-07-28 | 15-027E-21 | 850 | [6 empty] | 250 |  | 75 | 200 | 50 | 1475 | 73.75 | 1548.75 | 1151
2015-07-29 | 15-027E-22 | 850 | [6 empty] | 250 |  | 75 | 180 | 50 | 1450 | 72.5 | 1522.5 | 1151
2015-07-30 | 15-027E-23 | 850 | [6 empty] | 250 |  | 75 | 250 | 50 | 1537.5 | 76.875 | 1614.375 | 1151
2015-07-31 | 15-027E-24 | 850 | [6 empty] | 250 |  | 75 | 190 | 50 | 1462.5 | 73.125 | 1535.625 | 1151
2015-07-31 | 15-02707-31-15 | [12 empty] | 5636.06 | 281.803 | 5917.863 | 1143 | Third Party
2015-08-01 | 15-027E-26 | 850 | [6 empty] | 250 |  | 75 | 205 | 50 | 1481.25 | 74.0625 | 1555.3125 | 1156
2015-08-02 | 15-027E-27 | [7 empty] | 250 |  |  | 0 |  | 250 | 12.5 | 262.5 | 1156
2015-08-03 | 15-027E-28 | 850 | [6 empty] | 250 |  | 75 | 265 | 50 | 1556.25 | 77.8125 | 1634.0625 | 1156
2015-08-04 | 15-027E-29 | 850 | [6 empty] | 250 |  | 75 | 225 | 50 | 1506.25 | 75.3125 | 1581.5625 | 1156
2015-08-05 | 15-027E-30 | 850 | [6 empty] | 250 |  | 75 | 280 | 50 | 1575 | 78.75 | 1653.75 | 1156
2015-08-06 | 15-027E-31 | 850 | [6 empty] | 250 |  | 75 | 210 | 50 | 1487.5 | 74.375 | 1561.875 | 1156
2015-08-07 | 15-027E-32 | 850 | [6 empty] | 250 |  | 75 | 290 | 50 | 1587.5 | 79.375 | 1666.875 | 1156
2015-08-08 | 15-027E-33 | 850 | [6 empty] | 250 |  | 75 | 240 | 50 | 1525 | 76.25 | 1601.25 | 1156
2015-08-09 | 15-027E-34 | [7 empty] | 250 |  |  |  |  | 250 | 12.5 | 262.5 | 1156
2015-08-10 | 15-027E-35 | 850 | [6 empty] | 250 |  | 75 | 270 | 50 | 1562.5 | 78.125 | 1640.625 | 1156
2015-08-11 | 15-027E-36 | 850 | [6 empty] | 250 |  | 75 | 220 | 50 | 1500 | 75 | 1575 | 1156
2015-08-12 | 15-027E-37 | 850 | [6 empty] | 250 |  | 75 | 250 | 50 | 1537.5 | 76.875 | 1614.375 | 1156
2015-08-13 | 15-027E-38 | 850 | [6 empty] | 250 |  | 75 | 260 | 50 | 1550 | 77.5 | 1627.5 | 1156
2015-08-14 | 15-027E-39 | 850 | [6 empty] | 250 |  | 75 | 265 | 50 | 1556.25 | 77.8125 | 1634.0625 | 1156
2015-08-15 | 15-027E-40 | 850 | [6 empty] | 250 |  | 75 | 210 | 50 | 1487.5 | 74.375 | 1561.875 | 1156
2015-08-15 | [13 empty] | 14383.44 | 719.172 | 15102.612 | 1164 | Third Party
2015-08-16 | 15-027E-41 | [7 empty] | 250 |  |  |  |  | 250 | 12.5 | 262.5 | 1171
2015-08-17 | 15-027E-42 | 850 | [6 empty] | 250 |  | 75 | 255 | 50 | 1543.75 | 77.1875 | 1620.9375 | 1171
2015-08-18 | 15-027E-43 | 850 | [6 empty] | 250 |  | 75 | 225 | 50 | 1506.25 | 75.3125 | 1581.5625 | 1171
2015-08-19 | 15-027E-44 | 850 | [6 empty] | 250 |  | 75 | 290 | 50 | 1587.5 | 79.375 | 1666.875 | 1171
2015-08-20 | 15-027E-45 | 850 | [6 empty] | 250 |  | 75 | 205 | 50 | 1481.25 | 74.0625 | 1555.3125 | 1171
2015-08-21 | 15-027E-46 | 850 | [6 empty] | 250 |  | 75 | 215 | 50 | 1493.75 | 74.6875 | 1568.4375 | 1171
2015-08-22 | 15-027E-47 | 850 | [6 empty] | 250 |  | 75 | 260 | 50 | 1550 | 77.5 | 1627.5 | 1171
2015-08-23 | 15-027E-48 | [7 empty] | 250 |  |  |  |  | 250 | 12.5 | 262.5 | 1171
2015-08-24 | 15-027E-49 | 850 | [6 empty] | 250 |  | 75 | 260 | 50 | 1550 | 77.5 | 1627.5 | 1171
2015-08-25 | 15-027E-50 | 850 | 1147 | [5 empty] | 250 | 75 | 150 | 512 | 50 | 3162 | 158.1 | 3320.1 | 1171
2015-08-26 | 15-027E-51 | 850 | 1147 | [5 empty] | 250 | 75 | 150 | 397 | 50 | 3018.25 | 150.9125 | 3169.1625 | 1171
2015-08-27 | 15-027E-52 | 850 | 1147 | [5 empty] | 250 | 75 | 150 | 432 | 50 | 3062 | 153.1 | 3215.1 | 1171
2015-08-28 | 15-027E-53 | 850 | 1147 | [5 empty] | 250 | 75 | 150 | 459 | 50 | 3095.75 | 154.7875 | 3250.5375 | 1171
2015-08-29 | 15-027E-54 | 850 | 1147 | [5 empty] | 250 | 75 | 150 | 533 | 50 | 3188.25 | 159.4125 | 3347.6625 | 1171
2015-08-30 | 15-027E-55 | 850 | 1147 | [5 empty] | 250 | 75 | 150 | 377 | 50 | 2993.25 | 149.6625 | 3142.9125 | 1171
2015-08-31 | 15-027E-56 | 850 | 1147 | [5 empty] | 250 | 75 | 150 | 499 | 50 | 3145.75 | 157.2875 | 3303.0375 | 1171 |  | Invoice#1171 | 32877.75
2015-09-01 | 15-027E-57 | 850 |  |  | 850 |  |  |  | 500 |  | 150 | 583 | 50 | 3128.75 | 156.4375 | 3285.1875 | 1193
2015-09-01 | 15-027H-08 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 587 |  | 3300.75 | 165.0375 | 3465.7875 | 1193
2015-09-02 | 15-027E-58 | 850 |  |  | 850 |  |  |  | 500 |  | 150 | 466 | 50 | 2982.5 | 149.125 | 3131.625 | 1193
2015-09-02 | 15-027E-09 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 389 |  | 3053.25 | 152.6625 | 3205.9125 | 1193
2015-09-03 | 15-027H-59 | 850 |  |  | 850 |  |  |  | 500 |  | 150 | 506 | 50 | 3032.5 | 151.625 | 3184.125 | 1193
2015-09-03 | 15-027-10 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 397 |  | 3063.25 | 153.1625 | 3216.4125 | 1193
2015-09-04 | 15-027H-60 |  |  |  | 850 |  |  |  | 250 |  | 75 | 241 | 50 | 1526.25 | 76.3125 | 1602.5625 | 1193
| 15-027H-11 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 409 |  | 3078.25 | 153.9125 | 3232.1625
2015-09-05 | 15-027E-61 |  |  |  | 850 |  |  |  | 250 |  | 75 | 150 | 50 | 1412.5 | 70.625 | 1483.125 | 1193
| 15-027H-12 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 367 |  | 3025.75 | 151.2875 | 3177.0375
2015-09-06 | 15-027E-62 |  |  |  | 425 |  |  |  | 250 |  | 75 | 150 |  | 937.5 | 46.875 | 984.375 | 1193
| 15-027H-13 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 571 |  | 3280.75 | 164.0375 | 3444.7875
2015-09-07 | 15-027E-63 |  |  |  | 425 |  |  |  | 250 |  | 75 | 150 |  | 937.5 | 46.875 | 984.375 | 1193
2015-09-08 | 15-027H-15 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 577 |  | 3288.25 | 164.4125 | 3452.6625 | 1193
| 15-027E-64 |  |  |  | 850 |  |  |  | 250 |  | 75 | 216 | 50 | 1495 | 74.75 | 1569.75
2015-09-09 | 15-027H-16 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 372 |  | 3032 | 151.6 | 3183.6 | 1193
| 15-027E-65 |  |  |  | 850 |  |  |  | 250 |  | 75 | 150 | 50 | 1412.5 | 70.625 | 1483.125
2015-09-10 | 15-027H-17 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 388 |  | 3052 | 152.6 | 3204.6 | 1193
| 15-027E-66 |  |  |  | 850 |  |  |  | 250 |  | 75 | 150 | 50 | 1412.5 | 70.625 | 1483.125
2015-09-11 | 15-027H-18 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 371 |  | 3030.75 | 151.5375 | 3182.2875 | 1193
| 15-027E-67 |  |  |  | 850 |  |  |  | 250 |  | 75 | 289 | 50 | 1586.25 | 79.3125 | 1665.5625
2015-09-12 | 15-027H-19 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 391 |  | 3055.75 | 152.7875 | 3208.5375 | 1193
| 15-027E-68 |  |  |  | 850 |  |  |  | 250 |  | 75 | 261 | 50 | 1551.25 | 77.5625 | 1628.8125
2015-09-13 | 15-027H-20 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 408 |  | 3077 | 153.85 | 3230.85 | 1193
| 15-027E-69 |  |  |  | 850 |  |  |  | 250 |  | 75 | 150 | 50 | 1412.5 | 70.625 | 1483.125
2015-09-14 | 15-027H-21 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 377 |  | 3038.25 | 151.9125 | 3190.1625 | 1193
| 15-027E-70 |  |  |  | 850 |  |  |  | 250 |  | 75 | 174 | 50 | 1442.5 | 72.125 | 1514.625
2015-09-15 | 15-027E-71 |  |  |  | 425 |  |  |  | 250 |  | 75 | 150 |  | 937.5 | 46.875 | 984.375 | 1193 |  | Invoice#1193 | 65908.5
| 15-027H-22 | [7 empty] | 250 |  | 75 |  |  | 325 | 16.25 | 341.25
2015-09-16 | 15-027H-23 |  | 1147 |  |  |  | 945 |  | 250 | 75 | 150 | 375 |  | 3035.75 | 151.7875 | 3187.5375 | 1212 |  | Tammy Started Here
2015-09-16 | 15-027E-72 |  |  |  | 425 |  |  |  | 250 |  | 75 | 150 |  | 937.5 | 46.875 | 984.375 | 1212
2015-09-17 | 15-027H-24 |  | 1147 | [5 empty] | 75 |  | 75 | 222 |  | 1574.5 | 78.725 | 1653.225 | 1212
2015-09-17 | 15-027H-24 | [5 empty] | 945 |  | 250 |  | 75 | 150 |  | 1457.5 | 72.875 | 1530.375 | 1212
2015-09-17 | 15-087E-73 |  |  |  | 850 |  |  |  | 250 |  | 75 | 248 | 50 | 1535 | 76.75 | 1611.75 | 1212
2015-09-18 | 15-027H-25 |  | 1147 | [5 empty] | 75 |  | 75 | 221 |  | 1573.25 | 78.6625 | 1651.9125 | 1212
2015-09-18 | 15-027H-25 | [5 empty] | 945 |  | 250 |  | 75 | 150 |  | 1457.5 | 72.875 | 1530.375 | 1212
2015-09-18 | 15-087E-74 |  |  |  | 850 |  |  |  | 250 |  | 75 | 191 | 50 | 1463.75 | 73.1875 | 1536.9375 | 1212
2015-09-19 | 15-027H-26 |  | 1147 | [5 empty] | 75 |  | 75 | 251 |  | 1610.75 | 80.5375 | 1691.2875 | 1212
2015-09-19 | 15-027H-26 | [5 empty] | 945 |  | 250 |  | 75 | 150 |  | 1457.5 | 72.875 | 1530.375 | 1212
2015-09-19 | 15-027E-75 |  |  |  | 850 |  |  |  | 250 |  | 75 | 259 | 50 | 1548.75 | 77.4375 | 1626.1875 | 1212
2015-09-20 | 15-027H-27 |  | 1147 | [5 empty] | 75 |  | 75 | 239 |  | 1595.75 | 79.7875 | 1675.5375 | 1212
2015-09-20 | 15-027H-27 | [5 empty] | 945 |  | 250 |  | 75 | 150 |  | 1457.5 | 72.875 | 1530.375 | 1212
2015-09-20 | 15-027E-76 |  |  |  | 850 |  |  |  | 250 |  | 75 | 150 | 50 | 1412.5 | 70.625 | 1483.125 | 1212
2015-09-21 | 15-027E-77 |  |  |  | 850 |  |  |  | 250 |  | 75 | 150 | 50 | 1412.5 | 70.625 | 1483.125 | 1212
2015-09-21 | 15-027H-28 |  | 1147 | [5 empty] | 75 |  | 75 | 240 |  | 1597 | 79.85 | 1676.85 | 1212
2015-09-21 | 15-027H-28 | [5 empty] | 945 |  | 250 |  | 75 | 150 |  | 1457.5 | 72.875 | 1530.375 | 1212
2015-09-22 | 154-027E-78 |  |  |  | 850 |  |  |  | 250 |  | 75 | 183 | 50 | 1453.75 | 72.6875 | 1526.4375 | 1212
2015-09-22 | 15-027H-29 |  | 1147 | [5 empty] | 75 |  | 75 | 220 |  | 1572 | 78.6 | 1650.6 | 1212
2015-09-22 | 15-027H-29 | [5 empty] | 945 |  | 250 |  | 75 | 150 |  | 1457.5 | 72.875 | 1530.375 | 1212
2015-09-23 | 15-027E-9 |  |  |  | 850 |  |  |  | 250 |  | 75 | 256 | 50 | 1545 | 77.25 | 1622.25 | 1212
2015-09-23 | 15-027H-30 |  | 1147 | [5 empty] | 75 |  | 75 | 219 |  | 1570.75 | 78.5375 | 1649.2875 | 1212
2015-09-23 | 15-027H-30 | [5 empty] | 945 |  | 250 |  | 75 | 150 |  | 1457.5 | 72.875 | 1530.375 | 1212
2015-09-24 | 15-027E-80 |  |  |  | 850 |  |  |  | 250 |  | 75 | 239 | 50 | 1523.75 | 76.1875 | 1599.9375 | 1212
2015-09-24 | 15-027H-31 |  | 1147 | [5 empty] | 75 |  | 75 | 238 |  | 1594.5 | 79.725 | 1674.225 | 1212
2015-09-24 | 15-027H-31 | [5 empty] | 945 |  | 250 |  | 75 | 150 |  | 1457.5 | 72.875 | 1530.375 | 1212
2015-09-25 | 15-027H-32 |  | 1147 | [5 empty] | 75 |  | 75 | 238 |  | 1594.5 | 79.725 | 1674.225 | 1212
2015-09-25 | 15-027H-32 | [5 empty] | 945 |  | 250 |  | 75 | 150 |  | 1457.5 | 72.875 | 1530.375 | 1212
2015-09-25 | 15-027E-81 |  |  |  | 850 |  |  |  | 250 |  | 75 | 512 |  | 1815 | 90.75 | 1905.75 | 1212 |  | Last Day
Note on B57: sacookadmin: Lawrence Barry Ticket#15-027H-01
Note on D57: sacookadmin: Lawrence Barry Ticket#15-027H-01
Note on B58: sacookadmin: Lawrence Barry Ticket#15-027H-02
Note on D58: sacookadmin: Lawrence Barry Ticket#15-027H-02
Note on B59: sacookadmin: Lawrence Barry Ticket#15-027H-03
Note on D59: sacookadmin: Lawrence Barry Ticket#15-027H-03
Note on B60: sacookadmin: Lawrence Barry Ticket#15-027H-04
Note on D60: sacookadmin: Lawrence Barry Ticket#15-027H-04
Note on B61: sacookadmin: Lawrence Barry Ticket#15-027H-05
Note on D61: sacookadmin: Lawrence Barry Ticket#15-027H-05
Note on B62: sacookadmin: Lawrence Barry Ticket#15-027H-06
Note on D62: sacookadmin: Lawrence Barry Ticket#15-027H-06
Note on B63: sacookadmin: Lawrence Barry Ticket#15-027H-07
Note on D63: sacookadmin: Lawrence Barry Ticket#15-027H-07

## Hawk Enterprise
Hawk Enterprise
Date | Lem # | Paul and or Grant | Labourer class | Rate | Vehicle $150 | Rate | stats | Rate | Over time hrs | Rate | Rate | Subtotal | GST | LEM Amount | Affiliating Invoice | Approved By | SUM OF ALL LEM'S (before GST)
2015-06-10 |  | Paul | 10 | 120 | 1 | 150 |  | 600 |  |  |  | 1350 | 67.5 | 1417.5 | HE-043-15-PPL |  | 116045
2015-06-18 |  | Paul /Grant | 20 | 120 | 2 | 150 |  | 600 |  |  |  | 2700 | 135 | 2835 | HE-043-15-PPL
2015-06-19 |  | Paul | 10 | 120 | 1 | 150 |  | 600 |  |  |  | 1350 | 67.5 | 1417.5 | HE-043-15-PPL
2015-06-22 |  | Paul/Grant | 20 | 120 | 2 | 150 |  | 600 |  |  |  | 2700 | 135 | 2835 | HE-043-15-PPL
2015-06-23 |  | Paul/Grant | 20 | 120 | 2 | 150 |  | 600 | 1 | 120 |  | 2820 | 141 | 2961 | HE-043-15-PPL
2015-06-26 |  | Paul | 11 | 120 | 1 | 150 |  | 600 |  |  |  | 1470 | 73.5 | 1543.5 | HE-043-15-PPL
2015-06-25 |  | Paul | 11 | 120 | 1 | 150 |  | 600 |  |  |  | 1470 | 73.5 | 1543.5 | HE-043-15-PPL
2015-06-26 |  | Paul /Gary | 22 | 120 | 2 | 150 |  | 600 |  |  |  | 2940 | 147 | 3087 | HE-043-15-PPL
2015-06-27 |  | Paul | 5 | 120 | 0.5 | 150 |  | 600 |  |  |  | 675 | 33.75 | 708.75 | HE-043-15-PPL
2015-06-29 |  | Paul | 10 | 120 | 1 | 150 |  | 600 | 2 | 120 |  | 1590 | 79.5 | 1669.5 | HE-043-15-PPL
2015-06-30 |  | Paul | 10 | 120 | 1 | 150 |  | 600 |  |  |  | 1350 | 67.5 | 1417.5 | HE-043-15-PPL
2015-07-01 |  | Paul | 10 | 120 | 1 | 150 | 1 | 600 |  | 200 |  | 1950 | 97.5 | 2047.5 | HE-044-15-PPL
2015-07-02 |  | Paul | 11 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1470 | 73.5 | 1543.5 | HE-044-15-PPL
2015-07-03 |  | Paul | 22 | 120 | 2 | 150 |  | 600 |  | 200 |  | 2940 | 147 | 3087 | HE-044-15-PPL
2015-07-04 |  | Paul | 20 | 120 | 2 | 150 |  | 600 | 1 | 200 |  | 2900 | 145 | 3045 | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL |  |  |  |  | 2015-18
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL |  |  |  |  | 2015-18
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL |  |  |  |  | 2015-18
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL |  |  |  |  | 2015-18
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL |  |  |  |  | 2015-18
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL |  |  |  |  | 2015-18
[8 empty] | 600 |  | 200 |  | 0 |  |  | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-06 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-07 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-08 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-09 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-10 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-11 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-12 |  | Gary |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-13 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-14 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-15 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-044-15-PPL |  |  |  |  | 2015-18
2015-07-16 |  | Gary | 6 | 100 | 1 | 150 |  | 600 | 1 | 200 |  | 950 | 47.5 | 997.5 | HE-045-15-PPL
2015-07-17 |  | Gary | 6 | 100 | 1 | 150 |  | 600 |  | 200 |  | 750 | 37.5 | 787.5 | HE-045-15-PPL
2015-07-18 |  | Gary |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 | HE-045-15-PPL
2015-07-19 |  | Gary |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 | HE-045-15-PPL
2015-07-20 |  | Paul | 10 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1350 | 67.5 | 1417.5 | HE-045-15-PPL
2015-07-21 |  | Paul | 11 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1470 | 73.5 | 1543.5 | HE-045-15-PPL
2015-07-22 |  | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-045-15-PPL
2015-07-23 |  | Paul | 13 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1710 | 85.5 | 1795.5 | HE-045-15-PPL
2015-07-24 |  | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-045-15-PPL
2015-07-25 |  | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-045-15-PPL
2015-07-26 |  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 | HE-045-15-PPL
2015-07-27 |  | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-045-15-PPL
2015-07-28 |  | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-045-15-PPL
2015-07-29 |  | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-045-15-PPL
2015-07-30 |  | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-045-15-PPL
2015-07-31 |  | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-045-15-PPL
2015-08-01 |  | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-056-15-PPL
2015-08-02 |  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 | HE-056-15-PPL
2015-08-03 |  | Paul/Gary | 20 | 120 | 2 | 150 | 2 | 600 | 1 | 200 |  | 4100 | 205 | 4305 | HE-056-15-PPL
2015-08-04 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-056-15-PPL
2015-08-05 |  | Gary | 11 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1670 | 83.5 | 1753.5 | HE-056-15-PPL
2015-08-06 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-056-15-PPL
2015-08-07 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-056-15-PPL
2015-08-08 |  | Gary | 10 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1350 | 67.5 | 1417.5 | HE-056-15-PPL
2015-08-09 |  | Gary |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 | HE-056-15-PPL
2015-08-10 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-056-15-PPL
2015-08-11 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-056-15-PPL
2015-08-12 |  | Gary | 12 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1790 | 89.5 | 1879.5 | HE-056-15-PPL
2015-08-13 |  | Gary | 11 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1670 | 83.5 | 1753.5 | HE-056-15-PPL
2015-08-14 |  | Gary | 12 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1790 | 89.5 | 1879.5 | HE-056-15-PPL
2015-08-15 |  | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5 | HE-056-15-PPL |  | Invoice# HE-056 -15-PPL | 23260
2015-08-16 | 4500121211 | Day Off |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 | HE-059-15-PPL | Day Off
2015-08-17 | 4500121212 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-18 | 4500121213 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-19 | 4500121214 | Paul | 14 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1830 | 91.5 | 1921.5 | HE-059-15-PPL
2015-08-20 | 4500121215 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-21 | 4500121216 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-22 | 4500121217 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-23 | 4500121218 | Paul |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 | HE-059-15-PPL | Day Off
2015-08-24 | 4500121219 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-25 | 4500121220 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-26 | 4500121221 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-27 | 4500121222 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL |  | 41
2015-08-28 | 4500121223 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-29 | 4500121224 | Paul | 12 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1590 | 79.5 | 1669.5 | HE-059-15-PPL
2015-08-30 | 4500121225 | Day Off |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 | HE-059-15-PPL | Day Off
2015-08-31 | 4500121226 | Gary | 12 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1790 | 89.5 | 1879.5 | HE-059-15-PPL |  | Invoice# HE-059 -15-PPL |  | 21110
2015-09-01 | 4500123149 | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5
2015-09-02 | 4500123150 | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5
2015-09-03 | 4500123151 | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5
2015-09-04 |  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
2015-09-05 |  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
2015-09-06 |  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
2015-09-07 |  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
2015-09-08 | 4500123152 | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5
2015-09-09 | 4500123153 | Gary | 10 | 120 | 1 | 150 |  | 600 | 1 | 200 |  | 1550 | 77.5 | 1627.5
2015-09-10 | 4500123154 | Gary | 10 | 120 | 1 | 150 |  | 600 |  | 200 |  | 1350 | 67.5 | 1417.5
2015-09-11 |  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0 |  |  | Invoice# HE-071 -15-PPL |  | 9100
|  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
|  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
|  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
|  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
|  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
|  |  |  | 120 |  | 150 |  | 600 |  | 200 |  | 0 | 0 | 0
Note on D4: sacook000: 10hr day and overtime is same rate

## Acuren
Acuren
Date | Ticket Number | Supervisor | Rate | Supervisor OT | Rate | 3 man crew | day rate | 3 man OT | hr/day rate or 3 man crew | 2 man crew BACK END TIE-IN | day/rate | 2 man OT | hr/rate | 2 man crew Mainline crawler | day/rate | UT tech level 2 | rate /hour | UT tech level 1 | rate/hour | Meals |  | LOA | LOA | 24" 11.1 | Rate | 16" 9.5 | Rate | Butt Weld | Hotel Exp | Hotel | Subtotal | GST | LEM Amount | Affiliating Invoice | SUM OF ALL LEM'S (before GST) | TDL# | TDL#
2015-07-03 | Z387726 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 5 | 24 | 5 | 16 |  |  |  | 2300 | 115 | 2415 | 227911 | 832404.0163
2015-07-04 | Z433851 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 5 | 24 |  | 16 |  |  |  | 2220 | 111 | 2331 | 227911
2015-07-06 | Z433852 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 | 7 | 16 |  |  |  | 2212 | 110.6 | 2322.6 | 227911
2015-07-07 | GH070715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 9 | 24 |  | 16 |  |  |  | 2316 | 115.8 | 2431.8 | 227911 | Invoice total $18,320.00
2015-07-08 | GH070815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 4 | 24 | 10 | 16 |  |  |  | 2356 | 117.8 | 2473.8 | 227911
2015-07-09 | GH070915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 5 | 24 | 10 | 16 |  |  |  | 2380 | 119 | 2499 | 227911
2015-07-10 | GH071015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 5 | 24 | 3 | 16 |  |  |  | 2268 | 113.4 | 2381.4 | 227911
2015-07-11 | GH071115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 5 | 24 | 3 | 16 |  |  |  | 2268 | 113.4 | 2381.4 | 227911
2015-07-13 | GH071315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 9 | 24 | 4 | 16 |  |  |  | 2380 | 119 | 2499 | 227912
2015-07-14 | GH071415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1050 | 52.5 | 1102.5 | 227912
2015-07-15 | GH071515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 | 1 | 198 | [7 empty] | 0 |  | 0 | 5 | 24 | 10 | 16 |  |  |  | 2578 | 128.9 | 2706.9 | 227912
2015-07-16 | RD-071615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 2 | 24 | 4 | 16 |  |  |  | 2212 | 110.6 | 2322.6 | 227912
2015-07-16 | TN-071616 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 2100 | 105 | 2205 | 227912 | Invoice total 20706.67
2015-07-16 | GH071615 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1400 | 70 | 1470 | 227912
2015-07-17 | RD-071715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1050 | 52.5 | 1102.5 | 227912
2015-07-17 | TN-071715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1050 | 52.5 | 1102.5 | 227912
2015-07-17 | GH071715 | 0.833 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1166.2 | 58.31 | 1224.51 | 227912
2015-07-18 | RD-071815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 5 | 24 |  | 16 |  |  |  | 2220 | 111 | 2331 | 227912
2015-07-18 | TN-071815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 2100 | 105 | 2205 | 227912
2015-07-18 | GH071815 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1400 | 70 | 1470 | 227912
2015-07-20 | GH072015 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1400 | 70 | 1470 | 227913
2015-07-20 | TN-072015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 | 1 | 198 | [7 empty] | 0 |  | 0 | 5 | 24 | 5 | 16 |  |  |  | 2498 | 124.9 | 2622.9 | 227913
2015-07-21 | GH072115 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1400 | 70 | 1470 | 227913
2015-07-21 | TN-072115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 1050 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1050 | 52.5 | 1102.5 | 227913
2015-07-22 | GH072215 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1400 | 70 | 1470 | 227913
2015-07-22 | TN-072215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 | 0.5 | 198 | [7 empty] | 0 |  | 0 | 10 | 24 | 6 | 16 |  |  |  | 2535 | 126.75 | 2661.75 | 227913 | Invoice total $25,117
2015-07-23 | GH072315 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1400 | 70 | 1470 | 227913
2015-07-23 | TN-072315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 4 | 24 | 9 | 16 |  |  |  | 2340 | 117 | 2457 | 227913
2015-07-24 | GH072415 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1400 | 70 | 1470 | 227913
2015-07-24 | TN-072415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 6 | 24 | 6 | 16 |  |  |  | 2340 | 117 | 2457 | 227913
2015-07-25 | GH072515 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1400 | 70 | 1470 | 227913
2015-07-25 | TN-072515 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 | 31 | 16 |  |  |  | 3646 | 182.3 | 3828.3 | 227913
2015-07-25 | RWG-072515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 6 | 24 | 4 | 16 |  |  |  | 2308 | 115.4 | 2423.4 | 227913
2015-07-27 | GH072715 | 1 | 1400 | 0 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 |  | 16 |  |  |  | 1400 | 70 | 1470 | 227914
2015-07-27 | TN-072715 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 | 53 | 16 |  |  |  | 4838 | 241.9 | 5079.9 | 227914
2015-07-27 | RWG-072715 |  | 1400 |  | 132 |  | 3990 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 3 | 24 | 5 | 16 |  |  |  | 2252 | 112.6 | 2364.6 | 227914
2015-07-27 | RD-072719 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 2 | 24 | 2 | 16 |  |  |  | 2180 | 109 | 2289 | 227914
2015-07-28 | GH072815 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 |  | 16 |  |  |  | 1532 | 76.6 | 1608.6 | 227914
2015-07-28 | TN-072815 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 | 64 | 16 |  |  |  | 4174 | 208.7 | 4382.7 | 227914
2015-07-28 | RWG-072815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 4 | 24 | 5 | 16 |  |  |  | 2276 | 113.8 | 2389.8 | 227914
2015-07-28 | RD-072815 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 3 | 0 |  | 0 | 26 | 24 |  | 16 |  |  |  | 3774 | 188.7 | 3962.7 | 227914
2015-07-29 | GH072915 | 1 | 1400 | 2 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 |  | 16 |  |  |  | 1664 | 83.2 | 1747.2 | 227914
2015-07-29 | TN-072915 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 | 64 | 16 |  |  |  | 4174 | 208.7 | 4382.7 | 227914 | Invoice total $58,864.99
2015-07-29 | RWG-072915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 9 | 24 | 4 | 16 |  |  |  | 2380 | 119 | 2499 | 227914 | missing 3 x 16" welds RWG-073115
2015-07-29 | RD-072915 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 3 | 0 |  | 0 | 12 | 24 |  | 16 |  |  |  | 3438 | 171.9 | 3609.9 | 227914
2015-07-30 | GH073015 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 |  | 16 |  |  |  | 1532 | 76.6 | 1608.6 | 227914
2015-07-30 | TN-073015 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 | 64 | 16 |  |  |  | 4174 | 208.7 | 4382.7 | 227914
2015-07-30 | RWG-073015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 7 | 24 | 10 | 16 |  |  |  | 2428 | 121.4 | 2549.4 | 227914
2015-07-30 | RD-073015 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 3 | 0 |  | 0 | 60 | 24 |  | 16 |  |  |  | 4590 | 229.5 | 4819.5 | 227914
2015-07-31 | GH073115 | 1 | 1400 | 2 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 |  | 16 |  |  |  | 1664 | 83.2 | 1747.2 | 227914
2015-07-31 | TN-073115 |  | 1400 |  | 132 | 0.72222 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 | 1 | 0 |  | 24 | 96 | 16 |  |  |  | 3810.993 | 190.5497 | 4001.5426 | 227914
2015-07-31 | RWG-073115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 0 |  | 0 | 7 | 24 |  | 16 |  |  |  | 2268 | 113.4 | 2381.4 | 227914
2015-07-31 | RD-073115 |  | 1400 |  | 132 | 1 | 3150 | 2 | 271 |  | 2100 |  | 198 | [6 empty] | 3 | 0 |  | 0 | 26 | 24 |  | 16 |  |  |  | 4316 | 215.8 | 4531.8 | 227914
2015-08-01 | GH080115 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 0 |  | 0 |  | 24 |  | 16 |  |  |  | 1532 | 76.6 | 1608.6 | 227915
2015-08-01 | RWG-080115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 0 | 60 |  | 150 | 4 | 24 | 11 | 16 |  |  |  | 2372 | 118.6 | 2490.6 | 227915
2015-08-01 | RD-080115 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 0 | 150 | 60 | 24 |  | 16 |  |  |  | 4590 | 229.5 | 4819.5 | 227915
2015-08-01 | TN080115 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 |  | 150 |  | 24 | 74 | 16 |  |  |  | 4334 | 216.7 | 4550.7 | 227915
2015-08-01 | GMH-080115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 |  | 150 | 2 | 24 | 4 | 16 |  |  |  | 2212 | 110.6 | 2322.6 | 227915
2015-08-03 | GH080315 | 1 | 1750 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.6 | 2082.6 | 104.13 | 2186.73 | 227915
2015-08-03 | RWG-080315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2650 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 7 | 24 | 8 | 16 |  | 1 | 144.15 | 3300.15 | 165.0075 | 3465.1575 | 227915
2015-08-03 | RD-080315 |  | 1400 |  | 132 | 1 | 3950 |  | 0 |  | 2100 |  | 198 | [6 empty] | 2 | 60 | 1 | 150 | 60 | 24 |  | 16 |  | 1 | 260.19 | 5920.19 | 296.0095 | 6216.1995 | 227915
2015-08-03 | TN080315 |  | 1400 |  | 132 | 1 | 3950 |  |  |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 64 | 16 |  |  |  | 5424 | 271.2 | 5695.2 | 227915
2015-08-03 | GMH-080315 |  | 1400 |  | 132 |  | 3150 |  |  | 1 | 2650 |  | 198 | [7 empty] | 60 | 2 | 150 | 2 | 24 | 4 | 16 |  |  |  | 3062 | 153.1 | 3215.1 | 227915
2015-08-04 | GH080415 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.6 | 1732.6 | 86.63 | 1819.23 | 227915
2015-08-04 | RWG-080415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 4 | 24 | 7 | 16 |  | 1 | 144.15 | 2662.15 | 133.1075 | 2795.2575 | 227915
2015-08-04 | RD-080415 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 64 | 24 |  | 16 |  | 1 | 390.28 | 6246.28 | 312.314 | 6558.594 | 227915
2015-08-04 | TN080415 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 64 | 16 |  |  |  | 4624 | 231.2 | 4855.2 | 227915
2015-08-04 | GMH080415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 | 5 | 16 |  |  |  | 2480 | 124 | 2604 | 227915
2015-08-05 | GH080515 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.6 | 1732.6 | 86.63 | 1819.23 | 227915
2015-08-05 | RWG-080515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 7 | 24 | 5 | 16 |  | 1 | 144.14 | 2702.14 | 135.107 | 2837.247 | 227915
2015-08-05 | RD-080515 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 77 | 24 |  | 16 |  | 1 | 390.28 | 6558.28 | 327.914 | 6886.194 | 227915 | INVOICE TOTAL 122538.11
2015-08-05 | TN080515 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 33 | 16 |  |  |  | 4128 | 206.4 | 4334.4 | 227915 | need credit OF $439.99
2015-08-05 | GMH-080515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 8 | 24 | 2 | 16 |  |  |  | 2624 | 131.2 | 2755.2 | 227915
2015-08-06 | GH080615 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.6 | 1732.6 | 86.63 | 1819.23 | 227915
2015-08-06 | RWG-080615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 19 | 16 |  | 1 | 144.14 | 2758.14 | 137.907 | 2896.047 | 227915
2015-08-06 | RD-080615 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 45 | 24 |  | 16 |  | 1 | 390.28 | 5790.28 | 289.514 | 6079.794 | 227915
2015-08-06 | TN080615 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 53 | 16 |  |  |  | 4448 | 222.4 | 4670.4 | 227915
2015-08-06 | GMH080615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 3 | 24 |  | 16 |  |  |  | 2472 | 123.6 | 2595.6 | 227915
2015-08-07 | GH080715 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.6 | 1732.6 | 86.63 | 1819.23 | 227915
2015-08-07 | RWG-080715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 8 | 24 |  | 16 |  | 1 | 144.14 | 2646.14 | 132.307 | 2778.447 | 227915
2015-08-07 | RD-080715 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 43 | 24 |  | 16 |  | 1 | 390.28 | 5742.28 | 287.114 | 6029.394 | 227915
2015-08-07 | TN080715 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 64 | 16 |  |  |  | 4624 | 231.2 | 4855.2 | 227915
2015-08-07 | GMH-080715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 4 | 24 | 3 | 16 |  |  |  | 2544 | 127.2 | 2671.2 | 227915
2015-08-08 | GH080815 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.63 | 1732.63 | 86.6315 | 1819.2615 | 227915
2015-08-08 | RWG-080815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 6 | 24 | 4 | 16 |  | 1 | 144.14 | 2662.14 | 133.107 | 2795.247 | 227915
2015-08-08 | RD-080815 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 51 | 24 |  | 16 |  | 1 | 390.31 | 5934.31 | 296.7155 | 6231.0255 | 227915
2015-08-08 | TN080815 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 84 | 16 |  |  |  | 4944 | 247.2 | 5191.2 | 227915
2015-08-08 | GMH080815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 1 | 24 | 2 | 16 |  |  |  | 2456 | 122.8 | 2578.8 | 227915
2015-08-10 | GH081015 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.6 | 1732.6 | 86.63 | 1819.23 | 227916
2015-08-10 | RWG081015-1 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 6 | 24 | 10 | 16 |  | 1 | 144.14 | 2758.14 | 137.907 | 2896.047 | 227916
2015-08-10 | GMH081015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 | 1 | 198 | [7 empty] | 60 | 2 | 150 | 3 | 24 | 0 | 16 |  |  |  | 2670 | 133.5 | 2803.5 | 227916
2015-08-10 | RD-081015 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 56 | 24 |  | 16 |  | 1 | 390.29 | 6054.29 | 302.7145 | 6357.0045 | 227916
2015-08-10 | TN081015 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 64 | 16 |  |  |  | 4624 | 231.2 | 4855.2 | 227916
2015-08-11 | GH081115 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.6 | 1732.6 | 86.63 | 1819.23 | 227916
2015-08-11 | RWG081115-1 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 7 | 24 | 4 | 16 |  | 1 | 144.14 | 2686.14 | 134.307 | 2820.447 | 227916
2015-08-11 | GMH081115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 6 | 24 | 2 | 16 |  |  |  | 2576 | 128.8 | 2704.8 | 227916
2015-08-11 | RD-081115 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 49 | 24 |  | 16 |  | 1 | 390.29 | 5886.29 | 294.3145 | 6180.6045 | 227916
2015-08-11 | TN081115 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 64 | 16 |  |  |  | 4624 | 231.2 | 4855.2 | 227916
2015-08-12 | GH081215 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.6 | 1732.6 | 86.63 | 1819.23 | 227916
2015-08-12 | RWG081215-1 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 5 | 24 | 10 | 16 |  | 1 | 144.15 | 2734.15 | 136.7075 | 2870.8575 | 227916
2015-08-12 | GMH081215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 4 | 24 | 4 | 16 |  |  |  | 2560 | 128 | 2688 | 227916 | Invoice total $ 101,402.11
2015-08-12 | RD-081215 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 68 | 24 |  | 16 |  | 1 | 390.29 | 6342.29 | 317.1145 | 6659.4045 | 227916 | need credit OF $615.99
2015-08-12 | TN081215 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 64 | 16 |  |  |  | 4624 | 231.2 | 4855.2 | 227916
2015-08-13 | GH081315 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.61 | 1732.61 | 86.6305 | 1819.2405 | 227916
2015-08-13 | RWG081315-1 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 3 | 24 | 4 | 16 |  | 1 | 144.15 | 2590.15 | 129.5075 | 2719.6575 | 227916
2015-08-13 | GMH081315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 5 | 24 | 2 | 16 |  |  |  | 2552 | 127.6 | 2679.6 | 227916
2015-08-13 | RD-081315 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 67 | 24 |  | 16 |  | 1 | 390.28 | 6318.28 | 315.914 | 6634.194 | 227916
2015-08-13 | TN081315 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 64 | 16 |  |  |  | 4624 | 231.2 | 4855.2 | 227916
2015-08-14 | GH081415 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.61 | 1732.61 | 86.6305 | 1819.2405 | 227916
2015-08-14 | RWG081415-1 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 7 | 24 | 5 | 16 |  | 1 | 144.14 | 2702.14 | 135.107 | 2837.247 | 227916
2015-08-14 | GMH081415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 3 | 24 | 5 | 16 |  |  |  | 2552 | 127.6 | 2679.6 | 227916
2015-08-14 | RD-081415 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 |  | 24 |  | 16 |  | 1 | 390.28 | 4710.28 | 235.514 | 4945.794 | 227916
2015-08-14 | TN081415 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 108 | 16 |  |  |  | 5328 | 266.4 | 5594.4 | 227916
2015-08-15 | GH081515 | 1 | 1400 | 1 | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 0 |  | 24 |  | 16 |  | 1 | 140.61 | 1732.61 | 86.6305 | 1819.2405 | 227916
2015-08-15 | RWG081515-1 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 4 | 24 | 5 | 16 |  | 1 | 144.14 | 2630.14 | 131.507 | 2761.647 | 227916
2015-08-15 | GMH081515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 0 | 150 | 2 | 24 | 7 | 16 |  |  |  | 2260 | 113 | 2373 | 227916
2015-08-15 | RD-081515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 5 | 24 | 5 | 16 |  | 1 | 260.19 | 2680.19 | 134.0095 | 2814.1995 | 227916
2015-08-15 | TN081515 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 |  | 24 | 20 | 16 |  |  |  | 3920 | 196 | 4116 | 227916
2015-08-17 | GH081715 | 1 | 1400 | 1 | 132 | 0 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1732.6 | 86.63 | 1819.23 | 227917
2015-08-17 | RWG081715 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 6 | 24 | 8 | 16 |  | 1 | 144.14 | 2726.14 | 136.307 | 2862.447 | 227917
2015-08-17 | GMH081715 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 | 2 | 198 | [7 empty] | 60 | 2 | 150 | 5 | 24 | 1 | 16 |  |  |  | 2932 | 146.6 | 3078.6 | 227917
2015-08-17 | TN081715 |  | 1400 | 0 | 132 | 1 | 3150 |  | 0 | 0 | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 | 0 | 24 | 44 | 16 |  |  |  | 4304 | 215.2 | 4519.2 | 227917
2015-08-17 | RD-081715 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 32 | 24 |  | 16 |  | 1 | 390.29 | 5478.29 | 273.9145 | 5752.2045 | 227917
2015-08-18 | GH081816 | 1 | 1400 | 1 | 132 | 0 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1732.61 | 86.6305 | 1819.2405 | 227917
2015-08-18 | RWG081815 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 11 | 24 | 2 | 16 |  | 1 | 144.14 | 2750.14 | 137.507 | 2887.647 | 227917
2015-08-18 | GMH081815 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 2 | 24 | 4 | 16 |  |  |  | 2512 | 125.6 | 2637.6 | 227917
2015-08-18 | TN081815 |  | 1400 | 0 | 132 | 1 | 3150 |  | 0 | 0 | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 | 0 | 24 | 40 | 16 |  |  |  | 4240 | 212 | 4452 | 227917
2015-08-18 | RD-081815 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 22 | 24 |  | 16 |  | 1 | 390.29 | 5238.29 | 261.9145 | 5500.2045 | 227917
2015-08-19 | GH081917 | 1 | 1400 | 1 | 132 | 0 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1732.61 | 86.6305 | 1819.2405 | 227917
2015-08-19 | RWG081915 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 8 | 24 | 12 | 16 |  | 1 | 144.14 | 2838.14 | 141.907 | 2980.047 | 227917 | Invoice total $86,628.01
2015-08-19 | GMH081915 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 1 | 24 | 2 | 16 |  |  |  | 2456 | 122.8 | 2578.8 | 227917 | Needs credit of $176.94
2015-08-19 | TN081915 |  | 1400 | 0 | 132 | 1 | 3150 |  | 0 | 0 | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 | 0 | 24 | 24 | 16 |  |  |  | 3984 | 199.2 | 4183.2 | 227917
2015-08-19 | RD-081915 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 19 | 24 | 1 | 16 |  | 1 | 390.28 | 5182.28 | 259.114 | 5441.394 | 227917
2015-08-20 | GH082018 | 1 | 1400 | 1 | 132 | 0 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1732.61 | 86.6305 | 1819.2405 | 227917
2015-08-20 | RWG082015 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 15 | 24 |  | 16 |  | 1 | 144.14 | 2814.14 | 140.707 | 2954.847 | 227917
2015-08-20 | GMH082015 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 2 | 24 | 3 | 16 |  |  |  | 2496 | 124.8 | 2620.8 | 227917
2015-08-20 | TN082015 |  | 1400 | 0 | 132 | 1 | 3150 |  | 0 | 0 | 2100 |  | 198 | [7 empty] | 60 | 3 | 150 | 0 | 24 | 62 | 16 |  |  |  | 4592 | 229.6 | 4821.6 | 227917
2015-08-20 | RD-082015 |  | 1400 |  | 132 | 1 | 3150 | 1 | 840 |  | 2100 |  | 198 | [6 empty] | 3 | 60 | 1 | 150 | 31 | 24 |  | 16 |  | 1 | 390.28 | 5454.28 | 272.714 | 5726.994 | 227917
2015-08-21 | GH082119 | 1 | 1400 | 0 | 132 | 0 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 227917
2015-08-21 | RWG082115 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 8 | 24 | 10 | 16 |  | 1 | 144.15 | 2806.15 | 140.3075 | 2946.4575 | 227917
2015-08-21 | GMH082115 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 5 | 24 | 7 | 16 |  |  |  | 2632 | 131.6 | 2763.6 | 227917
2015-08-21 | RD-082115 |  | 1400 |  | 132 | 0.72222 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 1 | 24 | 4 | 16 |  | 1 | 260.19 | 2743.183 | 137.1592 | 2880.3421 | 227917
2015-08-22 | GH082220 | 1 | 1400 | 0 | 132 | 0 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 227917
2015-08-22 | RWG082215 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 6 | 24 | 8 | 16 |  | 1 | 144.15 | 2726.15 | 136.3075 | 2862.4575 | 227917
2015-08-22 | GMH082215 |  | 1400 | 0 | 132 | 0 | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 6 | 24 | 6 | 16 |  |  |  | 2640 | 132 | 2772 | 227917
2015-08-22 | RD-082215 |  | 1400 |  | 132 | 0.72222 | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 7 | 24 | 8 | 16 |  | 1 | 260.19 | 2951.183 | 147.5592 | 3098.7422 | 227917
2015-08-24 | TN082415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 5 | 24 | 4 | 16 |  |  |  | 2584 | 129.2 | 2713.2 | 229624
2015-08-24 | RWG082415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 8 | 24 | 13 | 16 |  | 1 | 144.15 | 2854.15 | 142.7075 | 2996.8575 | 229624
2015-08-24 | GMH082415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 4 | 24 | 4 | 16 |  |  |  | 2560 | 128 | 2688 | 229624
2015-08-24 | RD-082415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 4 | 24 | 5 | 16 |  | 1 | 260.19 | 2656.19 | 132.8095 | 2788.9995 | 229624
2015-08-25 | TN082515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 4 | 24 | 4 | 16 |  |  |  | 2560 | 128 | 2688 | 229624
2015-08-25 | GH082515 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1600.61 | 80.0305 | 1680.6405 | 229624
2015-08-25 | RWG082515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 7 | 24 | 9 | 16 |  | 1 | 144.15 | 2766.15 | 138.3075 | 2904.4575 | 229624
2015-08-25 | GMH082515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 4 | 24 | 2 | 16 |  |  |  | 2528 | 126.4 | 2654.4 | 229624
2015-08-25 | RD-082515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 4 | 24 | 6 | 16 | 24 | 1 | 260.19 | 2696.19 | 134.8095 | 2830.9995 | 229624
2015-08-26 | TN082615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 3 | 24 | 3 | 16 |  |  |  | 2520 | 126 | 2646 | 229624
2015-08-26 | GH082615 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1600.61 | 80.0305 | 1680.6405 | 229624
2015-08-26 | RWG082615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 9 | 24 | 3 | 16 |  | 1 | 144.15 | 2718.15 | 135.9075 | 2854.0575 | 229624 | Invoice total of $ 79,215.97
2015-08-26 | GMH082615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 3 | 24 | 1 | 16 |  |  |  | 2488 | 124.4 | 2612.4 | 229624 | Need credit of $180.38
2015-08-26 | RD-082615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 3 | 24 | 4 | 16 |  | 1 | 260.19 | 2616.19 | 130.8095 | 2746.9995 | 229624
2015-08-27 | TN082715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 9 | 24 | 8 | 16 |  |  |  | 2744 | 137.2 | 2881.2 | 229624
2015-08-27 | GH082715 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1600.61 | 80.0305 | 1680.6405 | 229624
2015-08-27 | RWG082715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 13 | 24 | 7 | 16 |  | 1 | 144.14 | 2878.14 | 143.907 | 3022.047 | 229624
2015-08-27 | GMH082715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 3 | 24 | 1 | 16 |  |  |  | 2488 | 124.4 | 2612.4 | 229624
2015-08-27 | RD-082715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 3 | 24 | 3 | 16 | 108 | 1 | 260.19 | 2708.19 | 135.4095 | 2843.5995 | 229624
2015-08-28 | TN082815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 1 | 24 | 7 | 16 |  |  |  | 2536 | 126.8 | 2662.8 | 229624
2015-08-28 | GH082815 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 229624
2015-08-28 | RWG082815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 4 | 24 | 14 | 16 |  | 1 | 144.14 | 2774.14 | 138.707 | 2912.847 | 229624
2015-08-28 | RD-082815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 6 | 24 | 6 | 16 | 48 | 1 | 260.19 | 2768.19 | 138.4095 | 2906.5995 | 229624
2015-08-29 | TN082915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 7 | 24 | 7 | 16 |  |  |  | 2680 | 134 | 2814 | 229624
2015-08-29 | GH082915 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 229624
2015-08-29 | RWG082915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 20 | 16 |  | 1 | 144.14 | 2774.14 | 138.707 | 2912.847 | 229624
2015-08-29 | RD-082915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 4 | 24 | 5 | 16 | 28 | 1 | 260.19 | 2684.19 | 134.2095 | 2818.3995 | 229624
2015-08-31 | TN083115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 6 | 24 | 6 | 16 |  |  |  | 2640 | 132 | 2772 | 229624
2015-08-31 | GH083115 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 229624
2015-08-31 | RWG083115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 31 | 16 |  | 1 | 144.14 | 2950.14 | 147.507 | 3097.647 | 229624
2015-08-31 | GMH083115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 6 | 24 | 4 | 16 |  |  |  | 2608 | 130.4 | 2738.4 | 229624
2015-08-31 | RD-083115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 |  | 24 |  | 16 | 352 | 1 | 260.19 | 2832.19 | 141.6095 | 2973.7995 | 229624
2015-09-01 | GH090115 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 229626
2015-09-01 | TN090115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 5 | 24 | 4 | 16 |  |  |  | 2584 | 129.2 | 2713.2 | 229626
2015-09-01 | RWG090115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 | 1 | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 22 | 16 |  | 1 | 144.14 | 3004.14 | 150.207 | 3154.347 | 229626
2015-09-01 | GMH090115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 5 | 24 | 5 | 16 |  |  |  | 2600 | 130 | 2730 | 229626
2015-09-01 | RD090115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 |  | 24 |  | 16 | 222 | 1 | 260.19 | 2702.19 | 135.1095 | 2837.2995 | 229626
2015-09-02 | GH090215 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1600.61 | 80.0305 | 1680.6405 | 229626 | Invoice total $ 36582.82
2015-09-02 | TN090215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 3 | 24 | 3 | 16 |  |  |  | 2520 | 126 | 2646 | 229626 | Need credit of $74.37
2015-09-02 | RWG090215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 3 | 24 | 4 | 16 |  | 1 | 144.15 | 2590.15 | 129.5075 | 2719.6575 | 229626
2015-09-02 | GMH090215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 6 | 24 | 6 | 16 |  |  |  | 2640 | 132 | 2772 | 229626
2015-09-02 | RD090215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 |  | 24 |  | 16 | 358 | 1 | 260.19 | 2838.19 | 141.9095 | 2980.0995 | 229626
2015-09-03 | GH090315 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1600.61 | 80.0305 | 1680.6405 | 229626
2015-09-03 | TN090315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 4 | 24 | 6 | 16 |  |  |  | 2592 | 129.6 | 2721.6 | 229626
2015-09-03 | RWG090315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 4 | 24 | 4 | 16 |  | 1 | 144.15 | 2614.15 | 130.7075 | 2744.8575 | 229626
2015-09-03 | GMH090315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 2 | 24 | 2 | 16 |  |  |  | 2480 | 124 | 2604 | 229626
2015-09-03 | RD090315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 3 | 24 | 4 | 16 |  | 1 | 260.19 | 2616.19 | 130.8095 | 2746.9995 | 229626
2015-09-08 | GH090815 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 229630
2015-09-08 | TN-090815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [7 empty] | 60 | 1 | 150 |  | 24 |  | 16 |  |  |  | 1200 | 60 | 1260 | 229630
2015-09-08 | RWG090815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 144.14 | 1254.14 | 62.707 | 1316.847 | 229630
2015-09-08 | GMH090815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [7 empty] | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 1050 | 52.5 | 1102.5 | 229630
2015-09-08 | RD-090815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 |  | 24 |  | 16 | 324 | 1 | 260.19 | 2804.19 | 140.2095 | 2944.3995 | 229630
2015-09-09 | GH090915 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1600.61 | 80.0305 | 1680.6405 | 229630
2015-09-09 | TN-090915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [7 empty] | 60 | 1 | 150 |  | 24 |  | 16 |  |  |  | 1200 | 60 | 1260 | 229630
2015-09-09 | RWG090915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 144.14 | 1254.14 | 62.707 | 1316.847 | 229630
2015-09-09 | GMH090915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [7 empty] | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 1050 | 52.5 | 1102.5 | 229630
2015-09-09 | RD-090915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 3 | 24 |  | 16 | 136 | 1 | 260.19 | 2688.19 | 134.4095 | 2822.5995 | 229630
2015-09-10 | GH091015 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1600.61 | 80.0305 | 1680.6405 | 229630
2015-09-10 | TN-091015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 | 1 | 198 | [7 empty] | 60 | 2 | 150 | 3 | 24 | 2 | 16 |  |  |  | 2702 | 135.1 | 2837.1 | 229630
2015-09-10 | RWG091015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 | 1 | 198 | [6 empty] | 1 | 60 | 1 | 150 | 5 | 24 | 5 | 16 |  | 1 | 144.14 | 2852.14 | 142.607 | 2994.747 | 229630 | Invoice total $62,571.64
2015-09-10 | GMH091015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [7 empty] | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 1050 | 52.5 | 1102.5 | 229630 | Need credit of $156.74
2015-09-10 | RD-091015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 |  | 24 |  | 16 | 400 | 1 | 260.19 | 2880.19 | 144.0095 | 3024.1995 | 229630
2015-09-11 | GH091115 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.61 | 1600.61 | 80.0305 | 1680.6405 | 229630
2015-09-11 | TN-091115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 9 | 24 | 3 | 16 |  |  |  | 2664 | 133.2 | 2797.2 | 229630
2015-09-11 | RWG091115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 5 | 24 | 9 | 16 |  | 1 | 144.15 | 2718.15 | 135.9075 | 2854.0575 | 229630
2015-09-11 | GMH091115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 3 | 24 | 5 | 16 |  |  |  | 2552 | 127.6 | 2679.6 | 229630
2015-09-11 | RD-091115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 |  | 24 |  | 16 | 248 | 1 | 260.19 | 2728.19 | 136.4095 | 2864.5995 | 229630
2015-09-12 | GH091215 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 229630
2015-09-12 | TN-091215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 5 | 24 | 4 | 16 |  |  |  | 2584 | 129.2 | 2713.2 | 229630
2015-09-12 | RWG091215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 5 | 24 | 8 | 16 |  | 1 | 144.14 | 2702.14 | 135.107 | 2837.247 | 229630
2015-09-12 | GMH091215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 5 | 24 | 8 | 16 |  |  |  | 2648 | 132.4 | 2780.4 | 229630
2015-09-12 | RD-091215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 |  | 24 |  | 16 | 200 | 1 | 260.19 | 2680.19 | 134.0095 | 2814.1995 | 229630
2015-09-13 | GH091315 | 1 | 1750 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [7 empty] | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1890.6 | 94.53 | 1985.13 | 229630
2015-09-13 | RWG091315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2650 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 5 | 16 |  | 1 | 144.15 | 3084.15 | 154.2075 | 3238.3575 | 229630
2015-09-13 | GMH091315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2650 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 | 8 | 16 |  |  |  | 3078 | 153.9 | 3231.9 | 229630
2015-09-13 | RD-091315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2650 |  | 198 | [6 empty] | 2 | 60 |  | 150 | 6 | 24 | 5 | 16 |  | 1 | 260.19 | 3254.19 | 162.7095 | 3416.8995 | 229630
2015-09-14 | GH091415 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 339632
2015-09-14 | TN-091415 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 | 4 | 24 | 3 | 16 |  |  |  | 2544 | 127.2 | 2671.2 | 339632
2015-09-14 | RWG-091415 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 7 | 16 |  | 1 | 144.14 | 2566.14 | 128.307 | 2694.447 | 339632
2015-09-14 | GMH091415 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 | 11 | 16 | 44 |  |  | 2620 | 131 | 2751 | 339632
2015-09-14 | RD091415 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 2 | 60 |  | 150 |  | 24 | 7 | 16 |  | 1 | 260.19 | 2592.19 | 129.6095 | 2721.7995 | 339632
2015-09-15 | GH091515 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 339632
2015-09-15 | RWG-091515 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 0.5 | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 144.14 | 1254.14 | 62.707 | 1316.847 | 339632
2015-09-15 | GMH091515 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 |  | 16 |  |  |  | 2400 | 120 | 2520 | 339632
2015-09-16 | GH091615 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 339632 | Invoice total $42,190.69
2015-09-16 | TN-091615 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 |  | 16 | 100 |  |  | 2500 | 125 | 2625 | 339632 | Need credit of $78.24
2015-09-16 | RWG091615 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 0.5 | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 144.14 | 1254.14 | 62.707 | 1316.847 | 339632
2015-09-17 | GH091715 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 339632
2015-09-17 | TN-091715 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 |  | 16 | 166 |  |  | 2566 | 128.3 | 2694.3 | 339632
2015-09-17 | RWG-091715 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 0.66667 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 9 | 16 |  | 1 | 144.14 | 1898.147 | 94.9074 | 1993.0543 | 339632
2015-09-18 | GH091815 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 339632
2015-09-18 | TN-091815 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 | 5 | 16 |  |  |  | 2480 | 124 | 2604 | 339632
2015-09-18 | RWG-091815 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 10 | 16 |  | 1 | 144.14 | 2614.14 | 130.707 | 2744.847 | 339632
2015-09-19 | GH091915 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 140.6 | 1600.6 | 80.03 | 1680.63 | 339632
2015-09-19 | TN-091915 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 |  | 16 | 244 |  |  | 2644 | 132.2 | 2776.2 | 339632
2015-09-19 | RWG-091915 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 1 | 24 | 11 | 16 |  | 1 | 144.14 | 2654.14 | 132.707 | 2786.847 | 339632
2015-09-21 | GH092215 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236335
2015-09-21 | TN-092115 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 |  | 16 | 222 |  |  | 2622 | 131.1 | 2753.1 | 236335
2015-09-21 | RWG-092115 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 5 | 16 |  | 1 | 138.6 | 2528.6 | 126.43 | 2655.03 | 236335
2015-09-22 | GH092215 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236335 | TOTAL $29,450.30
2015-09-22 | TN092215 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [7 empty] | 60 | 2 | 150 |  | 24 |  | 16 | 172 |  |  | 2572 | 128.6 | 2700.6 | 236335
2015-09-22 | RWG092215 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 0.83333 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 5 | 16 |  | 1 | 138.6 | 2178.5993 | 108.93 | 2287.5293 | 236335
2015-09-23 | GH092315 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236335
2015-09-23 | TN092315 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 0.5 | 2100 |  | 198 | [7 empty] | 60 | 1 | 150 |  | 24 |  | 16 | 46 |  |  | 1246 | 62.3 | 1308.3 | 236335
2015-09-23 | RWG092315 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 4 | 24 | 5 | 16 |  | 1 | 138.6 | 2624.6 | 131.23 | 2755.83 | 236335
2015-09-24 | GH092415 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236335
2015-09-24 | RWG092415 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 0.83333 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 4 | 24 | 4 | 16 |  | 1 | 138.6 | 2258.5993 | 112.93 | 2371.5293 | 236335
2015-09-25 | GH092515 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236335
2015-09-25 | RWG092515 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 1050 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 |  | 16 |  | 1 | 138.6 | 1398.6 | 69.93 | 1468.53 | 236335
2015-09-26 | GH092615 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236335
2015-09-26 | RWG092615 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 |  | 16 |  | 1 | 138.6 | 2448.6 | 122.43 | 2571.03 | 236335
2015-09-28 | GH092815 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236339
2015-09-28 | RWG092815 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 3 | 24 | 5 | 16 |  | 1 | 138.6 | 2600.6 | 130.03 | 2730.63 | 236339
2015-09-29 | GH092915 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236339
2015-09-29 | RWG092915 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 0.66666 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 2 | 16 |  | 1 | 138.6 | 1780.5965 | 89.0298 | 1869.6263 | 236339
2015-09-30 | GH090315 | 1 | 1400 |  | 132 | 0 | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236339 | TOTAL $26,759.68
2015-09-30 | RWG-093015 |  | 1400 |  | 132 | 0 | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 3 | 24 | 4 | 16 |  | 1 | 138.6 | 2584.6 | 129.23 | 2713.83 | 236339 | Pending corrections
2015-10-01 | GH100115 | 1 | 1400 |  | 132 |  | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236339
2015-10-01 | RWG100115 |  | 1400 |  | 132 |  | 3150 | 0 | 0 | 0.66666 | 2100 | 1 | 198 | [6 empty] | 1 | 60 | 1 | 150 | 2 | 24 | 12 | 16 |  | 1 | 138.6 | 2186.5965 | 109.3298 | 2295.9263 | 236339
2015-10-02 | GH100215 | 0.5 | 1400 |  | 132 |  | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 895.45 | 44.7725 | 940.2225 | 236339
2015-10-02 | RWG100215 |  | 1400 |  | 132 |  | 3150 | 0 | 0 | 1 | 2100 | 1 | 198 | [6 empty] | 1 | 60 | 1 | 150 | 6 | 24 | 4 | 16 |  | 1 | 138.6 | 2854.6 | 142.73 | 2997.33 | 236339
2015-10-03 | GH100315 | 0.5 | 1400 |  | 132 |  | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 895.45 | 44.7725 | 940.2225 | 236339
2015-10-03 | RWG100315 |  | 1400 |  | 132 |  | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 7 | 24 | 6 | 16 |  | 1 | 138.6 | 2712.6 | 135.63 | 2848.23 | 236339
2015-10-04 | GH100415 | 0.5 | 1750 |  | 132 |  | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1070.45 | 53.5225 | 1123.9725 | 236339
2015-10-04 | RWG100415 |  | 1400 |  | 132 |  | 3150 | 0 | 0 | 0.83334 | 2650 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 8 | 24 | 3 | 16 |  | 1 | 138.6 | 2796.9378 | 139.8469 | 2936.7846 | 236339
2015-10-05 | GH100515 | 1 | 1400 |  | 132 |  | 3150 | 0 | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236347
2015-10-05 | RWG100515 |  | 1400 |  | 132 |  | 3150 | 0 | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 6 | 16 |  | 1 | 138.6 | 2544.6 | 127.23 | 2671.83 | 236347 | TOTAL $ 9,770.70
2015-10-06 | RWG100615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 | 2 | 24 | 1 | 16 | 60 | 1 | 138.6 | 2572.6 | 128.63 | 2701.23 | 236347 | Pending corrections
2015-10-07 | GH100715 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236347
2015-10-07 | RWG100715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 | 4 | 16 |  | 1 | 138.6 | 1462.6 | 73.13 | 1535.73 | 236347
2015-10-13 | GH101315 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | [6 empty] | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-13 | RWG101315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.33333 | 2100 |  | 198 | [6 empty] | 1 | 60 | 1 | 150 |  | 24 |  | 16 | 40 | 1 | 138.6 | 1088.5951 | 54.4298 | 1143.0249 | 235529
2015-10-14 | RWG-101415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  |  |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 17 | 16 |  | 1 | 138.6 | 2720.6 | 136.03 | 2856.63 | 235529
2015-10-14 | AJB-0032 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  |  | 8 | 88.48 | 8 | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 1284.96 | 64.248 | 1349.208 | 235529
2015-10-15 | GH-101515 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-15 | RD-101515 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 1 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 14 | 16 |  | 1 | 247.8 | 2866.8 | 143.34 | 3010.14 | 235529
2015-10-15 | RWG-101515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 1 | 16 |  | 1 | 138.6 | 2464.6 | 123.23 | 2587.83 | 235529
2015-10-16 | RD-101615 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 0.16667 | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 379.1743 | 18.9587 | 398.133 | 235529
2015-10-16 | RWG-101615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 | 7 | 24 |  | 16 |  | 1 | 138.6 | 2616.6 | 130.83 | 2747.43 | 235529
2015-10-17 | GH-101715 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-17 | RD-101715-2 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 0.25 | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 568.75 | 28.4375 | 597.1875 | 235529
2015-10-17 | RWG-101715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 | 0 | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 9 | 16 |  | 1 | 138.6 | 2592.6 | 129.63 | 2722.23 | 235529
2015-10-18 | GH-101815 | 1 | 1750 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1945.45 | 97.2725 | 2042.7225 | 235529
2015-10-18 | RWG-101815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2650 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 7 | 16 |  | 1 | 138.6 | 1785.6 | 89.28 | 1874.88 | 235529
2015-10-19 | RWG-101915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 6 | 16 |  | 1 | 138.6 | 1494.6 | 74.73 | 1569.33 | 235529
2015-10-20 | RWG-102015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.66666 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 3 | 16 |  | 1 | 138.6 | 1796.5965 | 89.8298 | 1886.4263 | 235529
2015-10-21 | GH-102115 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-21 | RD-102115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0 | 2100 |  | 198 | 1 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 13 | 16 |  | 1 | 247.8 | 2850.8 | 142.54 | 2993.34 | 235529
2015-10-21 | RWG-102115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 | 2 | 24 | 5 | 16 |  | 1 | 138.6 | 2576.6 | 128.83 | 2705.43 | 235529
2015-10-22 | GH-102215 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-22 | RD-102215 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 1 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 14 | 16 |  | 1 | 247.8 | 2866.8 | 143.34 | 3010.14 | 235529
2015-10-22 | RWG-102215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 4 | 16 |  | 1 | 138.6 | 2512.6 | 125.63 | 2638.23 | 235529
2015-10-23 | GH-102315 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-23 | RD-102315 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 1 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 3 | 16 |  | 1 | 247.8 | 2690.8 | 134.54 | 2825.34 | 235529
2015-10-23 | RWG-102315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 2 | 16 |  | 1 | 138.6 | 2480.6 | 124.03 | 2604.63 | 235529
2015-10-24 | GH-102415 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-24 | RWG-102415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 3 | 16 |  | 1 | 138.6 | 2496.6 | 124.83 | 2621.43 | 235529 | Invoice total $91,426.44
2015-10-24 | RD-102415 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 1 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 3 | 16 |  | 1 | 247.8 | 2690.8 | 134.54 | 2825.34 | 235529
2015-10-25 | GH-102515 | 1 | 1750 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1945.45 | 97.2725 | 2042.7225 | 235529
2015-10-25 | RWG-102515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2650 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 1 | 16 |  | 1 | 138.6 | 3014.6 | 150.73 | 3165.33 | 235529
2015-10-25 | RD-102515 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2650 |  | 198 | 1 | 2852 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 6 | 16 |  | 1 | 247.8 | 3315.8 | 165.79 | 3481.59 | 235529
2015-10-26 | RD-102615 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 1 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 9 | 16 |  | 1 | 247.8 | 2786.8 | 139.34 | 2926.14 | 235529
2015-10-27 | RD-102715-2&1 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 0.75 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 6 | 16 |  | 1 | 247.8 | 2170.05 | 108.5025 | 2278.5525 | 235529
2015-10-27 | RWG-102715 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 | 1 | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 | 2 | 24 | 2 | 16 |  | 1 | 138.6 | 1676.6 | 83.83 | 1760.43 | 235529
2015-10-27 | GH-102715 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-28 | RWG-102815 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.83333 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 2 | 16 | 12 | 1 | 138.6 | 2142.5999 | 107.13 | 2249.7299 | 235529
2015-10-28 | RD-102815 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 0.5 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 7 | 16 |  | 1 | 247.8 | 1617.3 | 80.865 | 1698.165 | 235529
2015-10-29 | RWG-102915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 | 1 | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 | 5 | 24 | 5 | 16 | 6 | 1 | 138.6 | 2852.6 | 142.63 | 2995.23 | 235529
2015-10-29 | RD-102915 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 | 0.91667 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 7 | 16 |  | 1 | 247.8 | 2565.2151 | 128.2608 | 2693.4759 | 235529
2015-10-29 | GH-102915 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-30 | GH-103015 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 235529
2015-10-30 | RD-103015 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 | 1 | 205 | 1 | 2275 |  | 88.48 |  | 72.14 | 2 | 60 |  | 150 |  | 24 | 6 | 16 |  | 1 | 247.8 | 2943.8 | 147.19 | 3090.99 | 235529
2015-10-30 | RWG-103015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 | 4 | 24 | 2 | 16 |  | 1 | 138.6 | 2576.6 | 128.83 | 2705.43 | 235529
2015-10-31 | RWG-103115 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 | 2 | 16 | 12 |  |  | 1094 | 54.7 | 1148.7 | 235529
2015-11-02 | RWG-110215 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 | 1 | 24 |  | 16 |  |  |  | 1074 | 53.7 | 1127.7 | 236395
2015-11-02 | AJB-0033 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 | 6 | 88.48 | 6 | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 963.72 | 48.186 | 1011.906 | 236395
2015-11-03 | RWG-110315 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 | 4 | 24 | 2 | 16 |  | 1 | 138.6 | 2576.6 | 128.83 | 2705.43 | 236395
2015-11-03 | RWG-110315 |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 | 2 | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 | 2 | 16 |  |  |  | 428 | 21.4 | 449.4 | 236395
2015-11-04 | RWG-110415 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 | 1 | 24 | 3 | 16 | 44 |  |  | 1166 | 58.3 | 1224.3 | 236395 | Invoice total $18514.47
2015-11-05 | RWG-110515 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.25 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 | 6 |  |  | 531 | 26.55 | 557.55 | 236395
2015-11-06 | RWG-110615 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.5 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 |  | 16 | 42 | 1 | 138.6 | 1440.6 | 72.03 | 1512.63 | 236395
2015-11-09 | GH-110915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 |  | 24 | 2 | 16 |  | 1 | 135.45 | 2477.45 | 123.8725 | 2601.3225 | 236395
2015-11-09 | RWG-110915 |  | 1400 |  | 132 |  | 3150 |  | 0 | 1 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 | 1 | 24 | 2 | 16 |  | 1 | 138.6 | 2504.6 | 125.23 | 2629.83 | 236395
2015-11-10 | GH-111015 | 1 | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1595.45 | 79.7725 | 1675.2225 | 236395
2015-11-10 | RWG-111015 |  | 1400 |  | 132 |  | 3150 |  | 0 | 0.67 | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 | 1 | 150 | 1 | 24 | 2 | 16 |  | 1 | 138.6 | 1811.6 | 90.58 | 1902.18 | 236395
2015-11-11 | GH-111115 | 1 | 1750 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 | 1 | 60 |  | 150 |  | 24 |  | 16 |  | 1 | 135.45 | 1945.45 | 97.2725 | 2042.7225 | 236395
2015-12-08 | RWG - 081215 |  | 1400 |  | 132 | 1 | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 | 3 | 150 | 1 | 24 |  | 16 | 4 |  |  | 3628 | 181.4 | 3809.4 | 237756
2015-12-14 | Credit |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | -1283.05 | -64.1525 | -1347.2025 | 237756
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  | 88.48 |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  |  |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 |  |  |  | 72.14 |  | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 | [5 empty] | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
|  |  | 1400 |  | 132 |  | 3150 |  | 0 |  | 2100 |  | 198 |  | 2275 | [5 empty] | 60 |  | 150 |  | 24 |  | 16 |  |  |  | 0 | 0 | 0
Note on U3: sacookadmin

## Paragon
Paragon
Date | Ticket Number | Stephanie Drobot | day Rate | Blair | Hr Rate | Vehicle | Rate | KM >150 | Rate | Equipment package | rate | ATV | Rate | LOA | Rate | KM's | Rate | 24" 11.1 | 16" 9.5 | 16" 7.1 | Films | Subtotal | GST | LEM Amount | Affiliating Invoice | SUM OF ALL LEM'S (before GST)
2015-06-08 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5420 | 131560.7
2015-06-09 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5420
2015-06-10 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5420
2015-06-15 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5420
2015-06-16 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5420
2015-06-17 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5420
2015-06-18 |  | 0.5 | 1000 |  | 125 | 0.5 | 150 |  | 0.9 | 0.5 | 50 | 0.5 | 150 | [8 empty] | 675 | 33.75 | 708.75 | 5420
2015-06-19 |  | 1 | 1000 |  | 125 | 1 | 150 | 30 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1377 | 68.85 | 1445.85 | 5420
2015-06-20 |  | 1 | 1000 |  | 125 | 1 | 150 | 30 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1377 | 68.85 | 1445.85 | 5420
2015-06-22 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5420
2015-06-23 |  | 1 | 1000 |  | 125 | 1 | 150 | 20 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1368 | 68.4 | 1436.4 | 5420
2015-06-24 |  | 1 | 1000 |  | 125 | 1 | 150 | 7 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1356.3 | 67.815 | 1424.115 | 5420
2015-06-25 |  | 1 | 1000 |  | 125 | 1 | 150 | 67 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1410.3 | 70.515 | 1480.815 | 5420
2015-06-26 |  | 1 | 1000 |  | 125 | 1 | 150 | 10 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1359 | 67.95 | 1426.95 | 5420
2015-06-27 |  | 1 | 1000 |  | 125 | 1 | 150 | 36 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1382.4 | 69.12 | 1451.52 | 5420
2015-06-29 |  | 1 | 1000 |  | 125 | 1 | 150 | 15 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1363.5 | 68.175 | 1431.675 | 5420
2015-06-30 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5420
2015-07-01 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5459
2015-07-02 |  | 1 | 1000 |  | 125 | 1 | 150 | 24 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1371.6 | 68.58 | 1440.18 | 5459
2015-07-03 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5459
2015-07-04 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5459
2015-07-06 |  | 1 | 1000 |  | 125 | 1 | 150 | 10 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1359 | 67.95 | 1426.95 | 5459
2015-07-07 |  | 1 | 1000 |  | 125 | 1 | 150 | 20 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1368 | 68.4 | 1436.4 | 5459
2015-07-08 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5459
2015-07-09 |  | 1 | 1000 |  | 125 | 1 | 150 | 10 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1359 | 67.95 | 1426.95 | 5459
2015-07-10 |  | 1 | 1000 |  | 125 | 1 | 150 | 13 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1361.7 | 68.085 | 1429.785 | 5459
2015-07-11 |  | 1 | 1000 |  | 125 | 1 | 150 | 10 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1359 | 67.95 | 1426.95 | 5459
2015-07-14 |  | 1 | 1000 |  | 125 | 1 | 150 | 50 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1395 | 69.75 | 1464.75 | 5459
2015-07-14 |  |  | 1000 | 10.5 | 125 | 1 | 150 |  | 0.9 | 1 | 50 |  | 150 | [8 empty] | 1512.5 | 75.625 | 1588.125 | 5459
2015-07-15 |  |  | 1000 | 12 | 125 | 1 | 150 |  | 0.9 | 1 | 50 |  | 150 | [8 empty] | 1700 | 85 | 1785 | 5459
2015-07-15 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5459
2015-07-16 |  | 0.5 | 1000 | 4 | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 0.5 | 150 | [8 empty] | 1275 | 63.75 | 1338.75 | 5459
2015-07-20 |  | 1 | 1000 | 1 | 125 | 1 | 150 | 17 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1490.3 | 74.515 | 1564.815 | 5459
2015-07-21 |  | 1 | 1000 |  | 125 | 1 | 150 | 64 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1407.6 | 70.38 | 1477.98 | 5459
2015-07-22 |  | 1 | 1000 |  | 125 | 1 | 150 | 94 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1434.6 | 71.73 | 1506.33 | 5459
2015-07-23 |  | 1 | 1000 |  | 125 | 1 | 150 | 57 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1401.3 | 70.065 | 1471.365 | 5459
2015-07-24 |  | 1 | 1000 |  | 125 | 1 | 150 | 47 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1392.3 | 69.615 | 1461.915 | 5459
2015-07-25 |  | 1 | 1000 |  | 125 | 1 | 150 | 100 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1440 | 72 | 1512 | 5459
2015-07-27 |  | 1 | 1000 |  | 125 | 1 | 150 | 50 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1395 | 69.75 | 1464.75 | 5459
2015-07-28 |  | 1 | 1000 |  | 125 | 1 | 150 | 20 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1368 | 68.4 | 1436.4 | 5459
2015-07-29 |  | 1 | 1000 |  | 125 | 1 | 150 | 0 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5459
2015-07-30 |  | 1 | 1000 |  | 125 | 1 | 150 | 0 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5459
2015-07-31 |  | 1 | 1000 |  | 125 | 1 | 150 | 26 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1373.4 | 68.67 | 1442.07 | 5459
2015-08-01 |  | 1 | 1000 |  | 125 | 1 | 150 | 50 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1395 | 69.75 | 1464.75 | 5502
2015-08-03 |  | 1 | 1000 |  | 125 | 1 | 150 | 61 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1404.9 | 70.245 | 1475.145 | 5502
2015-08-27 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5502
2015-08-28 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5502
2015-08-29 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5502
2015-08-30 |  |  | 1000 |  | 125 |  | 150 |  | 0.9 |  | 50 | [10 empty] | 0 | 0 | 0 | 5502
2015-08-31 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5502 | Invoice 5502 | 8199.9
2015-09-01 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-02 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-03 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-04 | [6 empty] | 0 |  | 0 |  |  |  | 0 | [8 empty] | 0 | 0 | 0
2015-09-05 | [6 empty] | 0 |  | 0 |  |  |  | 0 | [8 empty] | 0 | 0 | 0
2015-09-06 | [6 empty] | 0 |  | 0 |  |  |  | 0 | [8 empty] | 0 | 0 | 0
2015-09-07 | [6 empty] | 0 |  | 0 |  |  |  | 0 | [8 empty] | 0 | 0 | 0
2015-09-08 | [6 empty] | 0 |  | 0 |  |  |  | 0 | [8 empty] | 0 | 0 | 0
2015-09-09 | [6 empty] | 0 |  | 0 |  |  |  | 0 | [8 empty] | 0 | 0 | 0
2015-09-10 | [6 empty] | 0 |  | 0 |  |  |  | 0 | [8 empty] | 0 | 0 | 0
2015-09-11 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-12 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-13 |  | 0.5 | 1000 |  | 125 | 0.5 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 775 | 38.75 | 813.75 | 5582
2015-09-14 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-15 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-16 |  | 0 | 0 |  | 125 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0
2015-09-17 |  | 0 | 0 |  | 125 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0
2015-09-18 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-19 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-20 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-21 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-22 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-23 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-24 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-25 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-26 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-27 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-28 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-29 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582
2015-09-30 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5582 | Invoice 5582 29163.75
2015-10-01 |  | 1 | 1000 |  | 125 | 1 | 150 | 20 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1368 | 68.4 | 1436.4 | 5687
2015-10-02 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-03 |  | 1 | 1000 |  | 125 | 1 | 150 | 10 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1359 | 67.95 | 1426.95 | 5687
2015-10-04 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-05 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-06 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-07 |  | 1 | 1000 |  | 125 | 1 | 150 | 40 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1386 | 69.3 | 1455.3 | 5687
2015-10-08 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-14 |  | 1 | 1000 | 12 | 125 | 2 | 150 | 130 | 0.9 | 2 | 50 | 1 | 150 | [8 empty] | 3167 | 158.35 | 3325.35 | 5687
2015-10-15 |  | 1 | 1000 | 12 | 125 | 2 | 150 | 50 | 0.9 | 2 | 50 | 1 | 150 | [8 empty] | 3095 | 154.75 | 3249.75 | 5687
2015-10-16 |  | 1 | 1000 | 12 | 125 | 2 | 150 | 18 | 0.9 | 2 | 50 | 1 | 150 | [8 empty] | 3066.2 | 153.31 | 3219.51 | 5687
2015-10-17 |  | 1 | 1000 | 10 | 125 | 2 | 150 | 20 | 0.9 | 2 | 50 | 1 | 150 | [8 empty] | 2818 | 140.9 | 2958.9 | 5687
2015-10-18 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-19 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-20 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-21 |  | 1 | 1000 |  | 125 | 1 | 150 | 20 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1368 | 68.4 | 1436.4 | 5687
2015-10-22 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-23 |  | 1 | 1000 |  | 125 | 1 | 150 |  | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1350 | 67.5 | 1417.5 | 5687
2015-10-24 |  | 1 | 1000 |  | 125 | 1 | 150 | 95 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1435.5 | 71.775 | 1507.275 | 5687
2015-10-25 |  | 1 | 1000 |  | 125 | 1 | 150 | 125 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1462.5 | 73.125 | 1535.625 | 5687
2015-10-26 |  | 1 | 1000 |  | 125 | 1 | 150 | 32 | 0.9 | 1 | 50 | 1 | 150 | [8 empty] | 1378.8 | 68.94 | 1447.74 | 5687
2015-10-28 |  | 1 | 1000 |  | 125 |  | 150 |  | 0.9 |  | 50 | 0 | 150 | [8 empty] | 1000 | 50 | 1050 | 5687
Oct |  |  | 1000 | 4 | 125 |  | 150 |  | 0.9 |  | 50 |  | 150 | [8 empty] | 500 | 25 | 525 | 5687

## Corrpro
Corrpro
Date | Ticket Number | JAMES VAFAEI | Emre Tezcan/ Daniel Gorrill | 4X4 TRUCK | PIN BRAZER | TYPE A TEST STATION | Misc. Materials | Misc. Equipment | LOA | Continuity Test Bore 5 | Principal Engineer | Junior Tech. | EIT Level 1 | Project co-ordinator | Operator | equip op | Third party rental | LOA | Rate | KM's | Rate | 24" 11.1 | 16" 9.5 | 16" 7.1 | Films | Subtotal | GST | LEM Amount | Affiliating Invoice | SUM OF ALL LEM'S (before GST)
|  | PER DAY | per hour | PER DAY | PER DAY | PER UNIT | [23 empty] | 247659.15
RATE |  | 1260 | 90 | 324 | 150 | 461.6 | 1 | 1 | 25 | 90 | 210 | 75 | 90 | 115 | 80 | 60 | 1
2015-08-15 | 15076 | 1 |  | 1 | [21 empty] | 1584 | 79.2 | 1663.2 | 348497
2015-08-22 | 15080 | 1 |  | 1 | 1 | 2 | [19 empty] | 2657.2 | 132.86 | 2790.06 | 348497
2015-08-24 | 15082 | 1 |  | 1 | 1 | 2 | [19 empty] | 2657.2 | 132.86 | 2790.06 | 348497
2015-08-25 | 15081 | 1 |  | 1 | 1 | 2 | [19 empty] | 2657.2 | 132.86 | 2790.06 | 348497
2015-08-26 | 15083 | 1 |  | 1 | 1 | 2 | [19 empty] | 2657.2 | 132.86 | 2790.06 | 348497
2015-08-27 | 15084 | 1 |  | 1 | 1 | 0 | [19 empty] | 1734 | 86.7 | 1820.7 | 348497
2015-08-28 | 15085 | 1 |  | 1 | 1 | 0 | [19 empty] | 1734 | 86.7 | 1820.7 | 348497
2015-08-29 | 15087 | 1 |  | 1 | 1 | 0 | 923.2 | [18 empty] | 2657.2 | 132.86 | 2790.06 | 348497
2015-09-01 | 15089 | 1 |  | 1 | 1 | 0 | 923.2 | [18 empty] | 2657.2 | 132.86 | 2790.06 | 348497
2015-08-31 | 15090 | 1 |  | 1 | 1 | 0 | 1888.69 | [18 empty] | 3622.69 | 181.1345 | 3803.8245 | 348497
2015-09-02 | 15093 | 0 |  | 0 | 0 | 0 |  | 650 |  | 11 | [15 empty] | 1640 | 82 | 1722 | 348497
2015-09-11 | 15095 | 1 |  | 1 | 1 |  | 4464.9 | [18 empty] | 6198.9 | 309.945 | 6508.845 | 348497
2015-09-12 | 15096 | 1 |  | 1 | 1 |  | 1198.8 | [18 empty] | 2932.8 | 146.64 | 3079.44 | 348497
2015-09-14 | 15097 | 1 |  | 1 | 1 |  | 2191.3 | [18 empty] | 3925.3 | 196.265 | 4121.565 | 348497
2015-09-18 | 15098 | 1 |  | 1 | 1 |  | 923.2 | [18 empty] | 2657.2 | 132.86 | 2790.06 | 348497
2015-09-19 | 15099 | 1 |  | 1 | 1 |  | 468.9 | [18 empty] | 2202.9 | 110.145 | 2313.045 | 348497
2015-09-21 | 10503 | 1 |  | 1 | 0 |  | 143.75 | [18 empty] | 1727.75 | 86.3875 | 1814.1375 | 348497
2015-09-22 | 10504 | 1 |  | 1 | 0 |  | 1154.23 | [18 empty] | 2738.23 | 136.9115 | 2875.1415 | 348497
2015-09-23 | 10505 | 1 | 13.5 | 2 | 0 |  | 2494.65 | [18 empty] | 5617.65 | 280.8825 | 5898.5325 | 348497
2015-09-22 | 10509 | 0 | 15.5 | 1 | 0 | [20 empty] | 1719 | 85.95 | 1804.95 | 348497
2015-09-24 | 10506 | 1 | 11 | 1 | 0 |  |  | 2681.54 | 24.5 | [16 empty] | 5868.04 | 293.402 | 6161.442 | 348497
2015-09-25 | 10507 | 1 | 11.5 | 1 | 0 |  |  | 509.76 | 11.5 | [16 empty] | 3416.26 | 170.813 | 3587.073 | 348497
2015-09-27 | 10510 | [7 empty] | 10 | [16 empty] | 250 | 12.5 | 262.5 | 348497
2015-09-28 | 10511 | 1 | 11 | 1 | 0 |  |  | 2766.48 | 11 | [16 empty] | 5615.48 | 280.774 | 5896.254 | 348497
2015-09-29 | 10512 | 1 | 13.5 | 1 | 0 |  |  | 401.18 | 13.5 | [16 empty] | 3537.68 | 176.884 | 3714.564 | 348497
2015-09-30 | 10513 | 1 | 11.5 | 1 | 0 |  |  | 401.18 | 11.5 | [16 empty] | 3307.68 | 165.384 | 3473.064 | 348497
2015-10-01 | 10514 | 1 | 11 | 1 | 0 |  |  | 375 | 11 | [16 empty] | 3224 | 161.2 | 3385.2 | 348497
2015-09-26 | 10508 | 1 |  | 1 | 1 |  |  | 1334.7 | 11 | 11 | [15 empty] | 4333.7 | 216.685 | 4550.385 | 349399
2015-10-02 | 10515 | 1 |  | 2 |  |  |  |  | 12 | 12 | [15 empty] | 3288 | 164.4 | 3452.4 | 349399
2015-10-03 | 10516 | 1 |  | 1 | 1 |  |  | 923.2 | [17 empty] | 2657.2 | 132.86 | 2790.06 | 349399
2015-10-05 | 10517 | 1 |  | 1 | 1 |  |  | 1776.8 | [17 empty] | 3510.8 | 175.54 | 3686.34 | 349399
2015-10-06 | 10519 | 1 |  | 1 | 0 |  |  | 1929.44 | [17 empty] | 3513.44 | 175.672 | 3689.112 | 349399
2015-10-07 | 10520 | 1 |  | 1 | 0 |  |  | 5525 | [17 empty] | 7109 | 355.45 | 7464.45 | 349399
2015-10-14 | 110393 | 1 |  | 1 |  |  | 5647.67 | [18 empty] | 7231.67 | 361.5835 | 7593.2535 | 349399
2015-10-15 | 110394 | 1 |  | 1 |  |  | 5525 | [18 empty] | 7109 | 355.45 | 7464.45 | 349399
2015-10-16 | 110395 | 1 |  | 1 |  |  | 2762.5 | [18 empty] | 4346.5 | 217.325 | 4563.825 | 349399
2015-10-22 | 110396 | 1 | 15.5 | 2 | 1 |  | 2346.96 |  | 12 | [16 empty] | 6099.96 | 304.998 | 6404.958 | 349399
2015-10-23 | 110397 | 1 | 13 | 1 |  |  | 1378.58 |  | 13 | [16 empty] | 4457.58 | 222.879 | 4680.459 | 349399
2015-10-24 | 10521 | 1 | 12 | 1 |  |  | 998.43 |  | 12 | [16 empty] | 3962.43 | 198.1215 | 4160.5515 | 349399
2015-10-25 | 10522 | 1 | 12 | 1 |  |  | 1864.88 |  | 12 | [16 empty] | 4828.88 | 241.444 | 5070.324 | 349399
2015-10-26 | 10523 | 1 | 12 | 1 |  |  | 1792.38 |  | 12 | [16 empty] | 4756.38 | 237.819 | 4994.199 | 349399
2015-10-27 | 10525 | 1 | 11 | 2 |  |  | 917.24 |  | 11 | [16 empty] | 4090.24 | 204.512 | 4294.752 | 349399
2015-08-15 | 0001 | [9 empty] | 6.5 | 6 | 9 | 1 | [11 empty] | 2740 | 137 | 2877 | 349399
2015-08-22 | 0002 | [9 empty] | 20 | 1 | 23.5 | 0.5 | [11 empty] | 6447.5 | 322.375 | 6769.875 | 349399
2015-08-29 | 0003 | [9 empty] | 5.5 |  |  | 0.5 | [11 empty] | 1212.5 | 60.625 | 1273.125 | 349399
2015-09-05 | 0004 | [9 empty] | 16 |  | 7 | 1.5 | [11 empty] | 4162.5 | 208.125 | 4370.625 | 349399
2015-09-12 | 0005 | [9 empty] | 3 |  | 33.5 | [12 empty] | 3645 | 182.25 | 3827.25 | 349399
2015-09-26 | 0007 | [9 empty] | 5 |  | 11 | [12 empty] | 2040 | 102 | 2142 | 349399
2015-09-19 | 0006 | [9 empty] | 3 |  | 6 | [12 empty] | 1170 | 58.5 | 1228.5 | 349399
2015-10-03 | 0008 | [9 empty] | 5 |  | 10 | 1 | [11 empty] | 2065 | 103.25 | 2168.25 | 349399
2015-10-10 | 0009 | [9 empty] | 7 |  | 16 | 2 | [11 empty] | 3140 | 157 | 3297 | 349399
2015-10-17 | 00010 | [9 empty] | 3.5 |  | 8 | 2 | [11 empty] | 1685 | 84.25 | 1769.25 | 349399
2015-10-24 | 00011 | [9 empty] | 3 |  | 22 | [12 empty] | 2610 | 130.5 | 2740.5 | 349399
2015-11-03 | 0003 | [24 empty] | retracted | #VALUE! | #VALUE!
2015-11-04 | 0004 | [24 empty] | retracted | #VALUE! | #VALUE!
2015-11-03 | 0401 |  | 9 | 1 | [21 empty] | 1134 | 56.7 | 1190.7
2015-11-04 | 0402 |  | 24.5 | 2 |  |  |  | 320 | 21.5 | [16 empty] | 3710.5 | 185.525 | 3896.025
2015-11-10 | 427 |  | 12 | 1 | 1 |  | 536.6 | [18 empty] | 2090.6 | 104.53 | 2195.13
2015-11-22 | 100805 | [6 empty] | 270 | 20 |  |  |  | 15 |  | 5 | [10 empty] | 2520 | 126 | 2646
2015-12-03 | 100808 |  | 3 |  |  |  | 95.42 |  | 3 | [16 empty] | 440.42 | 22.021 | 462.441
2015-12-09 | 408 | [6 empty] | 175.5 | 11 |  |  |  | 6.5 |  |  | 4.5 | [9 empty] | 1305.5 | 65.275 | 1370.775
2015-12-06 | 100824 | [6 empty] | 1704 | 18 |  |  |  | 12 |  |  | 6 | [9 empty] | 3594 | 179.7 | 3773.7
2015-12-06 | 100825 | [5 empty] | 1893.94 | [18 empty] | 1893.94 | 94.697 | 1988.637
2016-12-11 | 412 | [6 empty] | 2698.5 | 21 |  |  |  | 10.5 |  |  | 10.5 | 6361.92 | [8 empty] | 11160.42 | 558.021 | 11718.441
2016-12-12 | 413 | [6 empty] | 2982 | 31.5 |  |  |  | 21 |  |  | 10.5 | 8234 | [8 empty] | 14523.5 | 726.175 | 15249.675
2016-12-13 | 414 | [6 empty] | 2982 | 31.5 |  |  |  | 21 |  |  | 10.5 | 4939.25 | [8 empty] | 11228.75 | 561.4375 | 11790.1875
2016-12-14 | 420 | [6 empty] | 2272 | 24 |  |  |  | 16 |  |  | 8 | [9 empty] | 4792 | 239.6 | 5031.6
2016-12-18 | 419 | [5 empty] | 5856.48 | [18 empty] | 5856.48 | 292.824 | 6149.304
[26 empty] | 0 | 0 | 0
[26 empty] | 0 | 0 | 0
[26 empty] | 0 | 0 | 0
[26 empty] | 0 | 0 | 0
[26 empty] | 0 | 0 | 0
[26 empty] | 0 | 0 | 0
[26 empty] | 0 | 0 | 0

## Corrpro AC MItigation Lump sum
Corrpro
Date | Ticket Number | EIT | EIT | EIT | Operator | Principal Engineer | LOA | Rate | KM's | Rate | 24" 11.1 | 16" 9.5 | 16" 7.1 | Films | Subtotal | GST | LEM Amount | Affiliating Invoice | SUM OF ALL LEM'S (before GST)
52915
RATE |  | 90 | 90 | 90 | 80
2015-11-14 | 100802 | 12 | 11 | 11 | 11 | 12 | [8 empty] | 3940 | 197 | 4137 | Lump sum
2015-11-20 | 100803 | 11 | 11 | 11 | 11 | [9 empty] | 3850 | 192.5 | 4042.5 | Lump sum
2015-11-21 | 100804 | 12 | 11 | 11 | 11 | [9 empty] | 3940 | 197 | 4137 | Lump sum
2015-11-22 | 100806 | 7 | 6 | 6 | 6 | [9 empty] | 2190 | 109.5 | 2299.5 | Lump sum
2015-11-23 | 100807 | 11 | 11 | 12 | 11 | [9 empty] | 3940 | 197 | 4137 | Lump sum
2015-11-24 | 100809 | 12 | 11 | 11 | 11 | [9 empty] | 3940 | 197 | 4137 | Lump sum
2015-11-25 | 100810 | 11 | 11 | 11 | 11 | [9 empty] | 3850 | 192.5 | 4042.5 | Lump sum
2015-11-26 | 100811 | 11 | 11 | 11 | 11 | [9 empty] | 3850 | 192.5 | 4042.5 | Lump sum
2015-11-27 | 100812 | 11.5 | 11.5 | 11.5 | 11.5 | [9 empty] | 4025 | 201.25 | 4226.25 | Lump sum
2015-11-28 | 100813 | 11 | 11 |  | 11 | [9 empty] | 2860 | 143 | 3003 | Lump sum
2015-11-30 | 100814 | 11 | 11 |  | 11 | [9 empty] | 2860 | 143 | 3003 | Lump sum
in calgary office billing box in Jack's office
2016-12-15 | 415 | 8 | 8 |  | 8 | [9 empty] | 2080 | 104 | 2184 | Lump sum
2016-12-16 | 416 | 10 | 11 |  | 11 | [9 empty] | 2770 | 138.5 | 2908.5 | Lump sum
2016-12-17 | 417 | 10 | 10 | [11 empty] | 1800 | 90 | 1890 | Lump sum
2016-12-18 | 418 | 10 | 10 | [11 empty] | 1800 | 90 | 1890 | Lump sum
2016-12-19 | 421 | 10 | 10 | [11 empty] | 1800 | 90 | 1890 | Lump sum
2016-12-20 | 422 | 10 | 10 | [11 empty] | 1800 | 90 | 1890 | Lump sum
2016-12-21 | 423 | 9 | 9 | [11 empty] | 1620 | 81 | 1701 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum
[15 empty] | 0 | 0 | 0 | Lump sum