## Slide 1: Pembina Pipeline Corporation
August 4, 2016
Major Projects
PIPELINE CONSTRUCTION AGREEMENT (PCA)
CHANGE AND RFI PROCESS FLOW SUMMARY

## Slide 2: 1.0 Change Order Flow Chart – Company Initiated Change Change Request (CR)
COMPANY requires immediate compliance with Change?
COMPANY initiates Change Request (Art.10.4)
NO COMPANY issues immediate CO
NO
Negotiate impacts as per Art. 10.3a
CONTRACTOR Proceeds with Work
Contractor has the right to claim for additional compensation and time (Art.10.3.a)
YES
COMPANY issues an immediate CO
Agreement Reached as per Art.10.3.a?
YES
COMPANY Issues CO
CONTRACTOR Proceeds with Work

## Slide 3: 2.0 Change Order Flow Chart – Contractor Initiated Change
COMPANY approves request?
CONTRACTOR initiates Change Request (CR) (Art.10.2 & 10.4)
Contractor Proceeds with Work
YES
COMPANY Issues CO (Art.10.5)
Agreement Reached as per Art.10.3.a?
YES
COMPANY Issues CO (Art.10.5)
NO Negotiate impacts as per Art. 10.3a
NO
YES
CONTRACTOR Proceeds with Work
Contractor has the right to claim for additional compensation and time (Art.10.3.a)

## Slide 4: 3.0 Contractor RFI Process Flow Chart
RFI Approved?
CONTRACTOR makes a Request For Information RFI (Art.10.1)
NO …No change to contract
YES
See CR Slide 2.0 (Art.10.1)
YES
RFI Impact Scope, Price or Time?
NO …No change to contract

## Slide 5: 4.0 Change Order Flow Chart – Company Initiated Change Change Order (CO)
COMPANY requires immediate compliance with Change?
COMPANY initiates Change Order (Art.10.3)
NO Negotiate impacts as per Art. 10.3a
CONTRACTOR Proceeds with Work
Contractor has the right to claim for additional compensation and time (Art.10.3.a)
YES
CONTRACTOR Proceeds with Work