| Weekly Reporting Format For Major Projects |  |  |
| --- | --- | --- |
| Issue | Reason | Resolution |
| Accruals not being submitted in a timely fashion; relates to daily tickets not being signed off by the CM weekly | -CMT not finalizing weekly tickets for sign off -CMT and/or contractor not submitting weekly statement -Contract not finalized so costing cannot take place | -Weekly statements to be issued in a timely fashion accrued numbers sent to the Project Coordinator -Copy of finalized contract accessible by field office |
| Daily tickets are not being submitted weekly; NO WEEKLY STATEMENT OR PROGRESS REPORT | -Contractor has not put costs to the field ticket -Contractor is not submitting a weekly statement -Contractor is late in submitting a weekly statement -Construction Management Team (CMT) is not preparing/requesting a weekly statement and/or is waiting on the contractor | -finalize WHO is to prepare the weekly statement/progress report to ensure a quicker turn around. -Most contracts say contractor is to prepare a progress report but there is no direction on the frequency of the report in the contract (weekly/bi-weekly/monthly) -Role of CMT not clear to office manager |
| Invoices are not being broken out according to PO | -Contractor is not aware of how to invoice according to the PO -Contractor has their “own system” of invoicing and feel they do not have to invoice according to the PO -CMT is not addressing the PO with the contractor as they are not enforcing correct PO structure on the weekly statement -CMT does not know the format with how the PO needs to be entered -CMT does not have a copy of the PO and the revised PO after change orders are signed off | -POs should be in a simple format with main items being captured -CMT must be familiar with PO structure so they can communicate with contractor on Pembina requirements. -I have sat with the office managers and showed them how the PO relates to the contract (exception being Shelley as she has been working with Liliana) |
| Invoices will not be paid Net 15 because progress reports are being held up by the Construction Management Team | -weekly statements not being signed off -CMT not addressing the lag time between tickets signed off in the field and making its way to the weekly statement -contractor sending in an invoice and expects fast turn around but nothing has been pre-approved | -CMT to be more involved with addressing the time sheet to payment schedule |
| Each spread is doing things differently | -Varying levels of cooperation depending on who the Construction Manager is -Varying levels of cooperation depending on what expectations are placed on the CMT (they are waiting on the Project Manager to address the issue) | -Identify issue to Construction Manager and have them propose a process to address the timeliness of the cost reporting |
| No consistent format on how costs are being validated and who is approving the costs | -Field level tickets are being generated but some are using calculators and not spreadsheets to check the work -Chief and CM are not checking the work of the office manager and are blindly signing off on what is in the back up. |  |

What we need:

-clearly defined expectations for the field office/CMT

- ie process for handling progress

-process for handling extra work- sign offs and information to be placed on the tickets

-process for handling billings- clear definitions and labeling of change orders, upis, base lay

-how do they handle invoicing issues with the contractor since they are the ones handling the daily tickets

-is their process valid and are they adhering to it?  Each time does it differently

From Us:

-Format for weekly cost reporting/statements- Do we demand weekly for say POs over $1,000,000.00

-Roles for who does what to create the report- ie Contractor or CMT

-Samples of progress report and a weekly statement