Weekly Reports & Statements

Statements for Smaller Contractors:

The Contractors Log is a sample log for keeping your daily tickets lined out for each PO- just modify a spreadsheet with what each contractor needs.  I left a bunch of tabs in the log in case there is a tab that suits a contractor you are working with.

The second sheet is a statement sample based on one of the vendors in the Log- namely Arete Design Solutions.  The statement attached is #2 for July 1-15 as June 21-30 would have been statement #1.

This statement was simply the tickets entered into the log, copied and pasted into a new workbook with the headings added in lines #1 and #3.  Liliana would like to keep the heading (lines 1 and 3) consistent for each Contractor (AR-002 means Arete Designs- statement 002) so come up with two letters for each contractor then change the statement number and date.  From here, the Construction Manager (CM) and office manager can just sign and pdf the page, attach the relevant back up and email to the vendor, project coordinator and contract admin.

When emailing to vendor and Calgary:

In the email heading, simply copy Row #1 of the statement and paste it into the subject line- this way the ladies in Calgary will be able to search their emails for the statement if needed.

The statement should be generated on a weekly basis and sent in so that the accruals in SAP can be up to date.  You can also use this as a good resource for the accruals sheet that you are sending to the project coordinator.

Progress Payments:

See attached Progress Billing Report for mainline contractors and contractors with complex lump sums:

The progress billing report sample is for the mainline contractors and will be used as the weekly They are pretty simple and can be modified for the contractor you are dealing with.  
UPIs- I will find out tomorrow if we need a separate change order like we did last job, otherwise just add in the new UPI amount each week as "Rev 1, Rev 2" as displayed.  
The change request or change order back up should have a neat summary page to show each lem#/ticket#, break down of costs and totals (you can use your own but I attached a sample I used on the Wapiti project- does not have to be the same).

The weekly report will be signed off by the CM, sent back to the vendor for payment purposes.

Notes for Progress Billing Reports & Statements:

The vendor/contractor can invoice according to the PO instructions and attach the progress report/statement as back up-but they must include all back up in the statements.

The Contractors are not allowed to add or delete items once the report/statement is signed.  If there are changes to be made, then a credit note or addition can be applied to the next report/statement stating the change and referencing the original statement if applicable.

If the statement/report has not been invoiced, changes can still be made if necessary, however, it is likely easier to include the change on the next statement.

The changes can be put down as a separate line at the end of the statement/report so they are easy to see.

Monthly charges such as office hours (in the case of Meridian) can just be added to the next statement and invoiced accordingly.

The purpose of this system is to ensure the POs have sufficient funds in advance of invoicing.  It also ensures the charges have been approved by the CM without the CM having to approve the invoice as the charges are already in Company’s SAP system.

The statements/reports should be generated weekly by the Inspection field office, however, there should be cutoffs made on the 15th and the 30th or the 31st of each month so the vendor can invoice according to their PO instructions.