DAILY REGULATORY COMPLIANCE REPORT

SMJV — Eagle Mountain Woodfibre Gas Pipeline

February 27, 2026  |  Job #2330  |  Squamish, BC

| TOTAL FINDINGS | ACTION REQUIRED | MONITOR | COMPLIANT |
| --- | --- | --- | --- |
| 93 | 13 | 12 | 72 |

Of 30 active crews in today's Daily Work Plan, 28 crews (93%) are operating within or adjacent to one or more regulatory zones. A total of 93 crew-zone intersections were identified. 13 require immediate attention.

## 1. COMPLIANCE ALERTS — ACTION REQUIRED

| SEVERITY | ALERT | DETAIL | LOCATION |
| --- | --- | --- | --- |
| HIGH | Fisheries Window Closing — 2 Days | Mamquam River crossing restriction begins Mar 1. Tie-in crew (Troy Young / Crew 3) working at KP 29+650. Verify all in-stream work completes before deadline. | KP 29.6 |
| MEDIUM | GD Pending — Active Work in Zone | Crew 9 (Quinn Braybrook) hauling knotweed topsoil at KP 33+800. GD checklist for Stawamus FSR section still under review. Confirm GD status with Brandon Thomas. | KP 33.8 |
| MEDIUM | Archaeological Monitor Zone | Active crushing and road work at KP 12-14. GD permit requires archaeological monitor for any new disturbance KP 12+200 to 12+800. Verify monitor on-site. | KP 12.5 |
| LOW | Mountain Goat Restriction Active | Helicopter noise restriction in effect through Apr 15 between KP 7-11. Any heli ops in this zone must be scheduled outside 0600-0900. | KP 8.5 |

## 2. FISHERIES TIMING WINDOWS (DFO)

3 fisheries timing windows are defined along the pipeline route. 14 active crew-zone intersections identified today.

| CROSSING | KP RANGE | STATUS | RESTRICTION | AUTHORITY |
| --- | --- | --- | --- | --- |
| Ray Creek Crossing | 31.0 - 31.3 | OPEN | No in-stream work Mar 1 – Jun 15 & Sep 1 – Nov 15 | DFO / Fisheries Act |
| Mamquam River Crossing | 29.2 - 29.8 | OPEN — CLOSES IN 2 DAYS | No in-stream work Mar 1 – Jun 30 & Aug 15 – Nov 30 | DFO / Fisheries Act |
| Stawamus River Zone | 33.5 - 34.2 | OPEN | No in-stream work Mar 15 – Jun 30 | DFO / Fisheries Act |

Crews Operating in Fisheries Zones:

| CREW | KP | ACTIVITY | ZONE |
| --- | --- | --- | --- |
| COATING CREW NORTH 1 | 29.594 | Crew 1, Final jeep on ARO bore section @ Finch RD, cut back blasting for UT on welded test heads and pigging heads @ Finch. Crew 2, SP coating @ kp 29 | Mamquam |
| MECHANICAyL CREW 1 | 29.650 | Continue in road tie ins at kp 29+650 Bending/ inroad sections set | Mamquam |
| CIVILS-GRADE/BLAST-CREW 5 | 29.659 | Continue ditching at KP 29+659 working NEG. Continue hauling beddiing and 3”- from Valleycliffe yard to KM 3.6 on the Stawamus. Support tie-in crew. G | Mamquam |
| CIVILS-GRADE/BLAST-CREW 9 | 31.110 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (31+180) to (31+130).- Resume dr | Ray |
| CIVILS-GRADE/BLAST-CREW 9 | 31.130 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (31+180) to (31+130).- Resume dr | Ray |
| CIVILS-GRADE/BLAST-CREW 9 | 31.160 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (31+180) to (31+130).- Resume dr | Ray |
| CIVILS-GRADE/BLAST-CREW 9 | 31.180 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (31+180) to (31+130).- Resume dr | Ray |
| CIVILS-GRADE/BLAST-CREW 9 | 31.190 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (31+180) to (31+130).- Resume dr | Ray |
| CIVILS-GRADE/BLAST-CREW 9 | 31.200 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (31+180) to (31+130).- Resume dr | Ray |
| CIVILS-GRADE/BLAST-CREW 9 | 31.250 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (31+180) to (31+130).- Resume dr | Ray |
| CIVILS-GRADE/BLAST-CREW 9 | 31.260 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (31+180) to (31+130).- Resume dr | Ray |
| CIVILS-GRADE/BLAST-CREW 6 | 33.800 | 33+800 - 33+850 Begin hauling knot weed topsoil offsite 100+850 - 101+000 Support McCaws ditch blast 318/319 101+200 - 101+850 Continue strip/grade/ha | Stawamus |
| CIVILS-GRADE/BLAST-CREW 6 | 33.850 | 33+800 - 33+850 Begin hauling knot weed topsoil offsite 100+850 - 101+000 Support McCaws ditch blast 318/319 101+200 - 101+850 Continue strip/grade/ha | Stawamus |
| MECHANICAL SUPPORT CREW 2 | 29.600 | Continued tie in support at Kp 29+600, begin engineering activities in road 5 | Mamquam |

## 3. ENVIRONMENTAL SENSITIVE AREAS

3 environmental sensitive areas are defined along the pipeline route. 13 active crew-zone intersections identified today.

| ESA | KP RANGE | STATUS | RESTRICTION | AUTHORITY |
| --- | --- | --- | --- | --- |
| Slope B/C Glacier — Steep Terrain ESA | 5.3 - 6.8 | ACTIVE WORK | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | BCER Permit Condition #47 |
| Wetland Complex | 3.4 - 3.8 | MONITORING | 30m setback from wetland boundary. Silt fencing mandatory. Turbidity monitoring required. | BCER / BC Water Sustainability Act |
| Mountain Goat Winter Range | 7.0 - 11.0 | RESTRICTION ACTIVE | Helicopter operations restricted Dec 1 – Apr 15. Minimize noise 0600-0900. | BCER Permit Condition #62 / BC Wildlife Act |

Crews Operating in ESAs:

| CREW | KP | ACTIVITY | ZONE |
| --- | --- | --- | --- |
| CIVILS-GRADE/BLAST-CREW 7 | 5.369 | 5+222 Backfiling activities, end haul 5+369 Ditching activities, isolation preparation of NCD 30 5+550 Support Glacier, expose rock for ditch blast 5+ | Slope B/C Glacier |
| CIVILS-GRADE/BLAST-CREW 7 | 5.550 | 5+222 Backfiling activities, end haul 5+369 Ditching activities, isolation preparation of NCD 30 5+550 Support Glacier, expose rock for ditch blast 5+ | Slope B/C Glacier |
| CIVILS-GRADE/BLAST-CREW 7 | 5.850 | 5+222 Backfiling activities, end haul 5+369 Ditching activities, isolation preparation of NCD 30 5+550 Support Glacier, expose rock for ditch blast 5+ | Slope B/C Glacier |
| COATING CREW NORTH 2 | 5.332 | Coat section welds at KP14 laydown. Coat TI at KP14+638. Coat TI at KP5+332. Coat SP weld at KP2+702. Coat section welds at KP12+800. Jeep and repair | Slope B/C Glacier |
| STEEP SLOPES CREW | 6.670 | Continue supporting glacier drilling and blasting ditchline on slope B. Continue moving grade material from the bottom of slope B to the crusher. Supp | Slope B/C Glacier |
| PUMP SUPPORT 2 NIGHT SHIFT | 5.400 | Assist with any daytime requests as needed Monitor and maintain all submersible pumps and trash pumps within work area (Slope A/Slope B/ Hixon Yard + | Slope B/C Glacier |
| PUMP SUPPORT 2 NIGHT SHIFT | 10.150 | Assist with any daytime requests as needed Monitor and maintain all submersible pumps and trash pumps within work area (Slope A/Slope B/ Hixon Yard + | Mountain Goat Winter Range |
| PUMP SUPPORT 2 NIGHT SHIFT | 10.275 | Assist with any daytime requests as needed Monitor and maintain all submersible pumps and trash pumps within work area (Slope A/Slope B/ Hixon Yard + | Mountain Goat Winter Range |
| MECHANICAL SUPPORT CREW 1 | 5.600 | Continue engineering at 5+600 | Slope B/C Glacier |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | 3.500 | Continue making progress with inroad backfill operation. Haul aggregate from km3.5 stock piles Cleanup up work areas Pump watch and pump off monitorin | Wetland Complex |
| CIVILS-GRADE/BLAST-CREW 5 | 3.600 | Continue ditching at KP 29+659 working NEG. Continue hauling beddiing and 3”- from Valleycliffe yard to KM 3.6 on the Stawamus. Support tie-in crew. G | Wetland Complex |
| CIVIL SUPPORT | 3.500 | Kp30+863 mechanically Assisting Spencer‘s crew with final daylight hole road 10 Starting road upgrades Stawamus FSR, from KM 0 to KM 3.5 | Wetland Complex |
| DESC CREW 2 | 7.550 | Install TB ditch breaker at KP 5+255 Brush ROW from KP 7+550 going positive for upcoming 8K fishery grading DESC pumping, maintenance, and repairs on | Mountain Goat Winter Range |

## 4. GROUND DISTURBANCE PERMITS

5 ground disturbance permits tracked. 4 valid, 1 pending. 60 crew-zone intersections today.

| PERMIT | KP RANGE | STATUS | CONDITIONS | AUTHORITY |
| --- | --- | --- | --- | --- |
| GD-2026-041 — Hixon Section | 2.0 - 6.5 | VALID | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | SMJV GD Program / OGC Act |
| GD-2026-038 — Mid Section | 10.0 - 15.5 | VALID | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | SMJV GD Program / Heritage Conservation Act |
| GD-2026-042 — South Section | 18.5 - 21.0 | VALID | Active GD permit. Monitoring well MW-14 within 50m at KP 19+400. | SMJV GD Program |
| GD-2026-039 — Mamquam/Urban | 29.0 - 32.0 | VALID | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | SMJV GD Program / Municipal Permit |
| GD PENDING — Stawamus FSR | 33.0 - 35.0 | PENDING | GD checklist under review. Road upgrades planned KM 0-3.5. Awaiting final sign-off. | SMJV GD Program |

## 5. SAFETY EXCLUSION ZONES

Blast Exclusion Zone — Active (KP 4.8 - 5.1): Active blasting operations. 500m exclusion during blast events. Blast schedule posted daily. Status: ACTIVE TODAY. Authority: WorkSafeBC / SMJV Blast Plan.

Helicopter Operations Zone (KP 30.8 - 31.0): Heli pad active. 100m ground exclusion during flight ops. Hard hat mandatory. Status: ACTIVE TODAY. Authority: Transport Canada / WorkSafeBC.

## 6. INVASIVE SPECIES MANAGEMENT

Knotweed Contamination Zone (KP 33.6 - 33.9): Contaminated topsoil — mandatory offsite disposal (GFL Abbotsford). Equipment wash mandatory on exit. Status: ACTIVE HAULING. Authority: BC Weed Control Act / BCER Condition #71.

2 crew(s) operating in invasive species zones today. Verify equipment wash and soil disposal protocols are being followed.

## 7. COMPLETE CREW-ZONE INTERSECTION LOG

The following table lists every intersection between active crew locations and regulatory zones for February 27, 2026. This log serves as the daily compliance record for audit purposes.

| CREW | KP | ZONE | RESTRICTION | STATUS |
| --- | --- | --- | --- | --- |
| CIVILS-GRADE/BLAST-CREW 10 | 2.7 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| BACKFILL NIGHTSHIFT HIXON | 2.7 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| CIVILS-GRADE/BLAST-CREW 8 | 5.0 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| CIVILS-GRADE/BLAST-CREW 8 | 5.0 | Blast Exclusion Zone — Active | Active blasting operations. 500m exclusion during ... | ACTIVE TODAY |
| ROCK CRUSHING HIXON | 2.0 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| CIVILS-GRADE/BLAST-CREW 7 | 5.2 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| CIVILS-GRADE/BLAST-CREW 7 | 5.4 | Slope B/C Glacier — Steep Terr... | Enhanced erosion control required. No work during ... | ACTIVE WORK |
| CIVILS-GRADE/BLAST-CREW 7 | 5.4 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| CIVILS-GRADE/BLAST-CREW 7 | 5.5 | Slope B/C Glacier — Steep Terr... | Enhanced erosion control required. No work during ... | ACTIVE WORK |
| CIVILS-GRADE/BLAST-CREW 7 | 5.5 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| CIVILS-GRADE/BLAST-CREW 7 | 5.8 | Slope B/C Glacier — Steep Terr... | Enhanced erosion control required. No work during ... | ACTIVE WORK |
| CIVILS-GRADE/BLAST-CREW 7 | 5.8 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| MECHANICAL CREW 5 | 2.7 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| COATING CREW NORTH 2 | 2.7 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| COATING CREW NORTH 2 | 5.3 | Slope B/C Glacier — Steep Terr... | Enhanced erosion control required. No work during ... | ACTIVE WORK |
| COATING CREW NORTH 2 | 5.3 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| COATING CREW NORTH 2 | 12.8 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| COATING CREW NORTH 2 | 14.0 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| COATING CREW NORTH 2 | 14.6 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| STEEP SLOPES CREW | 6.7 | Slope B/C Glacier — Steep Terr... | Enhanced erosion control required. No work during ... | ACTIVE WORK |
| PUMP SUPPORT 2 NIGHT SHIFT | 2.3 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| PUMP SUPPORT 2 NIGHT SHIFT | 5.4 | Slope B/C Glacier — Steep Terr... | Enhanced erosion control required. No work during ... | ACTIVE WORK |
| PUMP SUPPORT 2 NIGHT SHIFT | 5.4 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| PUMP SUPPORT 2 NIGHT SHIFT | 10.2 | Mountain Goat Winter Range | Helicopter operations restricted Dec 1 – Apr 15. M... | RESTRICTION ACTIVE |
| PUMP SUPPORT 2 NIGHT SHIFT | 10.2 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| PUMP SUPPORT 2 NIGHT SHIFT | 10.3 | Mountain Goat Winter Range | Helicopter operations restricted Dec 1 – Apr 15. M... | RESTRICTION ACTIVE |
| PUMP SUPPORT 2 NIGHT SHIFT | 10.3 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| CIVILS-GRADE/BLAST-CREW 3 | 12.0 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| CIVILS-GRADE/BLAST-CREW 3 | 13.8 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| CIVILS-GRADE/BLAST-CREW 3 | 14.0 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| MECHANICAL CREW 2 | 14.0 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| MECHANICAL CREW 2 | 15.0 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| CIVILS-GRADE/BLAST-CREW 4 | 14.5 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| CIVILS-GRADE/BLAST-CREW 4 | 14.5 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| CIVILS-GRADE/BLAST-CREW 4 | 14.6 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| CIVILS-GRADE/BLAST-CREW 4 | 14.7 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| MECHANICAL CREW 4 | 12.8 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| MECHANICAL CREW 4 | 14.0 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| MECHANICAL CREW 4 | 19.2 | GD-2026-042 — South Section | Active GD permit. Monitoring well MW-14 within 50m... | VALID |
| CIVILS-GRADE/BLAST-CREW 11 | 14.0 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| CIVILS-GRADE/BLAST-CREW 11 | 19.2 | GD-2026-042 — South Section | Active GD permit. Monitoring well MW-14 within 50m... | VALID |
| CIVILS-GRADE/BLAST-CREW 11 | 20.1 | GD-2026-042 — South Section | Active GD permit. Monitoring well MW-14 within 50m... | VALID |
| BACKFILL NIGHTSHIFT | 19.1 | GD-2026-042 — South Section | Active GD permit. Monitoring well MW-14 within 50m... | VALID |
| MECHANICAL SUPPORT CREW 1 | 5.6 | Slope B/C Glacier — Steep Terr... | Enhanced erosion control required. No work during ... | ACTIVE WORK |
| MECHANICAL SUPPORT CREW 1 | 5.6 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| WELDING | 2.7 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| WELDING | 12.7 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| COATING CREW NORTH 1 | 29.6 | Mamquam River Crossing | No in-stream work Mar 1 – Jun 30 & Aug 15 – Nov 30 | OPEN |
| COATING CREW NORTH 1 | 29.6 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | 3.5 | Wetland Complex | 30m setback from wetland boundary. Silt fencing ma... | MONITORING |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | 3.5 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| MECHANICAyL CREW 1 | 29.6 | Mamquam River Crossing | No in-stream work Mar 1 – Jun 30 & Aug 15 – Nov 30 | OPEN |
| MECHANICAyL CREW 1 | 29.6 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVILS-GRADE/BLAST-CREW 5 | 3.6 | Wetland Complex | 30m setback from wetland boundary. Silt fencing ma... | MONITORING |
| CIVILS-GRADE/BLAST-CREW 5 | 3.6 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| CIVILS-GRADE/BLAST-CREW 5 | 29.7 | Mamquam River Crossing | No in-stream work Mar 1 – Jun 30 & Aug 15 – Nov 30 | OPEN |
| CIVILS-GRADE/BLAST-CREW 5 | 29.7 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVIL SUPPORT | 3.5 | Wetland Complex | 30m setback from wetland boundary. Silt fencing ma... | MONITORING |
| CIVIL SUPPORT | 3.5 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| CIVIL SUPPORT | 30.9 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVIL SUPPORT | 30.9 | Helicopter Operations Zone | Heli pad active. 100m ground exclusion during flig... | ACTIVE TODAY |
| CIVILS-GRADE/BLAST-CREW 9 | 30.9 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVILS-GRADE/BLAST-CREW 9 | 30.9 | Helicopter Operations Zone | Heli pad active. 100m ground exclusion during flig... | ACTIVE TODAY |
| CIVILS-GRADE/BLAST-CREW 9 | 31.1 | Ray Creek Crossing | No in-stream work Mar 1 – Jun 15 & Sep 1 – Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 | 31.1 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVILS-GRADE/BLAST-CREW 9 | 31.1 | Ray Creek Crossing | No in-stream work Mar 1 – Jun 15 & Sep 1 – Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 | 31.1 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVILS-GRADE/BLAST-CREW 9 | 31.2 | Ray Creek Crossing | No in-stream work Mar 1 – Jun 15 & Sep 1 – Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 | 31.2 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVILS-GRADE/BLAST-CREW 9 | 31.2 | Ray Creek Crossing | No in-stream work Mar 1 – Jun 15 & Sep 1 – Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 | 31.2 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVILS-GRADE/BLAST-CREW 9 | 31.2 | Ray Creek Crossing | No in-stream work Mar 1 – Jun 15 & Sep 1 – Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 | 31.2 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVILS-GRADE/BLAST-CREW 9 | 31.2 | Ray Creek Crossing | No in-stream work Mar 1 – Jun 15 & Sep 1 – Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 | 31.2 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVILS-GRADE/BLAST-CREW 9 | 31.3 | Ray Creek Crossing | No in-stream work Mar 1 – Jun 15 & Sep 1 – Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 | 31.3 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| CIVILS-GRADE/BLAST-CREW 9 | 31.3 | Ray Creek Crossing | No in-stream work Mar 1 – Jun 15 & Sep 1 – Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 | 31.3 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| ROCK CRUSHING SQUAMISH | 4.2 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| CIVILS-GRADE/BLAST-CREW 6 | 33.8 | Stawamus River Zone | No in-stream work Mar 15 – Jun 30 | OPEN |
| CIVILS-GRADE/BLAST-CREW 6 | 33.8 | GD PENDING — Stawamus FSR | GD checklist under review. Road upgrades planned K... | PENDING |
| CIVILS-GRADE/BLAST-CREW 6 | 33.8 | Knotweed Contamination Zone | Contaminated topsoil — mandatory offsite disposal ... | ACTIVE HAULING |
| CIVILS-GRADE/BLAST-CREW 6 | 33.9 | Stawamus River Zone | No in-stream work Mar 15 – Jun 30 | OPEN |
| CIVILS-GRADE/BLAST-CREW 6 | 33.9 | GD PENDING — Stawamus FSR | GD checklist under review. Road upgrades planned K... | PENDING |
| CIVILS-GRADE/BLAST-CREW 6 | 33.9 | Knotweed Contamination Zone | Contaminated topsoil — mandatory offsite disposal ... | ACTIVE HAULING |
| MECHANICAL SUPPORT CREW 2 | 29.6 | Mamquam River Crossing | No in-stream work Mar 1 – Jun 30 & Aug 15 – Nov 30 | OPEN |
| MECHANICAL SUPPORT CREW 2 | 29.6 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| UTILITY CREW 2 | 14.0 | GD-2026-038 — Mid Section | Active GD permit. Archaeological monitor required ... | VALID |
| UTILITY CREW 2 | 30.9 | GD-2026-039 — Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geote... | VALID |
| UTILITY CREW 2 | 30.9 | Helicopter Operations Zone | Heli pad active. 100m ground exclusion during flig... | ACTIVE TODAY |
| DESC CREW 2 | 5.3 | GD-2026-041 — Hixon Section | Active GD permit. Pre-disturbance assessment compl... | VALID |
| DESC CREW 2 | 7.5 | Mountain Goat Winter Range | Helicopter operations restricted Dec 1 – Apr 15. M... | RESTRICTION ACTIVE |

PREPARED BY:

Name: ___________________________    Signature: ___________________________    Date: _______________

REVIEWED BY:

Name: ___________________________    Signature: ___________________________    Date: _______________

This report was auto-generated by Pipe-Up Regulatory Compliance Engine. All findings are based on cross-referencing the Daily Work Plan crew locations against the project regulatory zone database. This report does not replace professional regulatory judgment.