DAILY REGULATORY COMPLIANCE REPORT

SMJV — Eagle Mountain Woodfibre Gas Pipeline

February 27, 2026  |  Job #2330  |  Squamish, BC

| TOTAL FINDINGS | ACTION REQUIRED | MONITOR | COMPLIANT |
| --- | --- | --- | --- |
| 96 | 14 | 12 | 70 |

Of 30 active crews reporting today, 28 crews (93%) are operating within or adjacent to one or more regulatory zones. A total of 96 crew-zone intersections were identified. 14 require immediate attention.

## 1. COMPLIANCE ALERTS — ACTION REQUIRED

| SEVERITY | ALERT | DETAIL | LOCATION |
| --- | --- | --- | --- |
| HIGH | Fisheries Window Closing — 2 Days | Welding crew (Al Letch / WELDING - Ian Kopp) working at KP 29.600. Verify all in-stream work completes before deadline. No in-stream work Mar 1 - Jun 30 & Aug 15 - Nov 30. | KP 29.2 |
| MEDIUM | Archaeological Monitor Zone | Coating crew (Dylan Gloeckler / COATING CREW NORTH 2 - Rob Cecka) working at KP 12.800. Archaeological monitoring required per permit conditions. Active GD permit. Archaeological monitor required KP 1 | KP 10.0 |
| MEDIUM | GD Pending — Active Work in Zone | Grading/Blasting crew (Blaine Friedel / CIVILS-GRADE/BLAST-CREW 6 - Ryan Beccherini) working at KP 33.800. GD permit pending — crews operating in zone without final sign-off. GD checklist under review | KP 33.0 |
| MEDIUM | Active Safety Zone — Blast Exclusion Zone - Active | Grading/Blasting crew (Jim Armstrong / CIVILS-GRADE/BLAST-CREW 8 - Daryl Holtskog) working at KP 4.975. Active blasting operations. 500m exclusion during blast events. Blast schedule posted daily.. | KP 4.8 |
| MEDIUM | Active Safety Zone — Helicopter Operations Zone | Grading/Blasting crew (Adam Ferretti / CIVIL SUPPORT - Kirk Haws) working at KP 30.863. Heli pad active. 100m ground exclusion during flight ops. Hard hat mandatory.. | KP 30.8 |
| LOW | Environmental Restriction — Slope B/C Glacier - Steep Terrain ESA | Grading/Blasting crew (Jared Paulson / CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson) working at KP 5.369. Enhanced erosion control required. No work during heavy rain events. Mandatory spotter.. | KP 5.3 |
| LOW | Environmental Restriction — Mountain Goat Winter Range | Pump Support crew (Stephen Swaim / PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna) working at KP 10.150. Helicopter operations restricted Dec 1 - Apr 15. Minimize noise 0600-0900.. | KP 7.0 |

## 2. FISHERIES TIMING WINDOWS (DFO)

3 fisheries timing windows are defined along the pipeline route. 15 active crew-zone intersections identified today.

| CROSSING | KP RANGE | STATUS | RESTRICTION | AUTHORITY |
| --- | --- | --- | --- | --- |
| Ray Creek Crossing | KP 31.0 — 31.3 | OPEN | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | DFO / Fisheries Act |
| Mamquam River Crossing | KP 29.2 — 29.8 | OPEN — CLOSES IN 2 DAYS | No in-stream work Mar 1 - Jun 30 & Aug 15 - Nov 30 | DFO / Fisheries Act |
| Stawamus River Zone | KP 33.5 — 34.2 | OPEN | No in-stream work Mar 15 - Jun 30 | DFO / Fisheries Act |

Crews Operating in Fisheries Timing Windows:

| CREW | KP | ACTIVITY | ZONE |
| --- | --- | --- | --- |
| WELDING - Ian Kopp | KP 29.600 | KP 2+710 - Bedomme / Deschamps Kp 12+700 - Wilson / Davis KP 29+600 - Becker / Albrecht KP 14+600 - Wilson / Smith EPP - | Mamquam River Crossing |
| COATING CREW NORTH 1 - Matt Fadden | KP 29.594 | Crew 1, Final jeep on ARO bore section @ Finch RD, cut back blasting for UT on welded test heads and pigging heads @ Fin | Mamquam River Crossing |
| MECHANICAyL CREW 1 - Travis Stacey | KP 29.650 | Continue in road tie ins at kp 29+650 Bending/ inroad sections set | Mamquam River Crossing |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 29.659 | Continue ditching at KP 29+659 working NEG. Continue hauling beddiing and 3”- from Valleycliffe yard to KM 3.6 on the St | Mamquam River Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.110 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (3 | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.130 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (3 | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.160 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (3 | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.180 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (3 | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.190 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (3 | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.200 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (3 | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.250 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (3 | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.260 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel.- Continue ECB/Soil mesh install KP (3 | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 6 - Ryan Beccherini | KP 33.800 | 33+800 - 33+850 Begin hauling knot weed topsoil offsite 100+850 - 101+000 Support McCaws ditch blast 318/319 101+200 - 1 | Stawamus River Zone |
| CIVILS-GRADE/BLAST-CREW 6 - Ryan Beccherini | KP 33.850 | 33+800 - 33+850 Begin hauling knot weed topsoil offsite 100+850 - 101+000 Support McCaws ditch blast 318/319 101+200 - 1 | Stawamus River Zone |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | KP 29.600 | Continued tie in support at Kp 29+600, begin engineering activities in road 5 | Mamquam River Crossing |

## 3. ENVIRONMENTAL SENSITIVE AREAS

3 environmentally sensitive areas identified. 13 crew-zone intersections today.

| ESA | KP RANGE | STATUS | RESTRICTION | AUTHORITY |
| --- | --- | --- | --- | --- |
| Slope B/C Glacier - Steep Terrain ESA | KP 5.3 — 6.8 | ACTIVE WORK | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | BCER Permit Condition #47 |
| Wetland Complex | KP 3.4 — 3.8 | MONITORING | 30m setback from wetland boundary. Silt fencing mandatory. Turbidity monitoring required. | BCER / BC Water Sustainability Act |
| Mountain Goat Winter Range | KP 7.0 — 11.0 | RESTRICTION ACTIVE | Helicopter operations restricted Dec 1 - Apr 15. Minimize noise 0600-0900. | BCER Permit Condition #62 / BC Wildlife Act |

Crews Operating in Environmental Sensitive Areas:

| CREW | KP | ACTIVITY | ZONE |
| --- | --- | --- | --- |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.369 | 5+222 Backfiling activities, end haul 5+369 Ditching activities, isolation preparation of NCD 30 5+550 Support Glacier, | Slope B/C Glacier - Steep Terrain ESA |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.550 | 5+222 Backfiling activities, end haul 5+369 Ditching activities, isolation preparation of NCD 30 5+550 Support Glacier, | Slope B/C Glacier - Steep Terrain ESA |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.850 | 5+222 Backfiling activities, end haul 5+369 Ditching activities, isolation preparation of NCD 30 5+550 Support Glacier, | Slope B/C Glacier - Steep Terrain ESA |
| COATING CREW NORTH 2 - Rob Cecka | KP 5.332 | Coat section welds at KP14 laydown. Coat TI at KP14+638. Coat TI at KP5+332. Coat SP weld at KP2+702. Coat section welds | Slope B/C Glacier - Steep Terrain ESA |
| STEEP SLOPES CREW - Mark Evans | KP 6.670 | Continue supporting glacier drilling and blasting ditchline on slope B. Continue moving grade material from the bottom o | Slope B/C Glacier - Steep Terrain ESA |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 5.400 | Assist with any daytime requests as needed Monitor and maintain all submersible pumps and trash pumps within work area ( | Slope B/C Glacier - Steep Terrain ESA |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 10.150 | Assist with any daytime requests as needed Monitor and maintain all submersible pumps and trash pumps within work area ( | Mountain Goat Winter Range |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 10.275 | Assist with any daytime requests as needed Monitor and maintain all submersible pumps and trash pumps within work area ( | Mountain Goat Winter Range |
| MECHANICAL SUPPORT CREW 1 - Daniel Jones | KP 5.600 | Continue engineering at 5+600 | Slope B/C Glacier - Steep Terrain ESA |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | KP 3.500 | Continue making progress with inroad backfill operation. Haul aggregate from km3.5 stock piles Cleanup up work areas Pum | Wetland Complex |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 3.600 | Continue ditching at KP 29+659 working NEG. Continue hauling beddiing and 3”- from Valleycliffe yard to KM 3.6 on the St | Wetland Complex |
| CIVIL SUPPORT - Kirk Haws | KP 3.500 | Kp30+863 mechanically Assisting Spencer‘s crew with final daylight hole road 10 Starting road upgrades Stawamus FSR, fro | Wetland Complex |
| DESC CREW 2 - Tyler Newton | KP 7.550 | Install TB ditch breaker at KP 5+255 Brush ROW from KP 7+550 going positive for upcoming 8K fishery grading DESC pumping | Mountain Goat Winter Range |

## 4. GROUND DISTURBANCE PERMITS

5 ground disturbance permits tracked. 4 valid, 1 pending. 62 crew-zone intersections today.

| PERMIT | KP RANGE | STATUS | CONDITIONS | AUTHORITY |
| --- | --- | --- | --- | --- |
| GD-2026-041 - Hixon Section | KP 2.0 — 6.5 | VALID | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | SMJV GD Program / OGC Act |
| GD-2026-038 - Mid Section | KP 10.0 — 15.5 | VALID | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | SMJV GD Program / Heritage Conservation Act |
| GD-2026-042 - South Section | KP 18.5 — 21.0 | VALID | Active GD permit. Monitoring well MW-14 within 50m at KP 19+400. | SMJV GD Program |
| GD-2026-039 - Mamquam/Urban | KP 29.0 — 32.0 | VALID | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | SMJV GD Program / Municipal Permit |
| GD PENDING - Stawamus FSR | KP 33.0 — 35.0 | PENDING | GD checklist under review. Road upgrades planned KM 0-3.5. Awaiting final sign-off. | SMJV GD Program |

## 5. SAFETY EXCLUSION ZONES

2 safety exclusion zones defined. 2 currently active. 4 crew-zone intersections today.

Blast Exclusion Zone - Active (KP 4.8 - 5.1): Active blasting operations. 500m exclusion during blast events. Blast schedule posted daily.. Status: ACTIVE TODAY. Authority: WorkSafeBC / SMJV Blast Plan.

Helicopter Operations Zone (KP 30.8 - 31.0): Heli pad active. 100m ground exclusion during flight ops. Hard hat mandatory.. Status: ACTIVE TODAY. Authority: Transport Canada / WorkSafeBC.

## 6. INVASIVE SPECIES MANAGEMENT

1 invasive species management zones along the pipeline route. 2 crew-zone intersections today.

Knotweed Contamination Zone (KP 33.6 - 33.9): Contaminated topsoil - mandatory offsite disposal (GFL Abbotsford). Equipment wash mandatory on exit.. Status: ACTIVE HAULING. Authority: BC Weed Control Act / BCER Condition #71.

1 crew(s) operating in invasive species zones today. Standard wash-down and inspection protocols apply.

## 7. COMPLETE CREW-ZONE INTERSECTION LOG

The following table lists every intersection between active crew locations and regulatory zones for February 27, 2026. This log serves as the daily compliance record for audit purposes.

| CREW | KP | ZONE | RESTRICTION | STATUS |
| --- | --- | --- | --- | --- |
| CIVILS-GRADE/BLAST-CREW 10 - Jordan Yarycky | KP 2.690 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| BACKFILL NIGHTSHIFT HIXON - Clayton Key | KP 2.700 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| CIVILS-GRADE/BLAST-CREW 8 - Daryl Holtskog | KP 4.975 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| CIVILS-GRADE/BLAST-CREW 8 - Daryl Holtskog | KP 4.975 | Blast Exclusion Zone - Active | Active blasting operations. 500m exclusion during blast events. Blast schedule posted daily. | ACTIVE TODAY |
| ROCK CRUSHING HIXON - Chris Davidson | KP 2.000 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.222 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.369 | Slope B/C Glacier - Steep Terrain ESA | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | ACTIVE WORK |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.369 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.550 | Slope B/C Glacier - Steep Terrain ESA | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | ACTIVE WORK |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.550 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.850 | Slope B/C Glacier - Steep Terrain ESA | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | ACTIVE WORK |
| CIVILS-GRADE/BLAST-CREW 7 - Wade Cuthbertson | KP 5.850 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| MECHANICAL CREW 5 - Roy Sparling | KP 2.710 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| COATING CREW NORTH 2 - Rob Cecka | KP 2.702 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| COATING CREW NORTH 2 - Rob Cecka | KP 5.332 | Slope B/C Glacier - Steep Terrain ESA | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | ACTIVE WORK |
| COATING CREW NORTH 2 - Rob Cecka | KP 5.332 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| COATING CREW NORTH 2 - Rob Cecka | KP 12.800 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| COATING CREW NORTH 2 - Rob Cecka | KP 14.000 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| COATING CREW NORTH 2 - Rob Cecka | KP 14.638 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| STEEP SLOPES CREW - Mark Evans | KP 6.670 | Slope B/C Glacier - Steep Terrain ESA | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | ACTIVE WORK |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 2.300 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 5.400 | Slope B/C Glacier - Steep Terrain ESA | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | ACTIVE WORK |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 5.400 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 10.150 | Mountain Goat Winter Range | Helicopter operations restricted Dec 1 - Apr 15. Minimize noise 0600-0900. | RESTRICTION ACTIVE |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 10.150 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 10.275 | Mountain Goat Winter Range | Helicopter operations restricted Dec 1 - Apr 15. Minimize noise 0600-0900. | RESTRICTION ACTIVE |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 10.275 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| CIVILS-GRADE/BLAST-CREW 3 - Brandon Hrycun | KP 12.000 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| CIVILS-GRADE/BLAST-CREW 3 - Brandon Hrycun | KP 13.800 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| CIVILS-GRADE/BLAST-CREW 3 - Brandon Hrycun | KP 14.000 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| MECHANICAL CREW 2 - Josh Norman | KP 14.000 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| MECHANICAL CREW 2 - Josh Norman | KP 15.000 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| CIVILS-GRADE/BLAST-CREW 4 - Linden Heidecker | KP 14.480 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| CIVILS-GRADE/BLAST-CREW 4 - Linden Heidecker | KP 14.530 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| CIVILS-GRADE/BLAST-CREW 4 - Linden Heidecker | KP 14.550 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| CIVILS-GRADE/BLAST-CREW 4 - Linden Heidecker | KP 14.650 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| MECHANICAL CREW 4 - Geoffrey Banks | KP 12.777 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| MECHANICAL CREW 4 - Geoffrey Banks | KP 14.000 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| MECHANICAL CREW 4 - Geoffrey Banks | KP 19.193 | GD-2026-042 - South Section | Active GD permit. Monitoring well MW-14 within 50m at KP 19+400. | VALID |
| CIVILS-GRADE/BLAST-CREW 11 - Kelly Shearer | KP 14.000 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| CIVILS-GRADE/BLAST-CREW 11 - Kelly Shearer | KP 19.195 | GD-2026-042 - South Section | Active GD permit. Monitoring well MW-14 within 50m at KP 19+400. | VALID |
| CIVILS-GRADE/BLAST-CREW 11 - Kelly Shearer | KP 20.100 | GD-2026-042 - South Section | Active GD permit. Monitoring well MW-14 within 50m at KP 19+400. | VALID |
| BACKFILL NIGHTSHIFT - Tom Flannery | KP 19.100 | GD-2026-042 - South Section | Active GD permit. Monitoring well MW-14 within 50m at KP 19+400. | VALID |
| MECHANICAL SUPPORT CREW 1 - Daniel Jones | KP 5.600 | Slope B/C Glacier - Steep Terrain ESA | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | ACTIVE WORK |
| MECHANICAL SUPPORT CREW 1 - Daniel Jones | KP 5.600 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| WELDING - Ian Kopp | KP 2.710 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| WELDING - Ian Kopp | KP 12.700 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| WELDING - Ian Kopp | KP 14.600 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| WELDING - Ian Kopp | KP 29.600 | Mamquam River Crossing | No in-stream work Mar 1 - Jun 30 & Aug 15 - Nov 30 | OPEN |
| WELDING - Ian Kopp | KP 29.600 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| COATING CREW NORTH 1 - Matt Fadden | KP 29.594 | Mamquam River Crossing | No in-stream work Mar 1 - Jun 30 & Aug 15 - Nov 30 | OPEN |
| COATING CREW NORTH 1 - Matt Fadden | KP 29.594 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | KP 3.500 | Wetland Complex | 30m setback from wetland boundary. Silt fencing mandatory. Turbidity monitoring required. | MONITORING |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | KP 3.500 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| MECHANICAyL CREW 1 - Travis Stacey | KP 29.650 | Mamquam River Crossing | No in-stream work Mar 1 - Jun 30 & Aug 15 - Nov 30 | OPEN |
| MECHANICAyL CREW 1 - Travis Stacey | KP 29.650 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 3.600 | Wetland Complex | 30m setback from wetland boundary. Silt fencing mandatory. Turbidity monitoring required. | MONITORING |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 3.600 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 29.659 | Mamquam River Crossing | No in-stream work Mar 1 - Jun 30 & Aug 15 - Nov 30 | OPEN |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 29.659 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVIL SUPPORT - Kirk Haws | KP 3.500 | Wetland Complex | 30m setback from wetland boundary. Silt fencing mandatory. Turbidity monitoring required. | MONITORING |
| CIVIL SUPPORT - Kirk Haws | KP 3.500 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| CIVIL SUPPORT - Kirk Haws | KP 30.863 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVIL SUPPORT - Kirk Haws | KP 30.863 | Helicopter Operations Zone | Heli pad active. 100m ground exclusion during flight ops. Hard hat mandatory. | ACTIVE TODAY |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 30.937 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 30.937 | Helicopter Operations Zone | Heli pad active. 100m ground exclusion during flight ops. Hard hat mandatory. | ACTIVE TODAY |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.110 | Ray Creek Crossing | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.110 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.130 | Ray Creek Crossing | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.130 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.160 | Ray Creek Crossing | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.160 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.180 | Ray Creek Crossing | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.180 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.190 | Ray Creek Crossing | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.190 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.200 | Ray Creek Crossing | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.200 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.250 | Ray Creek Crossing | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.250 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.260 | Ray Creek Crossing | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | OPEN |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.260 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| ROCK CRUSHING SQUAMISH - Stuart Baldwin | KP 4.200 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| CIVILS-GRADE/BLAST-CREW 6 - Ryan Beccherini | KP 33.800 | Stawamus River Zone | No in-stream work Mar 15 - Jun 30 | OPEN |
| CIVILS-GRADE/BLAST-CREW 6 - Ryan Beccherini | KP 33.800 | GD PENDING - Stawamus FSR | GD checklist under review. Road upgrades planned KM 0-3.5. Awaiting final sign-off. | PENDING |
| CIVILS-GRADE/BLAST-CREW 6 - Ryan Beccherini | KP 33.800 | Knotweed Contamination Zone | Contaminated topsoil - mandatory offsite disposal (GFL Abbotsford). Equipment wash mandatory on exit. | ACTIVE HAULING |
| CIVILS-GRADE/BLAST-CREW 6 - Ryan Beccherini | KP 33.850 | Stawamus River Zone | No in-stream work Mar 15 - Jun 30 | OPEN |
| CIVILS-GRADE/BLAST-CREW 6 - Ryan Beccherini | KP 33.850 | GD PENDING - Stawamus FSR | GD checklist under review. Road upgrades planned KM 0-3.5. Awaiting final sign-off. | PENDING |
| CIVILS-GRADE/BLAST-CREW 6 - Ryan Beccherini | KP 33.850 | Knotweed Contamination Zone | Contaminated topsoil - mandatory offsite disposal (GFL Abbotsford). Equipment wash mandatory on exit. | ACTIVE HAULING |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | KP 29.600 | Mamquam River Crossing | No in-stream work Mar 1 - Jun 30 & Aug 15 - Nov 30 | OPEN |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | KP 29.600 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| UTILITY CREW 2 - Spencer Lemoal | KP 14.000 | GD-2026-038 - Mid Section | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | VALID |
| UTILITY CREW 2 - Spencer Lemoal | KP 30.850 | GD-2026-039 - Mamquam/Urban | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | VALID |
| UTILITY CREW 2 - Spencer Lemoal | KP 30.850 | Helicopter Operations Zone | Heli pad active. 100m ground exclusion during flight ops. Hard hat mandatory. | ACTIVE TODAY |
| DESC CREW 2 - Tyler Newton | KP 5.255 | GD-2026-041 - Hixon Section | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | VALID |
| DESC CREW 2 - Tyler Newton | KP 7.550 | Mountain Goat Winter Range | Helicopter operations restricted Dec 1 - Apr 15. Minimize noise 0600-0900. | RESTRICTION ACTIVE |

PREPARED BY:

Name: ______________________________   Signature: ______________________________   Date: ____________________

REVIEWED BY:

Name: ______________________________   Signature: ______________________________   Date: ____________________

This report was auto-generated by the Pipe-Up Regulatory Compliance Engine. All crew locations and zone intersections are derived from daily work plan data and regulatory zone definitions. This report should be reviewed and verified by the responsible compliance officer before distribution.