DAILY REGULATORY COMPLIANCE REPORT

SMJV — Eagle Mountain Woodfibre Gas Pipeline
March 03, 2026
Job #2330 — Squamish, BC

| Total Findings | Action Required | Monitor | Compliant |
| --- | --- | --- | --- |
| 69 | 12 | 4 | 53 |

On March 03, 2026, 25 crews with mapped KP locations were cross-referenced against 14 regulatory zones, yielding 69 intersection findings. 12 require action, 4 are under active monitoring, and 53 are compliant.

# Compliance Alerts

| Severity | Alert | Detail | KP |
| --- | --- | --- | --- |
| HIGH | Fisheries Window Closing — Mamquam River Crossing | No in-stream work Mar 1 - Jun 30 & Aug 15 - Nov 30. Window closes in 2 day(s). Active crews in zone. | KP 29.2 |
| MEDIUM | Pending GD Permit — GD PENDING - Stawamus FSR | GD checklist under review. Road upgrades planned KM 0-3.5. Awaiting final sign-off.. Crews operating in zone without final sign-off. | KP 33.0 |
| MEDIUM | Active Safety Zone — Helicopter Operations Zone | Heli pad active. 100m ground exclusion during flight ops. Hard hat mandatory. | KP 30.8 |
| LOW | Environmental Restriction — Slope B/C Glacier - Steep Terrain ESA | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | KP 5.3 |

# Environmental Sensitive Areas

| Name | KP Range | Status | Restriction | Authority |
| --- | --- | --- | --- | --- |
| Slope B/C Glacier - Steep Terrain ESA | KP 5.3 — 6.8 | ACTIVE WORK | Enhanced erosion control required. No work during heavy rain events. Mandatory spotter. | BCER Permit Condition #47 |
| Wetland Complex | KP 3.4 — 3.8 | MONITORING | 30m setback from wetland boundary. Silt fencing mandatory. Turbidity monitoring required. | BCER / BC Water Sustainability Act |
| Mountain Goat Winter Range | KP 7.0 — 11.0 | RESTRICTION ACTIVE | Helicopter operations restricted Dec 1 - Apr 15. Minimize noise 0600-0900. | BCER Permit Condition #62 / BC Wildlife Act |

Crews Operating in Zone

| Crew Name | KP | Activity | Zone Name |
| --- | --- | --- | --- |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 5.400 | Assist with any daytime requests as needed Monitor and maintain all submersible pumps and trash pumps within work area ( | Slope B/C Glacier - Steep Terrain ESA |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 3.600 | Weather permitting** Continue ditching at KP 29+574 working NEG. Continue hauling beddiing and 3”- from Valleycliffe yar | Wetland Complex |
| CIVIL SUPPORT - Kirk Haws | KP 3.500 | Stawamus FSR road maintenance / upgrade km3.5 - km0 Grader Windrow soft materials. skid steer, pushing and piling materi | Wetland Complex |

# Fisheries Timing Windows

| Name | KP Range | Status | Restriction | Authority |
| --- | --- | --- | --- | --- |
| Ray Creek Crossing | KP 31.0 — 31.3 | OPEN | No in-stream work Mar 1 - Jun 15 & Sep 1 - Nov 15 | DFO / Fisheries Act |
| Mamquam River Crossing | KP 29.2 — 29.8 | OPEN (CLOSES IN 2 DAYS) | No in-stream work Mar 1 - Jun 30 & Aug 15 - Nov 30 | DFO / Fisheries Act |
| Stawamus River Zone | KP 33.5 — 34.2 | OPEN | No in-stream work Mar 15 - Jun 30 | DFO / Fisheries Act |

Crews Operating in Zone

| Crew Name | KP | Activity | Zone Name |
| --- | --- | --- | --- |
| WELDING - Ian Kopp | KP 29.579 | KP 12+636- Bedomme / Deschamps KP 14 yard - Wilson / Davis KP 29+579 - Becker / Albrecht KP 14 yard - Wilson / Smith KP | Mamquam River Crossing |
| WELDING - Ian Kopp | KP 34.000 | KP 12+636- Bedomme / Deschamps KP 14 yard - Wilson / Davis KP 29+579 - Becker / Albrecht KP 14 yard - Wilson / Smith KP | Stawamus River Zone |
| COATING CREW NORTH 1 - Matt Fadden | KP 29.579 | Crew 1, PB coating @ RD 6, cut back blasting as required, holiday testing and RG install. Crew 2, SP/PB coating for in R | Mamquam River Crossing |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | KP 29.600 | Pump support KP 29+600 Backfill inroad pipe - Weather depending on activity | Mamquam River Crossing |
| MECHANICAyL CREW 1 - Travis Stacey | KP 29.579 | Continue inroad tie ins at kp 29+579 | Mamquam River Crossing |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 29.574 | Weather permitting** Continue ditching at KP 29+574 working NEG. Continue hauling beddiing and 3”- from Valleycliffe yar | Mamquam River Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.110 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.130 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.180 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.200 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.220 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.250 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | Ray Creek Crossing |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.260 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | Ray Creek Crossing |
| MECHANICAL CREW 3 - Doug Yarycky | KP 34.000 | String pipe 32+600 Section welds 34+000 | Stawamus River Zone |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | KP 29.600 | Hydrovac support at Kp 33+777, tie in support at Kp 29+600 | Mamquam River Crossing |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | KP 33.777 | Hydrovac support at Kp 33+777, tie in support at Kp 29+600 | Stawamus River Zone |

# Ground Disturbance Permits

| Name | KP Range | Status | Restriction | Authority |
| --- | --- | --- | --- | --- |
| GD-2026-041 - Hixon Section | KP 2.0 — 6.5 | VALID | Active GD permit. Pre-disturbance assessment complete. Valid through Mar 31, 2026. | SMJV GD Program / OGC Act |
| GD-2026-038 - Mid Section | KP 10.0 — 15.5 | VALID | Active GD permit. Archaeological monitor required KP 12+200 to 12+800. | SMJV GD Program / Heritage Conservation Act |
| GD-2026-042 - South Section | KP 18.5 — 21.0 | VALID | Active GD permit. Monitoring well MW-14 within 50m at KP 19+400. | SMJV GD Program |
| GD-2026-039 - Mamquam/Urban | KP 29.0 — 32.0 | VALID | Active GD permit. Retaining wall zone KP 31. Geotechnical monitoring mandatory. | SMJV GD Program / Municipal Permit |
| GD PENDING - Stawamus FSR | KP 33.0 — 35.0 | PENDING | GD checklist under review. Road upgrades planned KM 0-3.5. Awaiting final sign-off. | SMJV GD Program |

Crews Operating in Zone

| Crew Name | KP | Activity | Zone Name |
| --- | --- | --- | --- |
| MECHANICAL CREW 6 - Josh Brideau | KP 2.727 | Stove pipe weld at kp 2+727 | GD-2026-041 - Hixon Section |
| BACKFILL NIGHTSHIFT HIXON - Clayton Key | KP 2.717 | Backfill at Kp 2+717 Ditch plug at Kp 2+720 | GD-2026-041 - Hixon Section |
| BACKFILL NIGHTSHIFT HIXON - Clayton Key | KP 2.720 | Backfill at Kp 2+717 Ditch plug at Kp 2+720 | GD-2026-041 - Hixon Section |
| ROCK CRUSHING HIXON - Chris Davidson | KP 2.000 | KM 2 Hixon - Continue crushing. | GD-2026-041 - Hixon Section |
| MECHANICAL CREW 5 - Roy Sparling | KP 12.636 | Section welding at 12+636. | GD-2026-038 - Mid Section |
| COATING CREW NORTH 2 - Rob Cecka | KP 2.711 | Coat SP weld at KP2+711. Coat section welds at 12+700. Coat section welds at 15+000. Coat SP weld at 19+268. | GD-2026-041 - Hixon Section |
| COATING CREW NORTH 2 - Rob Cecka | KP 12.700 | Coat SP weld at KP2+711. Coat section welds at 12+700. Coat section welds at 15+000. Coat SP weld at 19+268. | GD-2026-038 - Mid Section |
| COATING CREW NORTH 2 - Rob Cecka | KP 15.000 | Coat SP weld at KP2+711. Coat section welds at 12+700. Coat section welds at 15+000. Coat SP weld at 19+268. | GD-2026-038 - Mid Section |
| COATING CREW NORTH 2 - Rob Cecka | KP 19.268 | Coat SP weld at KP2+711. Coat section welds at 12+700. Coat section welds at 15+000. Coat SP weld at 19+268. | GD-2026-042 - South Section |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 2.300 | Assist with any daytime requests as needed Monitor and maintain all submersible pumps and trash pumps within work area ( | GD-2026-041 - Hixon Section |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | KP 5.400 | Assist with any daytime requests as needed Monitor and maintain all submersible pumps and trash pumps within work area ( | GD-2026-041 - Hixon Section |
| CIVILS-GRADE/BLAST-CREW 3 - Brandon Hrycun | KP 14.000 | Continue crushing at kp14 | GD-2026-038 - Mid Section |
| MECHANICAL CREW 2 - Josh Norman | KP 14.000 | Section welds at KP 14 laydown | GD-2026-038 - Mid Section |
| CIVILS-GRADE/BLAST-CREW 1 - Dennis Rogers | KP 14.000 | KP 14 Yard - Placing and leveling office trailers Placing sea can with warehouse for coating materials Put in T post and | GD-2026-038 - Mid Section |
| MECHANICAL CREW 4 - Geoffrey Banks | KP 14.000 | Section welds Kp 14 Yard | GD-2026-038 - Mid Section |
| CIVILS-GRADE/BLAST-CREW 11 - Kelly Shearer | KP 14.000 | Continue with digging from 19+286 ,continue hauling fill material from hixon to km 14 extra workspace | GD-2026-038 - Mid Section |
| CIVILS-GRADE/BLAST-CREW 11 - Kelly Shearer | KP 19.286 | Continue with digging from 19+286 ,continue hauling fill material from hixon to km 14 extra workspace | GD-2026-042 - South Section |
| BACKFILL NIGHTSHIFT - Tom Flannery | KP 19.264 | Continue backfill 19+264 positive | GD-2026-042 - South Section |
| MECHANICAL SUPPORT CREW 1 - Daniel Jones | KP 14.000 | Stringing pipe in Hixon and KP 14 yard. Measuring and record. Building crotches. | GD-2026-038 - Mid Section |
| WELDING - Ian Kopp | KP 2.700 | KP 12+636- Bedomme / Deschamps KP 14 yard - Wilson / Davis KP 29+579 - Becker / Albrecht KP 14 yard - Wilson / Smith KP | GD-2026-041 - Hixon Section |
| WELDING - Ian Kopp | KP 12.636 | KP 12+636- Bedomme / Deschamps KP 14 yard - Wilson / Davis KP 29+579 - Becker / Albrecht KP 14 yard - Wilson / Smith KP | GD-2026-038 - Mid Section |
| WELDING - Ian Kopp | KP 14.000 | KP 12+636- Bedomme / Deschamps KP 14 yard - Wilson / Davis KP 29+579 - Becker / Albrecht KP 14 yard - Wilson / Smith KP | GD-2026-038 - Mid Section |
| WELDING - Ian Kopp | KP 29.579 | KP 12+636- Bedomme / Deschamps KP 14 yard - Wilson / Davis KP 29+579 - Becker / Albrecht KP 14 yard - Wilson / Smith KP | GD-2026-039 - Mamquam/Urban |
| WELDING - Ian Kopp | KP 34.000 | KP 12+636- Bedomme / Deschamps KP 14 yard - Wilson / Davis KP 29+579 - Becker / Albrecht KP 14 yard - Wilson / Smith KP | GD PENDING - Stawamus FSR |
| COATING CREW NORTH 1 - Matt Fadden | KP 29.579 | Crew 1, PB coating @ RD 6, cut back blasting as required, holiday testing and RG install. Crew 2, SP/PB coating for in R | GD-2026-039 - Mamquam/Urban |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | KP 29.600 | Pump support KP 29+600 Backfill inroad pipe - Weather depending on activity | GD-2026-039 - Mamquam/Urban |
| MECHANICAyL CREW 1 - Travis Stacey | KP 29.579 | Continue inroad tie ins at kp 29+579 | GD-2026-039 - Mamquam/Urban |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 3.600 | Weather permitting** Continue ditching at KP 29+574 working NEG. Continue hauling beddiing and 3”- from Valleycliffe yar | GD-2026-041 - Hixon Section |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | KP 29.574 | Weather permitting** Continue ditching at KP 29+574 working NEG. Continue hauling beddiing and 3”- from Valleycliffe yar | GD-2026-039 - Mamquam/Urban |
| CIVIL SUPPORT - Kirk Haws | KP 3.500 | Stawamus FSR road maintenance / upgrade km3.5 - km0 Grader Windrow soft materials. skid steer, pushing and piling materi | GD-2026-041 - Hixon Section |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | KP 30.240 | Cutting Subgrade design for GRS wall 30+850 positive. Hauling out soils from 30+800 to 30+240. Building up grade fill 30 | GD-2026-039 - Mamquam/Urban |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | KP 30.260 | Cutting Subgrade design for GRS wall 30+850 positive. Hauling out soils from 30+800 to 30+240. Building up grade fill 30 | GD-2026-039 - Mamquam/Urban |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | KP 30.800 | Cutting Subgrade design for GRS wall 30+850 positive. Hauling out soils from 30+800 to 30+240. Building up grade fill 30 | GD-2026-039 - Mamquam/Urban |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | KP 30.850 | Cutting Subgrade design for GRS wall 30+850 positive. Hauling out soils from 30+800 to 30+240. Building up grade fill 30 | GD-2026-039 - Mamquam/Urban |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 30.937 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | GD-2026-039 - Mamquam/Urban |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.110 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | GD-2026-039 - Mamquam/Urban |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.130 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | GD-2026-039 - Mamquam/Urban |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.180 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | GD-2026-039 - Mamquam/Urban |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.200 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | GD-2026-039 - Mamquam/Urban |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.220 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | GD-2026-039 - Mamquam/Urban |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.250 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | GD-2026-039 - Mamquam/Urban |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 31.260 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | GD-2026-039 - Mamquam/Urban |
| ROCK CRUSHING SQUAMISH - Stuart Baldwin | KP 4.200 | KM 4.2 Mamquam - Crushing 19mm and 4”-6” clear stone at km4.2, low on material Support truck haul from crusher to Valley | GD-2026-041 - Hixon Section |
| MECHANICAL CREW 3 - Doug Yarycky | KP 34.000 | String pipe 32+600 Section welds 34+000 | GD PENDING - Stawamus FSR |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | KP 29.600 | Hydrovac support at Kp 33+777, tie in support at Kp 29+600 | GD-2026-039 - Mamquam/Urban |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | KP 33.777 | Hydrovac support at Kp 33+777, tie in support at Kp 29+600 | GD PENDING - Stawamus FSR |

# Invasive Species Zones

| Name | KP Range | Status | Restriction | Authority |
| --- | --- | --- | --- | --- |
| Knotweed Contamination Zone | KP 33.6 — 33.9 | ACTIVE HAULING | Contaminated topsoil - mandatory offsite disposal (GFL Abbotsford). Equipment wash mandatory on exit. | BC Weed Control Act / BCER Condition #71 |

Crews Operating in Zone

| Crew Name | KP | Activity | Zone Name |
| --- | --- | --- | --- |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | KP 33.777 | Hydrovac support at Kp 33+777, tie in support at Kp 29+600 | Knotweed Contamination Zone |

# Safety / Exclusion Zones

| Name | KP Range | Status | Restriction | Authority |
| --- | --- | --- | --- | --- |
| Blast Exclusion Zone - Active | KP 4.8 — 5.1 | ACTIVE TODAY | Active blasting operations. 500m exclusion during blast events. Blast schedule posted daily. | WorkSafeBC / SMJV Blast Plan |
| Helicopter Operations Zone | KP 30.8 — 31.0 | ACTIVE TODAY | Heli pad active. 100m ground exclusion during flight ops. Hard hat mandatory. | Transport Canada / WorkSafeBC |

Crews Operating in Zone

| Crew Name | KP | Activity | Zone Name |
| --- | --- | --- | --- |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | KP 30.800 | Cutting Subgrade design for GRS wall 30+850 positive. Hauling out soils from 30+800 to 30+240. Building up grade fill 30 | Helicopter Operations Zone |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | KP 30.850 | Cutting Subgrade design for GRS wall 30+850 positive. Hauling out soils from 30+800 to 30+240. Building up grade fill 30 | Helicopter Operations Zone |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | KP 30.937 | Support ILP/GRW - Labour & equipment support/forwarding tools/materials/personnel. - Continue ECB/Soil mesh/Bolt tension | Helicopter Operations Zone |

# Complete Crew-Zone Intersection Log

This table is the audit trail for regulators. Every crew-zone intersection detected on this date is logged below.

| Crew | Inspector | KP | Zone | Status | Severity |
| --- | --- | --- | --- | --- | --- |
| MECHANICAL CREW 6 - Josh Brideau | Nicole Caron | KP 2.727 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| BACKFILL NIGHTSHIFT HIXON - Clayton Key | Bill Cherowka | KP 2.717 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| BACKFILL NIGHTSHIFT HIXON - Clayton Key | Bill Cherowka | KP 2.720 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| ROCK CRUSHING HIXON - Chris Davidson | Hamid Alikhani | KP 2.000 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| MECHANICAL CREW 5 - Roy Sparling | Lee McCarty | KP 12.636 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| COATING CREW NORTH 2 - Rob Cecka | Dylan Gloeckler | KP 2.711 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| COATING CREW NORTH 2 - Rob Cecka | Dylan Gloeckler | KP 12.700 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| COATING CREW NORTH 2 - Rob Cecka | Dylan Gloeckler | KP 15.000 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| COATING CREW NORTH 2 - Rob Cecka | Dylan Gloeckler | KP 19.268 | GD-2026-042 - South Section | VALID | COMPLIANT |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | Stephen Swaim | KP 2.300 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | Stephen Swaim | KP 5.400 | Slope B/C Glacier - Steep Terrain ESA | ACTIVE WORK | MONITOR |
| PUMP SUPPORT 2 NIGHT SHIFT - Brayden Hanna | Stephen Swaim | KP 5.400 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 3 - Brandon Hrycun | Robert Walsh | KP 14.000 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| MECHANICAL CREW 2 - Josh Norman | Mark Kruiger | KP 14.000 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 1 - Dennis Rogers | Robert Walsh | KP 14.000 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| MECHANICAL CREW 4 - Geoffrey Banks | Teliegha Markham | KP 14.000 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 11 - Kelly Shearer | Scott Middleton | KP 14.000 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 11 - Kelly Shearer | Scott Middleton | KP 19.286 | GD-2026-042 - South Section | VALID | COMPLIANT |
| BACKFILL NIGHTSHIFT - Tom Flannery | Bill Cherowka | KP 19.264 | GD-2026-042 - South Section | VALID | COMPLIANT |
| MECHANICAL SUPPORT CREW 1 - Daniel Jones | Teliegha Markham | KP 14.000 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| WELDING - Ian Kopp | Al Letch | KP 2.700 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| WELDING - Ian Kopp | Al Letch | KP 12.636 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| WELDING - Ian Kopp | Al Letch | KP 14.000 | GD-2026-038 - Mid Section | VALID | COMPLIANT |
| WELDING - Ian Kopp | Al Letch | KP 29.579 | Mamquam River Crossing | OPEN | HIGH |
| WELDING - Ian Kopp | Al Letch | KP 29.579 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| WELDING - Ian Kopp | Al Letch | KP 34.000 | Stawamus River Zone | OPEN | COMPLIANT |
| WELDING - Ian Kopp | Al Letch | KP 34.000 | GD PENDING - Stawamus FSR | PENDING | HIGH |
| COATING CREW NORTH 1 - Matt Fadden | Dylan Gloeckler | KP 29.579 | Mamquam River Crossing | OPEN | HIGH |
| COATING CREW NORTH 1 - Matt Fadden | Dylan Gloeckler | KP 29.579 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | Adam Ferretti | KP 29.600 | Mamquam River Crossing | OPEN | HIGH |
| PUMP SUPPORT-BACKFILL SUPPORT NIGHT SHIFT- Richard Kent | Adam Ferretti | KP 29.600 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| MECHANICAyL CREW 1 - Travis Stacey | Wade Gordon | KP 29.579 | Mamquam River Crossing | OPEN | HIGH |
| MECHANICAyL CREW 1 - Travis Stacey | Wade Gordon | KP 29.579 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | Troy Young | KP 3.600 | Wetland Complex | MONITORING | MONITOR |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | Troy Young | KP 3.600 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | Troy Young | KP 29.574 | Mamquam River Crossing | OPEN | HIGH |
| CIVILS-GRADE/BLAST-CREW 5 - Brent Hansen | Troy Young | KP 29.574 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| CIVIL SUPPORT - Kirk Haws | Troy Young | KP 3.500 | Wetland Complex | MONITORING | MONITOR |
| CIVIL SUPPORT - Kirk Haws | Troy Young | KP 3.500 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | Troy Young | KP 30.240 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | Troy Young | KP 30.260 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | Troy Young | KP 30.800 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | Troy Young | KP 30.800 | Helicopter Operations Zone | ACTIVE TODAY | HIGH |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | Troy Young | KP 30.850 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| RAY CREEK RETAINING WALL - Dalton Biesenthal | Troy Young | KP 30.850 | Helicopter Operations Zone | ACTIVE TODAY | HIGH |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 30.937 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 30.937 | Helicopter Operations Zone | ACTIVE TODAY | HIGH |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.110 | Ray Creek Crossing | OPEN | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.110 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.130 | Ray Creek Crossing | OPEN | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.130 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.180 | Ray Creek Crossing | OPEN | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.180 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.200 | Ray Creek Crossing | OPEN | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.200 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.220 | Ray Creek Crossing | OPEN | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.220 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.250 | Ray Creek Crossing | OPEN | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.250 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.260 | Ray Creek Crossing | OPEN | COMPLIANT |
| CIVILS-GRADE/BLAST-CREW 9 - Quinn Braybrook | Wade Gordon | KP 31.260 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| ROCK CRUSHING SQUAMISH - Stuart Baldwin | John Deveau | KP 4.200 | GD-2026-041 - Hixon Section | VALID | COMPLIANT |
| MECHANICAL CREW 3 - Doug Yarycky | Tylene Swanson | KP 34.000 | Stawamus River Zone | OPEN | COMPLIANT |
| MECHANICAL CREW 3 - Doug Yarycky | Tylene Swanson | KP 34.000 | GD PENDING - Stawamus FSR | PENDING | HIGH |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | Joel Jackson | KP 29.600 | Mamquam River Crossing | OPEN | HIGH |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | Joel Jackson | KP 29.600 | GD-2026-039 - Mamquam/Urban | VALID | COMPLIANT |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | Joel Jackson | KP 33.777 | Stawamus River Zone | OPEN | COMPLIANT |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | Joel Jackson | KP 33.777 | GD PENDING - Stawamus FSR | PENDING | HIGH |
| MECHANICAL SUPPORT CREW 2 - Jason Klimow | Joel Jackson | KP 33.777 | Knotweed Contamination Zone | ACTIVE HAULING | MONITOR |

Prepared By:  __________________________________________________  Date: ____________________

Reviewed By:  __________________________________________________  Date: ____________________